## Sheet1
ServiceID_Crid | SalesProjectID_ContractNumber | Customer name | Delta MRC | Delivery Project Manager | Segment Red. | ProjectTypeValue | 20250519 | 20250520 | 20250521 | 20250522 | 20250523 | 20250524 | 20250525 | 20250526 | 20250527 | 20250528 | 20250529 | 20250530 | 20250531 | 20250601 | 20250602 | 20250603 | 20250604 | 20250605 | 20250606 | 20250607 | 20250608 | 20250609 | 20250610 | 20250611 | 20250612 | 20250613 | 20250614 | 20250615 | 20250616 | 20250617 | 20250618 | 20250619 | 20250620 | 20250621 | 20250622 | 20250623 | 20250624 | 20250625 | 20250626 | 20250627 | 20250628 | 20250629 | 20250630 | 20250701 | 20250702 | 20250703 | 20250704 | 20250705 | 20250706 | 20250707 | 20250708 | 20250709 | 20250710 | 20250711 | 20250712 | 20250713 | 20250714 | 20250715 | 20250716 | 20250717 | 20250718 | 20250719 | 20250720 | 20250721 | 20250722 | 20250723 | 20250724 | 20250725 | 20250726 | 20250727 | 20250728 | 20250729 | 20250730 | 20250731 | 20250801 | 20250802 | 20250803 | 20250804 | 20250805 | 20250806 | 20250807 | 20250808 | 20250809 | 20250810 | 20250811 | 20250812 | 20250813 | 20250814 | 20250815 | 20250816 | 20250817 | 20250818 | 20250819 | 20250820 | 20250821 | 20250822 | 20250823 | 20250824 | 20250825 | 20250826 | 20250827 | 20250828 | 20250829 | 20250830 | 20250831 | 20250901 | 20250902 | 20250903 | 20250904 | 20250905 | 20250906 | 20250907 | 20250908 | 20250909 | 20250910 | 20250911 | 20250912 | 20250913 | 20250914 | 20250915 | 20250916 | 20250917 | 20250918 | 20250919 | 20250920 | 20250921 | 20250922 | 20250923 | 20250924 | 20250925 | 20250926 | 20250927 | 20250928 | 20250929 | 20250930 | 20251001 | 20251002 | 20251003 | 20251004 | 20251005 | 20251006 | 20251007 | 20251008 | 20251009 | 20251010 | 20251011 | 20251012 | 20251013 | 20251014 | 20251015 | 20251016 | 20251017 | 20251018 | 20251019 | 20251020 | 20251021 | 20251022 | 20251023 | 20251024 | 20251025 | 20251026 | 20251027 | 20251028 | 20251029 | 20251030 | 20251031 | 20251101 | 20251102 | 20251103 | 20251104 | 20251105 | 20251106 | 20251107 | 20251108 | 20251109 | 20251110 | 20251111 | 20251112 | 20251113 | 20251114 | 20251115 | 20251116 | 20251117 | 20251118 | 20251119 | 20251120 | 20251121 | 20251122 | 20251123 | 20251124 | 20251125 | 20251126 | 20251127 | 20251128 | 20251129 | 20251130 | 20251201 | 20251202 | 20251203 | 20251204 | 20251205 | 20251206 | 20251207 | 20251208 | 20251209 | 20251210 | 20251211 | 20251212 | 20251213 | 20251214 | 20251215 | 20251216 | 20251217 | 20251218 | 20251219 | 20251220 | 20251221 | 20251222 | 20251223 | 20251224 | 20251225 | 20251226 | 20251227 | 20251228 | 20251229 | 20251230 | 20251231
C31128-1133697-01 | 101164-043 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 4800 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Delivered
C31128-1133698-01 | 101164-043 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 1024 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31128-1133700-01 | 101164-043 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 4800 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31128-1133701-01 | 101164-043 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 1024 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
F31128-1133702-01 | 101164-043 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 1125 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-059687 | 102301 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 947.5 | Christoffer Møller Andersen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-059688 | 102301 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 947.5 | Christoffer Møller Andersen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060363 | 103678 | Aabenraa Kommune | 560 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060363 | 103680 | Aabenraa Kommune | 30 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-053695 | 95083 | Aabenraa Kommune | 560 | Kristijan Krsteski | Public DK |  | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
F30344-1133574-01 | 100625-014 | Aalborg Handelsskole | 753.22 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F30344-1133576-01 | 100625-014 | Aalborg Handelsskole | 753.22 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058344 | 101953 | Aarhus Business College | 845 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058767 | 102560 | Aarhus Business College | 845 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-006093 | 105408 | Aarhus Business College | 7625 | Morten Skytte | Public DK | Change
NKA-010029 | 105408 | Aarhus Business College | 6000 | Morten Skytte | Public DK | Change
NKA-053439 | 105408 | Aarhus Business College | 7000 | Morten Skytte | Public DK | Change
NKA-060636 | 103444 | Aarhus Kommune - Filmby Aarhus | 1210 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060637 | 103444 | Aarhus Kommune - Filmby Aarhus | 1210 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060638 | 103444 | Aarhus Kommune - Filmby Aarhus | 860 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060126 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060127 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060128 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060129 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060130 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060131 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060132 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060133 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060134 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060135 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060136 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060137 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060138 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060139 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060140 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060141 | 102649 | Abc Lavpris Hovedkontor | 1095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060172 | 102649 | Abc Lavpris Hovedkontor | 1725 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060173 | 102649 | Abc Lavpris Hovedkontor | 1725 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060124 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060142 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060144 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060146 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060148 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060150 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060152 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060154 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060156 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060158 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060160 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060162 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060164 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060166 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060168 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060170 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060125 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060143 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060145 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060147 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060149 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060151 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060153 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060155 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060157 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060159 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060161 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060163 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060165 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060167 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060169 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060171 | 102649 | Abc Lavpris Hovedkontor | 282.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060174 | 102649 | Abc Lavpris Hovedkontor | 700 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060175 | 102649 | Abc Lavpris Hovedkontor | 700 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059887 | 103420 | ABENA A/S | 4282 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059289 | 104678 | ALD AUTOMOTIVE A/S | 2299 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C34301-1134736-01 | 104799-016 | Amgros I/S | 6500 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C34301-1134737-01 | 104799-016 | Amgros I/S | 176 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C34301-1134738-01 | 104799-016 | Amgros I/S | 1408 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-057059 | 97681 | Ap Pension Livsforsikringsaktieselskab | 13740.4 | Flemming Skovdal | Enterprise DK | New Sales | 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-060419 | 102713 | Associated Danish Ports A/S | 1505 | Kristijan Krsteski | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060420 | 102713 | Associated Danish Ports A/S | 387.5 | Kristijan Krsteski | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060421 | 102713 | Associated Danish Ports A/S | 387.5 | Kristijan Krsteski | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-055598 | 93020 | Associated Danish Ports A/S | 0 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30955-1136310-01 | 100991-073 | B4restore A/S | 5050 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-020463 | 103135 | Banedanmark | 1725 | Morten Skytte | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059935 | 103381 | Banedanmark | 945 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-030336 | 101218 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 1050 | Michael Kronbach Leth | Enterprise DK |  | 20250519: Delivered; 20250520: Delivered
NKA-058586 | 101218 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 525 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-030337 | 101218 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 0 | Michael Kronbach Leth | Enterprise DK |  | 20250519: Delivered; 20250520: Delivered
NML-058587 | 101218 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 525 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060415 | 104945 | BELFOR Denmark A/S | 1250 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060416 | 104945 | BELFOR Denmark A/S | 375 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060417 | 105008 | BELFOR Denmark A/S | 1250 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060418 | 105008 | BELFOR Denmark A/S | 375 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060469 | 105316 | Better Energy Management A/S | 784.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060470 | 105316 | Better Energy Management A/S | 784.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-053364 | 91356 | Billigblomst Adm. A/S | 725 | Merete Helme | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053382 | 91356 | Billigblomst Adm. A/S | 725 | Merete Helme | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-053365 | 91356 | Billigblomst Adm. A/S | 725 | Merete Helme | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NML-053383 | 91356 | Billigblomst Adm. A/S | 725 | Merete Helme | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-009209 | 102199 | Billund Kommune | 1000 | Eva Eisner | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-009222 | 102199 | Billund Kommune | 450 | Eva Eisner | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-031743 | 102199 | Billund Kommune | 450 | Eva Eisner | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-031744 | 102199 | Billund Kommune | 600 | Eva Eisner | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NSF-060740 | 100084 | Brøndby Kommune Rådhuset | 1025 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060741 | 100084 | Brøndby Kommune Rådhuset | 1275 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060742 | 100084 | Brøndby Kommune Rådhuset | 1525 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
F30256-1136218-01 | 100557-003 | Brønderslev Kommune | -4168.6167 | Shazia Mobin | Public DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35749-1135627-01 | 106556-011 | CHANGE OF SCANDINAVIA RETAIL A/S | 1050 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35749-1135628-01 | 106556-011 | CHANGE OF SCANDINAVIA RETAIL A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35749-1135630-01 | 106556-011 | CHANGE OF SCANDINAVIA RETAIL A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C30278-1132145-01 | 100575-033 | Coloplast A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060339 | 104731 | COOP DANMARK A/S | 417.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060340 | 104731 | COOP DANMARK A/S | 417.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-017579 | 104776 | COOP DANMARK A/S |  | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-018730 | 105012 | COOP DANMARK A/S |  | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060297 | 105064 | COOP DANMARK A/S | 417.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060298 | 105064 | COOP DANMARK A/S | 417.5 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-052043 | 105537 | COOP DANMARK A/S |  | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NBM-051854 | 105572 | COOP DANMARK A/S | 110.61 | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-018460 | 105582 | COOP DANMARK A/S | 475 | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NML-018461 | 105582 | COOP DANMARK A/S | 475 | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NBM-052208 | 93108 | COOP DANMARK A/S | 0 | Gunvor Pagh | Enterprise DK | New Sales
NKA-041909 | 97456 | COOP DANMARK A/S |  | Jeppe Mutinda Mbinda | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-037393 | 103582 | Dalgas a/s | 1480 | Andrew David Lindsey | Enterprise DK | Change
C36570-1132546-01 | 107531-002 | DAMCO Poland sp. z o.o. | 4879.75 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36570-1132548-01 | 107531-002 | DAMCO Poland sp. z o.o. | 2682 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36570-1132550-01 | 107531-002 | DAMCO Poland sp. z o.o. | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36570-1132551-01 | 107531-002 | DAMCO Poland sp. z o.o. | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-051845 | 92961 | DAN`X A/S | 14157 | Julie Lillethorup Kierkegaard | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-051846 | 92961 | DAN`X A/S | 11956.7 | Julie Lillethorup Kierkegaard | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-033906 | 92963 | DAN`X A/S | 0 | Andrew David Lindsey | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-033907 | 92963 | DAN`X A/S | 0 | Andrew David Lindsey | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-051475 | 92963 | DAN`X A/S | 1634 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-051476 | 92963 | DAN`X A/S | 1634 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NRS-051477 | 92963 | DAN`X A/S | 2203.2 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-051845 | 98820 | DAN`X A/S | -9403.94 | Julie Lillethorup Kierkegaard | Enterprise DK | Change | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-051846 | 98820 | DAN`X A/S | -7203.64 | Julie Lillethorup Kierkegaard | Enterprise DK | Change | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059736 | 103326 | Danepork A/S | 977.5 | Christoffer Møller Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059737 | 103326 | Danepork A/S | 977.5 | Christoffer Møller Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C32553-1135648-01 | 102892-008 | Dan-Foam ApS | -0.87333 | Shazia Mobin | Enterprise DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32553-1135649-01 | 102892-008 | Dan-Foam ApS | 518.2 | Shazia Mobin | Enterprise DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32553-1135650-01 | 102892-008 | Dan-Foam ApS | 0 | Shazia Mobin | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-048437 | 88343 | Danica Ejendomme P/S | 2012 | Jan Dibbern | Enterprise DK | New Sales
NKA-048438 | 88343 | Danica Ejendomme P/S | 2012 | Jan Dibbern | Enterprise DK | New Sales
NKA-059003 | 102835 | Danmarks Meteorologiske Institut | 350 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F30176-1129804-01 | 100489-187 | Danmarks Tekniske Universitet | 821 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1129806-01 | 100489-187 | Danmarks Tekniske Universitet | 85 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1129808-01 | 100489-187 | Danmarks Tekniske Universitet | 94 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1129810-01 | 100489-187 | Danmarks Tekniske Universitet | 85 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1129812-01 | 100489-187 | Danmarks Tekniske Universitet | 146 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130153-01 | 100489-188 | Danmarks Tekniske Universitet | 638 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130598-01 | 100489-189 | Danmarks Tekniske Universitet | 629 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130600-01 | 100489-189 | Danmarks Tekniske Universitet | 92 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130602-01 | 100489-189 | Danmarks Tekniske Universitet | 96 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130604-01 | 100489-189 | Danmarks Tekniske Universitet | 85 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1130606-01 | 100489-189 | Danmarks Tekniske Universitet | 163 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1134864-01 | 100489-192 | Danmarks Tekniske Universitet | 117 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1135247-01 | 100489-195 | Danmarks Tekniske Universitet | 283 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F30176-1136654-01 | 100489-196 | Danmarks Tekniske Universitet | 188 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060072 | 104609 | Danpilot Svendborg | 475 | Eva Eisner | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058161 | 101097 | DANSK AVIS OMDELING A/S | 540 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-058162 | 101097 | DANSK AVIS OMDELING A/S | 540 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060488 | 103525 | DANSK AVIS OMDELING A/S | 2495 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060489 | 103525 | DANSK AVIS OMDELING A/S | 2495 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060490 | 103525 | DANSK AVIS OMDELING A/S | 1995 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060491 | 103525 | DANSK AVIS OMDELING A/S | 1995 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060492 | 103525 | DANSK AVIS OMDELING A/S | 2520 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060493 | 103525 | DANSK AVIS OMDELING A/S | 2520 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060494 | 103525 | DANSK AVIS OMDELING A/S | 2520 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060495 | 103525 | DANSK AVIS OMDELING A/S | 2520 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060496 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060497 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060498 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060499 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060500 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060501 | 103525 | DANSK AVIS OMDELING A/S | 1372.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-058841 | 102685 | Dansk Brand- og sikringsteknisk Institut | 2472.5 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NOC-997185 | 102685 | Dansk Brand- og sikringsteknisk Institut |  | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F31427-1136260-01 | 101461-008 | Dansk Cater A/S | 4275 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F31427-1136262-01 | 101461-008 | Dansk Cater A/S | 4575 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-057824 | 100785 | Dansk Retursystem A/S | 2091 | Peter Madsen | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-057825 | 100785 | Dansk Retursystem A/S | 2091 | Peter Madsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F31073-1125802-01 | 101109-042 | Danske Commodities A/S | 4500 | Camilla Olesen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F31073-1125804-01 | 101109-042 | Danske Commodities A/S | 4600 | Camilla Olesen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F31073-1125806-01 | 101109-042 | Danske Commodities A/S | 3900 | Camilla Olesen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F31073-1125808-01 | 101109-042 | Danske Commodities A/S | 4000 | Camilla Olesen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31073-1136532-01 | 101109-053 | Danske Commodities A/S | 1600 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C31073-1136533-01 | 101109-053 | Danske Commodities A/S | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NDD-058082 | 100670 | Danske Olieberedskabslagre | 1495 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NDD-058083 | 100670 | Danske Olieberedskabslagre | 1495 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-058049 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058057 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058061 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-058063 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-058075 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-058048 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-058056 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-058060 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-058062 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-058074 | 100670 | Danske Olieberedskabslagre | 837 | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-058049 | 103254 | Danske Olieberedskabslagre | -777 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058057 | 103254 | Danske Olieberedskabslagre | -777 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058061 | 103254 | Danske Olieberedskabslagre | -777 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-058063 | 103254 | Danske Olieberedskabslagre | -777 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-058069 | 103254 | Danske Olieberedskabslagre | -1439 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-058075 | 103254 | Danske Olieberedskabslagre | 60 | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059983 | 103254 | Danske Olieberedskabslagre | 955 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NML-059982 | 103254 | Danske Olieberedskabslagre | 955 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-058075 | 105234 | Danske Olieberedskabslagre |  | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058075 | 105246 | Danske Olieberedskabslagre | 787 | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: Delivered; 20250520: Delivered
NML-058074 | 105246 | Danske Olieberedskabslagre | 787 | Nanna Søndergaard Skov | Enterprise DK |  | 20250519: Delivered; 20250520: Delivered
NKA-055297 | 97337 | Deichmann Sko AB | 680 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055333 | 97337 | Deichmann Sko AB | 680 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055299 | 97337 | Deichmann Sko AB | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055335 | 97337 | Deichmann Sko AB | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055298 | 97337 | Deichmann Sko AB | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055334 | 97337 | Deichmann Sko AB | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055384 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055408 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055426 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055429 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055435 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055447 | 97347 | Deichmann-Sko ApS | 720 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055385 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055409 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055421 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-055427 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055430 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055436 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-055448 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055386 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055410 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055422 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-055428 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055431 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055437 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-055449 | 97347 | Deichmann-Sko ApS | 50 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059646 | 103177 | DGI | 900 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-060057 | 102543 | DI | 4620 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060058 | 102543 | DI | 4620 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060447 | 104919 | Diningsix A/S | 900 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059765 | 102480 | DLF Seeds A/S | 625 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NML-059766 | 102480 | DLF Seeds A/S | 625 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NII-060186 | 103016 | Dovista A/S | 2821 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060187 | 103016 | Dovista A/S | 2821 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060188 | 103016 | Dovista A/S | 5956 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060189 | 103016 | Dovista A/S | 5956 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060190 | 103016 | Dovista A/S | 5655 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060191 | 103016 | Dovista A/S | 5655 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060192 | 103016 | Dovista A/S | 5581 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060193 | 103016 | Dovista A/S | 5581 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060194 | 103016 | Dovista A/S | 3428 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060195 | 103016 | Dovista A/S | 3428 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060196 | 103016 | Dovista A/S | 3361.5 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060197 | 103016 | Dovista A/S | 3361.5 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060198 | 103016 | Dovista A/S | 5581 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060199 | 103016 | Dovista A/S | 5581 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060200 | 104664 | Dovista A/S | 4149 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-060201 | 104664 | Dovista A/S | 4149 | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30752-1120913-01 | 100789-076 | DSV A/S | 0 | Kasper Bruun Nielsen | Enterprise DK | New Sales
C30752-1131765-01 | 100789-085 | DSV A/S | 1600 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Delivered; 20250521: Delivered
C30752-1131767-01 | 100789-085 | DSV A/S | 1600 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Delivered; 20250521: Delivered
C30752-1131769-01 | 100789-085 | DSV A/S | 900 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 7. Service activation; 20250521: 7. Service activation
C30752-1131770-01 | 100789-085 | DSV A/S | 96 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 7. Service activation; 20250521: 7. Service activation
C30752-1136045-01 | 100789-088 | DSV A/S | 1050 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C30752-1136046-01 | 100789-088 | DSV A/S | 60 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060542 | 102414 | Elis Danmark A/S | 670 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060544 | 102414 | Elis Danmark A/S | 585 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060543 | 102414 | Elis Danmark A/S | 670 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060545 | 102414 | Elis Danmark A/S | 585 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044170 | 102414 | Elis Danmark A/S | -122.8 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044175 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044178 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044181 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044183 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044186 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044189 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044195 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044197 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044203 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044206 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044209 | 102414 | Elis Danmark A/S | -101.2 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044212 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044215 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044218 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044221 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044226 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-044229 | 102414 | Elis Danmark A/S | 850 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-046860 | 102414 | Elis Danmark A/S | -90 | Kristijan Krsteski | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060546 | 102414 | Elis Danmark A/S | 470 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060412 | 105207 | ENTERTAINMENT TRADING A/S | 1320 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NMA-060414 | 105207 | ENTERTAINMENT TRADING A/S | 387.5 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NSW-060413 | 105207 | ENTERTAINMENT TRADING A/S | 387.5 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-059755 | 103432 | European Energy A/S | 999 | Merete Helme | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-055965 | 97899 | European Energy A/S | 999 | Merete Helme | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055062 | 96513 | Fiftytwo A/S | 1650 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055063 | 96513 | Fiftytwo A/S | 1650 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060444 | 102960 | FLAMMEN A/S | 697.5 | Merete Helme | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060445 | 102960 | FLAMMEN A/S | 697.5 | Merete Helme | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-054774 | 93857 | Fleggaard It ApS | 1495 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-054775 | 93857 | Fleggaard It ApS | 1295 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-054776 | 93857 | Fleggaard It ApS | 1495 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058793 | 96792 | FLSMIDTH A/S | 2037 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058794 | 96792 | FLSMIDTH A/S | 2037 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059764 | 103456 | FOA Fag og Arbejde | 1586 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059241 | 98150 | FOA Fag og Arbejde | 4130 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NOC-997378 | 98150 | FOA Fag og Arbejde | -1846.86 | Andrew David Lindsey | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059243 | 98150 | FOA Fag og Arbejde | 1775 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-059244 | 98150 | FOA Fag og Arbejde | 1775 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056204 | 98346 | Foss Analytical A/S | 7100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-056205 | 98346 | Foss Analytical A/S | 7100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060669 | 103003 | FRELSENS HÆR SOCIALTJENESTEN | 1195 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060620 | 105079 | Frode Laursen A/S | 3995 | Andrew David Lindsey | Enterprise DK | New Sales
NKA-023538 | 89081 | Frode Laursen A/S | 4500 | Peter Madsen | Enterprise DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-033837 | 89081 | Frode Laursen A/S | 2500 | Peter Madsen | Enterprise DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NOC-998343 | 89081 | Frode Laursen A/S | 6000 | Peter Madsen | Enterprise DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NOC-998373 | 89081 | Frode Laursen A/S | 4000 | Peter Madsen | Enterprise DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-059759 | 103151 | GENERAL LOGISTICS SYSTEMS DENMARK A/S | 1760 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035592 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035593 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035594 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035595 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035596 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035599 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035600 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035601 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035602 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035603 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035604 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035605 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035606 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035607 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035608 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035609 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035610 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035611 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035612 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035613 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035614 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035615 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035616 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035617 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035618 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035620 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035622 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035625 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035626 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035627 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035628 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035631 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035632 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035633 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035634 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035635 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035636 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035637 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035638 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035640 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035641 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035642 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035644 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035645 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035646 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035647 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035648 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035649 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035650 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035651 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035652 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035653 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035654 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035655 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035656 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035658 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035659 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035660 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035661 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035662 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035663 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035664 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035665 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035666 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035667 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035668 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035669 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-035670 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration
NKA-035671 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035672 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035674 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035676 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035678 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035679 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035680 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035681 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035682 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035683 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035685 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035686 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035687 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035688 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035690 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035691 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035692 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035694 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035695 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035696 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035697 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035699 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035700 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035701 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035702 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035703 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035704 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035705 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035706 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035707 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035708 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035710 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035711 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035712 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035713 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035714 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035715 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035716 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035718 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035719 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035720 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035721 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035722 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035723 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035724 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035725 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035726 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035727 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035728 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035729 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035730 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035731 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035732 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035733 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035736 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035737 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035739 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035740 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035741 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035742 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035743 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035745 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035747 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035748 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035751 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035752 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035753 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035758 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035759 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035760 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035766 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035768 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035770 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035771 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035776 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035778 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035779 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035782 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035785 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035786 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035787 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035792 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035793 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035794 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035796 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-035797 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-035798 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-037694 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-038185 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-043334 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-043926 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-050668 | 102771 | GENTOFTE KOMMUNE | 0 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NBM-058822 | 102537 | Give Uddannelsescenter | 6048.86 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-058823 | 102537 | Give Uddannelsescenter | 1887.84 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-058824 | 102537 | Give Uddannelsescenter | 2257.71 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-060251 | 104905 | Give Uddannelsescenter | 1680.02 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-056919 | 100034 | Glostrup Kommune | 550 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-056921 | 100034 | Glostrup Kommune | 227.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-056920 | 100034 | Glostrup Kommune | 227.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-041535 | 105649 | Glostrup Kommune |  | Morten Skytte | Public DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-033744 | 105041 | Guldborgsund Kommune | 25 | Morten Skytte | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060502 | 105144 | Guldborgsund Kommune | 300 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060720 | 105648 | Guldborgsund Kommune | 300 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060721 | 105648 | Guldborgsund Kommune | 300 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050356 | 89321 | Haderslev kommune | 950 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-050357 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050369 | 89321 | Haderslev kommune | 1400 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-050376 | 89321 | Haderslev kommune | 1400 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-050381 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050382 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050383 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050384 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050385 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050386 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050387 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050388 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050389 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050390 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050395 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050396 | 89321 | Haderslev kommune | 475 | Morten Skytte | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-050350 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050355 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050356 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050357 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050369 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050374 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050376 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050377 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050381 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050382 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050383 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050384 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050385 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050386 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050387 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050388 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050389 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050390 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050395 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050396 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-050397 | 89440 | Haderslev kommune | 40 | Morten Skytte | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-060682 | 105673 | Halberg A/S | 1050 | Andrew David Lindsey | Enterprise DK | New Sales
NCI-058640 | 102376 | Harboes Bryggeri A/S | 0 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NSW-058639 | 102376 | Harboes Bryggeri A/S | 0 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-056499 | 98586 | Harboes Bryggeri A/S | 4950 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056501 | 98586 | Harboes Bryggeri A/S | 7600 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056503 | 98586 | Harboes Bryggeri A/S | 1450 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-056505 | 98586 | Harboes Bryggeri A/S | 2095 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NSW-056498 | 98586 | Harboes Bryggeri A/S | 1370 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-056500 | 98586 | Harboes Bryggeri A/S | 1680 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-056502 | 98586 | Harboes Bryggeri A/S | 840 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NSW-056504 | 98586 | Harboes Bryggeri A/S | 2670 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-058108 | 101434 | Hempel Fonden | 900 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-058110 | 101434 | Hempel Fonden | 200 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-058109 | 101434 | Hempel Fonden | 200 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-001283 | 102088 | Herningsholm Erhvervsskole & Gymnasier S/I |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-055508 | 102088 | Herningsholm Erhvervsskole & Gymnasier S/I |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-001283 | 103011 | Herningsholm Erhvervsskole & Gymnasier S/I |  | Michael Kronbach Leth | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-042377 | 103011 | Herningsholm Erhvervsskole & Gymnasier S/I | 720 | Michael Kronbach Leth | Public DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060067 | 103011 | Herningsholm Erhvervsskole & Gymnasier S/I | 845 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060068 | 103011 | Herningsholm Erhvervsskole & Gymnasier S/I | 845 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060069 | 103011 | Herningsholm Erhvervsskole & Gymnasier S/I | 845 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-001283 | 88766 | Herningsholm Erhvervsskole & Gymnasier S/I | 6000 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059846 | 104285 | Hi Five A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NDD-060179 | 104814 | Hillerød Kommune | 3238.5 | Morten Skytte | Public DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service
NKA-060178 | 104814 | Hillerød Kommune | 3238.5 | Morten Skytte | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
NKA-006159 | 101158 | Hjørring Gymnasium og HF-Kursus | 1725 | Morten Skytte | Public DK | Change | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NDD-059699 | 102177 | HKScan Denmark A/S | 5995 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-059700 | 102177 | HKScan Denmark A/S | 5995 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-059703 | 102177 | HKScan Denmark A/S | 1495 | Peter Madsen | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NDD-059704 | 102177 | HKScan Denmark A/S | 1495 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-051377 | 102177 | HKScan Denmark A/S | -61.64 | Peter Madsen | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059698 | 102177 | HKScan Denmark A/S | 1450 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NOC-996874 | 102177 | HKScan Denmark A/S | -1480.8 | Peter Madsen | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NOC-995822 | 103075 | Hoffmann A/S | 0 | Peter Madsen | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NOC-995895 | 103075 | Hoffmann A/S | 0 | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057346 | 100303 | Horsens kommune | 400 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NSW-057347 | 100303 | Horsens kommune | 325 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-057346 | 100321 | Horsens kommune |  | Morten Skytte | Public DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060203 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060204 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060205 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060206 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060207 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060208 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1230 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060209 | 103188 | HUSCOMPAGNIET HOLDING A/S | 5723 | Peter Madsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060210 | 103188 | HUSCOMPAGNIET HOLDING A/S | 5723 | Peter Madsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060212 | 103188 | HUSCOMPAGNIET HOLDING A/S | 299.5 | Peter Madsen | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060213 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1360 | Peter Madsen | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060214 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1500 | Peter Madsen | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060215 | 103188 | HUSCOMPAGNIET HOLDING A/S | 1660 | Peter Madsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NML-060211 | 103188 | HUSCOMPAGNIET HOLDING A/S | 299.5 | Peter Madsen | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060559 | 105286 | HUSCOMPAGNIET HOLDING A/S |  | Peter Madsen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-048925 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048931 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048933 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048935 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048937 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048939 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-048947 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-053054 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-053055 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-056750 | 103060 | I/S VESTFORBRÆNDING |  | Michael Kronbach Leth | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060023 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060025 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060027 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060024 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060026 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060028 | 104556 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060375 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060377 | 104579 | I/S VESTFORBRÆNDING | 475 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060378 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060380 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060382 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060384 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060376 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060379 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060381 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060383 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060385 | 104579 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-048922 | 88172 | I/S VESTFORBRÆNDING | 475 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-048939 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-048943 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-048940 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-048944 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F36205-1130134-01 | 107101-006 | INFRASTRUKTURSELSKABET LJ A/S | 93.75 | Mette Vinther | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-046566 | 105498 | It-Forsyningen I/S | 350 | Morten Skytte | Public DK | Change
NKA-057361 | 100796 | Jem & Fix A/S | 1038 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-058314 | 101288 | Jem & Fix A/S | 1038 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059840 | 103386 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059841 | 103386 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059866 | 104367 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060462 | 105311 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060463 | 105311 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060464 | 105311 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-048998 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-049011 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-049014 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-049085 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-049100 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-049106 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-049113 | 88683 | Jem & Fix A/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-049100 | 97729 | Jem & Fix A/S | 0 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-049113 | 97729 | Jem & Fix A/S | 0 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060581 | 102816 | Johs. Rasmussen, Svebølle A/S | 1650 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060580 | 102816 | Johs. Rasmussen, Svebølle A/S | 200 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NOC-997751 | 102816 | Johs. Rasmussen, Svebølle A/S | -285.8 | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36587-1135566-01 | 107550-009 | Jysk A/S | 5450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36587-1135568-01 | 107550-009 | Jysk A/S | 5934 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-049663 | 89637 | Jysk CTS A/S | 1308 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
B31457-1136860-01 | 101491-013 | Jyske Bank A/S | 599.94 | Shazia Mobin | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
B31457-1136861-01 | 101491-013 | Jyske Bank A/S | 0 | Shazia Mobin | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
B31457-1136862-01 | 101491-013 | Jyske Bank A/S | 0 | Shazia Mobin | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
B31457-1136863-01 | 101491-013 | Jyske Bank A/S | 0 | Shazia Mobin | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C31457-1136865-01 | 101491-013 | Jyske Bank A/S | -160.0133 | Shazia Mobin | Enterprise DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C31457-1136866-01 | 101491-013 | Jyske Bank A/S | 60 | Shazia Mobin | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-023151 | 93742 | Kalundborg kommune | 550 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001355 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001357 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001358 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001361 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001362 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001364 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001365 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001368 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001369 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001370 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001371 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001372 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001374 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001375 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001376 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001377 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001378 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-004657 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-004681 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-005732 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-005733 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-007073 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-008423 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-008678 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-015322 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-015571 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-015572 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-015573 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-016769 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-019741 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-020063 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-021079 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-021361 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-021785 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022148 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022164 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022346 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022777 | 94451 | Kalundborg kommune | 25 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022923 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-022946 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-023066 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-023116 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-023151 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-023194 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-024172 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-027189 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-028218 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-028441 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-034959 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-034973 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-044605 | 94451 | Kalundborg kommune | 650 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-004657 | 96656 | Kalundborg kommune | 950 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-058039 | 96128 | Kilroy International A/S | 2500 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058040 | 96128 | Kilroy International A/S | 2500 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060226 | 103535 | Kk Wind Solutions A/S | 1760 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-003429 | 82944 | Kolding Kommune Rådhuset | 560 | Michael Kronbach Leth | Public DK
NKA-029266 | 90629 | KPMG ACOR TAX PARTNERSELSKAB | -641.03 | Nanna Søndergaard Skov | Enterprise DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-050904 | 90629 | KPMG ACOR TAX PARTNERSELSKAB | 3366 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-056733 | 94179 | Kromann Reumert |  | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056734 | 94179 | Kromann Reumert |  | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-056737 | 98424 | Kromann Reumert | 522 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-056738 | 98424 | Kromann Reumert | 522 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056733 | 98424 | Kromann Reumert | 2720 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056734 | 98424 | Kromann Reumert | 2720 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-058420 | 101858 | Københavns Kommune | 11732.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-058422 | 101858 | Københavns Kommune | 11732.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058419 | 101858 | Københavns Kommune | 11732.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058421 | 101858 | Københavns Kommune | 11732.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058423 | 101858 | Københavns Kommune | 12015 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058424 | 101858 | Københavns Kommune | 12015 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058425 | 101858 | Københavns Kommune | 4140 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058426 | 101858 | Københavns Kommune | 4140 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058550 | 101913 | Københavns Kommune | 1070 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059158 | 102441 | Københavns Kommune | 415 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060367 | 105122 | Københavns Kommune | 490 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060435 | 105194 | Københavns Kommune | 490 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-023580 | 105737 | Københavns Kommune | 960 | Jane Birgitte Høgaard | Public DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-045993 | 84112 | Københavns Kommune | 550 | Michael Kronbach Leth | Public DK | New Sales
NKA-055121 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055125 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055126 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055128 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055134 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055135 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055137 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055138 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055143 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055144 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055145 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055146 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055147 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055148 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055149 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055150 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055151 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055153 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055156 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055159 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055160 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055161 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055165 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055168 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order
NKA-055170 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055172 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055173 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055174 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055175 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055176 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055177 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055178 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055179 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055181 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055182 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055184 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055185 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055187 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055188 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055189 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055191 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055193 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055194 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055195 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales
NKA-055196 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055197 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055198 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055199 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055201 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055202 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055203 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055204 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055206 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055207 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055208 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055212 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055215 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055216 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055217 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055218 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055219 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055220 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055221 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055222 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055224 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055225 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055226 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055227 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055228 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055229 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055230 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055232 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055233 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055234 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055239 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055240 | 97026 | Københavns Kommune | 1270 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055243 | 97026 | Københavns Kommune | 12450 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055244 | 97026 | Københavns Kommune | 12450 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055245 | 97026 | Københavns Kommune | 12300 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-055246 | 97026 | Københavns Kommune | 12300 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NBM-060528 | 105224 | Lagkagehuset A/S | 288.56 | Flemming Skovdal | Enterprise DK | New Sales | 20250520: Delivered
C31408-1131198-01 | 101442-031 | LEGO System A/S | -528 | Henrik Møller Fyhn | Enterprise DK | Change | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31408-1133379-01 | 101442-033 | LEGO System A/S | 1100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31408-1133380-01 | 101442-033 | LEGO System A/S | 176 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31408-1133382-01 | 101442-033 | LEGO System A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31408-1133383-01 | 101442-033 | LEGO System A/S | 1100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
C31408-1133385-01 | 101442-033 | LEGO System A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-058938 | 102732 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-058939 | 102732 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NGF-059283 | 102865 | Lidl Danmark K/S | 1750 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NDD-059641 | 102937 | Lidl Danmark K/S | 1815 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059307 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059308 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059309 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059310 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059311 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059312 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059313 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059314 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059315 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059316 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059317 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059318 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059319 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059320 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059321 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059322 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059323 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059324 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059325 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059326 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059327 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059328 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059329 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059330 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059331 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059332 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059333 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning
NKA-059334 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059335 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059336 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059337 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059338 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059339 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059340 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059341 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059342 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059343 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059344 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059345 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059346 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059347 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059348 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059349 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059350 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059351 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059352 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059353 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059354 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059355 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059356 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059357 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059358 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059359 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059360 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059361 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059362 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059363 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059364 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059365 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059366 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059367 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059368 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059369 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059370 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059371 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059372 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059373 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059374 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059375 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059376 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059377 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059378 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059379 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059380 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059381 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059382 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059383 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059384 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059385 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059386 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059387 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059388 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059389 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059390 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059391 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059392 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059393 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059394 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059395 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059396 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059397 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059398 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059399 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059400 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059401 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059402 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059403 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059404 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059405 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059406 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059407 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059408 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059409 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059410 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059411 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059412 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059413 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059414 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059415 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059416 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059417 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059418 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059419 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059420 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059421 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059422 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059423 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059424 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059425 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059426 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059427 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059428 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059429 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059430 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059431 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059432 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059433 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059434 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059435 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059436 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059437 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059438 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059439 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059440 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059441 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059442 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059443 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059444 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059445 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059446 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059447 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059448 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059449 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059450 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059451 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059452 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059453 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059454 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059455 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059456 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059457 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059458 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059459 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059460 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059461 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059462 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059463 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059464 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059465 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059466 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059467 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059468 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059469 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059470 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059471 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059472 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059473 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059474 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059475 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059476 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059477 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059478 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059479 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059480 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059481 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059482 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059483 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059484 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059485 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059486 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059487 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059488 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059489 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059490 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059491 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059492 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059493 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059494 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059495 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059496 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059497 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059498 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059499 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059500 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059501 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059502 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059503 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059504 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059505 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059506 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059507 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059508 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059509 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059510 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059511 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059512 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059513 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059514 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059515 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059516 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059517 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059518 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059519 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059520 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059521 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059522 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059523 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059524 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059525 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059526 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059527 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059528 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059529 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059530 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059531 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059532 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059533 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059534 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059535 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059536 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059537 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059538 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059539 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059540 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059541 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059542 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059543 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059544 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059545 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059546 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059547 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059548 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059549 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059550 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059551 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059552 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059553 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059554 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059555 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059556 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059557 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059558 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059559 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059560 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059561 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059562 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059563 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059564 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059565 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059566 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059567 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059568 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059569 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059570 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059571 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059572 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059573 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059574 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059575 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059576 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059577 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059578 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059579 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059580 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059581 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059582 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059583 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059584 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059585 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059586 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059587 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059588 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059589 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059590 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059591 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059592 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059593 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059594 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059595 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059596 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059597 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059598 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059599 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059600 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059601 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059602 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059603 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059604 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059605 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059606 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059607 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059608 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059609 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059610 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059611 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059612 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059613 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059614 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059617 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059618 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059619 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059620 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059621 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059622 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059623 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059624 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059625 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059626 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059627 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059628 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059629 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059630 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059631 | 102937 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059632 | 102937 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059635 | 102937 | Lidl Danmark K/S | 1800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-059636 | 102937 | Lidl Danmark K/S | 1800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-060548 | 105410 | Lidl Danmark K/S | 850 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-060549 | 105410 | Lidl Danmark K/S | 800 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-044433 | 105384 | Light Brick A/S | 1355 | Andrew David Lindsey | Enterprise DK | Change | 20250519: On Track; 20250520: On Track; 20250521: On Track
C31138-1130914-01 | 101174-010 | Lokaltog A/S | 1250 | Camilla Villumsen Kaimer | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31138-1130918-01 | 101174-010 | Lokaltog A/S | 1400 | Camilla Villumsen Kaimer | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31138-1130920-01 | 101174-010 | Lokaltog A/S | 0 | Camilla Villumsen Kaimer | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
C31138-1130921-01 | 101174-010 | Lokaltog A/S | 0 | Camilla Villumsen Kaimer | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060342 | 104921 | Lundsøe Køl & Frys A/S | 1395 | Line Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 8. Ready for service; 20250521: 8. Ready for service
C36565-1135209-01 | 107525-005 | MAERSK A/S | 2835 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36565-1135211-01 | 107525-005 | MAERSK A/S | 4200 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060667 | 105620 | Meyers A/S | 1000 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-059995 | 104668 | Molslinjen A/S | 2140 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060249 | 104526 | Munck Havne & Anlæg A/S | 1452 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-006801 | 79364 | Næstved Kommune | -982.5 | Natascha Orlung Baisgaard Andersen | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-007204 | 79364 | Næstved Kommune | -982.5 | Natascha Orlung Baisgaard Andersen | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSW-041184 | 79364 | Næstved Kommune | 650 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSW-041185 | 79364 | Næstved Kommune | 650 | Natascha Orlung Baisgaard Andersen | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-056844 | 98152 | Nagel Danmark A/S | 1237 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056845 | 98152 | Nagel Danmark A/S | 1237 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136120-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136122-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136124-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136126-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136128-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33271-1136130-01 | 103690-003 | Naviair | 1255 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31083-1135942-01 | 101119-042 | NCC Danmark A/S | 1700 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C31083-1135943-01 | 101119-042 | NCC Danmark A/S | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C31009-1133207-01 | 101045-063 | Nets Danmark A/S | 3950 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133208-01 | 101045-063 | Nets Danmark A/S | 3950 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133210-01 | 101045-063 | Nets Danmark A/S | 5850 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133211-01 | 101045-063 | Nets Danmark A/S | 5850 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133213-01 | 101045-063 | Nets Danmark A/S | 3950 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133215-01 | 101045-063 | Nets Danmark A/S | 3950 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133291-01 | 101045-064 | Nets Danmark A/S | -276.7733 | Henrik Møller Fyhn | Enterprise DK | Change | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133293-01 | 101045-064 | Nets Danmark A/S | -206.7167 | Henrik Møller Fyhn | Enterprise DK | Change | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31009-1133295-01 | 101045-064 | Nets Danmark A/S | -206.7167 | Henrik Møller Fyhn | Enterprise DK | Change | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C35716-1135836-01 | 106520-010 | NIC. CHRISTIANSEN GRUPPEN A/S | 4900 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35716-1135838-01 | 106520-010 | NIC. CHRISTIANSEN GRUPPEN A/S | 4900 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-057331 | 100351 | NIRAS A/S | 3025 | Andrew David Lindsey | Enterprise DK | New Sales
NKA-057332 | 100351 | NIRAS A/S | 3025 | Andrew David Lindsey | Enterprise DK | New Sales
NOC-997145 | 102343 | Norconsult Danmark A/S | 1500 | Peter Madsen | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-022194 | 77244 | Norddjurs Kommune | 400 | Morten Skytte | Public DK
NKA-022216 | 77244 | Norddjurs Kommune | 3149.11 | Morten Skytte | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation
NKA-022217 | 77244 | Norddjurs Kommune | -3400 | Morten Skytte | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation
NKA-027063 | 77244 | Norddjurs Kommune | 457.5 | Morten Skytte | Public DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-039758 | 77244 | Norddjurs Kommune | 325 | Morten Skytte | Public DK
NSW-039804 | 77244 | Norddjurs Kommune | 455 | Morten Skytte | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-047419 | 87005 | Norddjurs Kommune | 30 | Morten Skytte | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-057421 | 104653 | Nordstern ApS | -19882.52 | Natascha Orlung Baisgaard Andersen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060630 | 105629 | Normal A/S | 765 | Peter Madsen | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NDD-057468 | 100573 | NOVO NORDISK A/S | 1050 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-057467 | 100573 | NOVO NORDISK A/S | 1050 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-046207 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-046208 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-046263 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-046264 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-047446 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-047447 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-047864 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-047865 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-051434 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-051435 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-052794 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-052796 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053331 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053332 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053336 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053337 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053465 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053467 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053469 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-053470 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-054177 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-054178 | 102134 | NOVO NORDISK A/S |  | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NDD-059037 | 102632 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NDD-059038 | 102632 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059035 | 102632 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059036 | 102632 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSF-059181 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059182 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059183 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059184 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059185 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059186 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059187 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059188 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059189 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059190 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059191 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059192 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059193 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059194 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059195 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059196 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059197 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059198 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059199 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059200 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059201 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059202 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059203 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059204 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059205 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059206 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059207 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059208 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059209 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059210 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059211 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059212 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059213 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059214 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059215 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSF-059216 | 102754 | NOVO NORDISK A/S | 450 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-059734 | 103433 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NDD-059735 | 103433 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-059732 | 103433 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-059733 | 103433 | NOVO NORDISK A/S | 4525 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
F33710-1123338-01 | 104162-014 | NOVO NORDISK A/S | 4308 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-053971 | 95116 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-053970 | 95116 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-051424 | 96292 | NOVO NORDISK A/S | 0 | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-057882 | 96292 | NOVO NORDISK A/S | 500 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-051423 | 96292 | NOVO NORDISK A/S | 0 | Henrik Møller Fyhn | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-057881 | 96292 | NOVO NORDISK A/S | 1895 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-054872 | 96443 | NOVO NORDISK A/S | 2000 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-054873 | 96443 | NOVO NORDISK A/S | 2000 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-054870 | 96443 | NOVO NORDISK A/S | 7100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-054871 | 96443 | NOVO NORDISK A/S | 7100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-056001 | 98339 | NOVO NORDISK A/S | 1185 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NDD-057021 | 98917 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-057022 | 98917 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057019 | 98917 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057020 | 98917 | NOVO NORDISK A/S | 4550 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
F33253-1136084-01 | 103672-023 | Novozymes A/S | 1596 | Shazia Mobin | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F33253-1136086-01 | 103672-023 | Novozymes A/S | 2047 | Shazia Mobin | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059045 | 102906 | Nymølle Stenindustrier A/S | 329.5 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NML-059044 | 102906 | Nymølle Stenindustrier A/S | 329.5 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-060274 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060276 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060278 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060280 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060282 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060284 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060286 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060288 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060290 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060292 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060294 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060275 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060277 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060279 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060281 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NML-060283 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060285 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060287 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060289 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060291 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060293 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060295 | 103570 | Q-Park Operations Denmark A/S | 700 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C30130-1136192-01 | 100464-018 | Region Midtjylland | -1091.3833 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
F30130-1136190-01 | 100464-018 | Region Midtjylland | 0 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-052964 | 92989 | Region Sjælland | 4750 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30693-1109649-01 | 100730-063 | Region Syddanmark | 29500 | Michael Kronbach Leth | Public DK | New Sales
C30693-1109650-01 | 100730-063 | Region Syddanmark | 29500 | Michael Kronbach Leth | Public DK | New Sales
C30693-1134744-01 | 100730-079 | Region Syddanmark | 8490 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30693-1134746-01 | 100730-079 | Region Syddanmark | 8490 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060524 | 105413 | Region Syddanmark | 332 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35135-1136336-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136337-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136338-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136339-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136340-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136341-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136342-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136343-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136344-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136345-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136346-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136347-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136348-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136349-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136350-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136351-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136352-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136353-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136354-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C35135-1136355-01 | 105762-006 | Rigspolitiet | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
NKA-001880 | 102148 | Roskilde Kommune | 3350 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-019998 | 102148 | Roskilde Kommune | 3200 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060649 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060650 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060651 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060652 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060653 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060654 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060655 | 105266 | Røverkøb A/S | 1199 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060656 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060657 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060658 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060659 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060660 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060661 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060662 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060663 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060664 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060665 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-060666 | 105266 | Røverkøb A/S | 669 | Michael Kronbach Leth | Enterprise DK | New Sales
NKA-043240 | 105439 | Samsøe & Samsøe Whole Sale ApS |  | Jane Birgitte Høgaard | Enterprise DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-042995 | 80781 | Samsøe & Samsøe Whole Sale ApS | 6710 | Jane Birgitte Høgaard | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055088 | 97292 | Samsøe & Samsøe Whole Sale ApS | 5050 | Jane Birgitte Høgaard | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-055099 | 97335 | Samsøe & Samsøe Whole Sale ApS | 4125 | Jane Birgitte Høgaard | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35697-1136317-01 | 106496-012 | Schou Company A/S | 1850 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
C35697-1136318-01 | 106496-012 | Schou Company A/S | 60 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
C35697-1136320-01 | 106496-012 | Schou Company A/S | 1850 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-052897 | 93136 | SDI Media A/S | 750 | Merete Helme | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058912 | 101823 | Semco Maritime A/S | 2600 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056039 | 93328 | Semco Maritime A/S | 1950 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056041 | 93328 | Semco Maritime A/S | 1100 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056043 | 93328 | Semco Maritime A/S | 1500 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056051 | 93328 | Semco Maritime A/S | 4400 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056053 | 93328 | Semco Maritime A/S | 3080 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: Cancelled; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-056054 | 93328 | Semco Maritime A/S | 3080 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056055 | 93328 | Semco Maritime A/S | 3080 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057799 | 100219 | Skanderborg Kommune | 2375 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-057798 | 100962 | Skanderborg Kommune | 2375 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NBM-055817 | 97750 | Sluseholmen 7 A/S | 11130 | Flemming Skovdal | Enterprise DK | New Sales | 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-055818 | 97750 | Sluseholmen 7 A/S | 1675 | Flemming Skovdal | Enterprise DK | New Sales | 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-060243 | 104666 | Sol og Strand Feriehusudlejning A/S | 1428 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060242 | 104666 | Sol og Strand Feriehusudlejning A/S | 275 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060241 | 104666 | Sol og Strand Feriehusudlejning A/S | 275 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060021 | 104712 | Sol og Strand Feriehusudlejning A/S | 1350 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-060020 | 104712 | Sol og Strand Feriehusudlejning A/S | 275 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060019 | 104712 | Sol og Strand Feriehusudlejning A/S | 275 | Signe Fogh Mach Andersen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059916 | 103691 | SOLAR A/S | 1350 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-059917 | 103691 | SOLAR A/S | 710 | Kristijan Krsteski | Enterprise DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
F30221-1136761-01 | 100525-117 | Spar Nord Bank A/S | 0 | Camilla Olesen | Enterprise DK | Change
NBM-059303 | 103085 | Staten og Kommunernes Indkøbsservice A/S | 1773 | Kristijan Krsteski | Public DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-058786 | 102515 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060364 | 102921 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059157 | 102971 | Statens IT | 3125 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059898 | 103149 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NGF-060061 | 103184 | Statens IT | 7237.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-060062 | 103184 | Statens IT | 7237.5 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-060063 | 103184 | Statens IT | 2325 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-060064 | 103184 | Statens IT | 7650 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-060065 | 103184 | Statens IT | 7650 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NGF-060066 | 103184 | Statens IT | 3150 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060059 | 103184 | Statens IT | 1589.75 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSF-060060 | 103184 | Statens IT | 1589.75 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-057946 | 103385 | Statens IT | 0 | Morten Skytte | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059775 | 103385 | Statens IT | 3125 | Morten Skytte | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059970 | 104610 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059925 | 104656 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060252 | 104926 | Statens IT | 845 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060254 | 104926 | Statens IT | 290 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060253 | 104926 | Statens IT | 290 | Morten Skytte | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060366 | 105148 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060693 | 105711 | Statens IT | 350 | Morten Skytte | Public DK | New Sales
NKA-006121 | 85895 | Statens IT | 720 | Bonnie Jensen | Public DK
NKA-000777 | 86807 | Statens IT |  | Morten Skytte | Public DK
NKA-052754 | 86807 | Statens IT | 945 | Morten Skytte | Public DK
NKA-000521 | 87327 | Statens IT | 925 | Bonnie Jensen | Public DK
NKA-001316 | 87327 | Statens IT | 845 | Bonnie Jensen | Public DK
NKA-008572 | 87327 | Statens IT | 845 | Bonnie Jensen | Public DK
NKA-012063 | 87327 | Statens IT | 920 | Bonnie Jensen | Public DK
NKA-022293 | 87327 | Statens IT | 845 | Bonnie Jensen | Public DK
NKA-035134 | 87327 | Statens IT | 845 | Bonnie Jensen | Public DK
NKA-011368 | 90910 | Statens IT | 845 | Bonnie Jensen | Public DK
NKA-056300 | 98576 | Stevns Kommune | 450 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-056301 | 98576 | Stevns Kommune | 325 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059069 | 102893 | Styrelsen for It og Læring | 150 | Eva Eisner | Public DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-041907 | 82790 | Sund & Bælt Holding A/S | 9693 | Oliver Mariager | Public DK
NKA-046742 | 82790 | Sund & Bælt Holding A/S | 1907.4 | Oliver Mariager | Public DK
C33713-1136323-01 | 104165-012 | Sydbank A/S | 3079 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C33713-1136325-01 | 104165-012 | Sydbank A/S | 3079 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NDD-059299 | 103009 | Syddansk Erhvervsskole | 8500 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059298 | 103009 | Syddansk Erhvervsskole | 8500 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060523 | 105422 | Syddansk Erhvervsskole | 1625 | Eva Eisner | Public DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
F30928-1135939-01 | 100964-007 | Syddansk Universitet (university Of Southern Denmark) | 1990 | Shazia Mobin | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
F30928-1136815-01 | 100964-008 | Syddansk Universitet (university Of Southern Denmark) | 4000 | Michael Kronbach Leth | Public DK | New Sales
C30962-1135204-01 | 100998-028 | Søstrene Grenes Import A/S | 9588 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30962-1135206-01 | 100998-028 | Søstrene Grenes Import A/S | 9762 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060429 | 104957 | Søstrene Grenes Import A/S | 6250 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060430 | 104957 | Søstrene Grenes Import A/S | 750 | Michael Kronbach Leth | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059743 | 103415 | T HANSEN GRUPPEN A/S | 1450 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059745 | 103415 | T HANSEN GRUPPEN A/S | 425 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSF-059746 | 103415 | T HANSEN GRUPPEN A/S | 2300 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059744 | 103415 | T HANSEN GRUPPEN A/S | 425 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059877 | 103609 | T HANSEN GRUPPEN A/S | 750 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059879 | 103609 | T HANSEN GRUPPEN A/S | 162.5 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059878 | 103609 | T HANSEN GRUPPEN A/S | 162.5 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059880 | 104364 | T HANSEN GRUPPEN A/S | 750 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059882 | 104364 | T HANSEN GRUPPEN A/S | 162.5 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059881 | 104364 | T HANSEN GRUPPEN A/S | 162.5 | Jesper Olsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059870 | 104366 | T HANSEN GRUPPEN A/S | 1400 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059872 | 104366 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NSW-059871 | 104366 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060269 | 104597 | T HANSEN GRUPPEN A/S | 3850 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060270 | 104597 | T HANSEN GRUPPEN A/S | 3850 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-060272 | 104597 | T HANSEN GRUPPEN A/S | 537.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060271 | 104597 | T HANSEN GRUPPEN A/S | 537.5 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-060273 | 104597 | T HANSEN GRUPPEN A/S | 895 | Martin Rasmussen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060605 | 105628 | T HANSEN GRUPPEN A/S |  | Jesper Olsen | Enterprise DK | Change | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-036523 | 102940 | TCM Operations A/S | 1500 | Kristijan Krsteski | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NSW-036545 | 102940 | TCM Operations A/S | 350 | Kristijan Krsteski | Enterprise DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-060635 | 105617 | Techcollege | 845 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-001435 | 91284 | Techcollege | 13500 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-020212 | 91284 | Techcollege | 13500 | Jane Birgitte Høgaard | Public DK | Change | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
C36620-1135708-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.0066667 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135709-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.0066667 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135710-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135711-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.96667 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135712-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.11 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135713-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135714-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.19667 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135715-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.3 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135716-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135718-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.72333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135719-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.46 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135720-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135722-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.70333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135723-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135725-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.41333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135727-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135728-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.70333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135729-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135731-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.70333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135732-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135734-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.11333 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135735-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.61667 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135736-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135738-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.1 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135739-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | -0.52 | Cecilie Heidner Nielsen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135740-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C36620-1135742-01 | 107596-003 | The UK Branch Office of Awaze A/S (UC ) | 0 | Cecilie Heidner Nielsen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060244 | 103133 | Thisted Kommune | 800 | Eva Eisner | Public DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-060246 | 103133 | Thisted Kommune | 227.5 | Eva Eisner | Public DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-060245 | 103133 | Thisted Kommune | 227.5 | Eva Eisner | Public DK | New Sales | 20250519: Delivered; 20250520: Delivered
C31534-1135228-01 | 101568-032 | Thornico IT A/S | 2100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135230-01 | 101568-032 | Thornico IT A/S | 2100 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation
C31534-1135232-01 | 101568-032 | Thornico IT A/S | 2300 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135234-01 | 101568-032 | Thornico IT A/S | 2300 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135236-01 | 101568-032 | Thornico IT A/S | 3200 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135238-01 | 101568-032 | Thornico IT A/S | 3200 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135240-01 | 101568-032 | Thornico IT A/S | 1300 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135241-01 | 101568-032 | Thornico IT A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135243-01 | 101568-032 | Thornico IT A/S | 2625 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135245-01 | 101568-032 | Thornico IT A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31534-1135246-01 | 101568-032 | Thornico IT A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057949 | 100779 | Topsoe A/S | 4320 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
B30208-1136216-01 | 100514-117 | TV2¦DANMARK | 0 | Shazia Mobin | Public DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-055475 | 101493 | twoday Danmark A/S |  | Andrew David Lindsey | Enterprise DK | Change | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-055478 | 90369 | twoday Danmark A/S | 1450 | Nanna Søndergaard Skov | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058895 | 102621 | Tønder Kommune | 892 | Morten Skytte | Public DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-055059 | 97010 | Tønder Kommune | 895 | Morten Skytte | Public DK
NKA-055060 | 97010 | Tønder Kommune | 895 | Morten Skytte | Public DK
NBM-041174 | 105569 | Unisport A/S | -436.69 | Signe Fogh Mach Andersen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060256 | 104742 | United Petfood Denmark A/S | 1660 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: Delivered; 20250521: Delivered
NII-058952 | 101892 | Urban Partners A/S | 5100 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NII-058953 | 101892 | Urban Partners A/S | 2200 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: On Track; 20250520: On Track
NII-058975 | 102056 | Urban Partners A/S | 4600 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-058974 | 102056 | Urban Partners A/S | 1600 | Andrew David Lindsey | Enterprise DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-059771 | 103303 | Vattenfall Vindkraft A/S | 1399 | Peter Madsen | Enterprise DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C30318-1135745-01 | 100606-089 | Vejle Kommune | 812.25 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1135746-01 | 100606-089 | Vejle Kommune | 100 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1135825-01 | 100606-090 | Vejle Kommune | 812.25 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1135826-01 | 100606-090 | Vejle Kommune | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1128873-02 | 100606-093 | Vejle Kommune | 2265 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1128876-02 | 100606-093 | Vejle Kommune | 2265 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136287-01 | 100606-093 | Vejle Kommune | 163.5 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136288-01 | 100606-093 | Vejle Kommune | 163.5 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136289-01 | 100606-093 | Vejle Kommune | 163.5 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136290-01 | 100606-093 | Vejle Kommune | 163.5 | Michael Kronbach Leth | Public DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136291-01 | 100606-093 | Vejle Kommune | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30318-1136292-01 | 100606-093 | Vejle Kommune | 0 | Michael Kronbach Leth | Public DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060022 | 104738 | Vesthimmerlands Kommune | 600 | Eva Eisner | Public DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060022 | 104740 | Vesthimmerlands Kommune | 30 | Eva Eisner | Public DK | Change | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060401 | 105255 | Vesthimmerlands Kommune | 600 | Jane Birgitte Høgaard | Public DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059264 | 103119 | Viborg Kommune | 400.95 | Morten Skytte | Public DK | New Sales
NKA-059265 | 103119 | Viborg Kommune | 400.95 | Morten Skytte | Public DK | New Sales
NKA-059266 | 103119 | Viborg Kommune | 400.95 | Morten Skytte | Public DK | New Sales
NKA-059267 | 103119 | Viborg Kommune | 400.95 | Morten Skytte | Public DK | New Sales
NKA-059268 | 103119 | Viborg Kommune | 400.95 | Morten Skytte | Public DK | New Sales
NKA-059269 | 103119 | Viborg Kommune | 546.75 | Morten Skytte | Public DK | New Sales
C31500-1133908-01 | 101534-018 | Wismo Group A/S | 2300 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133909-01 | 101534-018 | Wismo Group A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133911-01 | 101534-018 | Wismo Group A/S | 2300 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133912-01 | 101534-018 | Wismo Group A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133913-01 | 101534-018 | Wismo Group A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133914-01 | 101534-018 | Wismo Group A/S | 1700 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133915-01 | 101534-018 | Wismo Group A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133917-01 | 101534-018 | Wismo Group A/S | 1700 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133918-01 | 101534-018 | Wismo Group A/S | 50 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31500-1133919-01 | 101534-018 | Wismo Group A/S | 0 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-040748 | 101796 | ZeroNorth A/S | -3458.02 | Natascha Orlung Baisgaard Andersen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NBM-047894 | 101796 | ZeroNorth A/S | 126.66 | Natascha Orlung Baisgaard Andersen | Enterprise DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NBM-058731 | 101796 | ZeroNorth A/S | 4718 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-011021 | 100271 | Øresunds Internationale Skole S/I | 2851.86 | Morten Skytte | Public DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C31349-1134123-01 | 101383-036 | Ørsted Services A/S | 176 | Henrik Møller Fyhn | Enterprise DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059824 | 103580 | A/B Lindegården | 3000 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NBM-060351 | 105070 | Aarhus Motion | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060348 | 105070 | Aarhus Motion | 900 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-060350 | 105070 | Aarhus Motion | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-060349 | 105070 | Aarhus Motion | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NBM-060387 | 105230 | ABCforsikringsagentur A/S | 1361.89 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-060388 | 105230 | ABCforsikringsagentur A/S | 1361.89 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060386 | 105230 | ABCforsikringsagentur A/S | 1195 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-060387 | 105465 | ABCforsikringsagentur A/S | -1050.89 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060181 | 103258 | Advokatfirmaet Grønbæk & Huuse I/S | 697.5 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NML-060182 | 103258 | Advokatfirmaet Grønbæk & Huuse I/S | 697.5 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-036952 | 74844 | ALFABO | 121.38 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 9. Documentation and vendor invoice; 20250520: 9. Documentation and vendor invoice; 20250521: 9. Documentation and vendor invoice
NBM-059109 | 102553 | Al-Irchad Skolen | 1350 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059110 | 102553 | Al-Irchad Skolen | 899 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-059107 | 102553 | Al-Irchad Skolen | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-059108 | 102553 | Al-Irchad Skolen | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059830 | 103536 | Andersen-Andersen ApS | 1055 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NBM-060607 | 105548 | Archon DK ApS | 2500 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060608 | 105548 | Archon DK ApS | 1395 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060343 | 103392 | AS3 A/S | 945 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058435 | 101911 | BESS Frederiksværk I ApS | 697.5 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NML-058436 | 101911 | BESS Frederiksværk I ApS | 697.5 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-060558 | 105526 | Best Ejendomme A/S | 1186 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-041031 | 79039 | BHS Logistics A/S | 520 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-041032 | 79039 | BHS Logistics A/S | 520 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059827 | 103578 | Bluebyte ApS | 665.5 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059828 | 103578 | Bluebyte ApS | 665.5 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C35256-1127937-01 | 105961-007 | BONE CONSULT A/S | 1250 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C35256-1127938-01 | 105961-007 | BONE CONSULT A/S | 0 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C35256-1127948-01 | 105961-007 | BONE CONSULT A/S | 1250 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C35256-1127950-01 | 105961-007 | BONE CONSULT A/S | 2500 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C35256-1127952-01 | 105961-007 | BONE CONSULT A/S | 0 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C35256-1135227-01 | 105961-008 | BONE CONSULT A/S | 96 | Camilla Villumsen Kaimer | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-016343 | 101934 | BRUUN & STENGADE A/S | -1321.62 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-060091 | 101934 | BRUUN & STENGADE A/S | 800 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-060093 | 101934 | BRUUN & STENGADE A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060095 | 101934 | BRUUN & STENGADE A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NSW-060092 | 101934 | BRUUN & STENGADE A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060094 | 101934 | BRUUN & STENGADE A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-028998 | 104739 | BSC Drift ApS | -312.71 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-060117 | 104739 | BSC Drift ApS | 230 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-060118 | 104739 | BSC Drift ApS | 230 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060120 | 103106 | Bysted & Partners ApS | 895 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060122 | 103106 | Bysted & Partners ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060121 | 103106 | Bysted & Partners ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-057576 | 101143 | Copenhagen Bamboo ApS | 1315 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NBM-060697 | 105359 | Copenhagen Coffee Lab Holding ApS | 1388.81 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060694 | 105359 | Copenhagen Coffee Lab Holding ApS | 860 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060698 | 105359 | Copenhagen Coffee Lab Holding ApS | 760 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060696 | 105359 | Copenhagen Coffee Lab Holding ApS | 200 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-060700 | 105359 | Copenhagen Coffee Lab Holding ApS | 150 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060695 | 105359 | Copenhagen Coffee Lab Holding ApS | 200 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSW-060699 | 105359 | Copenhagen Coffee Lab Holding ApS | 150 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059888 | 103312 | Danexplore ApS | 1095 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: Delivered
NKA-060076 | 103541 | Dansk Vegetarisk Forening (DVF) | 895 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-060078 | 103541 | Dansk Vegetarisk Forening (DVF) | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-060077 | 103541 | Dansk Vegetarisk Forening (DVF) | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-056366 | 97023 | DANSKE KONCEPT RESTAURANTER A/S | 1220 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056374 | 97023 | DANSKE KONCEPT RESTAURANTER A/S | 1220 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056601 | 98680 | DANSKE KONCEPT RESTAURANTER A/S | 1700 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-037789 | 100107 | Danske Shoppingcentre P/S |  | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060268 | 103605 | Den selvejende institution Friplejehjemmet Alba Marie | 1391 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
C32793-1136828-01 | 103176-004 | DIS Sølvgade A/S | -180.9967 | Henrik Møller Fyhn | SMB Portfolio DK | Change | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136829-01 | 103176-004 | DIS Sølvgade A/S | 0 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136830-01 | 103176-004 | DIS Sølvgade A/S | 0 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136831-01 | 103176-004 | DIS Sølvgade A/S | 30 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136833-01 | 103176-004 | DIS Sølvgade A/S | 3624 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136834-01 | 103176-004 | DIS Sølvgade A/S | 0 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32793-1136835-01 | 103176-004 | DIS Sølvgade A/S | 30 | Henrik Møller Fyhn | SMB Portfolio DK | New Sales | 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059059 | 102945 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 981 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059058 | 102945 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 981 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-059780 | 102578 | E45 ApS | 1350 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-053149 | 94182 | Ecm Industries A/S | 2643 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NBM-060202 | 91727 | Ejendomsanpartsselskabet MT 04 | 3569 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-015320 | 91727 | Ejendomsanpartsselskabet MT 04 | -929.74 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-015321 | 91727 | Ejendomsanpartsselskabet MT 04 | -248.28 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NDD-059940 | 103477 | Ejendomsselskabet Søkvæsthuset ApS | 584 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NDD-059941 | 103477 | Ejendomsselskabet Søkvæsthuset ApS | 584 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NDD-059942 | 103477 | Ejendomsselskabet Søkvæsthuset ApS | 584 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-059848 | 103697 | Ejerforeningen Beddingen | 995 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-059039 | 102676 | Eurographic Group A/S | 1416 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-059041 | 102676 | Eurographic Group A/S | 612 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-059040 | 102676 | Eurographic Group A/S | 612 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-058991 | 102767 | Flyers ApS | 3870.05 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NBM-058935 | 98741 | FUEGO ApS | 775 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058932 | 98741 | FUEGO ApS | 1000 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-058934 | 98741 | FUEGO ApS | 100 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-058933 | 98741 | FUEGO ApS | 100 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C30781-1136868-01 | 106418-746 | GlobalConnect GmbH (Intercompany 2) |  | Camilla Olesen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30781-1136871-01 | 106418-746 | GlobalConnect GmbH (Intercompany 2) |  | Camilla Olesen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NBM-060238 | 101916 | Go Autonomous ApS | 1592.7 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NBM-060240 | 101916 | Go Autonomous ApS | 1592.71 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060237 | 101916 | Go Autonomous ApS | 1400 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060239 | 101916 | Go Autonomous ApS | 1400 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
C35985-1126258-01 | 106840-006 | H. DAUGAARD A/S | 100 | Henrik Møller Fyhn | SMB Portfolio DK | Change | 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-060080 | 104913 | H.C. Andersens Flyttefirma A/S | 1495 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-060082 | 104913 | H.C. Andersens Flyttefirma A/S | 230 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-060081 | 104913 | H.C. Andersens Flyttefirma A/S | 230 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060438 | 105172 | Hoffmann Professional A/S | 1140 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060439 | 105172 | Hoffmann Professional A/S | 230 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060440 | 105172 | Hoffmann Professional A/S | 230 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NBM-056549 | 98963 | I/S Ugebladsdistribution | 14438.31 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058723 | 102436 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-058919 | 102528 | Imerco A/S | 1629 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059128 | 103032 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059137 | 103032 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060453 | 103321 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052427 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052428 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-052430 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-052431 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-052432 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-052436 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052440 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-052441 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-052451 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052452 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052454 | 93095 | Imerco A/S | 979 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NDD-059971 | 102843 | Immudex ApS | 795 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NDD-059972 | 102843 | Immudex ApS | 795 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-060611 | 105563 | Inco Svendborg Slagtehus A/S | 1185 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060320 | 104999 | India Royale ApS | 695 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-060322 | 104999 | India Royale ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-060321 | 104999 | India Royale ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NBM-060096 | 103238 | Intech | 2440 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NOC-997264 | 103238 | Intech | -2416.06 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060722 | 105696 | i-team Danmark ApS | 995 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-060723 | 105696 | i-team Danmark ApS | 150 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-060724 | 105696 | i-team Danmark ApS | 150 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060646 | 105521 | Kontorfællesskabet Wilders Plads ApS | 1395 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-058251 | 101484 | Labelless Media ApS | 400 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NMA-058253 | 101484 | Labelless Media ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NSW-058252 | 101484 | Labelless Media ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-058250 | 102390 | Labelless Media ApS | 0 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-058086 | 100684 | LaundryHouse ApS | 1395 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NMA-058088 | 100684 | LaundryHouse ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NSW-058087 | 100684 | LaundryHouse ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NBM-060392 | 105193 | LE-Fix Clothing ApS | 1487.98 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-060450 | 105322 | Legendary Gaming Group ApS | 1595 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059986 | 103229 | Limitless Reality ApS | 895 | Nanna Søndergaard Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-060606 | 105407 | Lise Frandsen ApS | 829.13 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-025349 | 105407 | Lise Frandsen ApS | 83.12 | Signe Fogh Mach Andersen | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-052835 | 91200 | Lokal Forsikring G/S | 2120 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052836 | 91200 | Lokal Forsikring G/S | 2120 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052837 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052838 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052839 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052840 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052841 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052842 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052843 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052844 | 91200 | Lokal Forsikring G/S | 970 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052845 | 91200 | Lokal Forsikring G/S | 825 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052846 | 91200 | Lokal Forsikring G/S | 825 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052847 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052848 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052849 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052850 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052851 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052852 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052853 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052854 | 91200 | Lokal Forsikring G/S | 530 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052845 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052847 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052848 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052849 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052850 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052851 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052852 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052853 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-052854 | 98237 | Lokal Forsikring G/S | 390 | Kristijan Krsteski | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NBM-059710 | 102189 | Lomax A/S | 662 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NBM-059711 | 102189 | Lomax A/S | 950 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NBM-059712 | 102189 | Lomax A/S | 950 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-059713 | 102189 | Lomax A/S | 2580.06 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059706 | 102189 | Lomax A/S | 2747.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059707 | 102189 | Lomax A/S | 2747.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059709 | 102189 | Lomax A/S | 2550 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-059162 | 102804 | LUTHERSK MISSIONSFORENING | 1245 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-059163 | 102804 | LUTHERSK MISSIONSFORENING | 225 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-059164 | 102804 | LUTHERSK MISSIONSFORENING | 225 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NBM-059950 | 103494 | Macarons Design I/S | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-059947 | 103494 | Macarons Design I/S | 995 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-059948 | 103494 | Macarons Design I/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NSW-059949 | 103494 | Macarons Design I/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-059654 | 100141 | Mano Event ApS | 895 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-059656 | 100141 | Mano Event ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-059655 | 100141 | Mano Event ApS | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060045 | 104652 | Møbelkompagniet ApS | 895 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060048 | 104652 | Møbelkompagniet ApS | 577.5 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-060047 | 104652 | Møbelkompagniet ApS | 180 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060049 | 104652 | Møbelkompagniet ApS | 577.5 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060046 | 104652 | Møbelkompagniet ApS | 180 | Kristijan Krsteski | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-060260 | 105044 | NGZC ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-060257 | 105044 | NGZC ApS | 1600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-060259 | 105044 | NGZC ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-060258 | 105044 | NGZC ApS | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-059937 | 104558 | Norrlyst ApS | 1095 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-059939 | 104558 | Norrlyst ApS | 180 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-059938 | 104558 | Norrlyst ApS | 180 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-059024 | 100681 | NOVARAM ApS | 1149 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NBM-060644 | 102967 | Ok A.M.B.A. | 350 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060641 | 102967 | Ok A.M.B.A. | 1050 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060643 | 102967 | Ok A.M.B.A. | 0 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060642 | 102967 | Ok A.M.B.A. | 0 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060551 | 103352 | Optinor ApS | 1095 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060553 | 103352 | Optinor ApS | 200 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060552 | 103352 | Optinor ApS | 200 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059019 | 100657 | Perspektiva IT ApS | 2968 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059020 | 100657 | Perspektiva IT ApS | 2968 | Andrew David Lindsey | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059980 | 104667 | Psykologhuset Trekanten ApS | 1095 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-060525 | 105341 | Radiant ApS | 1410 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060526 | 105341 | Radiant ApS | 1195 | Signe Fogh Mach Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-055484 | 97083 | Raw Power Games ApS | 1695 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060426 | 104811 | salting & dyrby ApS | 700 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060427 | 104811 | salting & dyrby ApS | 700 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-057251 | 100710 | Skousen NO | 1944 | Peter Madsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060603 | 105016 | Stavnskær Fragt A/S | 1355 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
F35739-1136632-01 | 106547-008 | STRATU ApS | 4051 | Cecilie Heidner Nielsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057300 | 101102 | SYGEFORSIKRINGEN "DANMARK" GS | 0 | Jeppe Mutinda Mbinda | SMB Portfolio DK | Change | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057969 | 101558 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057970 | 101558 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057308 | 101606 | SYGEFORSIKRINGEN "DANMARK" GS | -23427 | Jeppe Mutinda Mbinda | SMB Portfolio DK | Change | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057295 | 102563 | SYGEFORSIKRINGEN "DANMARK" GS |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | Change | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057301 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2096.58 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057302 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2096.58 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057303 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2577.88 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057304 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2411.24 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057305 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2096.58 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057306 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 2411.24 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057307 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 3325.92 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NBM-057308 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 24779 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057285 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057287 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057289 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057291 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057293 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057295 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057299 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 1945 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NKA-057300 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 1945 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057286 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057288 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057290 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057292 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057294 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NML-057296 | 96115 | SYGEFORSIKRINGEN "DANMARK" GS | 622.5 | Jeppe Mutinda Mbinda | SMB Portfolio DK | New Sales | 20250519: 1.9 PMO delivery planning; 20250520: 1.9 PMO delivery planning; 20250521: 1.9 PMO delivery planning
NCI-060727 | 104948 | Taconic Biosciences A/S | 695 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060725 | 104948 | Taconic Biosciences A/S | 1700 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060726 | 104948 | Taconic Biosciences A/S | 1700 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-056532 | 95792 | Trescal A/S | 1595 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-056533 | 95792 | Trescal A/S | 1595 | Jesper Olsen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-059996 | 104703 | Vækst+ ApS | 1242 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059149 | 103140 | VESTBO MEDICAL V/JØRGEN VESTBO | 895 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-059151 | 103140 | VESTBO MEDICAL V/JØRGEN VESTBO | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-059150 | 103140 | VESTBO MEDICAL V/JØRGEN VESTBO | 150 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059976 | 104677 | WOBA ApS | 1095 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-059977 | 104677 | WOBA ApS | 180 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-059978 | 104677 | WOBA ApS | 180 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-030523 | 105411 | Voldgiftsinstituttet | -312.19 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-060616 | 105411 | Voldgiftsinstituttet | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NSW-060617 | 105411 | Voldgiftsinstituttet | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060446 | 105303 | Wolt Services Danmark ApS | 995 | Martin Rasmussen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059275 | 102224 | ADDvision ApS | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059277 | 102224 | ADDvision ApS | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-059276 | 102224 | ADDvision ApS | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059278 | 102224 | ADDvision ApS | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-044529 | 101317 | A-One Solutions ApS | -4.2 | Michael Kronbach Leth | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059849 | 103579 | Basic & More A/S | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-059850 | 103579 | Basic & More A/S | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060730 | 105734 | Basic & More A/S | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060731 | 105734 | Basic & More A/S | 597.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-043321 | 81373 | Beat A/S | 995 | Oliver Mariager | SMB Portfolio DK |  | 20250519: 9. Documentation and vendor invoice; 20250520: 9. Documentation and vendor invoice; 20250521: 9. Documentation and vendor invoice
NKA-059806 | 103330 | BONE CONSULT A/S | 1255 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059807 | 103330 | BONE CONSULT A/S | 1255 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059960 | 103557 | ByFrame ApS | 1095 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-059961 | 103557 | ByFrame ApS | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-059962 | 103557 | ByFrame ApS | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059642 | 103186 | Christiansen & Essenbæk A/S | 1360 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060056 | 104897 | Dalsten Tandlægecenter ApS | 895 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058445 | 102100 | DANSK CAMPING UNION | 2200 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-058785 | 102499 | DANSK CAMPING UNION | 2100 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-059177 | 103124 | DANSK CAMPING UNION | 2100 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-014092 | 103430 | Dansk Miljørådgivning A/S (DMR Geoteknik, DMR Skimmel & DMR Arbejdsmiljø) |  | Eva Eisner | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059853 | 103694 | Estatetool A/S | 1135 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NMA-059855 | 103694 | Estatetool A/S | 230 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NSW-059854 | 103694 | Estatetool A/S | 230 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold
NKA-059900 | 103174 | Faxe Kommune - IT-afdelingen | 300 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059934 | 103026 | Forsvarsministeriets Ejendomsstyrelse | 475 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060338 | 103320 | Forsvarsministeriets Ejendomsstyrelse | 845 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-057854 | 100380 | Ganni A/S | 1395 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-057855 | 100380 | Ganni A/S | 1395 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-057859 | 100380 | Ganni A/S | 2500 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058736 | 102217 | Ganni A/S | 4600 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059070 | 95669 | Hansens Gamle Familiehave ApS | 1095 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059851 | 103074 | Hildebrandt & Brandi Danmark A/S | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059852 | 103074 | Hildebrandt & Brandi Danmark A/S | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060073 | 103099 | Hudklinik v/Henrik Rask Kralund | 1310 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059245 | 102968 | I/S Lægerne Sønderhøj | 995 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059273 | 103196 | Impero A/S | 1195 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059858 | 101089 | Koppers Denmark ApS | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-059859 | 101089 | Koppers Denmark ApS | 597.5 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 8. Ready for service; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-060451 | 102363 | Lelectric A/S | 1895 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060471 | 105337 | Moldow A/S | 2255 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-058872 | 102749 | Møgelhøj Arkitekter P/S | 1495 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057903 | 100652 | Naturstyrelsen | 1300 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-057905 | 100652 | Naturstyrelsen | 1300 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-004029 | 103616 | Nr. Snede Fængsel | 0 | Morten Skytte | SMB Portfolio DK | Change
NKA-005319 | 103616 | Nr. Snede Fængsel | 0 | Morten Skytte | SMB Portfolio DK | Change
NKA-059979 | 104549 | Peter Skafte ApS | 895 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059644 | 103176 | Region Nordjylland | 1555 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NML-059645 | 103176 | Region Nordjylland | 1555 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: On Track; 20250520: On Track; 20250521: On Track
NKA-057864 | 101555 | Riel Sikring ApS | 622.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-057865 | 101555 | Riel Sikring ApS | 622.5 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059836 | 102792 | Selmatec A/S | 895 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059838 | 102792 | Selmatec A/S | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059837 | 102792 | Selmatec A/S | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-054245 | 94395 | Skive Kommune | 1100 | Morten Skytte | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058894 | 102147 | Statens Museum For Kunst | 845 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059791 | 103393 | Statens Museum For Kunst | 845 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059719 | 103416 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060326 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060327 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060328 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060329 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060330 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060331 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060332 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-060333 | 105145 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-056784 | 98971 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-056783 | 99904 | Telenor A/S | 0 | Morten Skytte | SMB Portfolio DK | New Sales
NKA-059816 | 103086 | The Marketing Guy ApS | 1095 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059967 | 102597 | Unicontrol ApS | 995 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-059968 | 102597 | Unicontrol ApS | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-059969 | 102597 | Unicontrol ApS | 200 | Eva Eisner | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060728 | 105621 | VICURAS DK A/S | 1200 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059028 | 102707 | 101 Copenhagen ApS | 1278 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059030 | 102707 | 101 Copenhagen ApS | 255 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059029 | 102707 | 101 Copenhagen ApS | 255 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060441 | 105245 | Abstracta Interiør A/S | 1495 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060219 | 101976 | ADDvision ApS | 574.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060220 | 101976 | ADDvision ApS | 574.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-031201 | 102766 | ADDvision ApS |  | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060621 | 103431 | ADDvision ApS | 597.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060622 | 103431 | ADDvision ApS | 597.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060584 | 105459 | ADDvision ApS | 547.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NML-060585 | 105459 | ADDvision ApS | 547.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060472 | 105363 | Adminia ApS | 996 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060473 | 105363 | Adminia ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060474 | 105363 | Adminia ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060686 | 105327 | Advokaterne i Rosenborggade I/S | 1659 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059178 | 102096 | Aktieselskabet Bremen | 950 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NML-059179 | 102096 | Aktieselskabet Bremen | 950 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058503 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058504 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058516 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058517 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058520 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058523 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058524 | 102186 | Allunite A/S | 1195 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059831 | 102644 | Alphadyne Asset Management (Europe) A/S | 4000 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059834 | 102644 | Alphadyne Asset Management (Europe) A/S | 4000 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-032881 | 103946 | Anchor Lab K/S | 0 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060619 | 105420 | Andersen-Andersen ApS | 895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059168 | 102850 | Apel Fine Jewellery | 795 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-059170 | 102850 | Apel Fine Jewellery | 150 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-059169 | 102850 | Apel Fine Jewellery | 150 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060521 | 104918 | ARC Nordic A/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060522 | 104918 | ARC Nordic A/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060707 | 105688 | Arpe & Kjeldsholm A/S | 1295 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060099 | 102606 | Bagt ApS | 695 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060102 | 102606 | Bagt ApS | 995 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060105 | 102606 | Bagt ApS | 995 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060108 | 102606 | Bagt ApS | 1350 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060111 | 102606 | Bagt ApS | 1350 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060114 | 102606 | Bagt ApS | 1350 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060101 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060104 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060107 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060110 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060113 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060116 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060100 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060103 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060106 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060109 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060112 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060115 | 102606 | Bagt ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060598 | 105398 | BEGRAVELSESFORRETNINGEN DEN SIDSTEREJSE V/SOLVEJG RITZAU | 995 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060520 | 103050 | Begroni ApS | 1795 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-025618 | 104650 | Bionordika Denmark A/S | -100 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NMA-059963 | 104650 | Bionordika Denmark A/S | 230 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NSW-059964 | 104650 | Bionordika Denmark A/S | 230 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-057898 | 100868 | Blueprint | 1099 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056432 | 98852 | Bolig Buddy ApS | 1550 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
C36637-1136771-01 | 107620-002 | Boligforeningen Grønløkken | 1100 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C36637-1136772-01 | 107620-002 | Boligforeningen Grønløkken | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060529 | 105415 | Bomae ApS | 1395 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060422 | 97827 | Britt Sisseck | 895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-060424 | 97827 | Britt Sisseck | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060423 | 97827 | Britt Sisseck | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060465 | 105249 | C.F. Møller Norge AS | 1900 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060123 | 101983 | Cadesign base A/S | 2200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32152-1135219-01 | 102065-030 | Cadesign base A/S | 1371 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32152-1135220-01 | 102065-030 | Cadesign base A/S | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32152-1135221-01 | 102065-030 | Cadesign base A/S | -0.55333 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060054 | 104899 | Cadesign base A/S | 849.93 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060055 | 104899 | Cadesign base A/S | 849.93 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-059955 | 102720 | Cematech ApS | 1495 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059954 | 102720 | Cematech ApS | 1295 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059956 | 102720 | Cematech ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-052598 | 93246 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 1196 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NMA-052599 | 93246 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 199.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-052600 | 93246 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 199.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060436 | 105285 | Chatservice ApS | 1895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-057086 | 98795 | CIC Operations Odense ApS | 1495 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060263 | 105037 | Citrusmedia ApS | 1245 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
C32025-1134067-01 | 101944-014 | Compugroup Medical Denmark A/S | 2500 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32025-1134069-01 | 101944-014 | Compugroup Medical Denmark A/S | 2900 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060402 | 105120 | ConXus A/S | 794 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-060404 | 105120 | ConXus A/S | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-060403 | 105120 | ConXus A/S | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-054814 | 97085 | Danibo ApS | 997.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-054815 | 97085 | Danibo ApS | 997.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060222 | 104848 | Dan-Revision Taastrup ApS | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060221 | 104848 | Dan-Revision Taastrup ApS | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C30825-1136598-01 | 100862-014 | Dansk Arbejdsgiverforening | -1439.2667 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30825-1136599-01 | 100862-014 | Dansk Arbejdsgiverforening | 2500 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C30825-1136600-01 | 100862-014 | Dansk Arbejdsgiverforening | 134 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060359 | 105023 | Dansk It | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060360 | 105023 | Dansk It | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060668 | 105272 | Dansk Turbo Teknik A/S | 995 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-005674 | 103584 | Danske Advokater | -774.9 | Merete Helme | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060224 | 103584 | Danske Advokater | 1260 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-025351 | 102950 | Dayforce A/S | -2900.95 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-032475 | 102950 | Dayforce A/S | -1666.06 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059860 | 103142 | Dentorium ApS | 1326 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058696 | 102249 | Dignity - Dansk Institut Mod Tortur | 1994 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-058380 | 101227 | DKI Management A/S | 2050 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058381 | 101227 | DKI Management A/S | 2050 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058382 | 101227 | DKI Management A/S | 2400 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-028814 | 96319 | ed A/S | -468.61 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-049932 | 105533 | Edora A/S | -2218 | Merete Helme | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration
NKA-056809 | 99947 | Ejendomsselskabet Lyngby Hovedgade 78 ApS | 1395 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-025721 | 101232 | EKHO EKHO | 1195 | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-057697 | 101232 | EKHO EKHO | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-036803 | 103077 | Event Space ApS | -1268.61 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-036804 | 103077 | Event Space ApS | 213.27 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-034187 | 102304 | Executive Cognito A/S | -250.62 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NML-058724 | 102304 | Executive Cognito A/S | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060648 | 105610 | exs nordic A/S | 995 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C36378-1125451-01 | 107317-002 | FAB:IT ApS | 1500 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36378-1125453-01 | 107317-002 | FAB:IT ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36378-1125454-01 | 107317-002 | FAB:IT ApS | 2000 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36378-1125456-01 | 107317-002 | FAB:IT ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36378-1125457-01 | 107317-002 | FAB:IT ApS | 2000 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060261 | 104846 | Fænøsundlægerne I/S | 1200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36447-1136725-01 | 107397-003 | FEC Taby Ab | 1495 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
C36447-1136726-01 | 107397-003 | FEC Taby Ab | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-060610 | 105577 | Fiberline Building Profiles A/S | 1495 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-057312 | 105343 | Filmkontakt Nord. Fonden For Nordiske Kort- og Dokumentarfilm |  | Line Skov | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C33538-1134609-01 | 103973-004 | Finans Danmark | 977.3533 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C33538-1134611-01 | 103973-004 | Finans Danmark | -2285.79 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35898-1136681-01 | 106740-008 | FINN FROGNE A/S | 3000 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136682-01 | 106740-008 | FINN FROGNE A/S | 3000 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136684-01 | 106740-008 | FINN FROGNE A/S | 50 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136685-01 | 106740-008 | FINN FROGNE A/S | 50 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136686-01 | 106740-008 | FINN FROGNE A/S | 60 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136687-01 | 106740-008 | FINN FROGNE A/S | 60 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C35898-1136688-01 | 106740-008 | FINN FROGNE A/S | 176 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059957 | 102594 | Fjord Rådgivende Ingeniører A/S | 1395 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C32515-1136586-01 | 102845-005 | Flexdanmark | 1695 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32515-1136587-01 | 102845-005 | Flexdanmark | 0 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C32515-1136588-01 | 102845-005 | Flexdanmark | 100 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059152 | 101024 | Fonden for Herning Isstadion | 2500 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
C36592-1133981-01 | 107556-002 | Fonden Wonderful Copenhagen | 3600 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060079 | 104901 | Fondsmæglerselskabet Marselis A/S | 1510 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-046136 | 84553 | Foreningshuset Sundholm8 | 1116.9 | Lars Gottschalck | SMB Portfolio DK
C36635-1136705-01 | 107618-002 | Forum Cph ApS | 2550 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36635-1136706-01 | 107618-002 | Forum Cph ApS | 60 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36635-1136708-01 | 107618-002 | Forum Cph ApS | 9200 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36635-1136710-01 | 107618-002 | Forum Cph ApS | 60 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060708 | 105705 | Frederiksborggade Øjenklinik v/Hanne Göte | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059994 | 103173 | Fresh Out The Oven ApS | 984 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059903 | 103631 | Frøslev Træ A/S | 697.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059905 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059907 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059909 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059911 | 103631 | Frøslev Træ A/S | 697.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059904 | 103631 | Frøslev Træ A/S | 697.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059906 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059908 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059910 | 103631 | Frøslev Træ A/S | 597.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-059912 | 103631 | Frøslev Træ A/S | 697.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-040724 | 105176 | Fsb I Gladsaxe | -210.23 | Line Skov | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NMA-040726 | 105176 | Fsb I Gladsaxe | 200 | Line Skov | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NSW-040725 | 105176 | Fsb I Gladsaxe | -292.71 | Line Skov | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-050671 | 103391 | GORM x ENVISION A/S | 734.1 | Merete Helme | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-059820 | 103391 | GORM x ENVISION A/S | 2210 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-054920 | 95021 | GREEN STORAGE A/S | 949 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-060519 | 102958 | Gustaf Fagerberg A/S | 1295 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36634-1136549-01 | 107614-002 | H. BAASCH EJENDOMME ApS | 1100 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C36634-1136550-01 | 107614-002 | H. BAASCH EJENDOMME ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-035285 | 105390 | H+ A/S | 714.9 | Line Skov | SMB Portfolio DK | Change | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-021308 | 98474 | H9 ApS | -578.59 | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-056835 | 98474 | H9 ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-059810 | 103076 | Hallerupnet ApS | 1495 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-043808 | 103076 | Hallerupnet ApS | 1497.87 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059809 | 103076 | Hallerupnet ApS | 1888.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059811 | 103076 | Hallerupnet ApS | 1000 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NRS-043807 | 103076 | Hallerupnet ApS | -2141.4 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NRS-059808 | 103076 | Hallerupnet ApS | 1888.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-053529 | 94367 | Heimstaden Flintholm Kollegiet ApS | 2000 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C34237-1134236-01 | 104734-010 | Hesehus A/S | 1865 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C34237-1134237-01 | 104734-010 | Hesehus A/S | 842 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C34237-1134238-01 | 104734-010 | Hesehus A/S | 228 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059874 | 104453 | Holst-Group ApS | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059876 | 104453 | Holst-Group ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059875 | 104453 | Holst-Group ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation; 20250521: 7. Service activation
NKA-058900 | 100768 | Holtec Automatic A/S | 1395 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060089 | 103481 | Hudklinikken Helsingør I/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NML-060090 | 103481 | Hudklinikken Helsingør I/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060218 | 102404 | Infolink ApS | 749 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration
NKA-060437 | 105308 | Institutionen Thomas P.Hejles Ungdomshus | 995 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
C34376-1136842-01 | 104899-009 | Intecredo International ApS | -523.7133 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C34376-1136843-01 | 104899-009 | Intecredo International ApS | 1033.6567 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C34376-1136844-01 | 104899-009 | Intecredo International ApS | -505.0633 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C34376-1136848-01 | 104899-009 | Intecredo International ApS | -1084.9 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C34376-1136849-01 | 104899-009 | Intecredo International ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-057080 | 100480 | IntraVAT ApS | 995 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-057082 | 100480 | IntraVAT ApS | 150 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-057081 | 100480 | IntraVAT ApS | 150 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
C33943-1134819-01 | 104409-004 | Ismageriet ApS | 1495 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C33943-1134820-01 | 104409-004 | Ismageriet ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058983 | 102529 | IT Forum Gruppen A/S | 2460 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058984 | 102529 | IT Forum Gruppen A/S | 2460 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059689 | 102686 | IT Forum Gruppen A/S | 1324 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning
NKA-028737 | 105442 | Jelling Familie Camping ApS | -4800.92 | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 8. Ready for service
NKA-060361 | 105215 | Jeudan A/S | 0 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-025629 | 105609 | Jeudan A/S |  | Merete Helme | SMB Portfolio DK | Change | 20250519: Delivered; 20250520: Delivered
NKA-059116 | 102583 | Keepers ApS | 1895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 8. Ready for service; 20250521: 8. Ready for service
NKA-059862 | 102668 | Keepers ApS | 2495 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-046870 | 85903 | Kirkebjerg Køreskole ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-053097 | 93908 | Kjærgaard A/S | 847.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-053098 | 93908 | Kjærgaard A/S | 847.5 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060316 | 104717 | Klc Erhverv København ApS | 899 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C30991-1111651-01 | 101027-003 | Klimadan A/S | 443.688 | Shazia Mobin | SMB Portfolio DK |  | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NKA-060626 | 105223 | Koldby Optik, Østerbrogade 108 ApS | 955 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NMA-060627 | 105223 | Koldby Optik, Østerbrogade 108 ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-060628 | 105223 | Koldby Optik, Østerbrogade 108 ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060443 | 105153 | Konsulent Bjarne Aalbæk | 1695 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060357 | 103606 | Krogstrup ApS | 2000 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058447 | 102144 | Kuube Denmark ApS | 1299 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-058448 | 102144 | Kuube Denmark ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-058449 | 102144 | Kuube Denmark ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060582 | 105483 | Læge Torben Larsen | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060583 | 105483 | Læge Torben Larsen | 622.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059249 | 102373 | Landinspektørfirmaet Hyldegaard P/S | 912 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-060555 | 105301 | LEMAN A/S | 1700 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059865 | 103266 | Lokalbolig Hvidovre ApS | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NMA-059864 | 103266 | Lokalbolig Hvidovre ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NSW-059863 | 103266 | Lokalbolig Hvidovre ApS | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056963 | 100378 | Ls Montage ApS | 1345 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059812 | 103576 | Lyngby Låse & Alarm ApS | 1445 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation
NKA-060352 | 103839 | MOBILXPERTEN ApS | 952 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060684 | 105536 | MOBILXPERTEN ApS | 625 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060685 | 105536 | MOBILXPERTEN ApS | 625 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060075 | 103236 | Mos Mosh A/S | 3660 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060683 | 102737 | Move Innovation ApS | 995 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060527 | 103317 | N3 ApS | 1595 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Cancelled/terminated/On hold; 20250520: Cancelled/terminated/On hold; 20250521: Cancelled/terminated/On hold
NKA-060534 | 105329 | Najell Denmark ApS | 622.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NML-060535 | 105329 | Najell Denmark ApS | 622.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-019996 | 101313 | Natus Medical Denmark ApS | -181.16 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-057962 | 101313 | Natus Medical Denmark ApS | 1495 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060475 | 105323 | Noteless AS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-060477 | 105323 | Noteless AS | 225 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060476 | 105323 | Noteless AS | 225 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C35287-1136087-01 | 106002-016 | Ntrakker AB | 2100 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35287-1136088-01 | 106002-016 | Ntrakker AB | 60 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-059894 | 102585 | NØRGÅRD MIKKELSEN REKLAMEBUREAU A/S | 3313 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059760 | 103235 | Oreco A/S | 1778 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-060530 | 104852 | Our Units ApS | 647.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NML-060531 | 104852 | Our Units ApS | 647.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-056743 | 97994 | Oustrupgård Agro ApS | 1400 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-059174 | 103102 | Owayy ApS | 895 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-059175 | 103102 | Owayy ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-059176 | 103102 | Owayy ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059901 | 103316 | P+p Arkitekter A/S | 1295 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-013625 | 105456 | Penta Advokater A/S |  | Line Skov | SMB Portfolio DK | Change | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060629 | 105457 | Penta Advokater A/S | 1841 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-058679 | 98496 | Planet2030 | 1300 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NMA-058681 | 98496 | Planet2030 | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NSW-058680 | 98496 | Planet2030 | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-054033 | 94828 | Polaris Management A/S | 897.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-054034 | 94828 | Polaris Management A/S | 897.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060334 | 105163 | Pompette ApS | 895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-060336 | 105163 | Pompette ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-060335 | 105163 | Pompette ApS | 150 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C35226-1135895-01 | 105881-080 | PROCOPA IT ApS | 995 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35226-1135920-01 | 105881-081 | PROCOPA IT ApS | 995 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C35226-1136819-01 | 105881-082 | PROCOPA IT ApS | -231.9567 | Shazia Mobin | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36636-1136796-01 | 107619-003 | PROJECT OPEN ApS | 795 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
C36636-1136797-01 | 107619-003 | PROJECT OPEN ApS | 96 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
C36636-1136798-01 | 107619-003 | PROJECT OPEN ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-040572 | 105003 | Pålsson Arkitekter A/S | 31.53 | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060533 | 104737 | RareWine ApS | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-036506 | 102434 | Rasmussen Skilte ApS | -0.62 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-058842 | 102434 | Rasmussen Skilte ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-058843 | 102434 | Rasmussen Skilte ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
C36481-1135502-01 | 107438-003 | RIGHT PEOPLE GROUP ApS | 1195 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
C36481-1135503-01 | 107438-003 | RIGHT PEOPLE GROUP ApS | 0 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060039 | 104661 | Riverty Services Denmark A/S | 497.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060040 | 104661 | Riverty Services Denmark A/S | 497.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058845 | 102302 | Rosendahl Design Group A/S | 2600 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059253 | 103138 | Saint Revision ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-059254 | 103138 | Saint Revision ApS | 200 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-059255 | 103138 | Saint Revision ApS | 200 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-038507 | 100014 | Sephora Danmark ApS | -1099.31 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-038509 | 100014 | Sephora Danmark ApS | -1099.31 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NML-038508 | 100014 | Sephora Danmark ApS | 876.52 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NML-038510 | 100014 | Sephora Danmark ApS | 876.52 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-037347 | 100017 | Sephora Danmark ApS | -199.31 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NML-057260 | 100017 | Sephora Danmark ApS | 100 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 1.Order entry and validation; 20250520: 1.Order entry and validation; 20250521: 1.Order entry and validation
NKA-060180 | 103117 | Sharp Business Systems Danmark A/S | 1399 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-058992 | 102857 | Simons Padel Club ApS | 1245 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-059821 | 103041 | Sleep in Heaven ApS | 852 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059822 | 103041 | Sleep in Heaven ApS | 852 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059171 | 103111 | Smiley Fitness ApS | 895 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: afvneter installation and prov; 20250520: afvneter installation and prov
NMA-059172 | 103111 | Smiley Fitness ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NSW-059173 | 103111 | Smiley Fitness ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060442 | 105312 | Sofigate ApS | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060586 | 100398 | Space Composite Structures DENMARK APS | 1245 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-030643 | 101332 | Space gaming ApS | -435.9 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-057699 | 101332 | Space gaming ApS | 250 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-057698 | 101332 | Space gaming ApS | 250 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060597 | 105440 | Strøm Hansen A/S | 1421 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058362 | 102078 | Suaning Import | 895 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NMA-058364 | 102078 | Suaning Import | 149.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NSW-058363 | 102078 | Suaning Import | 149.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060408 | 105278 | Subit ApS | 1395 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-059659 | 102723 | Sulzer Pumps Denmark A/S | 500 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-035286 | 102723 | Sulzer Pumps Denmark A/S | -3267.91 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059658 | 102723 | Sulzer Pumps Denmark A/S | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-042793 | 105514 | SVEJSECENTER REHERMANN A/S | 1595 | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-060596 | 105514 | SVEJSECENTER REHERMANN A/S | 200 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059932 | 104593 | Tandlægeselskabet Klinik for Kæbekirurgi I/S | 447.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-059933 | 104593 | Tandlægeselskabet Klinik for Kæbekirurgi I/S | 447.5 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059682 | 103139 | Tariq ApS | 1095 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
C31680-1135555-01 | 101714-006 | Td-K A/S | 550 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
C31680-1135556-01 | 101714-006 | Td-K A/S | 550 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NKA-057597 | 101036 | Tegnestuen Vandkunsten A/S | 700 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-057598 | 101036 | Tegnestuen Vandkunsten A/S | 700 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060317 | 105083 | Telebesparelse ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-060318 | 105083 | Telebesparelse ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060319 | 105083 | Telebesparelse ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-034507 | 105378 | Telecom X ApS |  | Merete Helme | SMB Portfolio DK | Change | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-056221 | 98382 | Temashop ApS | 1317 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NML-056222 | 98382 | Temashop ApS | 1317 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-059007 | 102438 | The Company Group A/S | 1295 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059922 | 103231 | Topsil Globalwafers A/S | 2200 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NOC-995820 | 103231 | Topsil Globalwafers A/S | -763.73 | Line Skov | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060532 | 105380 | Totalklima ApS | 1295 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 4. Final design; 20250520: 4. Final design; 20250521: 4. Final design
NKA-060623 | 105461 | Truckplanner A/S | 995 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 7. Service activation; 20250520: 7. Service activation
NKA-058670 | 102182 | Tømrermester Jim Jensen A/S | 1495 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-010325 | 101127 | Væxthuset 3 ApS | -427.32 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NMA-057713 | 101127 | Væxthuset 3 ApS | 165 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NSW-057712 | 101127 | Væxthuset 3 ApS | 165 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060255 | 105019 | Vamdrup Fjernvarme A m b A | 1160 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-059797 | 103127 | Wennick Enterprise A/S | 2500 | Shazia Mobin | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered
NDD-059652 | 102743 | Veo Technologies ApS | 3111 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-035994 | 102743 | Veo Technologies ApS | -3051.47 | Merete Helme | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-058987 | 102530 | Verdens Skove, Århus | 895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 3. Installation preparation and digging order; 20250520: 3. Installation preparation and digging order; 20250521: 3. Installation preparation and digging order
NKA-060508 | 105347 | Vest Energi ApS | 2095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NDD-056466 | 97191 | Vilhelm Lauritzen Arkitekter A/S | 1495 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-030930 | 97191 | Vilhelm Lauritzen Arkitekter A/S | -1065.86 | Merete Helme | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NRK-030931 | 97191 | Vilhelm Lauritzen Arkitekter A/S | 57.89 | Merete Helme | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060325 | 105158 | Vurderingsmægler ApS | 895 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NKA-058379 | 101608 | Zauner Anlagentechnik GmbH | 2595 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NKA-056423 | 98482 | Zebnet ApS | 1400 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NML-056424 | 98482 | Zebnet ApS | 1400 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: Delivered; 20250520: Delivered; 20250521: Delivered
NML-056428 | 98482 | Zebnet ApS | 200 | Christoffer Møller Andersen | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NOC-995967 | 98482 | Zebnet ApS | -1710.58 | Christoffer Møller Andersen | SMB Portfolio DK | Change | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060681 | 105695 | ZTLment ApS | 4095 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 5. Configuration; 20250520: 5. Configuration; 20250521: 5. Configuration
NDD-060570 | 104749 | Zurface A/S | 855 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060569 | 104749 | Zurface A/S | 855 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060571 | 104749 | Zurface A/S | 1100 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060573 | 104749 | Zurface A/S | 299.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060575 | 104749 | Zurface A/S | 299.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060576 | 104749 | Zurface A/S | 1100 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-060577 | 104749 | Zurface A/S | 1250 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060572 | 104749 | Zurface A/S | 299.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NML-060574 | 104749 | Zurface A/S | 299.5 | Merete Helme | SMB Portfolio DK | New Sales | 20250519: 2. Delivery planning; 20250520: 2. Delivery planning; 20250521: 2. Delivery planning
NKA-059914 | 102565 | Ølsnedkeren ApS | 1495 | Line Skov | SMB Portfolio DK | New Sales | 20250519: 6. Cabling splicing and installation; 20250520: 6. Cabling splicing and installation; 20250521: 6. Cabling splicing and installation
NBM-052166 | 105760 | COOP DANMARK A/S | 110.61 | Jeppe Mutinda Mbinda | Enterprise DK | Change
NBM-052560 | 105761 | COOP DANMARK A/S | 110.61 | Jeppe Mutinda Mbinda | Enterprise DK | Change
NBM-060772 | 105766 | COOP DANMARK A/S | 766.41 | Jeppe Mutinda Mbinda | Enterprise DK | New Sales
NMA-060747 | 105716 | DAN`X A/S | 630 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales
NSW-060746 | 105716 | DAN`X A/S | 630 | Natascha Orlung Baisgaard Andersen | Enterprise DK | New Sales
NKA-060732 | 102738 | Dansk Revision A/S | 1125 | Peter Madsen | Enterprise DK | New Sales
NML-060733 | 102738 | Dansk Revision A/S | 1125 | Peter Madsen | Enterprise DK | New Sales
NKA-060745 | 105625 | Danske Olieberedskabslagre | 955 | Nanna Søndergaard Skov | Enterprise DK | New Sales
NML-060744 | 105625 | Danske Olieberedskabslagre | 955 | Nanna Søndergaard Skov | Enterprise DK | New Sales
NKA-058262 | 101523 | Forsvaret og Forsvarsministeriets styrelser | 475 | Michael Kronbach Leth | Public DK
NKA-058263 | 101523 | Forsvaret og Forsvarsministeriets styrelser | 475 | Michael Kronbach Leth | Public DK
NKA-058262 | 101766 | Forsvaret og Forsvarsministeriets styrelser |  | Michael Kronbach Leth | Public DK
NKA-058263 | 101766 | Forsvaret og Forsvarsministeriets styrelser |  | Michael Kronbach Leth | Public DK
NKA-058631 | 102351 | Forsvaret og Forsvarsministeriets styrelser | 925 | Jane Birgitte Høgaard | Public DK
NKA-058632 | 102351 | Forsvaret og Forsvarsministeriets styrelser | 925 | Jane Birgitte Høgaard | Public DK
NKA-060250 | 104956 | Forsvaret og Forsvarsministeriets styrelser | 675 | Eva Eisner | Public DK
NKA-002013 | 91996 | Forsvaret og Forsvarsministeriets styrelser | 475 | Michael Kronbach Leth | Public DK
NKA-060736 | 105554 | Friluftsland A/S | 615 | Peter Madsen | Enterprise DK | New Sales
NML-060737 | 105554 | Friluftsland A/S | 615 | Peter Madsen | Enterprise DK | New Sales
NKA-060799 | 103561 | I/S VESTFORBRÆNDING | 352.5 | Michael Kronbach Leth | Public DK | New Sales
NML-060800 | 103561 | I/S VESTFORBRÆNDING | 352.5 | Michael Kronbach Leth | Public DK | New Sales
NKA-048925 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales
NKA-048937 | 88172 | I/S VESTFORBRÆNDING | 237.5 | Michael Kronbach Leth | Public DK | New Sales
NML-048926 | 88172 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales
NML-048938 | 88172 | I/S VESTFORBRÆNDING | 15 | Michael Kronbach Leth | Public DK | New Sales
NKA-055617 | 97012 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales
NML-055618 | 97012 | I/S VESTFORBRÆNDING | 252.5 | Michael Kronbach Leth | Public DK | New Sales
NKA-060265 | 101723 | Nellemann Holding AS | 1400 | Peter Madsen | Enterprise DK | New Sales
NMA-060267 | 101723 | Nellemann Holding AS | 495 | Peter Madsen | Enterprise DK | New Sales
NSW-060266 | 101723 | Nellemann Holding AS | 495 | Peter Madsen | Enterprise DK | New Sales
NKA-060820 | 105830 | Normal A/S | 765 | Peter Madsen | Enterprise DK | New Sales
NKA-060729 | 105735 | Per Aarsleff A/S | 1800 | Peter Madsen | Enterprise DK | New Sales
NKA-009830 | 105276 | Sommerland Sjælland A/S | -2234.14 | Peter Madsen | Enterprise DK | Change
F30221-1136939-01 | 100525-118 | Spar Nord Bank A/S | 0 | Michael Kronbach Leth | Enterprise DK | Change
NKA-058340 | 105764 | Statens IT | 100 | Jane Birgitte Høgaard | Public DK | Change
NKA-053450 | 105799 | Statens IT |  | Jane Birgitte Høgaard | Public DK | Change
NKA-053451 | 105799 | Statens IT |  | Jane Birgitte Høgaard | Public DK | Change
NKA-060822 | 105804 | Statens IT | 845 | Jane Birgitte Høgaard | Public DK | New Sales
NKA-060750 | 105700 | T HANSEN GRUPPEN A/S | 1400 | Martin Rasmussen | Enterprise DK | New Sales
NMA-060752 | 105700 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales
NSW-060751 | 105700 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales
NKA-060753 | 105701 | T HANSEN GRUPPEN A/S | 1400 | Martin Rasmussen | Enterprise DK | New Sales
NMA-060755 | 105701 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales
NSW-060754 | 105701 | T HANSEN GRUPPEN A/S | 275 | Martin Rasmussen | Enterprise DK | New Sales
NKA-040716 | 105726 | T HANSEN GRUPPEN A/S | 1685 | Jesper Olsen | Enterprise DK | Change
NKA-060748 | 105726 | T HANSEN GRUPPEN A/S | 2350 | Jesper Olsen | Enterprise DK | New Sales
NMA-040718 | 105726 | T HANSEN GRUPPEN A/S | 315.5 | Jesper Olsen | Enterprise DK | Change
NSW-040717 | 105726 | T HANSEN GRUPPEN A/S | 67 | Jesper Olsen | Enterprise DK | Change
NSW-060749 | 105726 | T HANSEN GRUPPEN A/S | 645 | Jesper Olsen | Enterprise DK | New Sales
NBM-060810 | 105702 | EVE Group ApS | 1247.96 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NBM-060813 | 105702 | EVE Group ApS | 1282.04 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NBM-060816 | 105702 | EVE Group ApS | 1596.94 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NBM-060819 | 105702 | EVE Group ApS | 1771.43 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060808 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060811 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060814 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060817 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NML-060809 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NML-060812 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NML-060815 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NML-060818 | 105702 | EVE Group ApS | 600 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-031368 | 105806 | Plus A/S | 1455 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change
NMA-031351 | 105806 | Plus A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change
NSW-031350 | 105806 | Plus A/S | 200 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | Change
NKA-060791 | 105807 | Reversec Denmark A/S | 1693 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NMA-060793 | 105807 | Reversec Denmark A/S | 300 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NSW-060792 | 105807 | Reversec Denmark A/S | 300 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NBM-060807 | 101973 | Vaekst ApS | 1909.46 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060806 | 101973 | Vaekst ApS | 1000 | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | New Sales
NKA-060802 | 105821 | Ingeniør Huse A/S | 1555 | Jane Birgitte Høgaard | SMB Portfolio DK | New Sales
NKA-060743 | 103412 | Alpha Solutions A/S | 1460 | Line Skov | SMB Portfolio DK | New Sales
NKA-060821 | 105827 | Alveus Therapeutics ApS | 1095 | Line Skov | SMB Portfolio DK | New Sales
NKA-035834 | 105736 | Bauer Media ApS |  | Line Skov | SMB Portfolio DK | Change
NKA-060761 | 105746 | Blue Ocean Robotics ApS | 1711 | Line Skov | SMB Portfolio DK | New Sales
C31228-1136880-01 | 101264-028 | Boligselskabet Lejerbo | 522 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136881-01 | 101264-028 | Boligselskabet Lejerbo | 1914 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136882-01 | 101264-028 | Boligselskabet Lejerbo | 2342 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136883-01 | 101264-028 | Boligselskabet Lejerbo | 2181 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136884-01 | 101264-028 | Boligselskabet Lejerbo | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136886-01 | 101264-028 | Boligselskabet Lejerbo | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
C31228-1136887-01 | 101264-028 | Boligselskabet Lejerbo | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
NKA-060762 | 105656 | Borgernær Psykiatri Danmark P/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales
NML-060763 | 105656 | Borgernær Psykiatri Danmark P/S | 622.5 | Line Skov | SMB Portfolio DK | New Sales
C35824-1136898-01 | 106646-005 | CEGO A/S | 1375 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136899-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136900-01 | 106646-005 | CEGO A/S | 100 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136902-01 | 106646-005 | CEGO A/S | 1455 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136903-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136905-01 | 106646-005 | CEGO A/S | 1375 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136906-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136907-01 | 106646-005 | CEGO A/S | 100 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136909-01 | 106646-005 | CEGO A/S | 1375 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136910-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136911-01 | 106646-005 | CEGO A/S | 100 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136913-01 | 106646-005 | CEGO A/S | 1455 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136914-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136916-01 | 106646-005 | CEGO A/S | 1455 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136917-01 | 106646-005 | CEGO A/S | 345 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136919-01 | 106646-005 | CEGO A/S | 15 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136920-01 | 106646-005 | CEGO A/S | 128 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136921-01 | 106646-005 | CEGO A/S | 128 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136922-01 | 106646-005 | CEGO A/S | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136923-01 | 106646-005 | CEGO A/S | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136924-01 | 106646-005 | CEGO A/S | 0 | Shazia Mobin | SMB Portfolio DK | New Sales
C35824-1136925-01 | 106646-005 | CEGO A/S | 128 | Shazia Mobin | SMB Portfolio DK | New Sales
NKA-060770 | 105797 | Cim Industrial Systems A/S | 1782 | Merete Helme | SMB Portfolio DK | New Sales
NKA-060765 | 105335 | Conaxess Trade Denmark A/S | 1810 | Line Skov | SMB Portfolio DK | New Sales
NKA-060766 | 105770 | Dollarstore ApS | 1155 | Merete Helme | SMB Portfolio DK | New Sales
NKA-060788 | 105782 | Ecotree International ApS | 995 | Line Skov | SMB Portfolio DK | New Sales
NKA-060767 | 105749 | Emineral A/S | 797.5 | Line Skov | SMB Portfolio DK | New Sales
NML-060768 | 105749 | Emineral A/S | 797.5 | Line Skov | SMB Portfolio DK | New Sales
NKA-060776 | 105353 | N'age ApS | 1055 | Line Skov | SMB Portfolio DK | New Sales
NKA-060777 | 105353 | N'age ApS | 1055 | Line Skov | SMB Portfolio DK | New Sales
NKA-060790 | 105767 | PM-SOLUTIONS APS | 1755 | Line Skov | SMB Portfolio DK | New Sales
NKA-060764 | 105697 | Sentry Technologies ApS | 1595 | Line Skov | SMB Portfolio DK | New Sales
NKA-060769 | 105744 | Skypuzzler ApS | 1295 | Merete Helme | SMB Portfolio DK | New Sales