## 20250521
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 445 | 580 | 218 | 175 | 27 |  | 1445
| New Sales |  | 389 | 427 | 200 | 165 | 27 |  | 1208
| Change |  | 56 | 153 | 18 | 10 | 0 |  | 237
| MRC DKK | Total | 468123.7167 | 485585.69 | 203079.7967 | 209678.79 | 88499 |  | 1454966.9933
| New Sales |  | 517128.16 | 455048.13 | 195357.75 | 210358.81 | 88499 |  | 1466391.85
| Change |  | -49004.4433 | 30537.56 | 7722.0467 | -680.02 | 0 |  | -11424.8567
| MRC EUR | Total | 62765.4716 | 65106.7522 | 27228.6978 | 28113.483 | 11865.8407 |  | 195080.2453
| New Sales |  | 69335.9291 | 61012.3125 | 26193.3349 | 28204.6592 | 11865.8407 |  | 196612.0765
| Change |  | -6570.4575 | 4094.4398 | 1035.3628 | -91.1763 | 0 |  | -1531.8312
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 19 | 365 | 412 | 290 | 65 | 279 | 330 | 73 | 35 | 0 | 34 | 20 | 1922 | 2067 | 145
| New Sales |  | 14 | 360 | 284 | 274 | 63 | 153 | 300 | 51 | 12 | 0 | 26 | 18 | 1555 | 1682 | 127
| Change |  | 5 | 5 | 128 | 16 | 2 | 126 | 30 | 22 | 23 | 0 | 8 | 2 | 367 | 385 | 18
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 202 | 4 | 0 | 13 | 10 | 5 | 2 | 0 | 0 | 1 | 240 | 243
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 27 | 20 | 9 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 123 | 123
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 4 | 38 | 3 | 113 | 16 | 7 | 2 | 0 | 0 | 0 | 186 | 186
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 6 | 36 | 3 | 7 | 10 | 11 | 0 | 0 | 0 | 6 | 80 | 80
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 84 | 62 | 42 | 54 | 220 | 40 | 5 | 0 | 0 | 0 | 513 | 514
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 38 | 77 | 6 | 13 | 31 | 1 | 0 | 0 | 0 | 0 | 167 | 167
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 1 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 14 | 14
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 4 | 25 | 1 | 20 | 6 | 0 | 3 | 0 | 0 | 4 | 63 | 63
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 34 | 0 | 36 | 37
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 5 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 7 | 347 | 349
| Orders without status |  | 0 | 0 | 0 | 9 | 0 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 17 | 17
| Sum |  | 19 | 365 | 412 | 290 | 65 | 279 | 330 | 73 | 35 | 0 | 34 | 20 | 1922 | 1931
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 12422.11 | 343939.54 | 464231.15 | 273499.01 | 65827.06 | 264426.0867 | 389731.9267 | 67902.47 | 49082.5 | 0 | 39760.79 | 32776 | 2003598.6433 | 2188509.9833 | 184911.34 |  | All orders |  | 1665.5417 | 46115.0048 | 62243.5609 | 36670.4222 | 8826.014 | 35453.9354 | 52254.7935 | 9104.2825 | 6580.9233 | 0 | 5331.0795 | 4394.5671 | 268640.1249 | 293432.8176 | 24792.6927
| New Sales |  | 13067 | 383974.12 | 419859.31 | 273084.19 | 64072.06 | 289946.55 | 395868.14 | 52676.73 | 21242.5 | 0 | 40366 | 33204 | 1987360.6 | 2144318.22 | 156957.62 |  | New Sales |  | 1752.0078 | 51482.7937 | 56294.2373 | 36614.8036 | 8590.7057 | 38875.6888 | 53077.5297 | 7062.8334 | 2848.1692 | 0 | 5412.2253 | 4451.9529 | 266462.9473 | 287507.6385 | 21044.6911
| Change |  | -644.89 | -40034.58 | 44371.84 | 414.82 | 1755 | -25520.4633 | -6136.2133 | 15225.74 | 27840 | 0 | -605.21 | -428 | 16238.0433 | 44191.7633 | 27953.72 |  | Change |  | -86.4661 | -5367.7889 | 5949.3236 | 55.6186 | 235.3083 | -3421.7534 | -822.7362 | 2041.4491 | 3732.7541 | 0 | -81.1458 | -57.3857 | 2177.1776 | 5925.1791 | 3748.0016
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 84 | 34 | 55 | 0 | 54 | 125 | 48 | 5 | 0 | 24 | 1 | 432 | 445 | 13
| New Sales |  | 2 | 79 | 21 | 47 | 0 | 49 | 113 | 43 | 4 | 0 | 20 | 1 | 379 | 389 | 10
| Change |  | 0 | 5 | 13 | 8 | 0 | 5 | 12 | 5 | 1 | 0 | 4 | 0 | 53 | 56 | 3
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 14 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 28 | 28 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 27 | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 35 | 35 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 16 | 0 | 9 | 11 | 4 | 0 | 0 | 0 | 0 | 40 | 40 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 0 | 0 | 2 | 6 | 4 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 8 | 2 | 0 | 4 | 90 | 28 | 2 | 0 | 0 | 0 | 138 | 138 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 17 | 0 | 7 | 10 | 1 | 0 | 0 | 0 | 0 | 38 | 38 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 10 | 0 | 12 | 2 | 0 | 1 | 0 | 0 | 1 | 28 | 28 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 24 | 0 | 25 | 25 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 53 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| Sum |  | 2 | 84 | 34 | 55 | 0 | 54 | 125 | 48 | 5 | 0 | 24 | 1 | 432 | 432 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1958 | 86129.14 | 49904.46 | 51406.3767 | 0 | 63654.67 | 125694.07 | 44675.21 | 8600 | 0 | 23429.79 | 1315 | 456766.7167 | 468123.7167 | 11357 |  | All orders |  | 262.5263 | 11548.0927 | 6691.1307 | 6892.5059 | 0 | 8534.7425 | 16852.9115 | 5989.9991 | 1153.0778 | 0 | 3141.4384 | 176.3136 | 61242.7385 | XX
| New Sales |  | 1958 | 126163.72 | 36889 | 47572.94 | 0 | 88833.55 | 126703.22 | 45495.73 | 8560 | 0 | 24135 | 1315 | 507626.16 | 517128.16 | 9502 |  | New Sales |  | 262.5263 | 16915.8816 | 4946.0333 | 6378.5233 | 0 | 11910.6968 | 16988.2172 | 6100.0134 | 1147.7146 | 0 | 3235.9921 | 176.3136 | 68061.9122
| Change |  | 0 | -40034.58 | 13015.46 | 3833.4367 | 0 | -25178.88 | -1009.15 | -820.52 | 40 | 0 | -705.21 | 0 | -50859.4433 | -49004.4433 | 1855 |  | Change |  | 0 | -5367.7889 | 1745.0974 | 513.9826 | 0 | -3375.9543 | -135.3056 | -110.0143 | 5.3632 | 0 | -94.5537 | 0 | -6819.1737
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 78 | 54 | 63 | 26 | 188 | 125 | 14 | 5 | 0 | 4 | 7 | 567 | 580 | 13
| New Sales |  | 3 | 78 | 34 | 59 | 26 | 76 | 119 | 8 | 3 | 0 | 3 | 5 | 414 | 427 | 13
| Change |  | 0 | 0 | 20 | 4 | 0 | 112 | 6 | 6 | 2 | 0 | 1 | 2 | 153 | 153 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 16 | 16 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1 | 10 | 2 | 93 | 3 | 3 | 0 | 0 | 0 | 0 | 112 | 112 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 1 | 8 | 0 | 4 | 3 | 7 | 0 | 0 | 0 | 6 | 30 | 30 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 26 | 14 | 19 | 42 | 86 | 2 | 0 | 0 | 0 | 0 | 191 | 191 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 7 | 15 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 2 | 0 | 5 | 3 | 0 | 2 | 0 | 0 | 1 | 13 | 13 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 5 | 5 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 77 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 81 | 81 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| Sum |  | 3 | 78 | 54 | 63 | 26 | 188 | 125 | 14 | 5 | 0 | 4 | 7 | 567 | 567 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 77290.4 | 49131.8767 | 47901.8833 | 22246.5 | 47449.1667 | 134004.1033 | 23227.26 | 32405 | 0 | 5040 | 2048 | 442839.19 | 485585.69 | 42746.5 |  | All orders |  | 280.8951 | 10363.005 | 6587.5436 | 6422.6276 | 2982.7843 | 6361.9279 | 17967.1109 | 3114.2834 | 4344.8239 | 0 | 675.7572 | 274.5934 | 59375.3523
| New Sales |  | 2095 | 77290.4 | 54083.06 | 51320.5 | 22246.5 | 47768 | 137396.17 | 7181 | 5405 | 0 | 5040 | 2476 | 412301.63 | 455048.13 | 42746.5 |  | New Sales |  | 280.8951 | 10363.005 | 7251.3924 | 6880.9916 | 2982.7843 | 6404.6767 | 18421.9152 | 962.8199 | 724.696 | 0 | 675.7572 | 331.9791 | 55280.9125
| Change |  | 0 | 0 | -4951.1833 | -3418.6167 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -428 | 30537.56 | 30537.56 | 0 |  | Change |  | 0 | 0 | -663.8488 | -458.3641 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -57.3857 | 4094.4398
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 73 | 19 | 52 | 16 | 5 | 32 | 0 | 0 | 0 | 1 | 5 | 204 | 218 | 14
| New Sales |  | 1 | 73 | 13 | 50 | 14 | 5 | 26 | 0 | 0 | 0 | 0 | 5 | 187 | 200 | 13
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 8
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 41 | 36
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 112 | 108
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 11
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 14 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 53 | 191 | 138
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 17 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 24 | 32 | 8
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13 | 9
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5 | 4
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 78 | 81 | 3
| Orders without status |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 73 | 19 | 52 | 16 | 5 | 32 | 0 | 0 | 0 | 1 | 5 | 204 | 569 | 365
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 61150 | 17355.0433 | 40298.5 | 15849.5 | 6290 | 34613.2533 | 0 | 0 | 0 | 0 | 12773 | 192929.2967 | 203079.7967 | 10150.5 |  | All orders |  | 616.7625 | 8198.9193 | 2326.9436 | 5403.175 | 2125.0821 | 843.3557 | 4640.9039 | 0 | 0 | 0 | 0 | 1712.5887 | 25867.7308
| New Sales |  | 4600 | 61150 | 11207 | 40298.5 | 14094.5 | 6290 | 34794.25 | 0 | 0 | 0 | 0 | 12773 | 185207.25 | 195357.75 | 10150.5 |  | New Sales |  | 616.7625 | 8198.9193 | 1502.6212 | 5403.175 | 1889.7738 | 843.3557 | 4665.1717 | 0 | 0 | 0 | 0 | 1712.5887 | 24832.368
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | -180.9967 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | -24.2678 | 0 | 0 | 0 | 0 | 0 | 1035.3628
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 175 | 23
| New Sales |  | 2 | 34 | 84 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 142 | 165 | 23
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 16 | -58
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 112 | 109
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 17 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 191 | 169
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 30
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 13 | 8
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | 3
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 81 | 49
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 566 | 414
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 203079.7967 | 34160.0067 |  | All orders |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647
| New Sales |  | 1495 | 40220 | 79381 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 169599.81 | 195357.75 | 25757.94 |  | New Sales |  | 200.4478 | 5392.6498 | 10643.3101 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22739.741
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 7722.0467 | 8402.0667 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 175 | 148
| New Sales |  | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 165 | 138
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 16 | 15
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 112
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 191 | 187
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 12 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 32 | 17
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 81
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 566 | 539
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 0 | 63075 | 13149 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 203079.7967 | 114580.7967 |  | All orders |  | 0 | 0 | 8457.021 | 1763.0023 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| New Sales |  | 0 | 0 | 63075 | 13149 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 195357.75 | 106858.75 |  | New Sales |  | 0 | 0 | 8457.021 | 1763.0023 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 20250522
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 445 | 580 | 218 | 175 | 27 |  | 1445
| New Sales |  | 389 | 427 | 200 | 165 | 27 |  | 1208
| Change |  | 56 | 153 | 18 | 10 | 0 |  | 237
| MRC DKK | Total | 468123.7167 | 485585.69 | 203079.7967 | 209678.79 | 88499 |  | 1454966.9933
| New Sales |  | 517128.16 | 455048.13 | 195357.75 | 210358.81 | 88499 |  | 1466391.85
| Change |  | -49004.4433 | 30537.56 | 7722.0467 | -680.02 | 0 |  | -11424.8567
| MRC EUR | Total | 62765.4716 | 65106.7522 | 27228.6978 | 28113.483 | 11865.8407 |  | 195080.2453
| New Sales |  | 69335.9291 | 61012.3125 | 26193.3349 | 28204.6592 | 11865.8407 |  | 196612.0765
| Change |  | -6570.4575 | 4094.4398 | 1035.3628 | -91.1763 | 0 |  | -1531.8312
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 365 | 386 | 270 | 68 | 272 | 342 | 71 | 40 | 0 | 62 | 26 | 1922 | 2067 | 145
| New Sales |  | 15 | 360 | 260 | 255 | 66 | 147 | 312 | 50 | 16 | 0 | 52 | 22 | 1555 | 1682 | 127
| Change |  | 5 | 5 | 126 | 15 | 2 | 125 | 30 | 21 | 24 | 0 | 10 | 4 | 367 | 385 | 18
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 145 | 4 | 0 | 13 | 10 | 5 | 2 | 0 | 0 | 8 | 190 | 193
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 27 | 20 | 13 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 127 | 127
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 25 | 3 | 114 | 10 | 7 | 2 | 0 | 0 | 0 | 182 | 182
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 23 | 2 | 5 | 10 | 10 | 0 | 0 | 0 | 6 | 62 | 62
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 64 | 70 | 43 | 60 | 224 | 38 | 3 | 0 | 0 | 0 | 508 | 509
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 23 | 90 | 5 | 13 | 35 | 1 | 0 | 0 | 0 | 0 | 168 | 168
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 1 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 14 | 14
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 3 | 48 | 48
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 0 | 62 | 0 | 72 | 73
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 7 | 400 | 402
| Orders without status |  | 0 | 0 | 0 | 3 | 3 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 14 | 14
| Sum |  | 20 | 365 | 386 | 270 | 68 | 272 | 342 | 71 | 40 | 0 | 62 | 26 | 1922 | 1931
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 343939.54 | 384435.31 | 318289.51 | 67314.56 | 244361.7767 | 404756.0467 | 66402.47 | 50386.5 | 0 | 76672.79 | 33348.03 | 2003598.6433 | 2188509.9833 | 184911.34 |  | All orders |  | 1835.8218 | 46115.0048 | 51544.6295 | 42675.8792 | 9025.4562 | 32763.7366 | 54269.2097 | 8903.1643 | 6755.762 | 0 | 10280.1966 | 4471.2642 | 268640.1249 | 293432.8176 | 24792.6927
| New Sales |  | 14337 | 383974.12 | 339055.5 | 317874.69 | 65559.56 | 269445.55 | 412923.95 | 51076.73 | 22646.5 | 0 | 75683 | 34784 | 1987360.6 | 2144318.22 | 156957.62 |  | New Sales |  | 1922.2879 | 51482.7937 | 45460.1585 | 42620.2606 | 8790.1479 | 36126.9391 | 55364.3525 | 6848.3073 | 3036.4158 | 0 | 10147.4867 | 4663.7974 | 266462.9473 | 287507.6385 | 21044.6911
| Change |  | -644.89 | -40034.58 | 45379.81 | 414.82 | 1755 | -25083.7733 | -8167.9033 | 15325.74 | 27740 | 0 | 989.79 | -1435.97 | 16238.0433 | 44191.7633 | 27953.72 |  | Change |  | -86.4661 | -5367.7889 | 6084.471 | 55.6186 | 235.3083 | -3363.2025 | -1095.1428 | 2054.857 | 3719.3462 | 0 | 132.7099 | -192.5332 | 2177.1776 | 5925.1791 | 3748.0016
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 199401.9567 | 14434 | 0 | 13105.66 | 29889.7933 | 2034 | 3510 | 0 | 0 | 3482.03 | 279982.44 | 280879.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 26735.5774 | 1935.2936 | 0 | 1757.1913 | 4007.588 | 272.7163 | 470.6166 | 0 | 0 | 466.8664 | 37539.7128 | 37659.9815
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 30973.02 | 25775 | 17580 | 14476.06 | 38505 | 44300 | 5985.41 | 0 | 0 | 0 | 9100 | 187643.49 | 187643.49 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 4152.8257 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 5939.6914 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 25159.0161 | 25159.0161
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 1040 | 0 | 0 | 0 | 0 | 0 | 11296.3 | 11296.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 139.442 | 0 | 0 | 0 | 0 | 0 | 1514.5945 | 1514.5945
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 16632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18617.47 | 18617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 2230.0618 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2496.2083 | 2496.2083
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 24587.5 | 3243.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3296.6628 | 434.8846 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 15624.6467 | 400 | -15580.02 | 24711.81 | 19355 | 0 | 0 | 0 | 1948 | 62097.5167 | 62097.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 2094.9341 | 53.6315 | -2088.9506 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | 261.1855 | 8325.9612 | 8325.9612
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 28258.5833 | 60775.61 | 36788 | 28832.2567 | 192770.9433 | 28326.3 | 4130 | 0 | 0 | 0 | 390162.8133 | 390999.8133 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3788.8773 | 8148.7216 | 4932.4913 | 3865.7947 | 25846.499 | 3797.9566 | 553.7455 | 0 | 0 | 0 | 52312.5663 | 52424.7903
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22195.28 | 151807 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 296211.03 | 296211.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 2975.9168 | 20354.1021 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39715.6229 | 39715.6229
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 11684.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1566.6519
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 1038 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 21222.97 | 21222.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 139.1738 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 2845.5506 | 2845.5506
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 4191.5633 | 0 | 0 | 1520 | 0 | 0 | 0 | 0 | 0 | 5711.5633 | 5711.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 561.9998 | 0 | 0 | 203.7998 | 0 | 0 | 0 | 0 | 0 | 765.7996 | 765.7996
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2200 | 103343.05 | 103343.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 294.9734 | 13856.1133 | 13856.1133
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 11359 | 0 | 76672.79 | 0 | 89526.79 | 89970.478 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1523.0012 | 0 | 10280.1966 | 0 | 12003.6456 | 12063.1348
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 16618 | 329554 | 330235.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 2228.1217 | 44186.2087 | 44277.5673
| Orders without status |  | 0 | 0 | 0 | 1260 | 1495 | 0 | 4615 | 942.5 | 0 | 0 | 0 | 0 | 8312.5 | 8312.5 |  |  | Orders without status |  | 0 | 0 | 0 | 168.9393 | 200.4478 | 0 | 618.7737 | 126.3693 | 0 | 0 | 0 | 0 | 1114.5301 | 1114.5301
| Sum |  | 13692.11 | 343939.54 | 384435.31 | 318289.51 | 67314.56 | 244361.7767 | 404756.0467 | 66402.47 | 50386.5 | 0 | 76672.79 | 33348.03 | 2003598.6433 | 2008307.7113 |  |  | Sum |  | 1835.8218 | 46115.0048 | 51544.6295 | 42675.8792 | 9025.4562 | 32763.7366 | 54269.2097 | 8903.1643 | 6755.762 | 0 | 10280.1966 | 4471.2642 | 268640.1249 | 269271.5111
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 84 | 31 | 49 | 0 | 42 | 119 | 46 | 8 | 0 | 48 | 3 | 432 | 445 | 13
| New Sales |  | 2 | 79 | 20 | 41 | 0 | 37 | 109 | 42 | 6 | 0 | 42 | 1 | 379 | 389 | 10
| Change |  | 0 | 5 | 11 | 8 | 0 | 5 | 10 | 4 | 2 | 0 | 6 | 2 | 53 | 56 | 3
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 11 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 3 | 28 | 28 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 27 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 33 | 33 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 4 | 0 | 2 | 5 | 3 | 0 | 0 | 0 | 0 | 17 | 17 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 8 | 0 | 2 | 85 | 26 | 0 | 0 | 0 | 0 | 129 | 129 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 17 | 0 | 7 | 10 | 1 | 0 | 0 | 0 | 0 | 38 | 38 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 7 | 0 | 1 | 0 | 0 | 0 | 16 | 16 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 48 | 0 | 55 | 55 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 53 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
| Orders without status |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| Sum |  | 2 | 84 | 31 | 49 | 0 | 42 | 119 | 46 | 8 | 0 | 48 | 3 | 432 | 432 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1958 | 86129.14 | 49417.43 | 43052.3767 | 0 | 45113.67 | 124771.07 | 43175.21 | 7159 | 0 | 55503.79 | 487.03 | 456766.7167 | 468123.7167 | 11357 |  | All orders |  | 262.5263 | 11548.0927 | 6625.8303 | 5772.4115 | 0 | 6048.7873 | 16729.1568 | 5788.8808 | 959.8702 | 0 | 7441.8822 | 65.3004 | 61242.7385 | XX
| New Sales |  | 1958 | 126163.72 | 35394 | 39218.94 | 0 | 70292.55 | 127375.22 | 43895.73 | 7219 | 0 | 54614 | 1495 | 507626.16 | 517128.16 | 9502 |  | New Sales |  | 262.5263 | 16915.8816 | 4745.5855 | 5258.4289 | 0 | 9424.7416 | 17078.3181 | 5885.4873 | 967.9149 | 0 | 7322.5802 | 200.4478 | 68061.9122
| Change |  | 0 | -40034.58 | 14023.43 | 3833.4367 | 0 | -25178.88 | -2604.15 | -720.52 | -60 | 0 | 889.79 | -1007.97 | -50859.4433 | -49004.4433 | 1855 |  | Change |  | 0 | -5367.7889 | 1880.2448 | 513.9826 | 0 | -3375.9543 | -349.1613 | -96.6065 | -8.0447 | 0 | 119.302 | -135.1474 | -6819.1737
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 13316 | 0 | 2034 | 0 | 0 | 0 | 487.03 | 39748.4867 | 39748.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1785.3935 | 0 | 272.7163 | 0 | 0 | 0 | 65.3004 | 5329.4299 | 5329.4299
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 30973.02 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 51158.43 | 51158.43 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 4152.8257 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 6859.2615 | 6859.2615
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 1040 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.442 | 0 | 0 | 0 | 0 | 0 | 139.442 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 1888.6467 | 0 | -18935.02 | 12335 | 1060 | 0 | 0 | 0 | 0 | -2083.6933 | -2083.6933 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 253.2275 | 0 | -2538.785 | 1653.8621 | 142.1235 | 0 | 0 | 0 | 0 | -279.3791 | -279.3791
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4914.2267 | 0 | 2669 | 72773.07 | 26266.3 | 0 | 0 | 0 | 0 | 117323.45 | 117323.45 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 658.8937 | 0 | 357.8563 | 9757.3267 | 3521.7543 | 0 | 0 | 0 | 0 | 15730.5887 | 15730.5887
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 19141 | 0 | 8890 | 16263 | 979 | 0 | 0 | 0 | 0 | 50673 | 50673 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2566.4025 | 0 | 1191.9606 | 2180.5237 | 131.2632 | 0 | 0 | 0 | 0 | 6794.1756 | 6794.1756
| 3.1.1 Pending external 3rd party: Open-Net |  | 1958 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.56 | 415.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 262.5263 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.7178 | 55.7178
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 1520 | 0 | 0 | 0 | 0 | 0 | 211.5633 | 211.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 203.7998 | 0 | 0 | 0 | 0 | 0 | 28.3662 | 28.3662
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 7100 | 0 | 400 | 0 | 0 | 0 | 33106.05 | 33106.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 951.9596 | 0 | 53.6315 | 0 | 0 | 0 | 4438.8198 | 4438.8198
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 6719 | 0 | 55503.79 | 0 | 63717.79 | 63717.79 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 900.8755 | 0 | 7441.8822 | 0 | 8543.2056 | 8543.2056
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 45650 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46730 | 46730 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 6120.6977 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6265.5029 | 6265.5029
| Orders without status |  | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 942.5 | 0 | 0 | 0 | 0 | 2202.5 | 2202.5 |  |  | Orders without status |  | 0 | 0 | 0 | 168.9393 | 0 | 0 | 0 | 126.3693 | 0 | 0 | 0 | 0 | 295.3086 | 295.3086
| Sum |  | 1958 | 86129.14 | 49417.43 | 43052.3767 | 0 | 45113.67 | 124771.07 | 43175.21 | 7159 | 0 | 55503.79 | 487.03 | 456766.7167 | 456766.7167 |  |  | Sum |  | 262.5263 | 11548.0927 | 6625.8303 | 5772.4115 | 0 | 6048.7873 | 16729.1568 | 5788.8808 | 959.8702 | 0 | 7441.8822 | 65.3004 | 61242.7385 | 61242.7385
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 78 | 48 | 63 | 24 | 185 | 132 | 14 | 7 | 0 | 6 | 7 | 567 | 580 | 13
| New Sales |  | 3 | 78 | 28 | 59 | 24 | 73 | 126 | 8 | 5 | 0 | 5 | 5 | 414 | 427 | 13
| Change |  | 0 | 0 | 20 | 4 | 0 | 112 | 6 | 6 | 2 | 0 | 1 | 2 | 153 | 153 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 8 | 2 | 93 | 3 | 3 | 0 | 0 | 0 | 0 | 116 | 116 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 8 | 0 | 3 | 4 | 7 | 0 | 0 | 0 | 6 | 29 | 29 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 14 | 17 | 43 | 90 | 2 | 0 | 0 | 0 | 0 | 186 | 186 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 19 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 1 | 8 | 8 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 0 | 9 | 9 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 77 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 82 | 82 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| Sum |  | 3 | 78 | 48 | 63 | 24 | 185 | 132 | 14 | 7 | 0 | 6 | 7 | 567 | 567 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 77290.4 | 33968.0667 | 56531.8833 | 20401.5 | 44434.1667 | 141457.9133 | 23227.26 | 35150 | 0 | 6235 | 2048 | 442839.19 | 485585.69 | 42746.5 |  | All orders |  | 280.8951 | 10363.005 | 4554.398 | 7579.7277 | 2735.4089 | 5957.6803 | 18966.5089 | 3114.2834 | 4712.8702 | 0 | 835.9814 | 274.5934 | 59375.3523
| New Sales |  | 2095 | 77290.4 | 38919.25 | 59950.5 | 20401.5 | 44753 | 144849.98 | 7181 | 8150 | 0 | 6235 | 2476 | 412301.63 | 455048.13 | 42746.5 |  | New Sales |  | 280.8951 | 10363.005 | 5218.2468 | 8038.0918 | 2735.4089 | 6000.4291 | 19421.3132 | 962.8199 | 1092.7423 | 0 | 835.9814 | 331.9791 | 55280.9125
| Change |  | 0 | 0 | -4951.1833 | -3418.6167 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -428 | 30537.56 | 30537.56 | 0 |  | Change |  | 0 | 0 | -663.8488 | -458.3641 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -57.3857 | 4094.4398
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 0 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 22184.3233 | 22184.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 0 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 2974.4477 | 2974.4477
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 51158.43 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 6859.2615
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 6882.5 | 2247.5 | 2177.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 22201.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 922.7974 | 301.3421 | 291.9982 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2976.6971 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 9881 | 0 | 3355 | 8376.81 | 18295 | 0 | 0 | 0 | 1948 | 55596.21 | -2083.6933 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 1324.8327 | 0 | 449.8344 | 1123.1527 | 2452.9719 | 0 | 0 | 0 | 261.1855 | 7454.2738 | -279.3791
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 4090.3833 | 14775 | 13378.3567 | 75544.06 | 2060 | 0 | 0 | 0 | 0 | 111748.7267 | 117323.45 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 548.4337 | 1981.0144 | 1793.7542 | 10128.8578 | 276.2024 | 0 | 0 | 0 | 0 | 14983.1365 | 15730.5887
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 27228 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 43365.86 | 50673 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3650.6979 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 5814.443 | 6794.1756
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | 415.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | 55.7178
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495 | 211.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334.5266 | 28.3662
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 3125 | 14462.25 | 0 | 27000 | 0 | 0 | 100 | 44687.25 | 33106.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 418.9963 | 1939.0813 | 0 | 3620.1279 | 0 | 0 | 13.4079 | 5991.6134 | 4438.8198
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4640 | 0 | 6235 | 0 | 10875 | 63717.79 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622.1257 | 0 | 835.9814 | 0 | 1458.1071 | 8543.2056
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 63550 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 69358 | 46730 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8520.7085 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9299.4382 | 6265.5029
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 475 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 63.6874 | 63.6874
| Sum |  | 2095 | 77290.4 | 33968.0667 | 56531.8833 | 20401.5 | 44434.1667 | 141457.9133 | 23227.26 | 35150 | 0 | 6235 | 2048 | 442839.19 | 437475.0533 |  |  | Sum |  | 280.8951 | 10363.005 | 4554.398 | 7579.7277 | 2735.4089 | 5957.6803 | 18966.5089 | 3114.2834 | 4712.8702 | 0 | 835.9814 | 274.5934 | 59375.3523 | 58656.1352
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 73 | 19 | 39 | 15 | 12 | 37 | 0 | 0 | 0 | 3 | 5 | 204 | 218 | 14
| New Sales |  | 1 | 73 | 13 | 37 | 13 | 12 | 31 | 0 | 0 | 0 | 2 | 5 | 187 | 200 | 13
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 15 | 8
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 41 | 30
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 116 | 114
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 29 | 27
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 9 | 14 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 66 | 186 | 120
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 24 | 35 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 6
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 9 | 6
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 73 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 79 | 82 | 3
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 73 | 19 | 39 | 15 | 12 | 37 | 0 | 0 | 0 | 3 | 5 | 204 | 569 | 365
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 61150 | 17355.0433 | 32558 | 15597 | 7040 | 38213.2533 | 0 | 0 | 0 | 3643 | 12773 | 192929.2967 | 203079.7967 | 10150.5 |  | All orders |  | 616.7625 | 8198.9193 | 2326.9436 | 4365.3379 | 2091.2272 | 943.9148 | 5123.5876 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 25867.7308
| New Sales |  | 4600 | 61150 | 11207 | 32558 | 13842 | 7040 | 38394.25 | 0 | 0 | 0 | 3643 | 12773 | 185207.25 | 195357.75 | 10150.5 |  | New Sales |  | 616.7625 | 8198.9193 | 1502.6212 | 4365.3379 | 1855.9189 | 943.9148 | 5147.8554 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 24832.368
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | -180.9967 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | -24.2678 | 0 | 0 | 0 | 0 | 0 | 1035.3628
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 0 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 7862 | 7862 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 0 | 0 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 1054.1276 | 1054.1276
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 12749 | 12749 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 0 | 0 | 0 | 0 | 0 | 0 | 1709.3708 | 1709.3708
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 999 | 999 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 133.9447 | 133.9447
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 5520 | 13872 | 5035 | 27322.5033 | 0 | 0 | 0 | 0 | 0 | 52342.5467 | 52342.5467 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 740.115 | 1859.9413 | 675.0868 | 3663.3688 | 0 | 0 | 0 | 0 | 0 | 7018.0264 | 7018.0264
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 8831.75 | 0 | 0 | 0 | 0 | 0 | 30645.75 | 30645.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1184.1505 | 0 | 0 | 0 | 0 | 0 | 4108.9457 | 4108.9457
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3643 | 0 | 3643 | 3643 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488.4491 | 0 | 488.4491 | 488.4491
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 61150 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12773 | 74573 | 74573 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8198.9193 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712.5887 | 9998.6592 | 9998.6592
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 61150 | 17355.0433 | 32558 | 15597 | 7040 | 38213.2533 | 0 | 0 | 0 | 3643 | 12773 | 192929.2967 | 192929.2967 |  |  | Sum |  | 616.7625 | 8198.9193 | 2326.9436 | 4365.3379 | 2091.2272 | 943.9148 | 5123.5876 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 25867.7308 | 25867.7308
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 175 | 23
| New Sales |  | 2 | 34 | 84 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 142 | 165 | 23
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 15 | -59
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 116 | 108
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 12 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 186 | 169
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 35 | 33
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 3
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 9 | 7
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 82 | 50
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 566 | 414
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 203079.7967 | 34160.0067 |  | All orders |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647
| New Sales |  | 1495 | 40220 | 79381 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 169599.81 | 195357.75 | 25757.94 |  | New Sales |  | 200.4478 | 5392.6498 | 10643.3101 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22739.741
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 7722.0467 | 8402.0667 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 67150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79955 | 79955 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 9003.3922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10720.2714 | 10720.2714
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 1395 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 4159.98 | 4159.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 187.0399 | 0 | 0 | 0 | 0 | 341.901 | 0 | 0 | 0 | 557.7652 | 557.7652
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 2800 | 475 | 400 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 5520 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 375.4207 | 63.6874 | 53.6315 | 247.3754 | 0 | 0 | 0 | 0 | 0 | 0 | 740.115 | 740.115
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 27415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27415 | 27415 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 3675.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3675.7706 | 3675.7706
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 168919.79 |  |  | Sum |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647 | 22648.5647
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 175 | 148
| New Sales |  | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 165 | 138
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 116
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 186 | 182
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 35 | 20
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 82
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 566 | 539
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 203079.7967 | 114580.7967 |  | All orders |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| New Sales |  | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 195357.75 | 106858.75 |  | New Sales |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375 | 2375 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.4372 | 318.4372
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 88499 |  |  | Sum |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407 | 11865.8407