## Step Metrics Summary
Step | Avg Days in Step | Avg Orders per Day | Avg MRC per Day
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 2.99 | 364.67 | 335657.74
2. Delivery planning | 2.87 | 404.33 | 461061.91
3. Installation preparation and digging order | 2.83 | 293 | 279384.01
4. Final design | 2.51 | 60.33 | 60773.39
5. Configuration | 2.85 | 291.33 | 262249.75
6. Cabling splicing and installation | 2.68 | 329.67 | 380387.36
7. Service activation | 2.88 | 74 | 67413.88
8. Ready for service | 2.61 | 35.67 | 46896.19
9. Vendor invoice | 0 | 0 | 0
Delivered | 1.98 | 125.33 | 58281.76
Cancelled/terminated/On hold | 2.1 | 42.67 | 45565
Data as of 20250519 - 20250521

## Step Entry-Exit Summary
Step | Entered | Stayed | Exited
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 0 | 366 | 0
2. Delivery planning | 4 | 410 | 8
3. Installation preparation and digging order | 3 | 291 | 17
4. Final design | 11 | 54 | 7
5. Configuration | 7 | 297 | 3
6. Cabling splicing and installation | 7 | 340 | 22
7. Service activation | 1 | 75 | 1
8. Ready for service | 7 | 32 | 4
9. Vendor invoice | 0 | 0 | 0
Delivered | 17 | 173 | 0
Cancelled/terminated/On hold | 3 | 58 | 0
Interval between T1 and T2: 20250519 - 20250521