## Step Metrics Summary
Step | Avg Days in Step | Avg Orders per Day | Avg MRC per Day
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 3.99 | 364.75 | 337728.19
2. Delivery planning | 3.79 | 400 | 442114.51
3. Installation preparation and digging order | 3.47 | 288 | 289782.13
4. Final design | 3.19 | 62.25 | 62408.68
5. Configuration | 3.58 | 286.5 | 257777.76
6. Cabling splicing and installation | 3.3 | 333.25 | 386182.04
7. Service activation | 3.81 | 73.25 | 67161.02
8. Ready for service | 3 | 36.75 | 47768.77
9. Vendor invoice | 0 | 0 | 0
Delivered | 2.01 | 109.75 | 62990.44
Cancelled/terminated/On hold | 2.28 | 38.75 | 42650.76
Data as of 20250519 - 20250522

## Step Entry-Exit Summary
Step | Entered | Stayed | Exited
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 0 | 366 | 0
2. Delivery planning | 4 | 384 | 34
3. Installation preparation and digging order | 23 | 250 | 57
4. Final design | 17 | 52 | 10
5. Configuration | 20 | 277 | 23
6. Cabling splicing and installation | 41 | 317 | 44
7. Service activation | 1 | 73 | 3
8. Ready for service | 15 | 32 | 7
9. Vendor invoice | 0 | 0 | 0
Delivered | 45 | 173 | 0
Cancelled/terminated/On hold | 10 | 58 | 1
Interval between T1 and T2: 20250519 - 20250522

## DPM Avg Orders per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 9 | 2 | 0 | 3 | 7 | 0 | 1 | 0 | 0 | 0.75
Camilla Olesen | 0 | 0 | 2 | 0.5 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 2 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 7 | 0 | 27 | 2 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 50 | 7 | 3 | 10.75 | 7.5 | 3.25 | 0.5 | 0 | 6 | 0
Eva Eisner | 0 | 0 | 0 | 5 | 5.5 | 1.5 | 8.75 | 0 | 1.25 | 0 | 8.5 | 1.5
Flemming Skovdal | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0
Henrik Møller Fyhn | 0 | 0 | 2 | 6 | 2 | 41.75 | 45.25 | 1.5 | 0.75 | 0 | 4.75 | 26.5
Jane Birgitte Høgaard | 0 | 0 | 16 | 23.5 | 0.5 | 97 | 6.25 | 0 | 2 | 0 | 43.25 | 0
Jeppe Mutinda Mbinda | 0 | 27 | 58 | 1 | 1 | 3 | 8 | 0 | 6 | 0 | 2 | 0
Jesper Olsen | 0 | 0 | 3 | 6 | 6 | 2 | 16.75 | 0 | 0.25 | 0 | 0 | 0.5
Julie Lillethorup Kierkegaard | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 55.25 | 0.75 | 0 | 0 | 36 | 3 | 0 | 0 | 2 | 1
Line Skov | 0 | 0 | 1.5 | 34 | 11 | 3.75 | 37.25 | 0 | 0.25 | 0 | 8.25 | 1
Martin Rasmussen | 0 | 0 | 21.5 | 0 | 0 | 1.5 | 10 | 0 | 0 | 0 | 2.5 | 0
Merete Helme | 0 | 0 | 15.75 | 21 | 5.5 | 8.75 | 43.25 | 1 | 1.25 | 0 | 4.25 | 2.25
Mette Vinther | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 85 | 73.25 | 7.75 | 37.25 | 22.75 | 12 | 0 | 0 | 2.25 | 0
Morten Skytte | 0 | 0 | 15 | 9 | 1 | 3.5 | 8 | 4 | 21.5 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 331.5 | 9 | 32.25 | 7.25 | 10 | 20 | 4.5 | 0.5 | 0 | 6.5 | 2.5
Natascha Orlung Baisgaard Andersen | 0 | 0 | 3.75 | 15 | 6 | 17 | 8 | 38 | 1.25 | 0 | 7.5 | 0
Peter Madsen | 0 | 0 | 18.25 | 8.25 | 5 | 6 | 26.75 | 4 | 0.25 | 0 | 6.75 | 1.75
Shazia Mobin | 0 | 0 | 26 | 28 | 0 | 3 | 10 | 0 | 0 | 0 | 5 | 0
Signe Fogh Mach Andersen | 0 | 0 | 9 | 7.5 | 0.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 1
Data as of 20250519 - 20250522

## DPM Avg MRC per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 23172 | 4550 | 0 | 1453.14 | 11631.2 | 0 | 4130 | 0 | 0 | 2310
Camilla Olesen | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 5096 | 2650 | 0 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 8835 | 0 | -6.64 | 8476 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 31029.88 | 6122.5 | 1800 | 5391.79 | 7872.09 | 882.5 | 623.75 | 0 | 5198.5 | 0
Eva Eisner | 0 | 0 | 0 | 3227.5 | 3782.5 | 2122.5 | 5851.25 | 0 | 821.25 | 0 | 5420 | 797.5
Flemming Skovdal | 0 | 19909.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.14 | 0
Henrik Møller Fyhn | 0 | 0 | 6158 | 13801 | 9050 | 30900 | 101570.66 | 747 | 2073.75 | 0 | 10550 | 31958.25
Jane Birgitte Høgaard | 0 | 0 | 46412 | 34692.5 | 422.5 | 79662.5 | 3943.75 | 0 | 27000 | 0 | 7848.75 | 0
Jeppe Mutinda Mbinda | 0 | 30973.02 | 40905.61 | 662 | 2580.06 | 5495 | 9785 | 0 | 7832.5 | 0 | 2247.5 | 0
Jesper Olsen | 0 | 0 | 4095 | 4149 | 6309 | 2650 | 16199.5 | 0 | 187.5 | 0 | 0 | 0
Julie Lillethorup Kierkegaard | 0 | 9506.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 25276 | 570 | 0 | 0 | 11905 | 3833 | 0 | 0 | 975 | 560
Line Skov | 0 | 0 | 141.27 | 24428 | 11633.25 | 6916.15 | 28220.25 | 0 | 348.75 | 0 | 4599.03 | 1595
Martin Rasmussen | 0 | 0 | 35210 | 0 | 0 | 1393 | 25259.81 | 0 | 0 | 0 | 1910 | 0
Merete Helme | 0 | 0 | 10398.8 | 13899.85 | 5085.5 | 10538 | 45236.36 | 200 | 594.77 | 0 | 2621.51 | 1346.26
Mette Vinther | 0 | 0 | 0 | 93.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 116524.92 | 75398.32 | 5433.12 | 74926.25 | 18709.75 | 0 | 0 | 0 | 1367.5 | 0
Morten Skytte | 0 | 0 | 7925 | 6460 | 1725 | 7596.11 | 6779.5 | 817.06 | 2459.25 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 277340 | 12606 | 28091.25 | 5616.5 | 11093 | 15646.5 | 5231.47 | 457.25 | 0 | 4199 | 2005
Natascha Orlung Baisgaard Andersen | 0 | 0 | 1195 | 5354 | 2047.5 | -10320.52 | 3371.43 | 38450 | 800 | 0 | 175.88 | 0
Peter Madsen | 0 | 0 | 55231.74 | 33224.5 | 6550 | 17605 | 35612.45 | 17000 | 440 | 0 | 11964.25 | 1728.75
Shazia Mobin | 0 | 0 | 18648.68 | 23204.22 | 0 | 4174 | 8395 | 0 | 0 | 0 | 3841.38 | 0
Signe Fogh Mach Andersen | 0 | 0 | 7184.61 | 3018.75 | 373.75 | 1092.48 | 2066.53 | 0 | 0 | 0 | 0 | 350
Data as of 20250519 - 20250522

## DPM Avg Days in Step
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 3
Camilla Olesen | 0 | 0 | 4 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 3.5 | 0 | 4 | 2.67 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 4 | 4 | 4 | 3.91 | 3.75 | 3.25 | 1 | 0 | 2.4 | 0
Eva Eisner | 0 | 0 | 0 | 4 | 3.67 | 3 | 3.89 | 0 | 2.5 | 0 | 2 | 2
Flemming Skovdal | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Henrik Møller Fyhn | 0 | 0 | 4 | 3.43 | 4 | 3.98 | 2.83 | 3 | 1 | 0 | 1.46 | 2.47
Jane Birgitte Høgaard | 0 | 0 | 3.37 | 3.62 | 2 | 3.96 | 3.57 | 0 | 4 | 0 | 2.01 | 0
Jeppe Mutinda Mbinda | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 3.43 | 0 | 2 | 0
Jesper Olsen | 0 | 0 | 4 | 4 | 4 | 4 | 3.72 | 0 | 1 | 0 | 0 | 2
Julie Lillethorup Kierkegaard | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 3.95 | 1 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Line Skov | 0 | 0 | 3 | 3.32 | 2.44 | 3 | 3.47 | 0 | 1 | 0 | 1.65 | 4
Martin Rasmussen | 0 | 0 | 3.44 | 0 | 0 | 2 | 3.08 | 0 | 0 | 0 | 2.5 | 0
Merete Helme | 0 | 0 | 3.71 | 3.65 | 3.14 | 2.92 | 3.46 | 4 | 1.67 | 0 | 1.7 | 1.5
Mette Vinther | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 4 | 3.62 | 3.44 | 2.66 | 2.27 | 4 | 0 | 0 | 1.8 | 0
Morten Skytte | 0 | 0 | 4 | 4 | 4 | 3.5 | 3.56 | 3.2 | 3.91 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 3.99 | 4 | 3.79 | 3.22 | 3.64 | 3.81 | 3.6 | 1 | 0 | 1.86 | 2
Natascha Orlung Baisgaard Andersen | 0 | 0 | 3.75 | 4 | 3.43 | 3.78 | 3.2 | 3.9 | 2.5 | 0 | 3.75 | 0
Peter Madsen | 0 | 0 | 2.7 | 1.57 | 4 | 4 | 3.24 | 4 | 1 | 0 | 2.45 | 2.33
Shazia Mobin | 0 | 0 | 4 | 3.86 | 0 | 3 | 4 | 0 | 0 | 0 | 1.82 | 0
Signe Fogh Mach Andersen | 0 | 0 | 2.77 | 2.5 | 1 | 2.14 | 1.67 | 0 | 0 | 0 | 0 | 1
Data as of 20250519 - 20250522

## 1.9 PMO delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Flemming Skovdal | 0 | 3 | 0
Jeppe Mutinda Mbinda | 0 | 27 | 0
Julie Lillethorup Kierkegaard | 0 | 4 | 0
Nanna Søndergaard Skov | 0 | 332 | 0

## 2. Delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 9 | 0
Camilla Olesen | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 50 | 0
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 0 | 16 | 3
Jeppe Mutinda Mbinda | 0 | 58 | 0
Jesper Olsen | 0 | 3 | 0
Kristijan Krsteski | 3 | 53 | 0
Line Skov | 0 | 2 | 0
Martin Rasmussen | 0 | 24 | 1
Merete Helme | 0 | 14 | 3
Michael Kronbach Leth | 0 | 85 | 0
Morten Skytte | 0 | 15 | 0
Nanna Søndergaard Skov | 0 | 9 | 0
Natascha Orlung Baisgaard Andersen | 1 | 3 | 0
Peter Madsen | 0 | 10 | 17
Shazia Mobin | 0 | 26 | 0
Signe Fogh Mach Andersen | 0 | 3 | 10

## 3. Installation preparation and
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 2 | 0
Camilla Olesen | 0 | 1 | 0
Cecilie Heidner Nielsen | 0 | 6 | 2
Christoffer Møller Andersen | 0 | 7 | 0
Eva Eisner | 0 | 5 | 0
Henrik Møller Fyhn | 0 | 7 | 0
Jane Birgitte Høgaard | 3 | 23 | 0
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Kristijan Krsteski | 0 | 0 | 3
Line Skov | 0 | 31 | 10
Merete Helme | 0 | 20 | 3
Mette Vinther | 0 | 1 | 0
Michael Kronbach Leth | 0 | 56 | 23
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 1 | 31 | 2
Natascha Orlung Baisgaard Andersen | 0 | 15 | 0
Peter Madsen | 16 | 4 | 1
Shazia Mobin | 0 | 25 | 4
Signe Fogh Mach Andersen | 3 | 0 | 9

## 4. Final design
Delivery Project Manager | Entered | Stayed | Exited
Christoffer Møller Andersen | 0 | 3 | 0
Eva Eisner | 0 | 5 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 0 | 0 | 1
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Line Skov | 9 | 8 | 1
Merete Helme | 1 | 4 | 2
Michael Kronbach Leth | 2 | 7 | 1
Morten Skytte | 0 | 1 | 0
Nanna Søndergaard Skov | 2 | 5 | 2
Natascha Orlung Baisgaard Andersen | 0 | 5 | 2
Peter Madsen | 0 | 5 | 0
Signe Fogh Mach Andersen | 3 | 0 | 0

## 5. Configuration
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 3 | 0
Camilla Villumsen Kaimer | 0 | 6 | 0
Cecilie Heidner Nielsen | 0 | 27 | 0
Christoffer Møller Andersen | 0 | 10 | 1
Eva Eisner | 1 | 1 | 0
Henrik Møller Fyhn | 0 | 42 | 0
Jane Birgitte Høgaard | 1 | 97 | 0
Jeppe Mutinda Mbinda | 0 | 3 | 0
Jesper Olsen | 0 | 2 | 0
Line Skov | 0 | 4 | 1
Martin Rasmussen | 0 | 0 | 3
Merete Helme | 4 | 7 | 1
Michael Kronbach Leth | 8 | 37 | 11
Morten Skytte | 0 | 4 | 0
Nanna Søndergaard Skov | 1 | 8 | 2
Natascha Orlung Baisgaard Andersen | 2 | 16 | 0
Peter Madsen | 0 | 6 | 0
Shazia Mobin | 0 | 4 | 0
Signe Fogh Mach Andersen | 3 | 0 | 4

## 6. Cabling splicing and install
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 7 | 0
Camilla Olesen | 0 | 4 | 0
Camilla Villumsen Kaimer | 0 | 2 | 0
Cecilie Heidner Nielsen | 2 | 1 | 0
Christoffer Møller Andersen | 0 | 8 | 0
Eva Eisner | 0 | 8 | 1
Henrik Møller Fyhn | 0 | 52 | 12
Jane Birgitte Høgaard | 0 | 5 | 2
Jeppe Mutinda Mbinda | 0 | 8 | 0
Jesper Olsen | 0 | 17 | 1
Kristijan Krsteski | 0 | 36 | 0
Line Skov | 3 | 32 | 8
Martin Rasmussen | 4 | 7 | 2
Merete Helme | 1 | 39 | 10
Michael Kronbach Leth | 23 | 17 | 0
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 0 | 18 | 3
Natascha Orlung Baisgaard Andersen | 0 | 10 | 0
Peter Madsen | 1 | 25 | 5
Shazia Mobin | 0 | 10 | 0
Signe Fogh Mach Andersen | 7 | 2 | 0

## 7. Service activation
Delivery Project Manager | Entered | Stayed | Exited
Camilla Villumsen Kaimer | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 3 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Kristijan Krsteski | 0 | 3 | 0
Merete Helme | 0 | 1 | 0
Michael Kronbach Leth | 0 | 12 | 0
Morten Skytte | 0 | 5 | 0
Nanna Søndergaard Skov | 1 | 4 | 0
Natascha Orlung Baisgaard Andersen | 0 | 37 | 2
Peter Madsen | 0 | 4 | 0

## 8. Ready for service
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 1 | 0
Christoffer Møller Andersen | 2 | 0 | 0
Eva Eisner | 1 | 1 | 0
Henrik Møller Fyhn | 3 | 0 | 2
Jane Birgitte Høgaard | 0 | 2 | 0
Jeppe Mutinda Mbinda | 0 | 5 | 2
Jesper Olsen | 1 | 0 | 0
Line Skov | 1 | 0 | 1
Merete Helme | 3 | 0 | 1
Morten Skytte | 0 | 22 | 0
Nanna Søndergaard Skov | 2 | 0 | 0
Natascha Orlung Baisgaard Andersen | 1 | 1 | 0
Peter Madsen | 1 | 0 | 1