## 20250521
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 445 | 580 | 218 | 175 | 27 |  | 1445
| New Sales |  | 389 | 427 | 200 | 165 | 27 |  | 1208
| Change |  | 56 | 153 | 18 | 10 | 0 |  | 237
| MRC DKK | Total | 468123.7167 | 485585.69 | 203079.7967 | 209678.79 | 88499 |  | 1454966.9933
| New Sales |  | 517128.16 | 455048.13 | 195357.75 | 210358.81 | 88499 |  | 1466391.85
| Change |  | -49004.4433 | 30537.56 | 7722.0467 | -680.02 | 0 |  | -11424.8567
| MRC EUR | Total | 62765.4716 | 65106.7522 | 27228.6978 | 28113.483 | 11865.8407 |  | 195080.2453
| New Sales |  | 69335.9291 | 61012.3125 | 26193.3349 | 28204.6592 | 11865.8407 |  | 196612.0765
| Change |  | -6570.4575 | 4094.4398 | 1035.3628 | -91.1763 | 0 |  | -1531.8312
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 19 | 365 | 412 | 290 | 65 | 279 | 330 | 73 | 35 | 0 | 34 | 20 | 1922 | 2067 | 145
| New Sales |  | 14 | 360 | 284 | 274 | 63 | 153 | 300 | 51 | 12 | 0 | 26 | 18 | 1555 | 1682 | 127
| Change |  | 5 | 5 | 128 | 16 | 2 | 126 | 30 | 22 | 23 | 0 | 8 | 2 | 367 | 385 | 18
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 202 | 4 | 0 | 13 | 10 | 5 | 2 | 0 | 0 | 1 | 240 | 243
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 27 | 20 | 9 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 123 | 123
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 4 | 38 | 3 | 113 | 16 | 7 | 2 | 0 | 0 | 0 | 186 | 186
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 6 | 36 | 3 | 7 | 10 | 11 | 0 | 0 | 0 | 6 | 80 | 80
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 84 | 62 | 42 | 54 | 220 | 40 | 5 | 0 | 0 | 0 | 513 | 514
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 38 | 77 | 6 | 13 | 31 | 1 | 0 | 0 | 0 | 0 | 167 | 167
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 1 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 14 | 14
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 4 | 25 | 1 | 20 | 6 | 0 | 3 | 0 | 0 | 4 | 63 | 63
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 34 | 0 | 36 | 37
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 5 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 7 | 347 | 349
| Orders without status |  | 0 | 0 | 0 | 9 | 0 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 17 | 17
| Sum |  | 19 | 365 | 412 | 290 | 65 | 279 | 330 | 73 | 35 | 0 | 34 | 20 | 1922 | 1931
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 12422.11 | 343939.54 | 464231.15 | 273499.01 | 65827.06 | 264426.0867 | 389731.9267 | 67902.47 | 49082.5 | 0 | 39760.79 | 32776 | 2003598.6433 | 2188509.9833 | 184911.34 |  | All orders |  | 1665.5417 | 46115.0048 | 62243.5609 | 36670.4222 | 8826.014 | 35453.9354 | 52254.7935 | 9104.2825 | 6580.9233 | 0 | 5331.0795 | 4394.5671 | 268640.1249 | 293432.8176 | 24792.6927
| New Sales |  | 13067 | 383974.12 | 419859.31 | 273084.19 | 64072.06 | 289946.55 | 395868.14 | 52676.73 | 21242.5 | 0 | 40366 | 33204 | 1987360.6 | 2144318.22 | 156957.62 |  | New Sales |  | 1752.0078 | 51482.7937 | 56294.2373 | 36614.8036 | 8590.7057 | 38875.6888 | 53077.5297 | 7062.8334 | 2848.1692 | 0 | 5412.2253 | 4451.9529 | 266462.9473 | 287507.6385 | 21044.6911
| Change |  | -644.89 | -40034.58 | 44371.84 | 414.82 | 1755 | -25520.4633 | -6136.2133 | 15225.74 | 27840 | 0 | -605.21 | -428 | 16238.0433 | 44191.7633 | 27953.72 |  | Change |  | -86.4661 | -5367.7889 | 5949.3236 | 55.6186 | 235.3083 | -3421.7534 | -822.7362 | 2041.4491 | 3732.7541 | 0 | -81.1458 | -57.3857 | 2177.1776 | 5925.1791 | 3748.0016
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 84 | 34 | 55 | 0 | 54 | 125 | 48 | 5 | 0 | 24 | 1 | 432 | 445 | 13
| New Sales |  | 2 | 79 | 21 | 47 | 0 | 49 | 113 | 43 | 4 | 0 | 20 | 1 | 379 | 389 | 10
| Change |  | 0 | 5 | 13 | 8 | 0 | 5 | 12 | 5 | 1 | 0 | 4 | 0 | 53 | 56 | 3
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 14 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 28 | 28 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 27 | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 35 | 35 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 16 | 0 | 9 | 11 | 4 | 0 | 0 | 0 | 0 | 40 | 40 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 0 | 0 | 2 | 6 | 4 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 8 | 2 | 0 | 4 | 90 | 28 | 2 | 0 | 0 | 0 | 138 | 138 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 17 | 0 | 7 | 10 | 1 | 0 | 0 | 0 | 0 | 38 | 38 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 10 | 0 | 12 | 2 | 0 | 1 | 0 | 0 | 1 | 28 | 28 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 24 | 0 | 25 | 25 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 53 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| Sum |  | 2 | 84 | 34 | 55 | 0 | 54 | 125 | 48 | 5 | 0 | 24 | 1 | 432 | 432 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1958 | 86129.14 | 49904.46 | 51406.3767 | 0 | 63654.67 | 125694.07 | 44675.21 | 8600 | 0 | 23429.79 | 1315 | 456766.7167 | 468123.7167 | 11357 |  | All orders |  | 262.5263 | 11548.0927 | 6691.1307 | 6892.5059 | 0 | 8534.7425 | 16852.9115 | 5989.9991 | 1153.0778 | 0 | 3141.4384 | 176.3136 | 61242.7385 | XX
| New Sales |  | 1958 | 126163.72 | 36889 | 47572.94 | 0 | 88833.55 | 126703.22 | 45495.73 | 8560 | 0 | 24135 | 1315 | 507626.16 | 517128.16 | 9502 |  | New Sales |  | 262.5263 | 16915.8816 | 4946.0333 | 6378.5233 | 0 | 11910.6968 | 16988.2172 | 6100.0134 | 1147.7146 | 0 | 3235.9921 | 176.3136 | 68061.9122
| Change |  | 0 | -40034.58 | 13015.46 | 3833.4367 | 0 | -25178.88 | -1009.15 | -820.52 | 40 | 0 | -705.21 | 0 | -50859.4433 | -49004.4433 | 1855 |  | Change |  | 0 | -5367.7889 | 1745.0974 | 513.9826 | 0 | -3375.9543 | -135.3056 | -110.0143 | 5.3632 | 0 | -94.5537 | 0 | -6819.1737
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 78 | 54 | 63 | 26 | 188 | 125 | 14 | 5 | 0 | 4 | 7 | 567 | 580 | 13
| New Sales |  | 3 | 78 | 34 | 59 | 26 | 76 | 119 | 8 | 3 | 0 | 3 | 5 | 414 | 427 | 13
| Change |  | 0 | 0 | 20 | 4 | 0 | 112 | 6 | 6 | 2 | 0 | 1 | 2 | 153 | 153 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 16 | 16 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1 | 10 | 2 | 93 | 3 | 3 | 0 | 0 | 0 | 0 | 112 | 112 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 1 | 8 | 0 | 4 | 3 | 7 | 0 | 0 | 0 | 6 | 30 | 30 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 26 | 14 | 19 | 42 | 86 | 2 | 0 | 0 | 0 | 0 | 191 | 191 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 7 | 15 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 2 | 0 | 5 | 3 | 0 | 2 | 0 | 0 | 1 | 13 | 13 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 5 | 5 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 77 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 81 | 81 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| Sum |  | 3 | 78 | 54 | 63 | 26 | 188 | 125 | 14 | 5 | 0 | 4 | 7 | 567 | 567 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 77290.4 | 49131.8767 | 47901.8833 | 22246.5 | 47449.1667 | 134004.1033 | 23227.26 | 32405 | 0 | 5040 | 2048 | 442839.19 | 485585.69 | 42746.5 |  | All orders |  | 280.8951 | 10363.005 | 6587.5436 | 6422.6276 | 2982.7843 | 6361.9279 | 17967.1109 | 3114.2834 | 4344.8239 | 0 | 675.7572 | 274.5934 | 59375.3523
| New Sales |  | 2095 | 77290.4 | 54083.06 | 51320.5 | 22246.5 | 47768 | 137396.17 | 7181 | 5405 | 0 | 5040 | 2476 | 412301.63 | 455048.13 | 42746.5 |  | New Sales |  | 280.8951 | 10363.005 | 7251.3924 | 6880.9916 | 2982.7843 | 6404.6767 | 18421.9152 | 962.8199 | 724.696 | 0 | 675.7572 | 331.9791 | 55280.9125
| Change |  | 0 | 0 | -4951.1833 | -3418.6167 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -428 | 30537.56 | 30537.56 | 0 |  | Change |  | 0 | 0 | -663.8488 | -458.3641 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -57.3857 | 4094.4398
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 73 | 19 | 52 | 16 | 5 | 32 | 0 | 0 | 0 | 1 | 5 | 204 | 218 | 14
| New Sales |  | 1 | 73 | 13 | 50 | 14 | 5 | 26 | 0 | 0 | 0 | 0 | 5 | 187 | 200 | 13
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 8
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 41 | 36
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 112 | 108
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 11
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 14 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 53 | 191 | 138
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 17 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 24 | 32 | 8
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13 | 9
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5 | 4
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 78 | 81 | 3
| Orders without status |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 73 | 19 | 52 | 16 | 5 | 32 | 0 | 0 | 0 | 1 | 5 | 204 | 569 | 365
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 61150 | 17355.0433 | 40298.5 | 15849.5 | 6290 | 34613.2533 | 0 | 0 | 0 | 0 | 12773 | 192929.2967 | 203079.7967 | 10150.5 |  | All orders |  | 616.7625 | 8198.9193 | 2326.9436 | 5403.175 | 2125.0821 | 843.3557 | 4640.9039 | 0 | 0 | 0 | 0 | 1712.5887 | 25867.7308
| New Sales |  | 4600 | 61150 | 11207 | 40298.5 | 14094.5 | 6290 | 34794.25 | 0 | 0 | 0 | 0 | 12773 | 185207.25 | 195357.75 | 10150.5 |  | New Sales |  | 616.7625 | 8198.9193 | 1502.6212 | 5403.175 | 1889.7738 | 843.3557 | 4665.1717 | 0 | 0 | 0 | 0 | 1712.5887 | 24832.368
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | -180.9967 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | -24.2678 | 0 | 0 | 0 | 0 | 0 | 1035.3628
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 175 | 23
| New Sales |  | 2 | 34 | 84 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 142 | 165 | 23
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 16 | -58
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 112 | 109
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 17 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 191 | 169
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 30
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 13 | 8
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | 3
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 81 | 49
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 566 | 414
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 203079.7967 | 34160.0067 |  | All orders |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647
| New Sales |  | 1495 | 40220 | 79381 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 169599.81 | 195357.75 | 25757.94 |  | New Sales |  | 200.4478 | 5392.6498 | 10643.3101 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22739.741
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 7722.0467 | 8402.0667 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 175 | 148
| New Sales |  | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 165 | 138
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 16 | 15
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 112
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 191 | 187
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 12 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 32 | 17
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 81
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 13 | 7 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 566 | 539
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 0 | 63075 | 13149 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 203079.7967 | 114580.7967 |  | All orders |  | 0 | 0 | 8457.021 | 1763.0023 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| New Sales |  | 0 | 0 | 63075 | 13149 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 195357.75 | 106858.75 |  | New Sales |  | 0 | 0 | 8457.021 | 1763.0023 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 20250522
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 445 | 580 | 218 | 175 | 27 |  | 1445
| New Sales |  | 389 | 427 | 200 | 165 | 27 |  | 1208
| Change |  | 56 | 153 | 18 | 10 | 0 |  | 237
| MRC DKK | Total | 468123.7167 | 485585.69 | 203079.7967 | 209678.79 | 88499 |  | 1454966.9933
| New Sales |  | 517128.16 | 455048.13 | 195357.75 | 210358.81 | 88499 |  | 1466391.85
| Change |  | -49004.4433 | 30537.56 | 7722.0467 | -680.02 | 0 |  | -11424.8567
| MRC EUR | Total | 62765.4716 | 65106.7522 | 27228.6978 | 28113.483 | 11865.8407 |  | 195080.2453
| New Sales |  | 69335.9291 | 61012.3125 | 26193.3349 | 28204.6592 | 11865.8407 |  | 196612.0765
| Change |  | -6570.4575 | 4094.4398 | 1035.3628 | -91.1763 | 0 |  | -1531.8312
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 365 | 386 | 270 | 68 | 272 | 342 | 71 | 40 | 0 | 62 | 26 | 1922 | 2067 | 145
| New Sales |  | 15 | 360 | 260 | 255 | 66 | 147 | 312 | 50 | 16 | 0 | 52 | 22 | 1555 | 1682 | 127
| Change |  | 5 | 5 | 126 | 15 | 2 | 125 | 30 | 21 | 24 | 0 | 10 | 4 | 367 | 385 | 18
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 145 | 4 | 0 | 13 | 10 | 5 | 2 | 0 | 0 | 8 | 190 | 193
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 27 | 20 | 13 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 127 | 127
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 25 | 3 | 114 | 10 | 7 | 2 | 0 | 0 | 0 | 182 | 182
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 23 | 2 | 5 | 10 | 10 | 0 | 0 | 0 | 6 | 62 | 62
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 64 | 70 | 43 | 60 | 224 | 38 | 3 | 0 | 0 | 0 | 508 | 509
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 23 | 90 | 5 | 13 | 35 | 1 | 0 | 0 | 0 | 0 | 168 | 168
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 1 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 14 | 14
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 3 | 48 | 48
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 0 | 62 | 0 | 72 | 73
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 7 | 400 | 402
| Orders without status |  | 0 | 0 | 0 | 3 | 3 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 14 | 14
| Sum |  | 20 | 365 | 386 | 270 | 68 | 272 | 342 | 71 | 40 | 0 | 62 | 26 | 1922 | 1931
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 343939.54 | 384435.31 | 318289.51 | 67314.56 | 244361.7767 | 404756.0467 | 66402.47 | 50386.5 | 0 | 76672.79 | 33348.03 | 2003598.6433 | 2188509.9833 | 184911.34 |  | All orders |  | 1835.8218 | 46115.0048 | 51544.6295 | 42675.8792 | 9025.4562 | 32763.7366 | 54269.2097 | 8903.1643 | 6755.762 | 0 | 10280.1966 | 4471.2642 | 268640.1249 | 293432.8176 | 24792.6927
| New Sales |  | 14337 | 383974.12 | 339055.5 | 317874.69 | 65559.56 | 269445.55 | 412923.95 | 51076.73 | 22646.5 | 0 | 75683 | 34784 | 1987360.6 | 2144318.22 | 156957.62 |  | New Sales |  | 1922.2879 | 51482.7937 | 45460.1585 | 42620.2606 | 8790.1479 | 36126.9391 | 55364.3525 | 6848.3073 | 3036.4158 | 0 | 10147.4867 | 4663.7974 | 266462.9473 | 287507.6385 | 21044.6911
| Change |  | -644.89 | -40034.58 | 45379.81 | 414.82 | 1755 | -25083.7733 | -8167.9033 | 15325.74 | 27740 | 0 | 989.79 | -1435.97 | 16238.0433 | 44191.7633 | 27953.72 |  | Change |  | -86.4661 | -5367.7889 | 6084.471 | 55.6186 | 235.3083 | -3363.2025 | -1095.1428 | 2054.857 | 3719.3462 | 0 | 132.7099 | -192.5332 | 2177.1776 | 5925.1791 | 3748.0016
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 199401.9567 | 14434 | 0 | 13105.66 | 29889.7933 | 2034 | 3510 | 0 | 0 | 3482.03 | 279982.44 | 280879.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 26735.5774 | 1935.2936 | 0 | 1757.1913 | 4007.588 | 272.7163 | 470.6166 | 0 | 0 | 466.8664 | 37539.7128 | 37659.9815
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 30973.02 | 25775 | 17580 | 14476.06 | 38505 | 44300 | 5985.41 | 0 | 0 | 0 | 9100 | 187643.49 | 187643.49 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 4152.8257 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 5939.6914 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 25159.0161 | 25159.0161
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 1040 | 0 | 0 | 0 | 0 | 0 | 11296.3 | 11296.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 139.442 | 0 | 0 | 0 | 0 | 0 | 1514.5945 | 1514.5945
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 16632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18617.47 | 18617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 2230.0618 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2496.2083 | 2496.2083
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 24587.5 | 3243.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3296.6628 | 434.8846 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 15624.6467 | 400 | -15580.02 | 24711.81 | 19355 | 0 | 0 | 0 | 1948 | 62097.5167 | 62097.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 2094.9341 | 53.6315 | -2088.9506 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | 261.1855 | 8325.9612 | 8325.9612
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 28258.5833 | 60775.61 | 36788 | 28832.2567 | 192770.9433 | 28326.3 | 4130 | 0 | 0 | 0 | 390162.8133 | 390999.8133 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3788.8773 | 8148.7216 | 4932.4913 | 3865.7947 | 25846.499 | 3797.9566 | 553.7455 | 0 | 0 | 0 | 52312.5663 | 52424.7903
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22195.28 | 151807 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 296211.03 | 296211.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 2975.9168 | 20354.1021 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39715.6229 | 39715.6229
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 11684.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1566.6519
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 1038 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 21222.97 | 21222.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 139.1738 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 2845.5506 | 2845.5506
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 4191.5633 | 0 | 0 | 1520 | 0 | 0 | 0 | 0 | 0 | 5711.5633 | 5711.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 561.9998 | 0 | 0 | 203.7998 | 0 | 0 | 0 | 0 | 0 | 765.7996 | 765.7996
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2200 | 103343.05 | 103343.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 294.9734 | 13856.1133 | 13856.1133
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 11359 | 0 | 76672.79 | 0 | 89526.79 | 89970.478 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1523.0012 | 0 | 10280.1966 | 0 | 12003.6456 | 12063.1348
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 16618 | 329554 | 330235.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 2228.1217 | 44186.2087 | 44277.5673
| Orders without status |  | 0 | 0 | 0 | 1260 | 1495 | 0 | 4615 | 942.5 | 0 | 0 | 0 | 0 | 8312.5 | 8312.5 |  |  | Orders without status |  | 0 | 0 | 0 | 168.9393 | 200.4478 | 0 | 618.7737 | 126.3693 | 0 | 0 | 0 | 0 | 1114.5301 | 1114.5301
| Sum |  | 13692.11 | 343939.54 | 384435.31 | 318289.51 | 67314.56 | 244361.7767 | 404756.0467 | 66402.47 | 50386.5 | 0 | 76672.79 | 33348.03 | 2003598.6433 | 2008307.7113 |  |  | Sum |  | 1835.8218 | 46115.0048 | 51544.6295 | 42675.8792 | 9025.4562 | 32763.7366 | 54269.2097 | 8903.1643 | 6755.762 | 0 | 10280.1966 | 4471.2642 | 268640.1249 | 269271.5111
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 84 | 31 | 49 | 0 | 42 | 119 | 46 | 8 | 0 | 48 | 3 | 432 | 445 | 13
| New Sales |  | 2 | 79 | 20 | 41 | 0 | 37 | 109 | 42 | 6 | 0 | 42 | 1 | 379 | 389 | 10
| Change |  | 0 | 5 | 11 | 8 | 0 | 5 | 10 | 4 | 2 | 0 | 6 | 2 | 53 | 56 | 3
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 11 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 3 | 28 | 28 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 27 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 33 | 33 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 4 | 0 | 2 | 5 | 3 | 0 | 0 | 0 | 0 | 17 | 17 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 8 | 0 | 2 | 85 | 26 | 0 | 0 | 0 | 0 | 129 | 129 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 17 | 0 | 7 | 10 | 1 | 0 | 0 | 0 | 0 | 38 | 38 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 7 | 0 | 1 | 0 | 0 | 0 | 16 | 16 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 48 | 0 | 55 | 55 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 53 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
| Orders without status |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| Sum |  | 2 | 84 | 31 | 49 | 0 | 42 | 119 | 46 | 8 | 0 | 48 | 3 | 432 | 432 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1958 | 86129.14 | 49417.43 | 43052.3767 | 0 | 45113.67 | 124771.07 | 43175.21 | 7159 | 0 | 55503.79 | 487.03 | 456766.7167 | 468123.7167 | 11357 |  | All orders |  | 262.5263 | 11548.0927 | 6625.8303 | 5772.4115 | 0 | 6048.7873 | 16729.1568 | 5788.8808 | 959.8702 | 0 | 7441.8822 | 65.3004 | 61242.7385 | XX
| New Sales |  | 1958 | 126163.72 | 35394 | 39218.94 | 0 | 70292.55 | 127375.22 | 43895.73 | 7219 | 0 | 54614 | 1495 | 507626.16 | 517128.16 | 9502 |  | New Sales |  | 262.5263 | 16915.8816 | 4745.5855 | 5258.4289 | 0 | 9424.7416 | 17078.3181 | 5885.4873 | 967.9149 | 0 | 7322.5802 | 200.4478 | 68061.9122
| Change |  | 0 | -40034.58 | 14023.43 | 3833.4367 | 0 | -25178.88 | -2604.15 | -720.52 | -60 | 0 | 889.79 | -1007.97 | -50859.4433 | -49004.4433 | 1855 |  | Change |  | 0 | -5367.7889 | 1880.2448 | 513.9826 | 0 | -3375.9543 | -349.1613 | -96.6065 | -8.0447 | 0 | 119.302 | -135.1474 | -6819.1737
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 13316 | 0 | 2034 | 0 | 0 | 0 | 487.03 | 39748.4867 | 39748.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1785.3935 | 0 | 272.7163 | 0 | 0 | 0 | 65.3004 | 5329.4299 | 5329.4299
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 30973.02 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 51158.43 | 51158.43 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 4152.8257 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 6859.2615 | 6859.2615
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 1040 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.442 | 0 | 0 | 0 | 0 | 0 | 139.442 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 1888.6467 | 0 | -18935.02 | 12335 | 1060 | 0 | 0 | 0 | 0 | -2083.6933 | -2083.6933 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 253.2275 | 0 | -2538.785 | 1653.8621 | 142.1235 | 0 | 0 | 0 | 0 | -279.3791 | -279.3791
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4914.2267 | 0 | 2669 | 72773.07 | 26266.3 | 0 | 0 | 0 | 0 | 117323.45 | 117323.45 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 658.8937 | 0 | 357.8563 | 9757.3267 | 3521.7543 | 0 | 0 | 0 | 0 | 15730.5887 | 15730.5887
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 19141 | 0 | 8890 | 16263 | 979 | 0 | 0 | 0 | 0 | 50673 | 50673 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2566.4025 | 0 | 1191.9606 | 2180.5237 | 131.2632 | 0 | 0 | 0 | 0 | 6794.1756 | 6794.1756
| 3.1.1 Pending external 3rd party: Open-Net |  | 1958 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.56 | 415.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 262.5263 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.7178 | 55.7178
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 1520 | 0 | 0 | 0 | 0 | 0 | 211.5633 | 211.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 203.7998 | 0 | 0 | 0 | 0 | 0 | 28.3662 | 28.3662
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 7100 | 0 | 400 | 0 | 0 | 0 | 33106.05 | 33106.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 951.9596 | 0 | 53.6315 | 0 | 0 | 0 | 4438.8198 | 4438.8198
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 6719 | 0 | 55503.79 | 0 | 63717.79 | 63717.79 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 900.8755 | 0 | 7441.8822 | 0 | 8543.2056 | 8543.2056
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 45650 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46730 | 46730 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 6120.6977 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6265.5029 | 6265.5029
| Orders without status |  | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 942.5 | 0 | 0 | 0 | 0 | 2202.5 | 2202.5 |  |  | Orders without status |  | 0 | 0 | 0 | 168.9393 | 0 | 0 | 0 | 126.3693 | 0 | 0 | 0 | 0 | 295.3086 | 295.3086
| Sum |  | 1958 | 86129.14 | 49417.43 | 43052.3767 | 0 | 45113.67 | 124771.07 | 43175.21 | 7159 | 0 | 55503.79 | 487.03 | 456766.7167 | 456766.7167 |  |  | Sum |  | 262.5263 | 11548.0927 | 6625.8303 | 5772.4115 | 0 | 6048.7873 | 16729.1568 | 5788.8808 | 959.8702 | 0 | 7441.8822 | 65.3004 | 61242.7385 | 61242.7385
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 78 | 48 | 63 | 24 | 185 | 132 | 14 | 7 | 0 | 6 | 7 | 567 | 580 | 13
| New Sales |  | 3 | 78 | 28 | 59 | 24 | 73 | 126 | 8 | 5 | 0 | 5 | 5 | 414 | 427 | 13
| Change |  | 0 | 0 | 20 | 4 | 0 | 112 | 6 | 6 | 2 | 0 | 1 | 2 | 153 | 153 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 8 | 2 | 93 | 3 | 3 | 0 | 0 | 0 | 0 | 116 | 116 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 8 | 0 | 3 | 4 | 7 | 0 | 0 | 0 | 6 | 29 | 29 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 14 | 17 | 43 | 90 | 2 | 0 | 0 | 0 | 0 | 186 | 186 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 19 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 1 | 8 | 8 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 0 | 9 | 9 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 77 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 82 | 82 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| Sum |  | 3 | 78 | 48 | 63 | 24 | 185 | 132 | 14 | 7 | 0 | 6 | 7 | 567 | 567 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 77290.4 | 33968.0667 | 56531.8833 | 20401.5 | 44434.1667 | 141457.9133 | 23227.26 | 35150 | 0 | 6235 | 2048 | 442839.19 | 485585.69 | 42746.5 |  | All orders |  | 280.8951 | 10363.005 | 4554.398 | 7579.7277 | 2735.4089 | 5957.6803 | 18966.5089 | 3114.2834 | 4712.8702 | 0 | 835.9814 | 274.5934 | 59375.3523
| New Sales |  | 2095 | 77290.4 | 38919.25 | 59950.5 | 20401.5 | 44753 | 144849.98 | 7181 | 8150 | 0 | 6235 | 2476 | 412301.63 | 455048.13 | 42746.5 |  | New Sales |  | 280.8951 | 10363.005 | 5218.2468 | 8038.0918 | 2735.4089 | 6000.4291 | 19421.3132 | 962.8199 | 1092.7423 | 0 | 835.9814 | 331.9791 | 55280.9125
| Change |  | 0 | 0 | -4951.1833 | -3418.6167 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -428 | 30537.56 | 30537.56 | 0 |  | Change |  | 0 | 0 | -663.8488 | -458.3641 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -57.3857 | 4094.4398
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 0 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 22184.3233 | 22184.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 0 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 2974.4477 | 2974.4477
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 51158.43 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 6859.2615
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 6882.5 | 2247.5 | 2177.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 22201.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 922.7974 | 301.3421 | 291.9982 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2976.6971 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 9881 | 0 | 3355 | 8376.81 | 18295 | 0 | 0 | 0 | 1948 | 55596.21 | -2083.6933 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 1324.8327 | 0 | 449.8344 | 1123.1527 | 2452.9719 | 0 | 0 | 0 | 261.1855 | 7454.2738 | -279.3791
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 4090.3833 | 14775 | 13378.3567 | 75544.06 | 2060 | 0 | 0 | 0 | 0 | 111748.7267 | 117323.45 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 548.4337 | 1981.0144 | 1793.7542 | 10128.8578 | 276.2024 | 0 | 0 | 0 | 0 | 14983.1365 | 15730.5887
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 27228 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 43365.86 | 50673 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3650.6979 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 5814.443 | 6794.1756
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | 415.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | 55.7178
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495 | 211.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334.5266 | 28.3662
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 3125 | 14462.25 | 0 | 27000 | 0 | 0 | 100 | 44687.25 | 33106.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 418.9963 | 1939.0813 | 0 | 3620.1279 | 0 | 0 | 13.4079 | 5991.6134 | 4438.8198
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4640 | 0 | 6235 | 0 | 10875 | 63717.79 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622.1257 | 0 | 835.9814 | 0 | 1458.1071 | 8543.2056
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 63550 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 69358 | 46730 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8520.7085 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9299.4382 | 6265.5029
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 475 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 63.6874 | 63.6874
| Sum |  | 2095 | 77290.4 | 33968.0667 | 56531.8833 | 20401.5 | 44434.1667 | 141457.9133 | 23227.26 | 35150 | 0 | 6235 | 2048 | 442839.19 | 437475.0533 |  |  | Sum |  | 280.8951 | 10363.005 | 4554.398 | 7579.7277 | 2735.4089 | 5957.6803 | 18966.5089 | 3114.2834 | 4712.8702 | 0 | 835.9814 | 274.5934 | 59375.3523 | 58656.1352
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 73 | 19 | 39 | 15 | 12 | 37 | 0 | 0 | 0 | 3 | 5 | 204 | 218 | 14
| New Sales |  | 1 | 73 | 13 | 37 | 13 | 12 | 31 | 0 | 0 | 0 | 2 | 5 | 187 | 200 | 13
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 15 | 8
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 41 | 30
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 116 | 114
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 29 | 27
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 9 | 14 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 66 | 186 | 120
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 24 | 35 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 6
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 9 | 6
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 73 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 79 | 82 | 3
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 73 | 19 | 39 | 15 | 12 | 37 | 0 | 0 | 0 | 3 | 5 | 204 | 569 | 365
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 61150 | 17355.0433 | 32558 | 15597 | 7040 | 38213.2533 | 0 | 0 | 0 | 3643 | 12773 | 192929.2967 | 203079.7967 | 10150.5 |  | All orders |  | 616.7625 | 8198.9193 | 2326.9436 | 4365.3379 | 2091.2272 | 943.9148 | 5123.5876 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 25867.7308
| New Sales |  | 4600 | 61150 | 11207 | 32558 | 13842 | 7040 | 38394.25 | 0 | 0 | 0 | 3643 | 12773 | 185207.25 | 195357.75 | 10150.5 |  | New Sales |  | 616.7625 | 8198.9193 | 1502.6212 | 4365.3379 | 1855.9189 | 943.9148 | 5147.8554 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 24832.368
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | -180.9967 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | -24.2678 | 0 | 0 | 0 | 0 | 0 | 1035.3628
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 0 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 7862 | 7862 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 0 | 0 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 1054.1276 | 1054.1276
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 12749 | 12749 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 0 | 0 | 0 | 0 | 0 | 0 | 1709.3708 | 1709.3708
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 999 | 999 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 133.9447 | 133.9447
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 5520 | 13872 | 5035 | 27322.5033 | 0 | 0 | 0 | 0 | 0 | 52342.5467 | 52342.5467 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 740.115 | 1859.9413 | 675.0868 | 3663.3688 | 0 | 0 | 0 | 0 | 0 | 7018.0264 | 7018.0264
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 8831.75 | 0 | 0 | 0 | 0 | 0 | 30645.75 | 30645.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1184.1505 | 0 | 0 | 0 | 0 | 0 | 4108.9457 | 4108.9457
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3643 | 0 | 3643 | 3643 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488.4491 | 0 | 488.4491 | 488.4491
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 61150 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12773 | 74573 | 74573 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8198.9193 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712.5887 | 9998.6592 | 9998.6592
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 61150 | 17355.0433 | 32558 | 15597 | 7040 | 38213.2533 | 0 | 0 | 0 | 3643 | 12773 | 192929.2967 | 192929.2967 |  |  | Sum |  | 616.7625 | 8198.9193 | 2326.9436 | 4365.3379 | 2091.2272 | 943.9148 | 5123.5876 | 0 | 0 | 0 | 488.4491 | 1712.5887 | 25867.7308 | 25867.7308
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 175 | 23
| New Sales |  | 2 | 34 | 84 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 142 | 165 | 23
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 15 | -59
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 116 | 108
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 12 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 186 | 169
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 35 | 33
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 3
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 9 | 7
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 82 | 50
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2 | 34 | 94 | 6 | 4 | 4 | 3 | 0 | 1 | 0 | 2 | 2 | 152 | 566 | 414
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 203079.7967 | 34160.0067 |  | All orders |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647
| New Sales |  | 1495 | 40220 | 79381 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 169599.81 | 195357.75 | 25757.94 |  | New Sales |  | 200.4478 | 5392.6498 | 10643.3101 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22739.741
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 7722.0467 | 8402.0667 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 67150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79955 | 79955 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 9003.3922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10720.2714 | 10720.2714
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 1395 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 4159.98 | 4159.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 187.0399 | 0 | 0 | 0 | 0 | 341.901 | 0 | 0 | 0 | 557.7652 | 557.7652
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 2800 | 475 | 400 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 5520 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 375.4207 | 63.6874 | 53.6315 | 247.3754 | 0 | 0 | 0 | 0 | 0 | 0 | 740.115 | 740.115
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 27415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27415 | 27415 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 3675.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3675.7706 | 3675.7706
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 1495 | 40220 | 78700.98 | 4740.75 | 5623.06 | 7340 | 10050 | 0 | 2550 | 0 | 9100 | 9100 | 168919.79 | 168919.79 |  |  | Sum |  | 200.4478 | 5392.6498 | 10552.1339 | 635.6341 | 753.9332 | 984.1385 | 1347.4921 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 22648.5647 | 22648.5647
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 175 | 148
| New Sales |  | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 165 | 138
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 116
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 186 | 182
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 35 | 20
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 82
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | 566 | 539
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 203079.7967 | 114580.7967 |  | All orders |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| New Sales |  | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 195357.75 | 106858.75 |  | New Sales |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722.0467 | 7722.0467 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375 | 2375 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.4372 | 318.4372
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 0 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 88499 | 88499 |  |  | Sum |  | 0 | 0 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 11865.8407 | 11865.8407

## 20250523
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 380 | 589 | 277 | 172 | 30 |  | 1448
| New Sales |  | 331 | 445 | 259 | 162 | 30 |  | 1227
| Change |  | 49 | 144 | 18 | 10 | 0 |  | 221
| MRC DKK | Total | 402224.57 | 488845.8367 | 235153.0367 | 206356.79 | 115044.4 |  | 1447624.6333
| New Sales |  | 449694.16 | 459183.73 | 226417.21 | 207036.81 | 115044.4 |  | 1457376.31
| Change |  | -47469.59 | 29662.1067 | 8735.8267 | -680.02 | 0 |  | -9751.6767
| MRC EUR | Total | 53929.7923 | 65543.8688 | 31529.0397 | 27668.0732 | 15425.0164 |  | 194095.7904
| New Sales |  | 60294.4585 | 61566.8088 | 30357.7504 | 27759.2494 | 15425.0164 |  | 195403.2836
| Change |  | -6364.6662 | 3977.06 | 1171.2893 | -91.1763 | 0 |  | -1307.4932
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 2257 | 395
| New Sales |  | 15 | 336 | 261 | 250 | 66 | 153 | 307 | 44 | 14 | 0 | 53 | 11 | 1510 | 1655 | 145
| Change |  | 5 | 2 | 127 | 15 | 2 | 74 | 30 | 20 | 24 | 0 | 50 | 3 | 352 | 602 | 250
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 144 | 6 | 0 | 12 | 10 | 3 | 2 | 0 | 0 | 8 | 188 | 191
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 0 | 20 | 13 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 100 | 100
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 24 | 4 | 62 | 10 | 7 | 2 | 0 | 0 | 0 | 130 | 130
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 22 | 3 | 5 | 10 | 10 | 0 | 0 | 0 | 1 | 57 | 57
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 67 | 66 | 41 | 67 | 220 | 36 | 3 | 0 | 0 | 0 | 506 | 507
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 25 | 89 | 5 | 13 | 35 | 1 | 0 | 0 | 0 | 0 | 169 | 169
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 2 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 15 | 15
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 2 | 47 | 47
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 103 | 0 | 111 | 112
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 394 | 396
| Orders without status |  | 0 | 0 | 0 | 2 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 11 | 11
| Sum |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 1871
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 2135401.4333 | 194479.92 |  | All orders |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 286312.0863 | 26075.6365
| New Sales |  | 14337 | 329574.1 | 332624.5 | 314631.19 | 65298.56 | 274713.05 | 409383.95 | 48416.73 | 19772.5 | 0 | 92102.02 | 18770 | 1919623.6 | 2089796.22 | 170172.62 |  | New Sales |  | 1922.2879 | 44188.9036 | 44597.8976 | 42185.376 | 8755.1533 | 36833.1993 | 54889.7135 | 6491.6576 | 2651.0733 | 0 | 12348.9294 | 2516.6593 | 257380.8509 | 280197.3935 | 22816.5426
| Change |  | -644.89 | -16607.58 | 46574.81 | 414.82 | 1755 | -20958.7733 | -7681.5133 | 14868.24 | 27740 | 0 | -22626.23 | -1535.97 | 21297.9133 | 45605.2133 | 24307.3 |  | Change |  | -86.4661 | -2226.7246 | 6244.6952 | 55.6186 | 235.3083 | -2810.1274 | -1029.9282 | 1993.5159 | 3719.3462 | 0 | -3033.698 | -205.941 | 2855.5989 | 6114.6928 | 3259.0939
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 199351.9567 | 16574 | 0 | 12260.66 | 29889.7933 | 1038 | 3510 | 0 | 0 | 3482.03 | 280231.44 | 281128.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 26728.8734 | 2222.2222 | 0 | 1643.8947 | 4007.588 | 139.1738 | 470.6166 | 0 | 0 | 466.8664 | 37573.0984 | 37693.3671
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 0 | 25775 | 17580 | 14476.06 | 38505 | 44786.39 | 5985.41 | 0 | 0 | 0 | 9100 | 157156.86 | 157156.86 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 0 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 6004.9059 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 21071.405 | 21071.405
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 1040 | 0 | 0 | 0 | 0 | 0 | 11296.3 | 11296.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 139.442 | 0 | 0 | 0 | 0 | 0 | 1514.5945 | 1514.5945
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 9632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11617.47 | 11617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 1291.5101 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.6566 | 1557.6566
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 23432.5 | 4398.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3141.8018 | 589.7457 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 14729.6467 | 1295 | -15580.02 | 24711.81 | 19355 | 0 | 0 | 0 | -528 | 59621.5167 | 59621.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 1974.9335 | 173.6321 | -2088.9506 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | -70.7936 | 7993.9821 | 7993.9821
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 29472.5833 | 57448.11 | 34477 | 38209.7567 | 189530.9433 | 27147.3 | 4130 | 0 | 0 | 0 | 390696.8133 | 391533.8133 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3951.6489 | 7702.5743 | 4622.6352 | 5123.1188 | 25412.0836 | 3639.8777 | 553.7455 | 0 | 0 | 0 | 52384.1644 | 52496.3884
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22795.28 | 150851 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 295855.03 | 295855.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 3056.3641 | 20225.9228 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39667.8908 | 39667.8908
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 11684.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1566.6519
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 2848 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 23032.97 | 23032.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 381.8565 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 3088.2332 | 3088.2332
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 4191.5633 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 5411.5633 | 5411.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 561.9998 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 725.576 | 725.576
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2100 | 103243.05 | 103243.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 281.5655 | 13842.7054 | 13842.7054
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 8485 | 0 | 69475.79 | 0 | 79455.79 | 79899.478 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1137.6587 | 0 | 9315.2314 | 0 | 10653.3379 | 10712.827
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 3080 | 316016 | 316697.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 412.9627 | 42371.0497 | 42462.4083
| Orders without status |  | 0 | 0 | 0 | 400 | 1495 | 860 | 4615 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 200.4478 | 115.3078 | 618.7737 | 0 | 0 | 0 | 0 | 0 | 988.1608 | 988.1608
| Sum |  | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 1945630.5813 |  |  | Sum |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 260867.836
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 380 | 10
| New Sales |  | 1 | 51 | 20 | 35 | 0 | 36 | 93 | 33 | 4 | 0 | 47 | 1 | 321 | 331 | 10
| Change |  | 0 | 2 | 10 | 6 | 0 | 6 | 11 | 3 | 2 | 0 | 7 | 2 | 49 | 49 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 10 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 3 | 23 | 23 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 1 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 6 | 0 | 4 | 78 | 22 | 0 | 0 | 0 | 0 | 118 | 118 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 15 | 0 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 34 | 34 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 11 | 11 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 54 | 0 | 59 | 59 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 49 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0
| Orders without status |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 370 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 402224.57 | 9502 |  | All orders |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | XX
| New Sales |  | 979 | 68463.7 | 35394 | 34596.94 | 0 | 67527.55 | 111461.22 | 40235.73 | 4640 | 0 | 75399.02 | 1495 | 440192.16 | 449694.16 | 9502 |  | New Sales |  | 131.2632 | 9179.5315 | 4745.5855 | 4638.7166 | 0 | 9054.0136 | 14944.5879 | 5394.7589 | 622.1257 | 0 | 10109.411 | 200.4478 | 59020.4417
| Change |  | 0 | -16607.58 | 14023.43 | 4608.89 | 0 | -21053.88 | -3040.84 | -1178.02 | -60 | 0 | -23153.62 | -1007.97 | -47469.59 | -47469.59 | 0 |  | Change |  | 0 | -2226.7246 | 1880.2448 | 617.9545 | 0 | -2822.8792 | -407.7122 | -157.9475 | -8.0447 | 0 | -3104.4099 | -135.1474 | -6364.6662
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 10016 | 0 | 1038 | 0 | 0 | 0 | 487.03 | 35452.4867 | 35452.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1342.9334 | 0 | 139.1738 | 0 | 0 | 0 | 65.3004 | 4753.4273 | 4753.4273
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 20185.41 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 2706.4358 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 1040 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.442 | 0 | 0 | 0 | 0 | 0 | 139.442 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 518.2 | 0 | -18935.02 | 12335 | 460 | 0 | 0 | 0 | 0 | -4054.14 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 69.4796 | 0 | -2538.785 | 1653.8621 | 61.6763 | 0 | 0 | 0 | 0 | -543.5743 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4744.1267 | 0 | 7739 | 64421.38 | 24687.3 | 0 | 0 | 0 | 0 | 112292.66 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 636.0869 | 0 | 1037.6359 | 8637.5421 | 3310.0438 | 0 | 0 | 0 | 0 | 15056.0664 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 17695 | 0 | 7620 | 15284 | 979 | 0 | 0 | 0 | 0 | 46978 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2372.5246 | 0 | 1021.6805 | 2049.2606 | 131.2632 | 0 | 0 | 0 | 0 | 6298.7544 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75.5454 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308.4367 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175.4336 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 1600 | 0 | 400 | 0 | 0 | 0 | 27606.05 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 214.5261 | 0 | 53.6315 | 0 | 0 | 0 | 3701.3864 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 4140 | 0 | 52245.4 | 0 | 57880.4 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 555.0863 | 0 | 7005.0011 | 0 | 7760.5352 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42350 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43430 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 5678.2377 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823.0428 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 400 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 0 | 115.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 168.9393 | 168.9393
| Sum |  | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 392722.57 |  |  | Sum |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | 52655.7754
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 589 | 17
| New Sales |  | 3 | 79 | 28 | 57 | 26 | 82 | 135 | 11 | 5 | 0 | 2 | 0 | 428 | 445 | 17
| Change |  | 0 | 0 | 20 | 6 | 0 | 60 | 7 | 6 | 2 | 0 | 42 | 1 | 144 | 144 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 17 | 17 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 4 | 3 | 40 | 3 | 3 | 0 | 0 | 0 | 0 | 60 | 60 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10 | 1 | 3 | 4 | 8 | 0 | 0 | 0 | 1 | 27 | 27 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 15 | 14 | 48 | 94 | 4 | 0 | 0 | 0 | 0 | 195 | 195 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 20 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 44 | 0 | 47 | 47 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 79 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| Sum |  | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 572 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 488845.8367 | 44141.5 |  | All orders |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289
| New Sales |  | 2095 | 65200 | 38919.25 | 61232.5 | 21294 | 53065.5 | 153809.98 | 8181 | 7855 | 0 | 3390 | 0 | 415042.23 | 459183.73 | 44141.5 |  | New Sales |  | 280.8951 | 8741.9385 | 5218.2468 | 8209.9808 | 2855.0742 | 7114.9592 | 20622.6593 | 1096.8988 | 1053.1891 | 0 | 454.5272 | 0 | 55648.3689
| Change |  | 0 | 0 | -4951.1833 | -4194.07 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -528 | 29662.1067 | 29662.1067 | 0 |  | Change |  | 0 | 0 | -663.8488 | -562.3359 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -70.7936 | 3977.06
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 3300 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 25484.3233 | 25484.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 442.4601 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 3416.9078 | 3416.9078
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 2142.5 | 3402.5 | 982.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 17421.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 287.2639 | 456.2032 | 131.774 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2335.8004 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10356.4467 | 895 | 3355 | 8376.81 | 18895 | 0 | 0 | 0 | -528 | 41350.2567 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1388.5801 | 120.0005 | 449.8344 | 1123.1527 | 2533.4191 | 0 | 0 | 0 | -70.7936 | 5544.1933 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 7466.4833 | 12122.5 | 17685.8567 | 77784.06 | 2460 | 0 | 0 | 0 | 0 | 119419.8267 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 1001.0972 | 1625.3704 | 2371.2986 | 10429.1943 | 329.8339 | 0 | 0 | 0 | 0 | 16011.6684 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 28623 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 44760.86 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3837.7378 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 6001.4829 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 3715 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 498.1028 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5025 | 19962.25 | 0 | 27000 | 0 | 0 | 0 | 51987.25 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 673.746 | 2676.5148 | 0 | 3620.1279 | 0 | 0 | 0 | 6970.3887 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345 | 0 | 3390 | 0 | 7735 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.5724 | 0 | 454.5272 | 0 | 1037.0996 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 65200 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 71008 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8741.9385 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9520.6682 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 0 | 1495 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 1970 | 1970 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 200.4478 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 264.1353 | 264.1353
| Sum |  | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 383464.4067 |  |  | Sum |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289 | 51414.4519
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 277 | 42
| New Sales |  | 1 | 101 | 13 | 36 | 17 | 11 | 34 | 0 | 0 | 0 | 1 | 4 | 218 | 259 | 41
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 17 | 6
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 41 | 30
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 60 | 55
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 17 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 67 | 195 | 128
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 84 | -18
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 571 | 336
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 235153.0367 | 26508.96 |  | All orders |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498
| New Sales |  | 4600 | 84250 | 11207 | 30270.5 | 18285.5 | 6195 | 41653.25 | 0 | 0 | 0 | 2047 | 1400 | 199908.25 | 226417.21 | 26508.96 |  | New Sales |  | 616.7625 | 11296.1399 | 1502.6212 | 4058.6327 | 2451.6981 | 830.6182 | 5584.8183 | 0 | 0 | 0 | 274.4593 | 187.7103 | 26803.4606
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | 305.3933 | 0 | 0 | 0 | 527.39 | 0 | 8735.8267 | 8735.8267 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | 40.9468 | 0 | 0 | 0 | 70.7118 | 0 | 1171.2893
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 9262 | 9262 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7103 | 1241.838 | 1241.838
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 486.39 | 0 | 0 | 0 | 0 | 0 | 13235.39 | 13235.39 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 65.2146 | 0 | 0 | 0 | 0 | 0 | 1774.5854 | 1774.5854
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 400 | 996 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 2395 | 2395 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 53.6315 | 133.5425 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 321.1188 | 321.1188
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 1987.5 | 17319.5 | 5035 | 29602.5033 | 0 | 0 | 0 | 0 | 0 | 54537.5467 | 54537.5467 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 266.4816 | 2322.178 | 675.0868 | 3969.0685 | 0 | 0 | 0 | 0 | 0 | 7312.3294 | 7312.3294
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 9810.75 | 0 | 0 | 0 | 0 | 0 | 31624.75 | 31624.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1315.4137 | 0 | 0 | 0 | 0 | 0 | 4240.2089 | 4240.2089
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.39 | 0 | 2574.39 | 2574.39 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.1712 | 0 | 345.1712 | 345.1712
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 84250 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84900 | 84900 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 11296.1399 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383.2911 | 11383.2911
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 208644.0767 |  |  | Sum |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498 | 27974.7498
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 172 | 2
| New Sales |  | 3 | 42 | 86 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 160 | 162 | 2
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 17 | -56
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 60 | 48
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 13 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 21 | 195 | 174
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 36 | 34
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 84 | 42
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 568 | 398
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 235153.0367 | 59191.2467 |  | All orders |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477
| New Sales |  | 2474 | 35665 | 81574 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 176641.81 | 226417.21 | 49775.4 |  | New Sales |  | 331.711 | 4781.9208 | 10937.345 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23683.924
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 8735.8267 | 9415.8467 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 68578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68578 | 68578 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 9194.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9194.8567 | 9194.8567
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 4980 | 0 | 1195 | 0 | 0 | 2550 | 0 | 0 | 0 | 8939.98 | 8939.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 667.7125 | 0 | 160.2242 | 0 | 0 | 341.901 | 0 | 0 | 0 | 1198.6619 | 1198.6619
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 3565 | 475 | 400 | 1845 | 3645 | 0 | 0 | 0 | 0 | 0 | 9930 | 9930 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 477.991 | 63.6874 | 53.6315 | 247.3754 | 488.7173 | 0 | 0 | 0 | 0 | 0 | 1331.4026 | 1331.4026
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979 | 979 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.2632 | 131.2632
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 35665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35665 | 35665 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 4781.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.9208 | 4781.9208
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 175961.79 |  |  | Sum |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477 | 23592.7477
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 172 | 142
| New Sales |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 162 | 132
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 26
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 195 | 191
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36 | 21
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 568 | 538
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 235153.0367 | 120108.6367 |  | All orders |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| New Sales |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 226417.21 | 111372.81 |  | New Sales |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8735.8267 | 8735.8267 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 15180 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035.3164 | 2035.3164
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13740.4 | 13740.4 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.2965 | 1842.2965
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 115044.4 |  |  | Sum |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164 | 15425.0164

## 20250524
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 380 | 589 | 277 | 172 | 30 |  | 1448
| New Sales |  | 331 | 445 | 259 | 162 | 30 |  | 1227
| Change |  | 49 | 144 | 18 | 10 | 0 |  | 221
| MRC DKK | Total | 402224.57 | 488845.8367 | 235153.0367 | 206356.79 | 115044.4 |  | 1447624.6333
| New Sales |  | 449694.16 | 459183.73 | 226417.21 | 207036.81 | 115044.4 |  | 1457376.31
| Change |  | -47469.59 | 29662.1067 | 8735.8267 | -680.02 | 0 |  | -9751.6767
| MRC EUR | Total | 53929.7923 | 65543.8688 | 31529.0397 | 27668.0732 | 15425.0164 |  | 194095.7904
| New Sales |  | 60294.4585 | 61566.8088 | 30357.7504 | 27759.2494 | 15425.0164 |  | 195403.2836
| Change |  | -6364.6662 | 3977.06 | 1171.2893 | -91.1763 | 0 |  | -1307.4932
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 2257 | 395
| New Sales |  | 15 | 336 | 261 | 250 | 66 | 153 | 307 | 44 | 14 | 0 | 53 | 11 | 1510 | 1655 | 145
| Change |  | 5 | 2 | 127 | 15 | 2 | 74 | 30 | 20 | 24 | 0 | 50 | 3 | 352 | 602 | 250
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 144 | 6 | 0 | 12 | 10 | 3 | 2 | 0 | 0 | 8 | 188 | 191
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 0 | 20 | 13 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 100 | 100
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 24 | 4 | 62 | 10 | 7 | 2 | 0 | 0 | 0 | 130 | 130
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 22 | 3 | 5 | 10 | 10 | 0 | 0 | 0 | 1 | 57 | 57
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 67 | 66 | 41 | 67 | 220 | 36 | 3 | 0 | 0 | 0 | 506 | 507
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 25 | 89 | 5 | 13 | 35 | 1 | 0 | 0 | 0 | 0 | 169 | 169
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 2 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 15 | 15
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 2 | 47 | 47
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 103 | 0 | 111 | 112
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 394 | 396
| Orders without status |  | 0 | 0 | 0 | 2 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 11 | 11
| Sum |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 1871
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 2135401.4333 | 194479.92 |  | All orders |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 286312.0863 | 26075.6365
| New Sales |  | 14337 | 329574.1 | 332624.5 | 314631.19 | 65298.56 | 274713.05 | 409383.95 | 48416.73 | 19772.5 | 0 | 92102.02 | 18770 | 1919623.6 | 2089796.22 | 170172.62 |  | New Sales |  | 1922.2879 | 44188.9036 | 44597.8976 | 42185.376 | 8755.1533 | 36833.1993 | 54889.7135 | 6491.6576 | 2651.0733 | 0 | 12348.9294 | 2516.6593 | 257380.8509 | 280197.3935 | 22816.5426
| Change |  | -644.89 | -16607.58 | 46574.81 | 414.82 | 1755 | -20958.7733 | -7681.5133 | 14868.24 | 27740 | 0 | -22626.23 | -1535.97 | 21297.9133 | 45605.2133 | 24307.3 |  | Change |  | -86.4661 | -2226.7246 | 6244.6952 | 55.6186 | 235.3083 | -2810.1274 | -1029.9282 | 1993.5159 | 3719.3462 | 0 | -3033.698 | -205.941 | 2855.5989 | 6114.6928 | 3259.0939
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 199351.9567 | 16574 | 0 | 12260.66 | 29889.7933 | 1038 | 3510 | 0 | 0 | 3482.03 | 280231.44 | 281128.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 26728.8734 | 2222.2222 | 0 | 1643.8947 | 4007.588 | 139.1738 | 470.6166 | 0 | 0 | 466.8664 | 37573.0984 | 37693.3671
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 0 | 25775 | 17580 | 14476.06 | 38505 | 44786.39 | 5985.41 | 0 | 0 | 0 | 9100 | 157156.86 | 157156.86 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 0 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 6004.9059 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 21071.405 | 21071.405
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 1040 | 0 | 0 | 0 | 0 | 0 | 11296.3 | 11296.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 139.442 | 0 | 0 | 0 | 0 | 0 | 1514.5945 | 1514.5945
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 9632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11617.47 | 11617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 1291.5101 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.6566 | 1557.6566
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 23432.5 | 4398.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3141.8018 | 589.7457 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 14729.6467 | 1295 | -15580.02 | 24711.81 | 19355 | 0 | 0 | 0 | -528 | 59621.5167 | 59621.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 1974.9335 | 173.6321 | -2088.9506 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | -70.7936 | 7993.9821 | 7993.9821
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 29472.5833 | 57448.11 | 34477 | 38209.7567 | 189530.9433 | 27147.3 | 4130 | 0 | 0 | 0 | 390696.8133 | 391533.8133 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3951.6489 | 7702.5743 | 4622.6352 | 5123.1188 | 25412.0836 | 3639.8777 | 553.7455 | 0 | 0 | 0 | 52384.1644 | 52496.3884
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22795.28 | 150851 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 295855.03 | 295855.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 3056.3641 | 20225.9228 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39667.8908 | 39667.8908
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 11684.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1566.6519
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 2848 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 23032.97 | 23032.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 381.8565 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 3088.2332 | 3088.2332
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 4191.5633 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 5411.5633 | 5411.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 561.9998 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 725.576 | 725.576
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2100 | 103243.05 | 103243.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 281.5655 | 13842.7054 | 13842.7054
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 8485 | 0 | 69475.79 | 0 | 79455.79 | 79899.478 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1137.6587 | 0 | 9315.2314 | 0 | 10653.3379 | 10712.827
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 3080 | 316016 | 316697.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 412.9627 | 42371.0497 | 42462.4083
| Orders without status |  | 0 | 0 | 0 | 400 | 1495 | 860 | 4615 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 200.4478 | 115.3078 | 618.7737 | 0 | 0 | 0 | 0 | 0 | 988.1608 | 988.1608
| Sum |  | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 1945630.5813 |  |  | Sum |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 260867.836
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 380 | 10
| New Sales |  | 1 | 51 | 20 | 35 | 0 | 36 | 93 | 33 | 4 | 0 | 47 | 1 | 321 | 331 | 10
| Change |  | 0 | 2 | 10 | 6 | 0 | 6 | 11 | 3 | 2 | 0 | 7 | 2 | 49 | 49 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 10 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 3 | 23 | 23 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 1 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 6 | 0 | 4 | 78 | 22 | 0 | 0 | 0 | 0 | 118 | 118 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 15 | 0 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 34 | 34 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 11 | 11 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 54 | 0 | 59 | 59 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 49 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0
| Orders without status |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 370 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 402224.57 | 9502 |  | All orders |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | XX
| New Sales |  | 979 | 68463.7 | 35394 | 34596.94 | 0 | 67527.55 | 111461.22 | 40235.73 | 4640 | 0 | 75399.02 | 1495 | 440192.16 | 449694.16 | 9502 |  | New Sales |  | 131.2632 | 9179.5315 | 4745.5855 | 4638.7166 | 0 | 9054.0136 | 14944.5879 | 5394.7589 | 622.1257 | 0 | 10109.411 | 200.4478 | 59020.4417
| Change |  | 0 | -16607.58 | 14023.43 | 4608.89 | 0 | -21053.88 | -3040.84 | -1178.02 | -60 | 0 | -23153.62 | -1007.97 | -47469.59 | -47469.59 | 0 |  | Change |  | 0 | -2226.7246 | 1880.2448 | 617.9545 | 0 | -2822.8792 | -407.7122 | -157.9475 | -8.0447 | 0 | -3104.4099 | -135.1474 | -6364.6662
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 10016 | 0 | 1038 | 0 | 0 | 0 | 487.03 | 35452.4867 | 35452.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1342.9334 | 0 | 139.1738 | 0 | 0 | 0 | 65.3004 | 4753.4273 | 4753.4273
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 20185.41 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 2706.4358 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 1040 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.442 | 0 | 0 | 0 | 0 | 0 | 139.442 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 518.2 | 0 | -18935.02 | 12335 | 460 | 0 | 0 | 0 | 0 | -4054.14 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 69.4796 | 0 | -2538.785 | 1653.8621 | 61.6763 | 0 | 0 | 0 | 0 | -543.5743 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4744.1267 | 0 | 7739 | 64421.38 | 24687.3 | 0 | 0 | 0 | 0 | 112292.66 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 636.0869 | 0 | 1037.6359 | 8637.5421 | 3310.0438 | 0 | 0 | 0 | 0 | 15056.0664 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 17695 | 0 | 7620 | 15284 | 979 | 0 | 0 | 0 | 0 | 46978 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2372.5246 | 0 | 1021.6805 | 2049.2606 | 131.2632 | 0 | 0 | 0 | 0 | 6298.7544 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75.5454 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308.4367 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175.4336 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 1600 | 0 | 400 | 0 | 0 | 0 | 27606.05 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 214.5261 | 0 | 53.6315 | 0 | 0 | 0 | 3701.3864 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 4140 | 0 | 52245.4 | 0 | 57880.4 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 555.0863 | 0 | 7005.0011 | 0 | 7760.5352 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42350 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43430 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 5678.2377 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823.0428 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 400 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 0 | 115.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 168.9393 | 168.9393
| Sum |  | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 392722.57 |  |  | Sum |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | 52655.7754
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 589 | 17
| New Sales |  | 3 | 79 | 28 | 57 | 26 | 82 | 135 | 11 | 5 | 0 | 2 | 0 | 428 | 445 | 17
| Change |  | 0 | 0 | 20 | 6 | 0 | 60 | 7 | 6 | 2 | 0 | 42 | 1 | 144 | 144 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 17 | 17 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 4 | 3 | 40 | 3 | 3 | 0 | 0 | 0 | 0 | 60 | 60 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10 | 1 | 3 | 4 | 8 | 0 | 0 | 0 | 1 | 27 | 27 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 15 | 14 | 48 | 94 | 4 | 0 | 0 | 0 | 0 | 195 | 195 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 20 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 44 | 0 | 47 | 47 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 79 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| Sum |  | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 572 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 488845.8367 | 44141.5 |  | All orders |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289
| New Sales |  | 2095 | 65200 | 38919.25 | 61232.5 | 21294 | 53065.5 | 153809.98 | 8181 | 7855 | 0 | 3390 | 0 | 415042.23 | 459183.73 | 44141.5 |  | New Sales |  | 280.8951 | 8741.9385 | 5218.2468 | 8209.9808 | 2855.0742 | 7114.9592 | 20622.6593 | 1096.8988 | 1053.1891 | 0 | 454.5272 | 0 | 55648.3689
| Change |  | 0 | 0 | -4951.1833 | -4194.07 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -528 | 29662.1067 | 29662.1067 | 0 |  | Change |  | 0 | 0 | -663.8488 | -562.3359 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -70.7936 | 3977.06
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 3300 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 25484.3233 | 25484.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 442.4601 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 3416.9078 | 3416.9078
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 2142.5 | 3402.5 | 982.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 17421.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 287.2639 | 456.2032 | 131.774 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2335.8004 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10356.4467 | 895 | 3355 | 8376.81 | 18895 | 0 | 0 | 0 | -528 | 41350.2567 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1388.5801 | 120.0005 | 449.8344 | 1123.1527 | 2533.4191 | 0 | 0 | 0 | -70.7936 | 5544.1933 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 7466.4833 | 12122.5 | 17685.8567 | 77784.06 | 2460 | 0 | 0 | 0 | 0 | 119419.8267 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 1001.0972 | 1625.3704 | 2371.2986 | 10429.1943 | 329.8339 | 0 | 0 | 0 | 0 | 16011.6684 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 28623 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 44760.86 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3837.7378 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 6001.4829 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 3715 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 498.1028 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5025 | 19962.25 | 0 | 27000 | 0 | 0 | 0 | 51987.25 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 673.746 | 2676.5148 | 0 | 3620.1279 | 0 | 0 | 0 | 6970.3887 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345 | 0 | 3390 | 0 | 7735 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.5724 | 0 | 454.5272 | 0 | 1037.0996 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 65200 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 71008 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8741.9385 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9520.6682 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 0 | 1495 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 1970 | 1970 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 200.4478 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 264.1353 | 264.1353
| Sum |  | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 383464.4067 |  |  | Sum |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289 | 51414.4519
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 277 | 42
| New Sales |  | 1 | 101 | 13 | 36 | 17 | 11 | 34 | 0 | 0 | 0 | 1 | 4 | 218 | 259 | 41
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 17 | 6
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 41 | 30
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 60 | 55
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 17 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 67 | 195 | 128
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 84 | -18
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 571 | 336
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 235153.0367 | 26508.96 |  | All orders |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498
| New Sales |  | 4600 | 84250 | 11207 | 30270.5 | 18285.5 | 6195 | 41653.25 | 0 | 0 | 0 | 2047 | 1400 | 199908.25 | 226417.21 | 26508.96 |  | New Sales |  | 616.7625 | 11296.1399 | 1502.6212 | 4058.6327 | 2451.6981 | 830.6182 | 5584.8183 | 0 | 0 | 0 | 274.4593 | 187.7103 | 26803.4606
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | 305.3933 | 0 | 0 | 0 | 527.39 | 0 | 8735.8267 | 8735.8267 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | 40.9468 | 0 | 0 | 0 | 70.7118 | 0 | 1171.2893
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 9262 | 9262 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7103 | 1241.838 | 1241.838
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 486.39 | 0 | 0 | 0 | 0 | 0 | 13235.39 | 13235.39 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 65.2146 | 0 | 0 | 0 | 0 | 0 | 1774.5854 | 1774.5854
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 400 | 996 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 2395 | 2395 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 53.6315 | 133.5425 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 321.1188 | 321.1188
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 1987.5 | 17319.5 | 5035 | 29602.5033 | 0 | 0 | 0 | 0 | 0 | 54537.5467 | 54537.5467 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 266.4816 | 2322.178 | 675.0868 | 3969.0685 | 0 | 0 | 0 | 0 | 0 | 7312.3294 | 7312.3294
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 9810.75 | 0 | 0 | 0 | 0 | 0 | 31624.75 | 31624.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1315.4137 | 0 | 0 | 0 | 0 | 0 | 4240.2089 | 4240.2089
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.39 | 0 | 2574.39 | 2574.39 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.1712 | 0 | 345.1712 | 345.1712
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 84250 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84900 | 84900 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 11296.1399 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383.2911 | 11383.2911
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 208644.0767 |  |  | Sum |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498 | 27974.7498
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 172 | 2
| New Sales |  | 3 | 42 | 86 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 160 | 162 | 2
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 17 | -56
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 60 | 48
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 13 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 21 | 195 | 174
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 36 | 34
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 84 | 42
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 568 | 398
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 235153.0367 | 59191.2467 |  | All orders |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477
| New Sales |  | 2474 | 35665 | 81574 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 176641.81 | 226417.21 | 49775.4 |  | New Sales |  | 331.711 | 4781.9208 | 10937.345 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23683.924
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 8735.8267 | 9415.8467 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 68578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68578 | 68578 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 9194.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9194.8567 | 9194.8567
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 4980 | 0 | 1195 | 0 | 0 | 2550 | 0 | 0 | 0 | 8939.98 | 8939.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 667.7125 | 0 | 160.2242 | 0 | 0 | 341.901 | 0 | 0 | 0 | 1198.6619 | 1198.6619
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 3565 | 475 | 400 | 1845 | 3645 | 0 | 0 | 0 | 0 | 0 | 9930 | 9930 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 477.991 | 63.6874 | 53.6315 | 247.3754 | 488.7173 | 0 | 0 | 0 | 0 | 0 | 1331.4026 | 1331.4026
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979 | 979 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.2632 | 131.2632
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 35665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35665 | 35665 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 4781.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.9208 | 4781.9208
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 175961.79 |  |  | Sum |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477 | 23592.7477
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 172 | 142
| New Sales |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 162 | 132
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 26
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 195 | 191
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36 | 21
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 568 | 538
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 235153.0367 | 120108.6367 |  | All orders |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| New Sales |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 226417.21 | 111372.81 |  | New Sales |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8735.8267 | 8735.8267 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 15180 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035.3164 | 2035.3164
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13740.4 | 13740.4 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.2965 | 1842.2965
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 115044.4 |  |  | Sum |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164 | 15425.0164

## 20250525
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 380 | 589 | 277 | 172 | 30 |  | 1448
| New Sales |  | 331 | 445 | 259 | 162 | 30 |  | 1227
| Change |  | 49 | 144 | 18 | 10 | 0 |  | 221
| MRC DKK | Total | 402224.57 | 488845.8367 | 235153.0367 | 206356.79 | 115044.4 |  | 1447624.6333
| New Sales |  | 449694.16 | 459183.73 | 226417.21 | 207036.81 | 115044.4 |  | 1457376.31
| Change |  | -47469.59 | 29662.1067 | 8735.8267 | -680.02 | 0 |  | -9751.6767
| MRC EUR | Total | 53929.7923 | 65543.8688 | 31529.0397 | 27668.0732 | 15425.0164 |  | 194095.7904
| New Sales |  | 60294.4585 | 61566.8088 | 30357.7504 | 27759.2494 | 15425.0164 |  | 195403.2836
| Change |  | -6364.6662 | 3977.06 | 1171.2893 | -91.1763 | 0 |  | -1307.4932
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 2257 | 395
| New Sales |  | 15 | 336 | 261 | 250 | 66 | 153 | 307 | 44 | 14 | 0 | 53 | 11 | 1510 | 1655 | 145
| Change |  | 5 | 2 | 127 | 15 | 2 | 74 | 30 | 20 | 24 | 0 | 50 | 3 | 352 | 602 | 250
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 144 | 6 | 0 | 12 | 10 | 3 | 2 | 0 | 0 | 8 | 188 | 191
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 0 | 20 | 13 | 7 | 42 | 11 | 4 | 0 | 0 | 0 | 2 | 100 | 100
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 19 | 19
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 24 | 4 | 62 | 10 | 7 | 2 | 0 | 0 | 0 | 130 | 130
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 22 | 3 | 5 | 10 | 10 | 0 | 0 | 0 | 1 | 57 | 57
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 67 | 66 | 41 | 67 | 220 | 36 | 3 | 0 | 0 | 0 | 506 | 507
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 25 | 89 | 5 | 13 | 35 | 1 | 0 | 0 | 0 | 0 | 169 | 169
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 2 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 15 | 15
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 2 | 47 | 47
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 103 | 0 | 111 | 112
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 394 | 396
| Orders without status |  | 0 | 0 | 0 | 2 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 11 | 11
| Sum |  | 20 | 338 | 388 | 265 | 68 | 227 | 337 | 64 | 38 | 0 | 103 | 14 | 1862 | 1871
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 2135401.4333 | 194479.92 |  | All orders |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 286312.0863 | 26075.6365
| New Sales |  | 14337 | 329574.1 | 332624.5 | 314631.19 | 65298.56 | 274713.05 | 409383.95 | 48416.73 | 19772.5 | 0 | 92102.02 | 18770 | 1919623.6 | 2089796.22 | 170172.62 |  | New Sales |  | 1922.2879 | 44188.9036 | 44597.8976 | 42185.376 | 8755.1533 | 36833.1993 | 54889.7135 | 6491.6576 | 2651.0733 | 0 | 12348.9294 | 2516.6593 | 257380.8509 | 280197.3935 | 22816.5426
| Change |  | -644.89 | -16607.58 | 46574.81 | 414.82 | 1755 | -20958.7733 | -7681.5133 | 14868.24 | 27740 | 0 | -22626.23 | -1535.97 | 21297.9133 | 45605.2133 | 24307.3 |  | Change |  | -86.4661 | -2226.7246 | 6244.6952 | 55.6186 | 235.3083 | -2810.1274 | -1029.9282 | 1993.5159 | 3719.3462 | 0 | -3033.698 | -205.941 | 2855.5989 | 6114.6928 | 3259.0939
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 199351.9567 | 16574 | 0 | 12260.66 | 29889.7933 | 1038 | 3510 | 0 | 0 | 3482.03 | 280231.44 | 281128.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 26728.8734 | 2222.2222 | 0 | 1643.8947 | 4007.588 | 139.1738 | 470.6166 | 0 | 0 | 466.8664 | 37573.0984 | 37693.3671
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 0 | 25775 | 17580 | 14476.06 | 38505 | 44786.39 | 5985.41 | 0 | 0 | 0 | 9100 | 157156.86 | 157156.86 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 0 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 6004.9059 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 21071.405 | 21071.405
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 1040 | 0 | 0 | 0 | 0 | 0 | 11296.3 | 11296.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 139.442 | 0 | 0 | 0 | 0 | 0 | 1514.5945 | 1514.5945
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 9632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11617.47 | 11617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 1291.5101 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.6566 | 1557.6566
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 23432.5 | 4398.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3141.8018 | 589.7457 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 14729.6467 | 1295 | -15580.02 | 24711.81 | 19355 | 0 | 0 | 0 | -528 | 59621.5167 | 59621.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 1974.9335 | 173.6321 | -2088.9506 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | -70.7936 | 7993.9821 | 7993.9821
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 29472.5833 | 57448.11 | 34477 | 38209.7567 | 189530.9433 | 27147.3 | 4130 | 0 | 0 | 0 | 390696.8133 | 391533.8133 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3951.6489 | 7702.5743 | 4622.6352 | 5123.1188 | 25412.0836 | 3639.8777 | 553.7455 | 0 | 0 | 0 | 52384.1644 | 52496.3884
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22795.28 | 150851 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 295855.03 | 295855.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 3056.3641 | 20225.9228 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39667.8908 | 39667.8908
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 11684.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1566.6519
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 2848 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 23032.97 | 23032.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 381.8565 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 3088.2332 | 3088.2332
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 4191.5633 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 5411.5633 | 5411.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 561.9998 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 725.576 | 725.576
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2100 | 103243.05 | 103243.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 281.5655 | 13842.7054 | 13842.7054
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 8485 | 0 | 69475.79 | 0 | 79455.79 | 79899.478 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1137.6587 | 0 | 9315.2314 | 0 | 10653.3379 | 10712.827
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 3080 | 316016 | 316697.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 412.9627 | 42371.0497 | 42462.4083
| Orders without status |  | 0 | 0 | 0 | 400 | 1495 | 860 | 4615 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 200.4478 | 115.3078 | 618.7737 | 0 | 0 | 0 | 0 | 0 | 988.1608 | 988.1608
| Sum |  | 13692.11 | 312966.52 | 379199.31 | 315046.01 | 67053.56 | 253754.2767 | 401702.4367 | 63284.97 | 47512.5 | 0 | 69475.79 | 17234.03 | 1940921.5133 | 1945630.5813 |  |  | Sum |  | 1835.8218 | 41962.179 | 50842.5928 | 42240.9946 | 8990.4616 | 34023.0718 | 53859.7853 | 8485.1736 | 6370.4195 | 0 | 9315.2314 | 2310.7183 | 260236.4498 | 260867.836
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 380 | 10
| New Sales |  | 1 | 51 | 20 | 35 | 0 | 36 | 93 | 33 | 4 | 0 | 47 | 1 | 321 | 331 | 10
| Change |  | 0 | 2 | 10 | 6 | 0 | 6 | 11 | 3 | 2 | 0 | 7 | 2 | 49 | 49 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 10 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 3 | 23 | 23 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 1 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 6 | 0 | 4 | 78 | 22 | 0 | 0 | 0 | 0 | 118 | 118 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 15 | 0 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 34 | 34 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 11 | 11 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 54 | 0 | 59 | 59 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 49 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0
| Orders without status |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 53 | 30 | 41 | 0 | 42 | 104 | 36 | 6 | 0 | 54 | 3 | 370 | 370 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 402224.57 | 9502 |  | All orders |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | XX
| New Sales |  | 979 | 68463.7 | 35394 | 34596.94 | 0 | 67527.55 | 111461.22 | 40235.73 | 4640 | 0 | 75399.02 | 1495 | 440192.16 | 449694.16 | 9502 |  | New Sales |  | 131.2632 | 9179.5315 | 4745.5855 | 4638.7166 | 0 | 9054.0136 | 14944.5879 | 5394.7589 | 622.1257 | 0 | 10109.411 | 200.4478 | 59020.4417
| Change |  | 0 | -16607.58 | 14023.43 | 4608.89 | 0 | -21053.88 | -3040.84 | -1178.02 | -60 | 0 | -23153.62 | -1007.97 | -47469.59 | -47469.59 | 0 |  | Change |  | 0 | -2226.7246 | 1880.2448 | 617.9545 | 0 | -2822.8792 | -407.7122 | -157.9475 | -8.0447 | 0 | -3104.4099 | -135.1474 | -6364.6662
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 10016 | 0 | 1038 | 0 | 0 | 0 | 487.03 | 35452.4867 | 35452.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1342.9334 | 0 | 139.1738 | 0 | 0 | 0 | 65.3004 | 4753.4273 | 4753.4273
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 20185.41 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 2706.4358 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 1040 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.442 | 0 | 0 | 0 | 0 | 0 | 139.442 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 518.2 | 0 | -18935.02 | 12335 | 460 | 0 | 0 | 0 | 0 | -4054.14 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 69.4796 | 0 | -2538.785 | 1653.8621 | 61.6763 | 0 | 0 | 0 | 0 | -543.5743 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4744.1267 | 0 | 7739 | 64421.38 | 24687.3 | 0 | 0 | 0 | 0 | 112292.66 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 636.0869 | 0 | 1037.6359 | 8637.5421 | 3310.0438 | 0 | 0 | 0 | 0 | 15056.0664 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 17695 | 0 | 7620 | 15284 | 979 | 0 | 0 | 0 | 0 | 46978 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2372.5246 | 0 | 1021.6805 | 2049.2606 | 131.2632 | 0 | 0 | 0 | 0 | 6298.7544 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75.5454 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308.4367 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175.4336 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 1600 | 0 | 400 | 0 | 0 | 0 | 27606.05 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 214.5261 | 0 | 53.6315 | 0 | 0 | 0 | 3701.3864 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 4140 | 0 | 52245.4 | 0 | 57880.4 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 555.0863 | 0 | 7005.0011 | 0 | 7760.5352 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42350 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43430 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 5678.2377 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823.0428 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 400 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 0 | 115.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 168.9393 | 168.9393
| Sum |  | 979 | 51856.12 | 49417.43 | 39205.83 | 0 | 46473.67 | 108420.38 | 39057.71 | 4580 | 0 | 52245.4 | 487.03 | 392722.57 | 392722.57 |  |  | Sum |  | 131.2632 | 6952.8069 | 6625.8303 | 5256.6711 | 0 | 6231.1344 | 14536.8757 | 5236.8113 | 614.081 | 0 | 7005.0011 | 65.3004 | 52655.7754 | 52655.7754
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 589 | 17
| New Sales |  | 3 | 79 | 28 | 57 | 26 | 82 | 135 | 11 | 5 | 0 | 2 | 0 | 428 | 445 | 17
| Change |  | 0 | 0 | 20 | 6 | 0 | 60 | 7 | 6 | 2 | 0 | 42 | 1 | 144 | 144 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 17 | 17 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 4 | 3 | 40 | 3 | 3 | 0 | 0 | 0 | 0 | 60 | 60 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10 | 1 | 3 | 4 | 8 | 0 | 0 | 0 | 1 | 27 | 27 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 15 | 14 | 48 | 94 | 4 | 0 | 0 | 0 | 0 | 195 | 195 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 20 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 44 | 0 | 47 | 47 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 79 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| Sum |  | 3 | 79 | 48 | 63 | 26 | 142 | 142 | 17 | 7 | 0 | 44 | 1 | 572 | 572 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 488845.8367 | 44141.5 |  | All orders |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289
| New Sales |  | 2095 | 65200 | 38919.25 | 61232.5 | 21294 | 53065.5 | 153809.98 | 8181 | 7855 | 0 | 3390 | 0 | 415042.23 | 459183.73 | 44141.5 |  | New Sales |  | 280.8951 | 8741.9385 | 5218.2468 | 8209.9808 | 2855.0742 | 7114.9592 | 20622.6593 | 1096.8988 | 1053.1891 | 0 | 454.5272 | 0 | 55648.3689
| Change |  | 0 | 0 | -4951.1833 | -4194.07 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -528 | 29662.1067 | 29662.1067 | 0 |  | Change |  | 0 | 0 | -663.8488 | -562.3359 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -70.7936 | 3977.06
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 3300 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 25484.3233 | 25484.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 442.4601 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 3416.9078 | 3416.9078
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 1040 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 139.442
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 2142.5 | 3402.5 | 982.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 17421.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 287.2639 | 456.2032 | 131.774 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2335.8004 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10356.4467 | 895 | 3355 | 8376.81 | 18895 | 0 | 0 | 0 | -528 | 41350.2567 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1388.5801 | 120.0005 | 449.8344 | 1123.1527 | 2533.4191 | 0 | 0 | 0 | -70.7936 | 5544.1933 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 7466.4833 | 12122.5 | 17685.8567 | 77784.06 | 2460 | 0 | 0 | 0 | 0 | 119419.8267 | 112292.66 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 1001.0972 | 1625.3704 | 2371.2986 | 10429.1943 | 329.8339 | 0 | 0 | 0 | 0 | 16011.6684 | 15056.0664
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 28623 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 44760.86 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3837.7378 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 6001.4829 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 3715 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 498.1028 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5025 | 19962.25 | 0 | 27000 | 0 | 0 | 0 | 51987.25 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 673.746 | 2676.5148 | 0 | 3620.1279 | 0 | 0 | 0 | 6970.3887 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345 | 0 | 3390 | 0 | 7735 | 57880.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.5724 | 0 | 454.5272 | 0 | 1037.0996 | 7760.5352
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 65200 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 71008 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8741.9385 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9520.6682 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 0 | 1495 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 1970 | 1970 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 200.4478 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 264.1353 | 264.1353
| Sum |  | 2095 | 65200 | 33968.0667 | 57038.43 | 21294 | 52746.6667 | 150417.9133 | 24227.26 | 34855 | 0 | 3390 | -528 | 444704.3367 | 383464.4067 |  |  | Sum |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2855.0742 | 7072.2104 | 20167.8551 | 3248.3622 | 4673.317 | 0 | 454.5272 | -70.7936 | 59625.4289 | 51414.4519
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 277 | 42
| New Sales |  | 1 | 101 | 13 | 36 | 17 | 11 | 34 | 0 | 0 | 0 | 1 | 4 | 218 | 259 | 41
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 17 | 6
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 41 | 30
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 60 | 55
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 17 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 67 | 195 | 128
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 84 | -18
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 571 | 336
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 235153.0367 | 26508.96 |  | All orders |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498
| New Sales |  | 4600 | 84250 | 11207 | 30270.5 | 18285.5 | 6195 | 41653.25 | 0 | 0 | 0 | 2047 | 1400 | 199908.25 | 226417.21 | 26508.96 |  | New Sales |  | 616.7625 | 11296.1399 | 1502.6212 | 4058.6327 | 2451.6981 | 830.6182 | 5584.8183 | 0 | 0 | 0 | 274.4593 | 187.7103 | 26803.4606
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | 305.3933 | 0 | 0 | 0 | 527.39 | 0 | 8735.8267 | 8735.8267 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | 40.9468 | 0 | 0 | 0 | 70.7118 | 0 | 1171.2893
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 9262 | 9262 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7103 | 1241.838 | 1241.838
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 486.39 | 0 | 0 | 0 | 0 | 0 | 13235.39 | 13235.39 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 65.2146 | 0 | 0 | 0 | 0 | 0 | 1774.5854 | 1774.5854
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 400 | 996 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 2395 | 2395 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 53.6315 | 133.5425 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 321.1188 | 321.1188
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 1987.5 | 17319.5 | 5035 | 29602.5033 | 0 | 0 | 0 | 0 | 0 | 54537.5467 | 54537.5467 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 266.4816 | 2322.178 | 675.0868 | 3969.0685 | 0 | 0 | 0 | 0 | 0 | 7312.3294 | 7312.3294
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 9810.75 | 0 | 0 | 0 | 0 | 0 | 31624.75 | 31624.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1315.4137 | 0 | 0 | 0 | 0 | 0 | 4240.2089 | 4240.2089
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.39 | 0 | 2574.39 | 2574.39 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.1712 | 0 | 345.1712 | 345.1712
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 84250 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84900 | 84900 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 11296.1399 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383.2911 | 11383.2911
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 208644.0767 |  |  | Sum |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498 | 27974.7498
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 172 | 2
| New Sales |  | 3 | 42 | 86 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 160 | 162 | 2
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 17 | -56
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 60 | 48
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 13 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 21 | 195 | 174
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 36 | 34
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 47 | 45
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 84 | 42
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 3 | 42 | 96 | 9 | 4 | 5 | 6 | 0 | 1 | 0 | 2 | 2 | 170 | 568 | 398
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 235153.0367 | 59191.2467 |  | All orders |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477
| New Sales |  | 2474 | 35665 | 81574 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 176641.81 | 226417.21 | 49775.4 |  | New Sales |  | 331.711 | 4781.9208 | 10937.345 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23683.924
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 8735.8267 | 9415.8467 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 68578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68578 | 68578 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 9194.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9194.8567 | 9194.8567
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 4980 | 0 | 1195 | 0 | 0 | 2550 | 0 | 0 | 0 | 8939.98 | 8939.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 667.7125 | 0 | 160.2242 | 0 | 0 | 341.901 | 0 | 0 | 0 | 1198.6619 | 1198.6619
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 3565 | 475 | 400 | 1845 | 3645 | 0 | 0 | 0 | 0 | 0 | 9930 | 9930 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 477.991 | 63.6874 | 53.6315 | 247.3754 | 488.7173 | 0 | 0 | 0 | 0 | 0 | 1331.4026 | 1331.4026
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979 | 979 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.2632 | 131.2632
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 35665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35665 | 35665 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 4781.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.9208 | 4781.9208
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2474 | 35665 | 80893.98 | 8325.75 | 5623.06 | 8535 | 13695 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 175961.79 |  |  | Sum |  | 331.711 | 4781.9208 | 10846.1687 | 1116.3067 | 753.9332 | 1144.3627 | 1836.2093 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477 | 23592.7477
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 172 | 142
| New Sales |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 162 | 132
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 26
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 195 | 191
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36 | 21
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 568 | 538
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 235153.0367 | 120108.6367 |  | All orders |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| New Sales |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 226417.21 | 111372.81 |  | New Sales |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8735.8267 | 8735.8267 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 15180 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035.3164 | 2035.3164
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13740.4 | 13740.4 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.2965 | 1842.2965
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 115044.4 |  |  | Sum |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164 | 15425.0164

## 20250526
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 380 | 589 | 277 | 172 | 30 |  | 1448
| New Sales |  | 331 | 445 | 259 | 162 | 30 |  | 1227
| Change |  | 49 | 144 | 18 | 10 | 0 |  | 221
| MRC DKK | Total | 402224.57 | 488845.8367 | 235153.0367 | 206356.79 | 115044.4 |  | 1447624.6333
| New Sales |  | 449694.16 | 459183.73 | 226417.21 | 207036.81 | 115044.4 |  | 1457376.31
| Change |  | -47469.59 | 29662.1067 | 8735.8267 | -680.02 | 0 |  | -9751.6767
| MRC EUR | Total | 53929.7923 | 65543.8688 | 31529.0397 | 27668.0732 | 15425.0164 |  | 194095.7904
| New Sales |  | 60294.4585 | 61566.8088 | 30357.7504 | 27759.2494 | 15425.0164 |  | 195403.2836
| Change |  | -6364.6662 | 3977.06 | 1171.2893 | -91.1763 | 0 |  | -1307.4932
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 338 | 331 | 263 | 68 | 256 | 335 | 64 | 40 | 0 | 138 | 14 | 1867 | 2257 | 390
| New Sales |  | 15 | 336 | 206 | 249 | 66 | 205 | 304 | 44 | 14 | 0 | 63 | 11 | 1513 | 1655 | 142
| Change |  | 5 | 2 | 125 | 14 | 2 | 51 | 31 | 20 | 26 | 0 | 75 | 3 | 354 | 602 | 248
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 90 | 6 | 0 | 12 | 12 | 3 | 2 | 0 | 0 | 8 | 136 | 139
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 0 | 20 | 13 | 7 | 42 | 10 | 4 | 0 | 0 | 0 | 2 | 99 | 99
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 17
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 24 | 4 | 39 | 10 | 7 | 2 | 0 | 0 | 0 | 107 | 107
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 22 | 3 | 57 | 10 | 10 | 0 | 0 | 0 | 1 | 109 | 109
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 64 | 65 | 41 | 67 | 218 | 36 | 3 | 0 | 0 | 0 | 500 | 503
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 25 | 89 | 5 | 13 | 36 | 1 | 0 | 0 | 0 | 0 | 170 | 171
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 2 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 15 | 15
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 2 | 47 | 47
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 0 | 138 | 0 | 148 | 149
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 394 | 396
| Orders without status |  | 0 | 0 | 0 | 2 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 11 | 11
| Sum |  | 20 | 338 | 331 | 263 | 68 | 256 | 335 | 64 | 40 | 0 | 138 | 14 | 1867 | 1877
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 312966.52 | 338962.31 | 314936.01 | 68208.56 | 283839.2767 | 401704.0967 | 63284.97 | 53892.5 | 0 | 73499.71 | 17234.03 | 1942220.0933 | 2135401.4333 | 193181.34 |  | All orders |  | 1835.8218 | 41962.179 | 45447.6637 | 42226.2459 | 9145.3227 | 38056.8329 | 53860.0079 | 8485.1736 | 7225.8424 | 0 | 9854.7538 | 2310.7183 | 260410.5618 | 286312.0863 | 25901.5245
| New Sales |  | 14337 | 329574.1 | 298937.5 | 314521.19 | 66453.56 | 304798.05 | 410520.95 | 48416.73 | 19602.5 | 0 | 96782.02 | 18770 | 1922713.6 | 2089796.22 | 167082.62 |  | New Sales |  | 1922.2879 | 44188.9036 | 40081.1847 | 42170.6274 | 8910.0143 | 40866.9603 | 55042.1611 | 6491.6576 | 2628.2799 | 0 | 12976.4182 | 2516.6593 | 257795.1544 | 280197.3935 | 22402.2391
| Change |  | -644.89 | -16607.58 | 40024.81 | 414.82 | 1755 | -20958.7733 | -8816.8533 | 14868.24 | 34290 | 0 | -23282.31 | -1535.97 | 19506.4933 | 45605.2133 | 26098.72 |  | Change |  | -86.4661 | -2226.7246 | 5366.479 | 55.6186 | 235.3083 | -2810.1274 | -1182.1532 | 1993.5159 | 4597.5624 | 0 | -3121.6645 | -205.941 | 2615.4074 | 6114.6928 | 3499.2854
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 161391.9567 | 16574 | 0 | 12260.66 | 30929.7933 | 1038 | 3510 | 0 | 0 | 3482.03 | 243311.44 | 244208.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 21639.2417 | 2222.2222 | 0 | 1643.8947 | 4147.0299 | 139.1738 | 470.6166 | 0 | 0 | 466.8664 | 32622.9087 | 32743.1774
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 0 | 25775 | 17580 | 14476.06 | 38505 | 44300 | 5985.41 | 0 | 0 | 0 | 9100 | 156670.47 | 156670.47 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 0 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 5939.6914 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 21006.1904 | 21006.1904
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 10256.3 | 10256.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 1375.1525 | 1375.1525
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 9632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11617.47 | 11617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 1291.5101 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.6566 | 1557.6566
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 23432.5 | 4398.5 | 88097.83 | 14839 | 4560.29 | 3147.5 | 0 | 0 | 0 | 159506.6 | 159506.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3141.8018 | 589.7457 | 11812.0523 | 1989.5955 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21386.4554 | 21386.4554
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 14729.6467 | 1295 | 15829.98 | 24711.81 | 19355 | 0 | 0 | 0 | -528 | 91031.5167 | 91031.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 1974.9335 | 173.6321 | 2122.4649 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | -70.7936 | 12205.3976 | 12205.3976
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 27195.5833 | 57338.11 | 35632 | 36884.7567 | 190018.9933 | 27147.3 | 4130 | 0 | 0 | 0 | 388627.8633 | 391314.8633 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3646.3515 | 7687.8256 | 4777.4962 | 4945.4643 | 25477.5208 | 3639.8777 | 553.7455 | 0 | 0 | 0 | 52106.762 | 52467.0318
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22795.28 | 151696 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 296700.03 | 297375.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 3056.3641 | 20339.2194 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39781.1874 | 39871.6906
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 9834.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1318.6061
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 2848 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 23032.97 | 23032.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 381.8565 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 3088.2332 | 3088.2332
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 3346.5633 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 4566.5633 | 4566.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 448.7032 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 612.2794 | 612.2794
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2100 | 103243.05 | 103243.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 281.5655 | 13842.7054 | 13842.7054
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 14865 | 0 | 73499.71 | 0 | 89859.71 | 90303.398 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1993.0815 | 0 | 9854.7538 | 0 | 12048.2831 | 12107.7723
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 3080 | 316016 | 316697.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 412.9627 | 42371.0497 | 42462.4083
| Orders without status |  | 0 | 0 | 0 | 400 | 1495 | 860 | 4615 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 200.4478 | 115.3078 | 618.7737 | 0 | 0 | 0 | 0 | 0 | 988.1608 | 988.1608
| Sum |  | 13692.11 | 312966.52 | 338962.31 | 314936.01 | 68208.56 | 283839.2767 | 401704.0967 | 63284.97 | 53892.5 | 0 | 73499.71 | 17234.03 | 1942220.0933 | 1947604.1613 |  |  | Sum |  | 1835.8218 | 41962.179 | 45447.6637 | 42226.2459 | 9145.3227 | 38056.8329 | 53860.0079 | 8485.1736 | 7225.8424 | 0 | 9854.7538 | 2310.7183 | 260410.5618 | 261132.4513
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 53 | 30 | 40 | 0 | 42 | 95 | 36 | 5 | 0 | 65 | 3 | 370 | 380 | 10
| New Sales |  | 1 | 51 | 20 | 34 | 0 | 36 | 85 | 33 | 3 | 0 | 57 | 1 | 321 | 331 | 10
| Change |  | 0 | 2 | 10 | 6 | 0 | 6 | 10 | 3 | 2 | 0 | 8 | 2 | 49 | 49 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 10 | 0 | 0 | 8 | 2 | 2 | 0 | 0 | 0 | 3 | 25 | 25 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 1 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 5 | 0 | 4 | 69 | 22 | 0 | 0 | 0 | 0 | 108 | 108 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 15 | 0 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 34 | 34 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 11 | 11 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 65 | 0 | 69 | 69 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 49 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0
| Orders without status |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 53 | 30 | 40 | 0 | 42 | 95 | 36 | 5 | 0 | 65 | 3 | 370 | 370 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 979 | 51856.12 | 49417.43 | 39055.83 | 0 | 46473.67 | 104785.38 | 39057.71 | 3685 | 0 | 56925.4 | 487.03 | 392722.57 | 402224.57 | 9502 |  | All orders |  | 131.2632 | 6952.8069 | 6625.8303 | 5236.5593 | 0 | 6231.1344 | 14049.4992 | 5236.8113 | 494.0804 | 0 | 7632.49 | 65.3004 | 52655.7754 | XX
| New Sales |  | 979 | 68463.7 | 35394 | 34446.94 | 0 | 67527.55 | 107826.22 | 40235.73 | 3745 | 0 | 80079.02 | 1495 | 440192.16 | 449694.16 | 9502 |  | New Sales |  | 131.2632 | 9179.5315 | 4745.5855 | 4618.6048 | 0 | 9054.0136 | 14457.2114 | 5394.7589 | 502.1251 | 0 | 10736.8998 | 200.4478 | 59020.4417
| Change |  | 0 | -16607.58 | 14023.43 | 4608.89 | 0 | -21053.88 | -3040.84 | -1178.02 | -60 | 0 | -23153.62 | -1007.97 | -47469.59 | -47469.59 | 0 |  | Change |  | 0 | -2226.7246 | 1880.2448 | 617.9545 | 0 | -2822.8792 | -407.7122 | -157.9475 | -8.0447 | 0 | -3104.4099 | -135.1474 | -6364.6662
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 10016 | 1040 | 1038 | 0 | 0 | 0 | 487.03 | 36492.4867 | 36492.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1342.9334 | 139.442 | 139.1738 | 0 | 0 | 0 | 65.3004 | 4892.8692 | 4892.8692
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 20185.41 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 2706.4358 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 518.2 | 0 | -18935.02 | 12335 | 460 | 0 | 0 | 0 | 0 | -4054.14 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 69.4796 | 0 | -2538.785 | 1653.8621 | 61.6763 | 0 | 0 | 0 | 0 | -543.5743 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4594.1267 | 0 | 7739 | 60786.38 | 24687.3 | 0 | 0 | 0 | 0 | 108507.66 | 108507.66 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 615.975 | 0 | 1037.6359 | 8150.1656 | 3310.0438 | 0 | 0 | 0 | 0 | 14548.5781 | 14548.5781
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 17695 | 0 | 7620 | 15284 | 979 | 0 | 0 | 0 | 0 | 46978 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2372.5246 | 0 | 1021.6805 | 2049.2606 | 131.2632 | 0 | 0 | 0 | 0 | 6298.7544 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75.5454 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308.4367 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175.4336 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 1600 | 0 | 400 | 0 | 0 | 0 | 27606.05 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 214.5261 | 0 | 53.6315 | 0 | 0 | 0 | 3701.3864 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 3245 | 0 | 56925.4 | 0 | 61665.4 | 61665.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 435.0857 | 0 | 7632.49 | 0 | 8268.0235 | 8268.0235
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42350 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43430 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 5678.2377 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823.0428 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 400 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 0 | 115.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 168.9393 | 168.9393
| Sum |  | 979 | 51856.12 | 49417.43 | 39055.83 | 0 | 46473.67 | 104785.38 | 39057.71 | 3685 | 0 | 56925.4 | 487.03 | 392722.57 | 392722.57 |  |  | Sum |  | 131.2632 | 6952.8069 | 6625.8303 | 5236.5593 | 0 | 6231.1344 | 14049.4992 | 5236.8113 | 494.0804 | 0 | 7632.49 | 65.3004 | 52655.7754 | 52655.7754
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 79 | 48 | 62 | 24 | 119 | 144 | 17 | 8 | 0 | 67 | 1 | 572 | 589 | 17
| New Sales |  | 3 | 79 | 28 | 57 | 24 | 82 | 136 | 11 | 6 | 0 | 2 | 0 | 428 | 445 | 17
| Change |  | 0 | 0 | 20 | 5 | 0 | 37 | 8 | 6 | 2 | 0 | 65 | 1 | 144 | 144 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 17 | 17 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 4 | 3 | 17 | 3 | 3 | 0 | 0 | 0 | 0 | 37 | 37 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10 | 1 | 3 | 4 | 8 | 0 | 0 | 0 | 1 | 27 | 27 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 15 | 12 | 48 | 95 | 4 | 0 | 0 | 0 | 0 | 194 | 194 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 19 | 2 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 67 | 0 | 71 | 71 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 79 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| Sum |  | 3 | 79 | 48 | 62 | 24 | 119 | 144 | 17 | 8 | 0 | 67 | 1 | 572 | 572 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 65200 | 33968.0667 | 57038.43 | 19699 | 51421.6667 | 152612.9133 | 24227.26 | 35580 | 0 | 3390 | -528 | 444704.3367 | 488845.8367 | 44141.5 |  | All orders |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2641.2185 | 6894.556 | 20462.158 | 3248.3622 | 4770.5241 | 0 | 454.5272 | -70.7936 | 59625.4289
| New Sales |  | 2095 | 65200 | 38919.25 | 61232.5 | 19699 | 51740.5 | 156004.98 | 8181 | 8580 | 0 | 3390 | 0 | 415042.23 | 459183.73 | 44141.5 |  | New Sales |  | 280.8951 | 8741.9385 | 5218.2468 | 8209.9808 | 2641.2185 | 6937.3047 | 20916.9623 | 1096.8988 | 1150.3962 | 0 | 454.5272 | 0 | 55648.3689
| Change |  | 0 | 0 | -4951.1833 | -4194.07 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -528 | 29662.1067 | 29662.1067 | 0 |  | Change |  | 0 | 0 | -663.8488 | -562.3359 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -70.7936 | 3977.06
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 3300 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 25484.3233 | 25484.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 442.4601 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 3416.9078 | 3416.9078
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 2142.5 | 3402.5 | 982.81 | 4350 | 147.29 | 0 | 0 | 0 | 0 | 17421.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 287.2639 | 456.2032 | 131.774 | 583.2428 | 19.7485 | 0 | 0 | 0 | 0 | 2335.8004 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10356.4467 | 895 | 3355 | 8376.81 | 18895 | 0 | 0 | 0 | -528 | 41350.2567 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1388.5801 | 120.0005 | 449.8344 | 1123.1527 | 2533.4191 | 0 | 0 | 0 | -70.7936 | 5544.1933 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 7466.4833 | 10527.5 | 16360.8567 | 79979.06 | 2460 | 0 | 0 | 0 | 0 | 118694.8267 | 108507.66 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 1001.0972 | 1411.5147 | 2193.6442 | 10723.4973 | 329.8339 | 0 | 0 | 0 | 0 | 15914.4613 | 14548.5781
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 28623 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 44760.86 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3837.7378 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 6001.4829 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 3715 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 498.1028 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5025 | 19962.25 | 0 | 27000 | 0 | 0 | 0 | 51987.25 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 673.746 | 2676.5148 | 0 | 3620.1279 | 0 | 0 | 0 | 6970.3887 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070 | 0 | 3390 | 0 | 8460 | 61665.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679.7796 | 0 | 454.5272 | 0 | 1134.3067 | 8268.0235
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 65200 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 71008 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8741.9385 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9520.6682 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 0 | 1495 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 1970 | 1970 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 200.4478 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 264.1353 | 264.1353
| Sum |  | 2095 | 65200 | 33968.0667 | 57038.43 | 19699 | 51421.6667 | 152612.9133 | 24227.26 | 35580 | 0 | 3390 | -528 | 444704.3367 | 382424.4067 |  |  | Sum |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2641.2185 | 6894.556 | 20462.158 | 3248.3622 | 4770.5241 | 0 | 454.5272 | -70.7936 | 59625.4289 | 51275.0099
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 277 | 42
| New Sales |  | 1 | 101 | 13 | 36 | 17 | 11 | 34 | 0 | 0 | 0 | 1 | 4 | 218 | 259 | 41
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 17 | 6
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 41 | 31
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 37 | 32
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 17 | 10 | 29 | 0 | 0 | 0 | 0 | 0 | 68 | 194 | 126
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 71 | 69
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 84 | -18
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 101 | 19 | 38 | 19 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 571 | 336
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 235153.0367 | 26508.96 |  | All orders |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498
| New Sales |  | 4600 | 84250 | 11207 | 30270.5 | 18285.5 | 6195 | 41653.25 | 0 | 0 | 0 | 2047 | 1400 | 199908.25 | 226417.21 | 26508.96 |  | New Sales |  | 616.7625 | 11296.1399 | 1502.6212 | 4058.6327 | 2451.6981 | 830.6182 | 5584.8183 | 0 | 0 | 0 | 274.4593 | 187.7103 | 26803.4606
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | 305.3933 | 0 | 0 | 0 | 527.39 | 0 | 8735.8267 | 8735.8267 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | 40.9468 | 0 | 0 | 0 | 70.7118 | 0 | 1171.2893
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 9262 | 9262 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7103 | 1241.838 | 1241.838
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 12749 | 12749 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 0 | 0 | 0 | 0 | 0 | 0 | 1709.3708 | 1709.3708
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 400 | 996 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 2395 | 2395 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 53.6315 | 133.5425 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 321.1188 | 321.1188
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 1987.5 | 17319.5 | 5035 | 30088.8933 | 0 | 0 | 0 | 0 | 0 | 55023.9367 | 55023.9367 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 266.4816 | 2322.178 | 675.0868 | 4034.2831 | 0 | 0 | 0 | 0 | 0 | 7377.544 | 7377.544
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 9810.75 | 0 | 0 | 0 | 0 | 0 | 31624.75 | 31624.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1315.4137 | 0 | 0 | 0 | 0 | 0 | 4240.2089 | 4240.2089
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.39 | 0 | 2574.39 | 2574.39 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.1712 | 0 | 345.1712 | 345.1712
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 84250 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84900 | 84900 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 11296.1399 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383.2911 | 11383.2911
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 84250 | 17355.0433 | 30270.5 | 20040.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 208644.0767 |  |  | Sum |  | 616.7625 | 11296.1399 | 2326.9436 | 4058.6327 | 2687.0064 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498 | 27974.7498
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 42 | 43 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 170 | 172 | 2
| New Sales |  | 3 | 42 | 33 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 160 | 162 | 2
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 17 | -4
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 37 | 25
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 27 | -25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 12 | 1 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 21 | 194 | 173
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 36 | 34
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 71 | 69
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 84 | 42
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 3 | 42 | 43 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 170 | 568 | 398
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2474 | 35665 | 48718.98 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 235153.0367 | 59191.2467 |  | All orders |  | 331.711 | 4781.9208 | 6532.1829 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477
| New Sales |  | 2474 | 35665 | 49399 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 176641.81 | 226417.21 | 49775.4 |  | New Sales |  | 331.711 | 4781.9208 | 6623.3592 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23683.924
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 8735.8267 | 9415.8467 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 37168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37168 | 37168 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 4983.4413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4983.4413 | 4983.4413
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 4980 | 0 | 1195 | 0 | 0 | 2550 | 0 | 0 | 0 | 8939.98 | 8939.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 667.7125 | 0 | 160.2242 | 0 | 0 | 341.901 | 0 | 0 | 0 | 1198.6619 | 1198.6619
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 31410 | 0 | 0 | 0 | 0 | 0 | 0 | 31410 | 31410 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 4211.4155 | 0 | 0 | 0 | 0 | 0 | 0 | 4211.4155 | 4211.4155
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 2800 | 475 | 400 | 1845 | 4410 | 0 | 0 | 0 | 0 | 0 | 9930 | 9930 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 375.4207 | 63.6874 | 53.6315 | 247.3754 | 591.2876 | 0 | 0 | 0 | 0 | 0 | 1331.4026 | 1331.4026
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979 | 979 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.2632 | 131.2632
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 35665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35665 | 35665 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 4781.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.9208 | 4781.9208
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2474 | 35665 | 48718.98 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 175961.79 |  |  | Sum |  | 331.711 | 4781.9208 | 6532.1829 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477 | 23592.7477
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 172 | 142
| New Sales |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 162 | 132
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 37
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 26
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 194 | 190
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36 | 21
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 71
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 3 | 1 | 19 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 568 | 538
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 235153.0367 | 120108.6367 |  | All orders |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| New Sales |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 226417.21 | 111372.81 |  | New Sales |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8735.8267 | 8735.8267 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 15180 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035.3164 | 2035.3164
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13740.4 | 13740.4 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.2965 | 1842.2965
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 62100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62800 | 62800 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 8326.2942 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420.1494 | 8420.1494
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 26545.4 | 2375 | 73849 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 0 | 0 | 115044.4 | 115044.4 |  |  | Sum |  | 0 | 3559.1757 | 318.4372 | 9901.5862 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 15425.0164 | 15425.0164

## 20250527
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35
Monthly summary
0.13408
Monthly summary
| Committed RFS |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | Sum
| Total orders | Total | 380 | 589 | 277 | 172 | 30 |  | 1448
| New Sales |  | 331 | 445 | 259 | 162 | 30 |  | 1227
| Change |  | 49 | 144 | 18 | 10 | 0 |  | 221
| MRC DKK | Total | 402224.57 | 488845.8367 | 235153.0367 | 206356.79 | 115044.4 |  | 1447624.6333
| New Sales |  | 449694.16 | 459183.73 | 226417.21 | 207036.81 | 115044.4 |  | 1457376.31
| Change |  | -47469.59 | 29662.1067 | 8735.8267 | -680.02 | 0 |  | -9751.6767
| MRC EUR | Total | 53929.7923 | 65543.8688 | 31529.0397 | 27668.0732 | 15425.0164 |  | 194095.7904
| New Sales |  | 60294.4585 | 61566.8088 | 30357.7504 | 27759.2494 | 15425.0164 |  | 195403.2836
| Change |  | -6364.6662 | 3977.06 | 1171.2893 | -91.1763 | 0 |  | -1307.4932
All orders
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped |  | 20 | 338 | 331 | 259 | 71 | 254 | 328 | 65 | 39 | 0 | 153 | 14 | 1872 | 2257 | 385
| New Sales |  | 15 | 336 | 206 | 245 | 69 | 203 | 297 | 45 | 13 | 0 | 78 | 11 | 1518 | 1655 | 137
| Change |  | 5 | 2 | 125 | 14 | 2 | 51 | 31 | 20 | 26 | 0 | 75 | 3 | 354 | 602 | 248
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1 | 2 | 90 | 5 | 1 | 12 | 12 | 3 | 2 | 0 | 0 | 8 | 136 | 137
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 2 | 3 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 21
| 1.3 Customer requested delay / change of timeline or site not ready |  | 1 | 0 | 20 | 13 | 7 | 42 | 10 | 4 | 0 | 0 | 0 | 2 | 99 | 99
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 13 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 17
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 3 | 0 | 18 | 24 | 4 | 39 | 9 | 7 | 2 | 0 | 0 | 0 | 106 | 106
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 5 | 22 | 3 | 57 | 10 | 10 | 0 | 0 | 0 | 1 | 109 | 109
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 2 | 10 | 3 | 9 | 0 | 0 | 21 | 0 | 0 | 0 | 45 | 45
| 2.6 Order in queue: Being processed |  | 2 | 4 | 64 | 63 | 43 | 65 | 212 | 37 | 3 | 0 | 0 | 0 | 493 | 498
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 25 | 88 | 5 | 13 | 36 | 1 | 0 | 0 | 0 | 0 | 169 | 170
| 3.1.1 Pending external 3rd party: Open-Net |  | 3 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 6 | 2 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 15 | 15
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| 3.4 Other installation obstacles and infratructure issues |  | 1 | 0 | 4 | 13 | 2 | 11 | 11 | 0 | 3 | 0 | 0 | 2 | 47 | 47
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 153 | 0 | 162 | 163
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 331 | 58 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 394 | 396
| Orders without status |  | 0 | 0 | 0 | 2 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 11 | 11
| Sum |  | 20 | 338 | 331 | 259 | 71 | 254 | 328 | 65 | 39 | 0 | 153 | 14 | 1872 | 1882
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| All orders | Total | 13692.11 | 312966.52 | 338962.31 | 307913.01 | 71803.56 | 282244.2767 | 394878.0967 | 64679.97 | 53167.5 | 0 | 88020.71 | 17234.03 | 1945562.0933 | 2135401.4333 | 189839.34 |  | All orders |  | 1835.8218 | 41962.179 | 45447.6637 | 41284.6104 | 9627.336 | 37842.9772 | 52944.7859 | 8672.2135 | 7128.6352 | 0 | 11801.7122 | 2310.7183 | 260858.6532 | 286312.0863 | 25453.4331
| New Sales |  | 14337 | 329574.1 | 298937.5 | 307498.19 | 70048.56 | 303203.05 | 403694.95 | 49811.73 | 18877.5 | 0 | 111303.02 | 18770 | 1926055.6 | 2089796.22 | 163740.62 |  | New Sales |  | 1922.2879 | 44188.9036 | 40081.1847 | 41228.9919 | 9392.0277 | 40653.1046 | 54126.9391 | 6678.6976 | 2531.0728 | 0 | 14923.3766 | 2516.6593 | 258243.2458 | 280197.3935 | 21954.1477
| Change |  | -644.89 | -16607.58 | 40024.81 | 414.82 | 1755 | -20958.7733 | -8816.8533 | 14868.24 | 34290 | 0 | -23282.31 | -1535.97 | 19506.4933 | 45605.2133 | 26098.72 |  | Change |  | -86.4661 | -2226.7246 | 5366.479 | 55.6186 | 235.3083 | -2810.1274 | -1182.1532 | 1993.5159 | 4597.5624 | 0 | -3121.6645 | -205.941 | 2615.4074 | 6114.6928 | 3499.2854
0.13408
| MRC (New sales and change) | DKK | [16 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 12805 | 161391.9567 | 15729 | 845 | 12260.66 | 30929.7933 | 1038 | 3510 | 0 | 0 | 3482.03 | 243311.44 | 244148.44 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 1716.8792 | 21639.2417 | 2108.9256 | 113.2966 | 1643.8947 | 4147.0299 | 139.1738 | 470.6166 | 0 | 0 | 466.8664 | 32622.9087 | 32735.1327
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 2877 | 0 | 1778 | 5684 | 0 | 0 | 0 | 0 | 0 | 15439 | 15439 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 385.7447 | 0 | 238.3921 | 762.104 | 0 | 0 | 0 | 0 | 0 | 2070.0428 | 2070.0428
| 1.3 Customer requested delay / change of timeline or site not ready |  | 949 | 0 | 25775 | 17580 | 14476.06 | 38505 | 44300 | 5985.41 | 0 | 0 | 0 | 9100 | 156670.47 | 156670.47 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 127.2408 | 0 | 3455.8814 | 2357.1055 | 1940.9329 | 5162.7046 | 5939.6914 | 802.5167 | 0 | 0 | 0 | 1220.1172 | 21006.1904 | 21006.1904
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 6904.3 | 2044 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 10256.3 | 10256.3 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 925.7203 | 274.0571 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 1375.1525 | 1375.1525
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 9632.47 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11617.47 | 11617.47 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 1291.5101 | 65.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.6566 | 1557.6566
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 891 | 0 | 20139.98 | 23432.5 | 4398.5 | 88097.83 | 13444 | 4560.29 | 3147.5 | 0 | 0 | 0 | 158111.6 | 158111.6 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 119.4642 | 0 | 2700.3446 | 3141.8018 | 589.7457 | 11812.0523 | 1802.5555 | 611.4383 | 422.0131 | 0 | 0 | 0 | 21199.4154 | 21199.4154
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 1897.68 | 14729.6467 | 1295 | 15829.98 | 24711.81 | 19355 | 0 | 0 | 0 | -528 | 91031.5167 | 91031.5167 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 254.4387 | 1974.9335 | 173.6321 | 2122.4649 | 3313.3301 | 2595.0954 | 0 | 0 | 0 | -70.7936 | 12205.3976 | 12205.3976
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 3550 | 3016.44 | 1000 | 3375 | 0 | 0 | 840 | 0 | 0 | 0 | 11781.44 | 11781.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 475.9798 | 404.4407 | 134.0788 | 452.516 | 0 | 0 | 112.6262 | 0 | 0 | 0 | 1579.6415 | 1579.6415
| 2.6 Order in queue: Being processed |  | 775 | 9506.12 | 27195.5833 | 54588.11 | 38382 | 35289.7567 | 184587.9933 | 28542.3 | 4130 | 0 | 0 | 0 | 382996.8633 | 385743.8633 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 1274.5693 | 3646.3515 | 7319.1089 | 5146.2129 | 4731.6086 | 24749.3388 | 3826.9177 | 553.7455 | 0 | 0 | 0 | 51351.7643 | 51720.0787
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 22795.28 | 148268 | 6917 | 60930 | 48782.75 | 979 | 0 | 0 | 0 | 0 | 293272.03 | 293947.03 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 3056.3641 | 19879.5972 | 927.4231 | 8169.422 | 6540.7331 | 131.2632 | 0 | 0 | 0 | 0 | 39321.5652 | 39412.0684
| 3.1.1 Pending external 3rd party: Open-Net |  | 2937 | 0 | 3667.56 | 3230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.56 | 9834.56 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 393.7895 | 0 | 491.7421 | 433.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318.6061 | 1318.6061
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 7677.5 | 2848 | 0 | 0 | 9782.5 | 2724.97 | 0 | 0 | 0 | 0 | 23032.97 | 23032.97 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1029.3901 | 381.8565 | 0 | 0 | 1311.626 | 365.3607 | 0 | 0 | 0 | 0 | 3088.2332 | 3088.2332
| 3.2.2 Pending internal 3rd party: GC Sweden |  | -544.89 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355.11 | 3355.11 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | -73.0582 | 0 | 522.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.8492 | 449.8492
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 3346.5633 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 4566.5633 | 4566.5633 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 448.7032 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 612.2794 | 612.2794
| 3.4 Other installation obstacles and infratructure issues |  | 1270 | 0 | 8472 | 15333.75 | 2995 | 23160.05 | 22512.25 | 0 | 27400 | 0 | 0 | 2100 | 103243.05 | 103243.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 170.2801 | 0 | 1135.9157 | 2055.931 | 401.566 | 3105.272 | 3018.4157 | 0 | 3673.7594 | 0 | 0 | 281.5655 | 13842.7054 | 13842.7054
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 14140 | 0 | 88020.71 | 0 | 103655.71 | 104099.398 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 1895.8744 | 0 | 11801.7122 | 0 | 13898.0344 | 13957.5236
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 276915 | 30863 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 3080 | 316016 | 316697.38 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 37128.4341 | 4138.0744 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 412.9627 | 42371.0497 | 42462.4083
| Orders without status |  | 0 | 0 | 0 | 400 | 1495 | 860 | 4615 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 200.4478 | 115.3078 | 618.7737 | 0 | 0 | 0 | 0 | 0 | 988.1608 | 988.1608
| Sum |  | 13692.11 | 312966.52 | 338962.31 | 307913.01 | 71803.56 | 282244.2767 | 394878.0967 | 64679.97 | 53167.5 | 0 | 88020.71 | 17234.03 | 1945562.0933 | 1950946.1613 |  |  | Sum |  | 1835.8218 | 41962.179 | 45447.6637 | 41284.6104 | 9627.336 | 37842.9772 | 52944.7859 | 8672.2135 | 7128.6352 | 0 | 11801.7122 | 2310.7183 | 260858.6532 | 261580.5427
May orders
Committed RFS | 2025-05-01 | 2025-06-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 53 | 30 | 40 | 0 | 42 | 94 | 36 | 5 | 0 | 71 | 3 | 375 | 380 | 5
| New Sales |  | 1 | 51 | 20 | 34 | 0 | 36 | 84 | 33 | 3 | 0 | 63 | 1 | 326 | 331 | 5
| Change |  | 0 | 2 | 10 | 6 | 0 | 6 | 10 | 3 | 2 | 0 | 8 | 2 | 49 | 49 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 10 | 0 | 0 | 8 | 2 | 2 | 0 | 0 | 0 | 3 | 25 | 25 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 6 | 6 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 4 | 7 | 0 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 30 | 30 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 3 | 1 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 9 | 0
| 2.6 Order in queue: Being processed |  | 0 | 4 | 4 | 5 | 0 | 4 | 68 | 22 | 0 | 0 | 0 | 0 | 107 | 107 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 3 | 15 | 0 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 34 | 34 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 11 | 11 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 71 | 0 | 75 | 75 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 49 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0
| Orders without status |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 53 | 30 | 40 | 0 | 42 | 94 | 36 | 5 | 0 | 71 | 3 | 375 | 375 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 979 | 51856.12 | 49417.43 | 39055.83 | 0 | 46473.67 | 103390.38 | 39057.71 | 3685 | 0 | 61662.4 | 487.03 | 396064.57 | 402224.57 | 6160 |  | All orders |  | 131.2632 | 6952.8069 | 6625.8303 | 5236.5593 | 0 | 6231.1344 | 13862.4593 | 5236.8113 | 494.0804 | 0 | 8267.6213 | 65.3004 | 53103.8668 | XX
| New Sales |  | 979 | 68463.7 | 35394 | 34446.94 | 0 | 67527.55 | 106431.22 | 40235.73 | 3745 | 0 | 84816.02 | 1495 | 443534.16 | 449694.16 | 6160 |  | New Sales |  | 131.2632 | 9179.5315 | 4745.5855 | 4618.6048 | 0 | 9054.0136 | 14270.1715 | 5394.7589 | 502.1251 | 0 | 11372.0312 | 200.4478 | 59468.533
| Change |  | 0 | -16607.58 | 14023.43 | 4608.89 | 0 | -21053.88 | -3040.84 | -1178.02 | -60 | 0 | -23153.62 | -1007.97 | -47469.59 | -47469.59 | 0 |  | Change |  | 0 | -2226.7246 | 1880.2448 | 617.9545 | 0 | -2822.8792 | -407.7122 | -157.9475 | -8.0447 | 0 | -3104.4099 | -135.1474 | -6364.6662
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 23911.4567 | 0 | 0 | 10016 | 1040 | 1038 | 0 | 0 | 0 | 487.03 | 36492.4867 | 36492.4867 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 3206.0197 | 0 | 0 | 1342.9334 | 139.442 | 139.1738 | 0 | 0 | 0 | 65.3004 | 4892.8692 | 4892.8692
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 995 | 0 | 1778 | 2350 | 0 | 0 | 0 | 0 | 0 | 5123 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 133.4084 | 0 | 238.3921 | 315.0852 | 0 | 0 | 0 | 0 | 0 | 686.8858 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 5985.41 | 0 | 0 | 0 | 0 | 20185.41 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 0 | 1903.9191 | 0 | 802.5167 | 0 | 0 | 0 | 0 | 2706.4358 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 11870 | 10777.5 | 0 | 6730.64 | 9490 | 4413 | 0 | 0 | 0 | 0 | 43281.14 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 1591.5155 | 1445.0344 | 0 | 902.4362 | 1272.4079 | 591.6898 | 0 | 0 | 0 | 0 | 5803.0838 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 1567.68 | 518.2 | 0 | -18935.02 | 12335 | 460 | 0 | 0 | 0 | 0 | -4054.14 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 210.1927 | 69.4796 | 0 | -2538.785 | 1653.8621 | 61.6763 | 0 | 0 | 0 | 0 | -543.5743 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1806.44 | 0 | -665 | 0 | 0 | 40 | 0 | 0 | 0 | 1181.44 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 242.2053 | 0 | -89.1624 | 0 | 0 | 5.3632 | 0 | 0 | 0 | 158.4061 | 158.4061
| 2.6 Order in queue: Being processed |  | 0 | 9506.12 | 1194.7333 | 4594.1267 | 0 | 7739 | 59391.38 | 24687.3 | 0 | 0 | 0 | 0 | 107112.66 | 107112.66 |  |  | 2.6 Order in queue: Being processed |  | 0 | 1274.5693 | 160.1884 | 615.975 | 0 | 1037.6359 | 7963.1256 | 3310.0438 | 0 | 0 | 0 | 0 | 14361.5382 | 14361.5382
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 5400 | 17695 | 0 | 7620 | 15284 | 979 | 0 | 0 | 0 | 0 | 46978 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 724.0256 | 2372.5246 | 0 | 1021.6805 | 2049.2606 | 131.2632 | 0 | 0 | 0 | 0 | 6298.7544 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | -1542.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | -206.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75.5454 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 1038 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 2938 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 139.1738 | 0 | 0 | 254.7497 | 0 | 0 | 0 | 0 | 0 | 393.9235 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | -1308.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308.4367 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | -175.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175.4336 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 5936 | 2540 | 0 | 17130.05 | 1600 | 0 | 400 | 0 | 0 | 0 | 27606.05 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 795.8918 | 340.5602 | 0 | 2296.7767 | 214.5261 | 0 | 53.6315 | 0 | 0 | 0 | 3701.3864 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 3245 | 0 | 61662.4 | 0 | 66402.4 | 66402.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 435.0857 | 0 | 8267.6213 | 0 | 8903.1549 | 8903.1549
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42350 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43430 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 5678.2377 | 144.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823.0428 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 400 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 |  |  | Orders without status |  | 0 | 0 | 0 | 53.6315 | 0 | 115.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 168.9393 | 168.9393
| Sum |  | 979 | 51856.12 | 49417.43 | 39055.83 | 0 | 46473.67 | 103390.38 | 39057.71 | 3685 | 0 | 61662.4 | 487.03 | 396064.57 | 396064.57 |  |  | Sum |  | 131.2632 | 6952.8069 | 6625.8303 | 5236.5593 | 0 | 6231.1344 | 13862.4593 | 5236.8113 | 494.0804 | 0 | 8267.6213 | 65.3004 | 53103.8668 | 53103.8668
June orders
Committed RFS | 2025-06-01 | 2025-07-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 79 | 48 | 62 | 24 | 117 | 138 | 18 | 7 | 0 | 75 | 1 | 572 | 589 | 17
| New Sales |  | 3 | 79 | 28 | 57 | 24 | 80 | 130 | 12 | 5 | 0 | 10 | 0 | 428 | 445 | 17
| Change |  | 0 | 0 | 20 | 5 | 0 | 37 | 8 | 6 | 2 | 0 | 65 | 1 | 144 | 144 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 1 | 0 | 9 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 17 | 17 | 0
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 0 | 0 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 0
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 7 | 4 | 3 | 17 | 2 | 3 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10 | 1 | 3 | 4 | 8 | 0 | 0 | 0 | 1 | 27 | 27 | 0
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 6 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0
| 2.6 Order in queue: Being processed |  | 2 | 0 | 18 | 15 | 12 | 46 | 90 | 5 | 0 | 0 | 0 | 0 | 188 | 188 | 0
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 4 | 19 | 2 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 2 | 0 | 0 | 0 | 15 | 15 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 75 | 0 | 78 | 78 | 0
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 79 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
| Sum |  | 3 | 79 | 48 | 62 | 24 | 117 | 138 | 18 | 7 | 0 | 75 | 1 | 572 | 572 | 0
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2095 | 65200 | 33968.0667 | 57038.43 | 19699 | 49826.6667 | 147181.9133 | 25622.26 | 34855 | 0 | 9746 | -528 | 444704.3367 | 488845.8367 | 44141.5 |  | All orders |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2641.2185 | 6680.7002 | 19733.976 | 3435.4022 | 4673.317 | 0 | 1306.7321 | -70.7936 | 59625.4289
| New Sales |  | 2095 | 65200 | 38919.25 | 61232.5 | 19699 | 50145.5 | 150573.98 | 9576 | 7855 | 0 | 9746 | 0 | 415042.23 | 459183.73 | 44141.5 |  | New Sales |  | 280.8951 | 8741.9385 | 5218.2468 | 8209.9808 | 2641.2185 | 6723.449 | 20188.7803 | 1283.9387 | 1053.1891 | 0 | 1306.7321 | 0 | 55648.3689
| Change |  | 0 | 0 | -4951.1833 | -4194.07 | 0 | -318.8333 | -3392.0667 | 16046.26 | 27000 | 0 | 0 | -528 | 29662.1067 | 29662.1067 | 0 |  | Change |  | 0 | 0 | -663.8488 | -562.3359 | 0 | -42.7488 | -454.8043 | 2151.4635 | 3620.1279 | 0 | 0 | -70.7936 | 3977.06
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 1320 | 0 | 18044.53 | 0 | 0 | 3300 | -690.2067 | 0 | 3510 | 0 | 0 | 0 | 25484.3233 | 25484.3233 |  |  | 1.1 Waiting on customer confirmation or input |  | 176.984 | 0 | 2419.3891 | 0 | 0 | 442.4601 | -92.5421 | 0 | 470.6166 | 0 | 0 | 0 | 3416.9078 | 3416.9078
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 1220 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 4554 | 5123 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 163.5762 | 0 | 0 | 447.0188 | 0 | 0 | 0 | 0 | 0 | 610.5949 | 686.8858
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 4900 | 0 | 0 | 16200 | 17000 | 0 | 0 | 0 | 0 | 0 | 38100 | 20185.41 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 656.9862 | 0 | 0 | 2172.0767 | 2279.3398 | 0 | 0 | 0 | 0 | 0 | 5108.4027 | 2706.4358
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 975.75 | 895 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.75 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 130.8274 | 120.0005 | 0 | 175.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 426.203 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 3.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.352 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6396 | 2142.5 | 3402.5 | 982.81 | 2955 | 147.29 | 0 | 0 | 0 | 0 | 16026.1 | 43281.14 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 857.5681 | 287.2639 | 456.2032 | 131.774 | 396.2029 | 19.7485 | 0 | 0 | 0 | 0 | 2148.7604 | 5803.0838
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 10356.4467 | 895 | 3355 | 8376.81 | 18895 | 0 | 0 | 0 | -528 | 41350.2567 | -4054.14 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1388.5801 | 120.0005 | 449.8344 | 1123.1527 | 2533.4191 | 0 | 0 | 0 | -70.7936 | 5544.1933 | -543.5743
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 1210 | 1000 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 1181.44 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 162.2354 | 134.0788 | 541.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 837.9926 | 158.4061
| 2.6 Order in queue: Being processed |  | 775 | 0 | 1125.9267 | 7466.4833 | 10527.5 | 14765.8567 | 75943.06 | 3855 | 0 | 0 | 0 | 0 | 114458.8267 | 107112.66 |  |  | 2.6 Order in queue: Being processed |  | 103.9111 | 0 | 150.9629 | 1001.0972 | 1411.5147 | 1979.7885 | 10182.3552 | 516.8738 | 0 | 0 | 0 | 0 | 15346.5034 | 14361.5382
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -539.14 | 28623 | 2379 | 0 | 14298 | 0 | 0 | 0 | 0 | 0 | 44760.86 | 46978 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | -72.2873 | 3837.7378 | 318.9735 | 0 | 1917.0588 | 0 | 0 | 0 | 0 | 0 | 6001.4829 | 6298.7544
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | -563.44 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 352.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.6273 | -75.5454
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 2724.97 | 0 | 0 | 0 | 0 | 5114.97 | 2938 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 320.4484 | 0 | 0 | 0 | 0 | 365.3607 | 0 | 0 | 0 | 0 | 685.8091 | 393.9235
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2495 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 3715 | -1308.4367 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 334.5266 | 0 | 0 | 163.5762 | 0 | 0 | 0 | 0 | 0 | 498.1028 | -175.4336
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 5025 | 19962.25 | 0 | 27000 | 0 | 0 | 0 | 51987.25 | 27606.05 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 673.746 | 2676.5148 | 0 | 3620.1279 | 0 | 0 | 0 | 6970.3887 | 3701.3864
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345 | 0 | 9746 | 0 | 14091 | 66402.4 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.5724 | 0 | 1306.7321 | 0 | 1889.3045 | 8903.1549
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 65200 | 650 | 0 | 0 | 850 | 4308 | 0 | 0 | 0 | 0 | 0 | 71008 | 43430 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 8741.9385 | 87.1512 | 0 | 0 | 113.967 | 577.6115 | 0 | 0 | 0 | 0 | 0 | 9520.6682 | 5823.0428
| Orders without status |  | 0 | 0 | 0 | 0 | 1495 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 1970 | 1970 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 200.4478 | 0 | 63.6874 | 0 | 0 | 0 | 0 | 0 | 264.1353 | 264.1353
| Sum |  | 2095 | 65200 | 33968.0667 | 57038.43 | 19699 | 49826.6667 | 147181.9133 | 25622.26 | 34855 | 0 | 9746 | -528 | 444704.3367 | 385766.4067 |  |  | Sum |  | 280.8951 | 8741.9385 | 4554.398 | 7647.6449 | 2641.2185 | 6680.7002 | 19733.976 | 3435.4022 | 4673.317 | 0 | 1306.7321 | -70.7936 | 59625.4289 | 51723.1013
July orders
Committed RFS | 2025-07-01 | 2025-08-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 1 | 101 | 19 | 37 | 20 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 277 | 42
| New Sales |  | 1 | 101 | 13 | 35 | 18 | 11 | 34 | 0 | 0 | 0 | 1 | 4 | 218 | 259 | 41
| Change |  | 0 | 0 | 6 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 1
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 17 | 6
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 1 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 41 | 31
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 36 | 31
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27 | 25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 7 | 5 | 17 | 10 | 29 | 0 | 0 | 0 | 0 | 0 | 68 | 188 | 120
| 3.1 Pending external 3rd party: Any 3rd party |  | 1 | 0 | 2 | 16 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 36 | 11
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 2
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 78 | 76
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 84 | -18
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
| Sum |  | 1 | 101 | 19 | 37 | 20 | 11 | 40 | 0 | 0 | 0 | 2 | 4 | 235 | 571 | 336
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 4600 | 84250 | 17355.0433 | 29425.5 | 20885.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 235153.0367 | 26508.96 |  | All orders |  | 616.7625 | 11296.1399 | 2326.9436 | 3945.3361 | 2800.303 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498
| New Sales |  | 4600 | 84250 | 11207 | 29425.5 | 19130.5 | 6195 | 41653.25 | 0 | 0 | 0 | 2047 | 1400 | 199908.25 | 226417.21 | 26508.96 |  | New Sales |  | 616.7625 | 11296.1399 | 1502.6212 | 3945.3361 | 2564.9947 | 830.6182 | 5584.8183 | 0 | 0 | 0 | 274.4593 | 187.7103 | 26803.4606
| Change |  | 0 | 0 | 6148.0433 | 0 | 1755 | 0 | 305.3933 | 0 | 0 | 0 | 527.39 | 0 | 8735.8267 | 8735.8267 | 0 |  | Change |  | 0 | 0 | 824.3223 | 0 | 235.3083 | 0 | 40.9468 | 0 | 0 | 0 | 70.7118 | 0 | 1171.2893
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 7017 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 9262 | 9262 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 940.831 | 0 | 113.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7103 | 1241.838 | 1241.838
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 6000 | 5589 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 12749 | 12749 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 804.4729 | 749.3665 | 0 | 155.5314 | 0 | 0 | 0 | 0 | 0 | 0 | 1709.3708 | 1709.3708
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 400 | 996 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 2395 | 2395 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 53.6315 | 133.5425 | 0 | 133.9447 | 0 | 0 | 0 | 0 | 0 | 321.1188 | 321.1188
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 214.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.5261 | 214.5261
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 593.0433 | 1987.5 | 17319.5 | 5035 | 30088.8933 | 0 | 0 | 0 | 0 | 0 | 55023.9367 | 55023.9367 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 79.5145 | 266.4816 | 2322.178 | 675.0868 | 4034.2831 | 0 | 0 | 0 | 0 | 0 | 7377.544 | 7377.544
| 3.1 Pending external 3rd party: Any 3rd party |  | 4600 | 0 | 1395 | 15819 | 0 | 0 | 9810.75 | 0 | 0 | 0 | 0 | 0 | 31624.75 | 31624.75 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 616.7625 | 0 | 187.0399 | 2120.9927 | 0 | 0 | 1315.4137 | 0 | 0 | 0 | 0 | 0 | 4240.2089 | 4240.2089
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 1700 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 227.934 | 80.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308.3813 | 308.3813
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 289.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.6102 | 289.6102
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 1270 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 170.2801 | 231.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.566 | 401.566
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.39 | 0 | 2574.39 | 2574.39 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.1712 | 0 | 345.1712 | 345.1712
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 84250 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84900 | 84900 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 11296.1399 | 87.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383.2911 | 11383.2911
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 0 | 0 | 0 | 0 | 0 | 142.1235 | 142.1235
| Sum |  | 4600 | 84250 | 17355.0433 | 29425.5 | 20885.5 | 6195 | 41958.6433 | 0 | 0 | 0 | 2574.39 | 1400 | 208644.0767 | 208644.0767 |  |  | Sum |  | 616.7625 | 11296.1399 | 2326.9436 | 3945.3361 | 2800.303 | 830.6182 | 5625.765 | 0 | 0 | 0 | 345.1712 | 187.7103 | 27974.7498 | 27974.7498
August orders
Committed RFS | 2025-08-01 | 2025-09-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 3 | 42 | 43 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 170 | 172 | 2
| New Sales |  | 3 | 42 | 33 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 160 | 162 | 2
| Change |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 17 | -4
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 13
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 7 | 41 | 34
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | -1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 6 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 36 | 24
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 27 | -25
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 12 | 1 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 21 | 188 | 167
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 36 | 34
| 3.1.1 Pending external 3rd party: Open-Net |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 10
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 78 | 76
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 84 | 42
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 3 | 42 | 43 | 9 | 4 | 57 | 7 | 0 | 1 | 0 | 2 | 2 | 170 | 568 | 398
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 2474 | 35665 | 48718.98 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 235153.0367 | 59191.2467 |  | All orders |  | 331.711 | 4781.9208 | 6532.1829 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477
| New Sales |  | 2474 | 35665 | 49399 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 176641.81 | 226417.21 | 49775.4 |  | New Sales |  | 331.711 | 4781.9208 | 6623.3592 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23683.924
| Change |  | 0 | 0 | -680.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680.02 | 8735.8267 | 9415.8467 |  | Change |  | 0 | 0 | -91.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91.1763
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 37168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37168 | 37168 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 0 | 4983.4413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4983.4413 | 4983.4413
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 5100 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5762 | 5762 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 683.8019 | 88.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.5621 | 772.5621
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 2580.06 | 5495 | 9100 | 0 | 0 | 0 | 0 | 9100 | 26275.06 | 26275.06 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 0 | 345.9314 | 736.7631 | 1220.1172 | 0 | 0 | 0 | 0 | 1220.1172 | 3522.9288 | 3522.9288
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 1495 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 200.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.4478 | 200.4478
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 214.98 | 4980 | 0 | 1195 | 0 | 0 | 2550 | 0 | 0 | 0 | 8939.98 | 8939.98 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 28.8243 | 667.7125 | 0 | 160.2242 | 0 | 0 | 341.901 | 0 | 0 | 0 | 1198.6619 | 1198.6619
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 31410 | 0 | 0 | 0 | 0 | 0 | 0 | 31410 | 31410 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 0 | 0 | 0 | 0 | 4211.4155 | 0 | 0 | 0 | 0 | 0 | 0 | 4211.4155 | 4211.4155
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 2800 | 475 | 400 | 1845 | 4410 | 0 | 0 | 0 | 0 | 0 | 9930 | 9930 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 375.4207 | 63.6874 | 53.6315 | 247.3754 | 591.2876 | 0 | 0 | 0 | 0 | 0 | 1331.4026 | 1331.4026
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 845 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3488 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 113.2966 | 354.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.6669 | 467.6669
| 3.1.1 Pending external 3rd party: Open-Net |  | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979 | 979 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 131.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.2632 | 131.2632
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 120.6709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.6709 | 120.6709
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 2536 | 1363.75 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 4849.75 | 4849.75 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 340.0239 | 182.85 | 0 | 0 | 127.3749 | 0 | 0 | 0 | 0 | 0 | 650.2487 | 650.2487
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 9100 | 9100 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220.1172 | 0 | 1220.1172 | 1220.1172
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 35665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35665 | 35665 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 4781.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.9208 | 4781.9208
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 2474 | 35665 | 48718.98 | 8325.75 | 5623.06 | 39945 | 14460 | 0 | 2550 | 0 | 9100 | 9100 | 175961.79 | 175961.79 |  |  | Sum |  | 331.711 | 4781.9208 | 6532.1829 | 1116.3067 | 753.9332 | 5355.7781 | 1938.7796 | 0 | 341.901 | 0 | 1220.1172 | 1220.1172 | 23592.7477 | 23592.7477
September orders
Committed RFS | 2025-09-01 | 2025-10-01
Number of orders
| All orders |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| Total orders mapped | Total | 0 | 3 | 1 | 18 | 3 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 30 | 172 | 142
| New Sales |  | 0 | 3 | 1 | 18 | 3 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 30 | 162 | 132
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Number of orders
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders
| 1.1 Waiting on customer confirmation or input |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 14
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 41 | 35
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 26
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 188 | 184
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 36 | 22
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 78 | 77
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 3 | 1 | 18 | 3 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 30 | 568 | 538
0.13408
| MRC | [17 empty] | MRC
| DKK |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog | Total in backlog (Marked as New sales or Change) | Total unmapped orders |  | EUR |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps in backlog
| All orders | Total | 0 | 26545.4 | 2375 | 70421 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 3428 | 0 | 115044.4 | 235153.0367 | 120108.6367 |  | All orders |  | 0 | 3559.1757 | 318.4372 | 9441.964 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 459.6222 | 0 | 15425.0164
| New Sales |  | 0 | 26545.4 | 2375 | 70421 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 3428 | 0 | 115044.4 | 226417.21 | 111372.81 |  | New Sales |  | 0 | 3559.1757 | 318.4372 | 9441.964 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 459.6222 | 0 | 15425.0164
| Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8735.8267 | 8735.8267 |  | Change |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRC (New sales and change) | [17 empty] | MRC (New sales and change) | EUR
| Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps) |  |  | Delivery status |  | 1.Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold | Total orders mapped to delivery steps and status in backlog | Total in backlog (Marked with delivery steps)
| 1.1 Waiting on customer confirmation or input |  | 0 | 12805 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 15180 |  |  | 1.1 Waiting on customer confirmation or input |  | 0 | 1716.8792 | 318.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035.3164 | 2035.3164
| 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.2 Customer not reachable / unresponsive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 9900 | 9050 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 |  |  | 1.3 Customer requested delay / change of timeline or site not ready |  | 0 | 0 | 0 | 1327.3802 | 1213.4132 | 194.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.2078 | 2735.2078
| 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 1149 |  |  | 2.1 Order forgotten, but back on track to be processed |  | 0 | 0 | 0 | 154.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.0566 | 154.0566
| 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 Pending equipment/product to be ready for installations |  | 0 | 13740.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13740.4 | 13740.4 |  |  | 2.4 Pending equipment/product to be ready for installations |  | 0 | 1842.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.2965 | 1842.2965
| 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.5 Internal or external data/documentation incomplete/ incorrect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 700 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 1775 | 1775 |  |  | 2.6 Order in queue: Being processed |  | 0 | 0 | 0 | 93.8552 | 0 | 0 | 144.1347 | 0 | 0 | 0 | 0 | 0 | 237.9899 | 237.9899
| 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 58672 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59372 | 59372 |  |  | 3.1 Pending external 3rd party: Any 3rd party |  | 0 | 0 | 0 | 7866.672 | 93.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7960.5272 | 7960.5272
| 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.1.1 Pending external 3rd party: Open-Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.1 Pending internal 3rd party: GC Norway |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.2.2 Pending internal 3rd party: GC Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.3 Third party resource constraint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4 Other installation obstacles and infratructure issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3428 | 0 | 3428 | 3428 |  |  | Delivered |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459.6222 | 0 | 459.6222 | 459.6222
| Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Other (incl. termination, on hold, unassigned statuses etc.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Orders without status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sum |  | 0 | 26545.4 | 2375 | 70421 | 9750 | 1450 | 1075 | 0 | 0 | 0 | 3428 | 0 | 115044.4 | 115044.4 |  |  | Sum |  | 0 | 3559.1757 | 318.4372 | 9441.964 | 1307.2684 | 194.4143 | 144.1347 | 0 | 0 | 0 | 459.6222 | 0 | 15425.0164 | 15425.0164