## Export
Focus Enterprise | # | EXPIDITE | Delta MRC | Customer name | SalesProjectID_ContractNumber | ServiceID_Crid | Project ID AX | Delivery Project Manager | Segment Red. | Project Stage | Dateofcreation_ContractApproved | Committed RFS | Customer AgreedRFS/ConfirmedDeliveryDate | DELIVERYCATEGORY
0 | 1 | 0 | 1228.71 | A.P.C. Denmark ApS | 67615 | NKA-032244 |  | Jesper Olsen | SMB Portfolio DK | Closed | 2020-11-06 |  |  | Own OnNet
0 | 1 | 0 | 3000 | A/B Lindegården | 103580 | NKA-059824 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-23 | 2025-05-23 | Own with Digging
0 | 1 | 0 | 600 | Aarhus Motion | 105070 | NBM-060351 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 900 | Aarhus Motion | 105070 | NKA-060348 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 200 | Aarhus Motion | 105070 | NMA-060350 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 200 | Aarhus Motion | 105070 | NSW-060349 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060388 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 1195 | ABCforsikringsagentur A/S | 105230 | NKA-060386 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | -1050.89 | ABCforsikringsagentur A/S | 105465 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-05-28 | 2025-05-28 | Change
0 | 1 | 0 | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NKA-060181 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NML-060182 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 |  | ADVOKATPARTNERSELSKABET KIRK LARSEN & ASCANIUS | 96024 | NCI-054226 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-04-26 |  |  | Own OnNet
0 | 1 | 0 |  | ADVOKATPARTNERSELSKABET KIRK LARSEN & ASCANIUS | 96024 | NSW-054227 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-04-26 |  |  | Own OnNet
0 | 1 | 0 | 1037.5 | Airmaster A/S | 102866 | NKA-059064 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2025-02-25 | 2025-05-09 | 2025-05-09 | Own OnNet
0 | 1 | 0 | 1037.5 | Airmaster A/S | 102866 | NML-059065 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2025-02-25 | 2025-05-09 | 2025-05-09 | 3rd Party
0 | 1 | 0 | 121.38 | ALFABO | 74844 | NKA-036952 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2021-09-07 |  |  | 3rd Party
0 | 1 | 0 | 1350 | Al-Irchad Skolen | 102553 | NBM-059109 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 899 | Al-Irchad Skolen | 102553 | NKA-059110 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own with Digging
0 | 1 | 0 | 200 | Al-Irchad Skolen | 102553 | NMA-059107 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 200 | Al-Irchad Skolen | 102553 | NSW-059108 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 1055 | Andersen-Andersen ApS | 103536 | NKA-059830 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 2500 | Archon DK ApS | 105548 | NBM-060607 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 1395 | Archon DK ApS | 105548 | NKA-060608 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1000.86 | Arka IT ApS | 85429 | NKA-011730 |  | Jesper Olsen | SMB Portfolio DK | Closed | 2023-02-02 |  |  | Change
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057736 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057738 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057739 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own with Digging
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057740 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057741 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057742 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 242.5 | AS3 A/S | 101070 | NKA-057744 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057745 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 242.5 | AS3 A/S | 101070 | NKA-057747 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057749 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057750 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own with Digging
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057751 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own with Digging
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057754 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057755 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057756 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own with Digging
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057758 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 1445 | AS3 A/S | 101070 | NKA-057759 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own with Digging
0 | 1 | 0 | 1145 | AS3 A/S | 101070 | NKA-057762 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057763 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057764 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | Own OnNet
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057765 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057766 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057767 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057768 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057769 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057770 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057771 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057772 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057773 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057774 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 895 | AS3 A/S | 101070 | NKA-057775 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 945 | AS3 A/S | 101070 | NKA-057776 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 242.5 | AS3 A/S | 101070 | NML-057743 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 242.5 | AS3 A/S | 101070 | NML-057746 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-12-06 |  |  | 3rd Party
0 | 1 | 0 | 945 | AS3 A/S | 103392 | NKA-060343 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-04-10 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1345 | Atra Arkitekter A/S | 100639 | NKA-059105 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2025-02-26 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 1345 | Atra Arkitekter A/S | 100639 | NKA-059106 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2025-02-26 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 675 | Bauer Media ApS | 71645 | NKA-035826 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2021-06-29 |  |  | Own OnNet
0 | 1 | 0 | 675 | Bauer Media ApS | 71645 | NKA-035829 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2021-06-29 |  |  | Own OnNet
0 | 1 | 0 | 697.5 | BESS Frederiksværk I ApS | 101183 | NKA-057638 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-12-02 |  |  | 3rd Party
0 | 1 | 0 | 1195 | BESS Frederiksværk I ApS | 101183 | NKA-057640 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-12-02 |  |  | Own OnNet
0 | 1 | 0 | 697.5 | BESS Frederiksværk I ApS | 101183 | NML-057639 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-12-02 |  |  | 3rd Party
0 | 1 | 0 | 697.5 | BESS Frederiksværk I ApS | 101911 | NKA-058435 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 |  |  | 3rd Party
0 | 1 | 0 | 697.5 | BESS Frederiksværk I ApS | 101911 | NML-058436 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 |  |  | 3rd Party
0 | 1 | 0 | 1186 | Best Ejendomme A/S | 105526 | NKA-060558 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 520 | BHS Logistics A/S | 79039 | NSW-041031 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 520 | BHS Logistics A/S | 79039 | NSW-041032 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 665.5 | Bluebyte ApS | 103578 | NKA-059827 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 665.5 | Bluebyte ApS | 103578 | NML-059828 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127937-01 | 105961-007-011 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127938-01 | 105961-007-012 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127948-01 | 105961-007-022 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | 2500 | BONE CONSULT A/S | 105961-007 | C35256-1127950-01 | 105961-007-024 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127952-01 | 105961-007-026 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | 96 | BONE CONSULT A/S | 105961-008 | C35256-1135227-01 | 105961-008-001 | Camilla Villumsen Kaimer | SMB Portfolio DK | In Process | 2025-03-12 | 2025-05-28 |  | Own OnNet
0 | 1 | 0 | -1321.62 | BRUUN & STENGADE A/S | 101934 | NKA-016343 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Change
0 | 1 | 0 | 800 | BRUUN & STENGADE A/S | 101934 | NKA-060091 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 200 | BRUUN & STENGADE A/S | 101934 | NMA-060093 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 200 | BRUUN & STENGADE A/S | 101934 | NMA-060095 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-12 | 2025-05-12 | 3rd Party
0 | 1 | 0 | 200 | BRUUN & STENGADE A/S | 101934 | NSW-060092 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 200 | BRUUN & STENGADE A/S | 101934 | NSW-060094 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-12 | 2025-05-12 | Own OnNet
0 | 1 | 0 | -312.71 | BSC Drift ApS | 104739 | NKA-028998 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Change
0 | 1 | 0 | 230 | BSC Drift ApS | 104739 | NMA-060117 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 230 | BSC Drift ApS | 104739 | NSW-060118 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 895 | Bysted & Partners ApS | 103106 | NKA-060120 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 150 | Bysted & Partners ApS | 103106 | NMA-060122 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 150 | Bysted & Partners ApS | 103106 | NSW-060121 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 1045 | Catering Danmark ApS Århus | 103037 | NKA-059295 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2025-03-06 | 2025-06-06 | 2025-05-09 | 3rd Party
0 | 1 | 0 | 1045 | Catering Danmark ApS Århus | 103037 | NML-059296 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2025-03-06 | 2025-06-06 | 2025-05-09 | 3rd Party
0 | 1 | 0 | 1315 | Copenhagen Bamboo ApS | 101143 | NKA-057576 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-26 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 1388.81 | Copenhagen Coffee Lab Holding ApS | 105359 | NBM-060697 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 860 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060694 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 760 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060698 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060696 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060700 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060695 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060699 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | -3808.24 | CS-Online A/S | 91558 | NKA-029727 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2023-12-28 |  |  | Change
0 | 1 | 0 | 3954.4 | CS-Online A/S | 91558 | NKA-030792 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2023-12-28 |  |  | Change
0 | 1 | 0 | 4476.35 | CS-Online A/S | 91558 | NKA-030793 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2023-12-28 |  |  | Change
0 | 1 | 0 | 7645 | CS-Online A/S | 91558 | NKA-052741 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2023-12-28 | 2024-04-05 | 2024-04-05 | Own with Digging
0 | 1 | 0 | 1095 | Cubenet ApS | 106901-005 | C36018-1124586-01 | 106901-005-003 | Camilla Olesen | SMB Portfolio DK | On Hold | 2023-12-19 | 2026-12-04 |  | Own OnNet
0 | 1 | 0 | 1095 | Danexplore ApS | 103312 | NKA-059888 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-21 | 2025-05-23 | 2025-05-23 | Own with Digging
0 | 1 | 0 | 895 | Dansk Vegetarisk Forening (DVF) | 103541 | NKA-060076 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NMA-060078 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NSW-060077 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056357 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | 3rd Party
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056366 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-05-30 | 2025-01-10 | Own with Digging
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056367 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | Own with Digging
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056370 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | 3rd Party
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056374 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056375 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | Own with Digging
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056381 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 | 2025-05-30 | 2025-01-10 | Own with Digging
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056383 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | Own with Digging
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056391 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 | 2025-03-28 | 2025-03-28 | Own OnNet
0 | 1 | 0 | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056396 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2024-09-23 |  |  | Own with Digging
0 | 1 | 0 | 1700 | DANSKE KONCEPT RESTAURANTER A/S | 98680 | NKA-056601 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-10-03 | 2025-06-06 | 2025-06-06 | Own with Digging
0 | 1 | 0 |  | Danske Shoppingcentre P/S | 100107 | NSW-037789 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-10-17 |  |  | Change
0 | 1 | 0 | 1372 | DEME Offshore DK A/S | 89766 | NKA-049658 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-08-22 |  |  | Own with Digging
0 | 1 | 0 | 1391 | Den selvejende institution Friplejehjemmet Alba Marie | 103605 | NKA-060268 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-06 | 2025-06-06 | Own with Digging
0 | 1 | 0 | -180.9967 | DIS Sølvgade A/S | 103176-004 | C32793-1136828-01 | 103176-004-001 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Change
0 | 1 | 0 | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136829-01 | 103176-004-002 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136830-01 | 103176-004-003 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136831-01 | 103176-004-004 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 3624 | DIS Sølvgade A/S | 103176-004 | C32793-1136833-01 | 103176-004-006 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own with Digging
0 | 1 | 0 | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136834-01 | 103176-004-007 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136835-01 | 103176-004-008 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 981 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 102945 | NKA-059059 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-25 | 2025-06-06 | 2025-06-06 | Own with Digging
0 | 1 | 0 | 981 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 102945 | NML-059058 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-25 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | -621.73 | DTK Road A/S | 77965 | NKA-020934 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2022-02-24 | 2022-08-26 | 2022-07-13 | Change
0 | 1 | 0 | 2105 | Dwarf A/S | 74702 | NBM-039869 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2022-01-13 |  |  | Own OnNet
0 | 1 | 0 | 1350 | E45 ApS | 102578 | NBM-059780 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-14 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 875 | Eagleburgmann Ke A/S | 94292 | NML-054592 |  | Jesper Olsen | SMB Portfolio DK | Closed | 2024-05-30 | 2024-07-19 | 2024-07-19 | 3rd Party
0 | 1 | 0 | 2643 | Ecm Industries A/S | 94182 | NKA-053149 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-02-06 | 2025-08-08 | 2025-08-08 | 3rd Party
0 | 1 | 0 | 1495 | Ejendommen Kronprinsessegade 42 | 90507 | NKA-050156 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2023-09-21 |  |  | Own OnNet
0 | 1 | 0 | 3569 | Ejendomsanpartsselskabet MT 04 | 91727 | NBM-060202 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | -929.74 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | Change
0 | 1 | 0 | -248.28 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | Change
0 | 1 | 0 | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059940 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet
0 | 1 | 0 | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059941 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet
0 | 1 | 0 | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059942 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet
0 | 1 | 0 | 995 | Ejerforeningen Beddingen | 103697 | NKA-059848 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | -1192.82 | Erenfred Pedersen A/S | 80816 | NKA-006114 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-04 |  |  | Change
0 | 1 | 0 | -114.6 | Erenfred Pedersen A/S | 80816 | NKA-006116 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-04 |  |  | Change
0 | 1 | 0 | 495 | Erenfred Pedersen A/S | 80816 | NMA-047473 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-04 |  |  | 3rd Party
0 | 1 | 0 | 495 | Erenfred Pedersen A/S | 80816 | NSW-047472 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-04 |  |  | Own OnNet
0 | 1 | 0 | 350 | Erenfred Pedersen A/S | 80816 | NSW-047474 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-04 |  |  | Own OnNet
0 | 1 | 0 | 1200 | Erenfred Pedersen A/S | 87677 | NKA-006116 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-05-12 |  |  | Change
0 | 1 | 0 | 995 | Erenfred Pedersen A/S | 87677 | NKA-048052 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-05-12 |  |  | Own OnNet
0 | 1 | 0 | 370 | Erenfred Pedersen A/S | 87677 | NSW-047474 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-05-12 |  |  | Change
0 | 1 | 0 | 840 | Erenfred Pedersen A/S | 87677 | NSW-048053 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-05-12 |  |  | Own OnNet
0 | 1 | 0 | 1416 | Eurographic Group A/S | 102676 | NKA-059039 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 612 | Eurographic Group A/S | 102676 | NMA-059041 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 612 | Eurographic Group A/S | 102676 | NSW-059040 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 1195 | Fjelsted Solutions | 101632 | NKA-057941 |  | Camilla Olesen | SMB Portfolio DK | On Hold | 2024-12-17 |  |  | Own with Digging
0 | 1 | 0 | 3870.05 | Flyers ApS | 102767 | NBM-058991 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-19 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 775 | FUEGO ApS | 98741 | NBM-058935 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 1000 | FUEGO ApS | 98741 | NKA-058932 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 100 | FUEGO ApS | 98741 | NMA-058934 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 100 | FUEGO ApS | 98741 | NSW-058933 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 995 | GLADSAXE NY STENHUGGERI ApS | 82863 | NKA-044904 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2022-09-23 |  |  | Own OnNet
0 | 1 | 0 | 150 | GLADSAXE NY STENHUGGERI ApS | 82863 | NMA-044906 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2022-09-23 |  |  | 3rd Party
0 | 1 | 0 | 150 | GLADSAXE NY STENHUGGERI ApS | 82863 | NSW-044905 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2022-09-23 |  |  | Own OnNet
0 | 1 | 0 | 1350 | Globalconnect A/S - Internal IT | 85642 | NKA-046673 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2023-02-03 |  |  | 3rd Party
0 | 1 | 0 |  | GlobalConnect GmbH (Intercompany 2) | 106418-544 | C30981-1128347-01 | 106418-544-001 | Camilla Villumsen Kaimer | SMB Portfolio DK | On Hold | 2024-05-28 | 2024-08-02 |  | Own OnNet
0 | 1 | 0 |  | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136868-01 | 106418-746-001 | Camilla Olesen | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 |  | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136871-01 | 106418-746-004 | Camilla Olesen | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own with Digging
0 | 1 | 0 | 1592.7 | Go Autonomous ApS | 101916 | NBM-060238 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 1592.71 | Go Autonomous ApS | 101916 | NBM-060240 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 1400 | Go Autonomous ApS | 101916 | NKA-060237 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1400 | Go Autonomous ApS | 101916 | NKA-060239 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 100 | H. DAUGAARD A/S | 106840-006 | C35985-1126258-01 | 106840-006-001 | Henrik Møller Fyhn | SMB Portfolio DK | In Process | 2024-03-06 | 2025-06-06 | 2024-12-13 | Change
0 | 1 | 0 | 1495 | H.C. Andersens Flyttefirma A/S | 104913 | NKA-060080 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 230 | H.C. Andersens Flyttefirma A/S | 104913 | NMA-060082 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 230 | H.C. Andersens Flyttefirma A/S | 104913 | NSW-060081 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 1140 | Hoffmann Professional A/S | 105172 | NKA-060438 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party
0 | 1 | 0 | 230 | Hoffmann Professional A/S | 105172 | NMA-060439 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party
0 | 1 | 0 | 230 | Hoffmann Professional A/S | 105172 | NSW-060440 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet
0 | 1 | 0 | 1921 | Håb i Psykiatrien | 97099 | NBM-054930 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-06-24 |  |  | Own OnNet
0 | 1 | 0 | 11418.82 | I/S Ugebladsdistribution | 97628 | NBM-055642 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-07-19 |  |  | 3rd Party
0 | 1 | 0 | 14438.31 | I/S Ugebladsdistribution | 98963 | NBM-056549 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2024-09-30 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 102436 | NKA-058723 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-01-31 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 1629 | Imerco A/S | 102528 | NKA-058919 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-13 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 103032 | NKA-059126 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2025-02-26 | 2025-05-16 | 2025-05-16 | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 103032 | NKA-059128 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-26 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 103032 | NKA-059137 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-26 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 103321 | NKA-060453 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-04-24 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 1269 | Imerco A/S | 87939 | NKA-048153 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-05-25 |  |  | Own OnNet
0 | 1 | 0 | 1269 | Imerco A/S | 87939 | NKA-048158 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-05-25 |  |  | 3rd Party
0 | 1 | 0 | 1269 | Imerco A/S | 87939 | NKA-048165 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-05-25 |  |  | Own with Digging
0 | 1 | 0 | 1269 | Imerco A/S | 87939 | NKA-048168 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-05-25 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052404 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052406 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052407 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052413 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own OnNet
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052415 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052418 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052419 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052423 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 | 2024-12-27 | 2024-12-27 | Own OnNet
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052425 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052427 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052428 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-07-18 | 2025-07-18 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052430 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052431 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052432 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052433 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052435 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052436 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052440 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052441 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 |  |  | Own OnNet
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052442 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052447 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052449 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052450 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052451 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052452 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-23 | 2025-05-23 | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052453 |  | Nanna Søndergaard Skov | SMB Portfolio DK | On Hold | 2023-12-21 |  |  | Own with Digging
0 | 1 | 0 | 979 | Imerco A/S | 93095 | NKA-052454 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 795 | Immudex ApS | 102843 | NDD-059971 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet
0 | 1 | 0 | 795 | Immudex ApS | 102843 | NDD-059972 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet
0 | 1 | 0 | 1185 | Inco Svendborg Slagtehus A/S | 105563 | NKA-060611 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 695 | India Royale ApS | 104999 | NKA-060320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 150 | India Royale ApS | 104999 | NMA-060322 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 150 | India Royale ApS | 104999 | NSW-060321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 2440 | Intech | 103238 | NBM-060096 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | -2416.06 | Intech | 103238 | NOC-997264 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | Change
0 | 1 | 0 | 995 | i-team Danmark ApS | 105696 | NKA-060722 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 150 | i-team Danmark ApS | 105696 | NMA-060723 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 150 | i-team Danmark ApS | 105696 | NSW-060724 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | -19.59 | KARBERGHUS A/S | 103325 | NKA-026156 |  | Peter Madsen | SMB Portfolio DK | On Hold | 2025-03-24 |  |  | Change
0 | 1 | 0 | 359 | KIRAN ApS | 101323 | NDD-057700 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-05 | 2025-01-14 | 2025-01-14 | Own OnNet
0 | 1 | 0 | -195 | KIRAN ApS | 101323 | NKA-055961 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-05 | 2025-01-14 | 2025-01-14 | Change
0 | 1 | 0 | 200 | KIRAN ApS | 101323 | NMA-055959 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-05 | 2025-01-14 | 2025-01-14 | Change
0 | 1 | 0 | -100 | KIRAN ApS | 101323 | NSW-055960 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-05 | 2025-01-14 | 2025-01-14 | Change
0 | 1 | 0 | 1076 | KIROPRAKTISK KLINIK FREDERICIA APS | 89486 | NKA-049745 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-08-24 |  |  | 3rd Party
0 | 1 | 0 | 895 | Knowledge Gate Group ApS | 103191 | NKA-059677 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-10 | 2025-05-02 | 2025-05-02 | Own OnNet
0 | 1 | 0 | 200 | Knowledge Gate Group ApS | 103191 | NMA-059678 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-10 | 2025-05-02 | 2025-05-02 | 3rd Party
0 | 1 | 0 | 200 | Knowledge Gate Group ApS | 103191 | NSW-059679 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-10 | 2025-05-02 | 2025-05-02 | Own OnNet
0 | 1 | 0 | 785 | Knowledge Gate Group ApS | 104359 | NBM-060029 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-28 |  |  | 3rd Party
0 | 1 | 0 |  | Knowledge Gate Group ApS | 104359 | NSW-059679 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-28 |  |  | Change
0 | 1 | 0 | 1395 | Kontorfællesskabet Wilders Plads ApS | 105521 | NKA-060646 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-08 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 420 | Kuehne & Nagel AB, Stockholm | 91817 | NMA-053349 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-02-16 |  |  | 3rd Party
0 | 1 | 0 | 420 | Kuehne & Nagel AB, Stockholm | 91817 | NSW-053348 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-02-16 |  |  | Own OnNet
0 | 1 | 0 | 400 | Labelless Media ApS | 101484 | NBM-058251 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 200 | Labelless Media ApS | 101484 | NMA-058253 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 200 | Labelless Media ApS | 101484 | NSW-058252 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 0 | Labelless Media ApS | 102390 | NKA-058250 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-30 | 2025-05-16 | 2025-05-16 | Change
0 | 1 | 0 | 1395 | LaundryHouse ApS | 100684 | NKA-058086 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own with Digging
0 | 1 | 0 | 200 | LaundryHouse ApS | 100684 | NMA-058088 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 200 | LaundryHouse ApS | 100684 | NSW-058087 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 1487.98 | LE-Fix Clothing ApS | 105193 | NBM-060392 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-15 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 1595 | Legendary Gaming Group ApS | 105322 | NKA-060450 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-23 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 775 | Levitate Technology ApS | 100599 | NBM-057009 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-10-31 |  |  | 3rd Party
0 | 1 | 0 |  | Levitate Technology ApS | 100599 | NSW-053038 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-10-31 |  |  | Change
0 | 1 | 0 | 895 | Limitless Reality ApS | 103229 | NKA-059986 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-16 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 829.13 | Lise Frandsen ApS | 105407 | NBM-060606 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 83.12 | Lise Frandsen ApS | 105407 | NKA-025349 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | 2120 | Lokal Forsikring G/S | 91200 | NKA-052835 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 2120 | Lokal Forsikring G/S | 91200 | NKA-052836 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own with Digging
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052837 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052838 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052839 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052840 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052841 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052842 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052843 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party
0 | 1 | 0 | 970 | Lokal Forsikring G/S | 91200 | NKA-052844 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 825 | Lokal Forsikring G/S | 91200 | NSW-052845 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 825 | Lokal Forsikring G/S | 91200 | NSW-052846 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052847 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052848 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052849 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052850 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052851 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052852 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052853 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 530 | Lokal Forsikring G/S | 91200 | NSW-052854 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052845 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052847 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052848 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052849 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052850 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052851 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052852 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052853 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 390 | Lokal Forsikring G/S | 98237 | NSW-052854 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change
0 | 1 | 0 | 1890 | Lokal Forsikring G/S | 98938 | NDD-056457 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-09-25 |  |  | Own OnNet
0 | 1 | 0 | 662 | Lomax A/S | 102189 | NBM-059710 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet
0 | 1 | 0 | 950 | Lomax A/S | 102189 | NBM-059711 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet
0 | 1 | 0 | 950 | Lomax A/S | 102189 | NBM-059712 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet
0 | 1 | 0 | 2580.06 | Lomax A/S | 102189 | NBM-059713 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet
0 | 1 | 0 | 2747.5 | Lomax A/S | 102189 | NKA-059706 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 2747.5 | Lomax A/S | 102189 | NKA-059707 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 1250 | Lomax A/S | 102189 | NKA-059708 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own with Digging
0 | 1 | 0 | 2550 | Lomax A/S | 102189 | NKA-059709 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | 3rd Party
0 | 1 | 0 | 2495 | Lowenco A/S | 94213 | NKA-053561 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-03-04 |  |  | 3rd Party
0 | 1 | 0 | 2495 | Lowenco A/S | 94213 | NKA-053562 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-03-04 |  |  | 3rd Party
0 | 1 | 0 | 1245 | LUTHERSK MISSIONSFORENING | 102804 | NKA-059162 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own with Digging
0 | 1 | 0 | 225 | LUTHERSK MISSIONSFORENING | 102804 | NMA-059163 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 225 | LUTHERSK MISSIONSFORENING | 102804 | NSW-059164 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 600 | Macarons Design I/S | 103494 | NBM-059950 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 995 | Macarons Design I/S | 103494 | NKA-059947 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own with Digging
0 | 1 | 0 | 200 | Macarons Design I/S | 103494 | NMA-059948 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 200 | Macarons Design I/S | 103494 | NSW-059949 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 895 | Mano Event ApS | 100141 | NKA-059654 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-06 | 2025-06-06 | Own with Digging
0 | 1 | 0 | 150 | Mano Event ApS | 100141 | NMA-059656 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 150 | Mano Event ApS | 100141 | NSW-059655 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 901 | Mello Media | 78064 | NKA-042043 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2022-04-21 |  |  | Own OnNet
0 | 1 | 0 | 600 | MIB VVS ApS | 101110 | NBM-057554 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-11-25 |  |  | Own OnNet
0 | 1 | 0 | 1595 | MIB VVS ApS | 101110 | NKA-057551 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-11-25 |  |  | Own with Digging
0 | 1 | 0 | 200 | MIB VVS ApS | 101110 | NMA-057553 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-11-25 |  |  | 3rd Party
0 | 1 | 0 | 200 | MIB VVS ApS | 101110 | NSW-057552 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-11-25 |  |  | Own OnNet
0 | 1 | 0 | 2462.08 | Møbelkompagniet ApS | 104652 | NBM-060044 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2025-03-28 |  |  | 3rd Party
0 | 1 | 0 | 895 | Møbelkompagniet ApS | 104652 | NKA-060045 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 577.5 | Møbelkompagniet ApS | 104652 | NKA-060048 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 180 | Møbelkompagniet ApS | 104652 | NMA-060047 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 |  |  | 3rd Party
0 | 1 | 0 | 577.5 | Møbelkompagniet ApS | 104652 | NML-060049 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 180 | Møbelkompagniet ApS | 104652 | NSW-060046 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Own OnNet
0 | 1 | 0 |  | NE Venture Management ApS | 98287 | NKA-043839 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-08-28 | 2025-02-28 | 2025-02-28 | Change
0 | 1 | 0 | 1608 | Netmark A/S | 89762 | NKA-049655 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-08-22 |  |  | 3rd Party
0 | 1 | 0 | 600 | NGZC ApS | 104487 | NBM-060015 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-27 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 1600 | NGZC ApS | 104487 | NKA-060012 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-27 |  |  | Own with Digging
0 | 1 | 0 | 200 | NGZC ApS | 104487 | NMA-060014 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-27 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 200 | NGZC ApS | 104487 | NSW-060013 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-27 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 600 | NGZC ApS | 105044 | NBM-060260 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 1600 | NGZC ApS | 105044 | NKA-060257 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 | 200 | NGZC ApS | 105044 | NMA-060259 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 200 | NGZC ApS | 105044 | NSW-060258 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | Own OnNet
0 | 1 | 0 |  | Nobia Denmark Retail A/S | 100506 | NKA-012876 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-12-05 |  |  | Change
0 | 1 | 0 | 4400 | Nordomatic Invest AB | 91915 | NKA-051373 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2023-12-05 |  |  | 3rd Party
0 | 1 | 0 | 1095 | Norrlyst ApS | 104558 | NKA-059937 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 180 | Norrlyst ApS | 104558 | NMA-059939 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 180 | Norrlyst ApS | 104558 | NSW-059938 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1149 | NOVARAM ApS | 100681 | NKA-059024 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-09-02 | 2025-05-02 | 3rd Party
0 | 1 | 0 | 923 | NOVATARIS A/S | 102780 | NBM-059695 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | On Hold | 2025-03-11 |  |  | 3rd Party
0 | 1 | 0 | -26.46 | NOVATARIS A/S | 102780 | NKA-014930 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | On Hold | 2025-03-11 | 2025-05-09 | 2025-05-09 | Change
0 | 1 | 0 | 250 | NOVATARIS A/S | 102780 | NML-059696 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | On Hold | 2025-03-11 | 2025-05-09 | 2025-05-09 | 3rd Party
0 | 1 | 0 | 350 | Ok A.M.B.A. | 102967 | NBM-060644 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | 3rd Party
0 | 1 | 0 | 1050 | Ok A.M.B.A. | 102967 | NKA-060641 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 0 | Ok A.M.B.A. | 102967 | NMA-060643 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | 3rd Party
0 | 1 | 0 | 0 | Ok A.M.B.A. | 102967 | NSW-060642 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 1095 | Optinor ApS | 103352 | NKA-060551 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | Own with Digging
0 | 1 | 0 | 200 | Optinor ApS | 103352 | NMA-060553 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | 3rd Party
0 | 1 | 0 | 200 | Optinor ApS | 103352 | NSW-060552 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | Own OnNet
0 | 1 | 0 | 525 | Otari ApS | 101249 | NBM-057645 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2024-12-03 |  |  | Own OnNet
0 | 1 | 0 | 350 | Otari ApS | 103573 | NBM-059847 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2025-03-19 |  |  | Own OnNet
0 | 1 | 0 |  | Otari ApS | 103659 | NSW-057643 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2025-03-19 |  |  | Change
0 | 1 | 0 | 2968 | Perspektiva IT ApS | 100657 | NKA-059019 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-02-20 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2968 | Perspektiva IT ApS | 100657 | NKA-059020 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-02-20 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1095 | Psykologhuset Trekanten ApS | 104667 | NKA-059980 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 1410 | Radiant ApS | 105341 | NBM-060525 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 1195 | Radiant ApS | 105341 | NKA-060526 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet
0 | 1 | 0 | 1695 | Raw Power Games ApS | 97083 | NKA-055484 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-07-01 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 700 | salting & dyrby ApS | 104811 | NKA-060426 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | Own with Digging
0 | 1 | 0 | 700 | salting & dyrby ApS | 104811 | NML-060427 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 1500 | Senia Systems ApS | 60851 | NSF-029770 |  | Peter Madsen | SMB Portfolio DK | Closed | 2020-01-30 |  |  | Own OnNet
0 | 1 | 0 | 1007.9 | Skanska A/S | 102800 | NBM-059148 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2025-02-27 |  |  | 3rd Party
0 | 1 | 0 | 1900 | Skanska A/S | 102800 | NKA-059147 |  | Kristijan Krsteski | SMB Portfolio DK | On Hold | 2025-02-27 | 2025-04-25 | 2025-04-25 | Own OnNet
0 | 1 | 0 | 1944 | Skousen NO | 100710 | NKA-057251 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-08 | 2025-05-28 | 2025-04-25 | 3rd Party
0 | 1 | 0 | 1195 | Spjald Entreprenørforretning A/S | 98762 | NKA-056313 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-09-19 | 2025-01-31 | 2025-01-31 | 3rd Party
0 | 1 | 0 | 1500 | SquareOne ApS | 73221 | NKA-035914 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2021-07-01 |  |  | Own OnNet
0 | 1 | 0 | 1355 | Stavnskær Fragt A/S | 105016 | NKA-060603 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-07-25 | 2025-07-25 | Own OnNet
0 | 1 | 0 | 579 | Steelcom ApS | 91369 | NKA-050803 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-10-27 |  |  | 3rd Party
0 | 1 | 0 | 4051 | STRATU ApS | 106547-008 | F35739-1136632-01 | 106547-008-001 | Cecilie Heidner Nielsen | SMB Portfolio DK | Created | 2025-04-30 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 0 | SYGEFORSIKRINGEN "DANMARK" GS | 101102 | NKA-057300 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-05 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 101558 | NKA-057969 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 101558 | NML-057970 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | -23427 | SYGEFORSIKRINGEN "DANMARK" GS | 101606 | NBM-057308 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-19 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 |  | SYGEFORSIKRINGEN "DANMARK" GS | 102563 | NKA-057295 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-02-10 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057301 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057302 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2577.88 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057303 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2411.24 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057304 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057305 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2411.24 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057306 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 3325.92 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057307 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 24779 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057308 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057285 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057287 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057289 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057291 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057293 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057295 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057297 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2024-11-11 |  |  | Own with Digging
0 | 1 | 0 | 1945 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057299 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 1945 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057300 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057286 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057288 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057290 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057292 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057294 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057296 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057298 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2024-11-11 |  |  | 3rd Party
0 | 1 | 0 | 695 | Taconic Biosciences A/S | 104948 | NCI-060727 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 1700 | Taconic Biosciences A/S | 104948 | NKA-060725 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 1700 | Taconic Biosciences A/S | 104948 | NML-060726 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party
0 | 1 | 0 | 1495 | Ticra Fond | 92237 | NKA-053560 |  | Andrew David Lindsey | SMB Portfolio DK | On Hold | 2024-03-04 |  |  | Own OnNet
0 | 1 | 0 | 1595 | Trescal A/S | 95792 | NKA-056532 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-09-30 | 2026-04-25 | 2026-04-25 | 3rd Party
0 | 1 | 0 | 1595 | Trescal A/S | 95792 | NKA-056533 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-09-30 | 2026-04-25 | 2026-04-25 | 3rd Party
0 | 1 | 0 | 1095 | Trescal A/S | 95792 | NKA-056535 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-09-30 |  |  | Own OnNet
0 | 1 | 0 | 995 | Triangelhus A/S | 101581 | NKA-057886 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 995 | Triangelhus A/S | 101581 | NKA-057889 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 995 | Triangelhus A/S | 101581 | NKA-057892 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 995 | Triangelhus A/S | 101581 | NKA-057895 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NMA-057888 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | 3rd Party
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NMA-057891 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | 3rd Party
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NMA-057894 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | 3rd Party
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NMA-057897 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | 3rd Party
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NSW-057887 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NSW-057890 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NSW-057893 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 150 | Triangelhus A/S | 101581 | NSW-057896 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-12-13 | 2025-03-17 | 2025-03-17 | Own OnNet
0 | 1 | 0 | 1242 | Vækst+ ApS | 104703 | NKA-059996 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2214.4 | Vejen Idrætscenter | 87155 | NKA-047535 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | Closed | 2023-04-05 |  |  | 3rd Party
0 | 1 | 0 | 2858.5 | Vendia Net ApS | 106295-004 | C35525-1120945-01 | 106295-004-001 | Mette Vinther | SMB Portfolio DK | On Hold | 2023-06-27 | 2024-01-16 |  | Own OnNet
0 | 1 | 0 | 2858.5 | Vendia Net ApS | 106295-004 | C35525-1120947-01 | 106295-004-003 | Mette Vinther | SMB Portfolio DK | On Hold | 2023-06-27 | 2024-01-16 |  | Own OnNet
0 | 1 | 0 | 2858.5 | Vendia Net ApS | 106295-004 | C35525-1120949-01 | 106295-004-005 | Mette Vinther | SMB Portfolio DK | On Hold | 2023-06-27 | 2024-01-16 |  | Own OnNet
0 | 1 | 0 | 895 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NKA-059149 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 |  |  | Own OnNet
0 | 1 | 0 | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NMA-059151 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | 3rd Party
0 | 1 | 0 | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NSW-059150 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | Own OnNet
0 | 1 | 0 | 1672 | Vica Ejendomme ApS | 89539 | NKA-049723 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-08-23 |  |  | Own OnNet
0 | 1 | 0 | 1945 | Vingmed Holding AS | 84885 | NKA-047774 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-18 |  |  | 3rd Party
0 | 1 | 0 | 1130 | Vingmed Holding AS | 84885 | NMA-047780 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-18 |  |  | 3rd Party
0 | 1 | 0 | 1130 | Vingmed Holding AS | 84885 | NSW-047779 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | On Hold | 2023-04-18 |  |  | Own OnNet
0 | 1 | 0 | 150 | WIP Denmark ApS | 103673 | NMA-059844 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-19 |  |  | 3rd Party
0 | 1 | 0 | 150 | WIP Denmark ApS | 103673 | NSW-059843 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2025-03-19 |  |  | Own OnNet
0 | 1 | 0 | 1095 | WOBA ApS | 104677 | NKA-059976 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 180 | WOBA ApS | 104677 | NMA-059977 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | 3rd Party
0 | 1 | 0 | 180 | WOBA ApS | 104677 | NSW-059978 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet
0 | 1 | 0 | -312.19 | Voldgiftsinstituttet | 105411 | NKA-030523 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Change
0 | 1 | 0 | 200 | Voldgiftsinstituttet | 105411 | NMA-060616 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 200 | Voldgiftsinstituttet | 105411 | NSW-060617 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 995 | Wolt Services Danmark ApS | 105303 | NKA-060446 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-23 |  |  | Own OnNet
0 | 1 | 0 | 775 | Vuffeli ApS | 98194 | NBM-056873 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-10-22 |  |  | 3rd Party
0 | 1 | 0 | 995 | Vuffeli ApS | 98194 | NKA-056870 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-10-22 |  |  | Own OnNet
0 | 1 | 0 | 200 | Vuffeli ApS | 98194 | NMA-056872 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-10-22 |  |  | 3rd Party
0 | 1 | 0 | 200 | Vuffeli ApS | 98194 | NSW-056871 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | On Hold | 2024-10-22 |  |  | Own OnNet
0 | 1 | 0 | 995 | ZRM ApS | 95570 | NKA-053984 |  | Jesper Olsen | SMB Portfolio DK | On Hold | 2024-04-05 | 2024-06-07 | 2024-06-07 | Own OnNet
Total | 443 | 0 | 412120.1433
Applied filters: Actual RFS is (Blank) Delivery Project Manager is not (Blank) #Booked is not blank Department is Enterprise Delivery DK, GCC Delivery DK, or Nordic SmartConnect Project Coordination Std. Delivery is STD. Delivery Segment Red. is SMB Portfolio DK Project Stage is not (Blank), Cancelled, Terminated, or Finished Customer name is not GlobalConnect A/S