## Sheet1
Latest backlog update: | Unnamed: 1 | Input: Which delivery step is the order in? (Drop down list) | Input: What is the status of the order? (Drop down list) | (Optional) Input: Comment | Delta MRC | Customer name | SalesProjectID_ContractNumber | ServiceID_Crid | Project ID AX | Delivery Project Manager | Segment Red. | Project Stage | Dateofcreation_ContractApproved | Committed RFS | Customer AgreedRFS/ConfirmedDeliveryDate | DELIVERYCATEGORY | Date signed | Planning complete date | Design complete date | Correct RFS | Actual RFS | Expected RFS | Deliveryconfirmationdate_Configsignoffdate | Customer Agreed RFS | CUSTOMERCONFIRMEDDELIVERYDATE | CUSTOMERDEFERREDDELIVERYDATE | ReadyForBilling | ProjectTypeValue | SOURCE
[5 empty] | 4800 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 101164-043 | C31128-1133697-01 | 101164-043-007 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-30 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-02-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 1024 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 101164-043 | C31128-1133698-01 | 101164-043-008 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-30 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-02-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 4800 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 101164-043 | C31128-1133700-01 | 101164-043-010 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-30 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-02-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 1024 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 101164-043 | C31128-1133701-01 | 101164-043-011 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-30 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-02-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 1125 | A.P. MØLLER - MÆRSK A/S ( Maersk A/S - IT ) | 101164-043 | F31128-1133702-01 | 101164-043-012 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-30 | 2025-07-04 |  | 3rd Party | [5 empty] | 2025-02-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design (var i tvivl om kolonne D er sat rigtig) | 947.5 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 102301 | NKA-059687 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-10 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-14 |  |  |  |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design (var i tvivl om kolonne D er sat rigtig) | 947.5 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 102301 | NML-059688 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-10 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-14 |  |  |  |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 560 | Aabenraa Kommune | 103678 | NKA-060363 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-25 | 2025-06-25 | 3rd Party | 2025-04-25 |  |  | 2025-06-20 |  | 2025-06-10 | 2025-05-14 | 2025-06-25 | 2025-06-25 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Follows projektID 103678 | 30 | Aabenraa Kommune | 103680 | NKA-060363 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-25 | 2025-06-25 | Change | 2025-04-25 |  |  |  |  | 2025-06-10 |  | 2025-06-25 | 2025-06-25 |  |  | Change | BO
|  |  | Other (incl. termination, on hold etc.) | Pending termination | 560 | Aabenraa Kommune | 95083 | NKA-053695 |  | Kristijan Krsteski | Public DK | RFS | 2024-03-14 |  |  | 3rd Party
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Fejl og mangler i Dok. | 753.22 | Aalborg Handelsskole | 100625-014 | F30344-1133574-01 | 100625-014-001 | Michael Kronbach Leth | Public DK | In Process | 2024-12-19 | 2025-05-30 | 2025-03-14 | Own with Digging |  |  |  | 2025-03-07 |  | 2025-03-13 |  | 2025-03-14 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Fejl og mangler i Dok. | 753.22 | Aalborg Handelsskole | 100625-014 | F30344-1133576-01 | 100625-014-003 | Michael Kronbach Leth | Public DK | In Process | 2024-12-19 | 2025-05-30 | 2025-03-14 | Own with Digging |  |  |  | 2025-03-07 |  | 2025-03-13 |  | 2025-03-14 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Ordering issues | 845 | Aarhus Business College | 101953 | NKA-058344 |  | Morten Skytte | Public DK | In Process | 2025-01-13 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-21 |  |  | 2025-06-06 |  | 2025-05-30 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Waiting for date from 3. part | 845 | Aarhus Business College | 102560 | NKA-058767 |  | Morten Skytte | Public DK | In Process | 2025-02-04 | 2025-06-29 | 2025-06-29 | 3rd Party | [7 empty] | 2025-06-29 | 2025-06-29 |  |  | New Sales | BO
[5 empty] | 7625 | Aarhus Business College | 105408 | NKA-006093 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | 2017-10-18 | 2017-10-18 14:06:00.000 | 2017-10-18 14:06:00.000 | [8 empty] | Change | BO
[5 empty] | 6000 | Aarhus Business College | 105408 | NKA-010029 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 7000 | Aarhus Business College | 105408 | NKA-053439 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | 2024-03-27 | 2024-04-15 12:08:00.000 | 2024-04-09 11:18:00.000 | [8 empty] | Change | BO
[5 empty] | 1210 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060636 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-05-09 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 1210 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060637 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-05-09 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 860 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060638 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-05-09 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060126 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060127 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060128 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060129 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060130 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060131 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party |  |  | 2025-04-02 08:21:00.000 | [8 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060132 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060133 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party |  |  | 2025-04-02 08:22:00.000 | [8 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060134 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060135 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060136 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060137 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060138 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060139 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060140 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060141 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1725 | Abc Lavpris Hovedkontor | 102649 | NKA-060172 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 1725 | Abc Lavpris Hovedkontor | 102649 | NKA-060173 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060124 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060142 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060144 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060146 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060148 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060150 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060152 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060154 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060156 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060158 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060160 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060162 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060164 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060166 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060168 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060170 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060125 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060143 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060145 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060147 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060149 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060151 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060153 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060155 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060157 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060159 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060161 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060163 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060165 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060167 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060169 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060171 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 700 | Abc Lavpris Hovedkontor | 102649 | NSW-060174 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | UnitIT is the legal owner of the infrastructure that the company ABC lavpris uses today. So in other words UnitIT buys the fiberline from GC and sells it to the end user ABC Lavpris. The account manager is working on a deal that insures that ABC kan get direct ownership and is in dialouge wtih both UnitIT and ABC. Therefore I am awaiting sales, before I can move on. | 700 | Abc Lavpris Hovedkontor | 102649 | NSW-060175 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Delivery is in Germany. Deliveries abroad can take much longer than domestec deliveries. | 4282 | ABENA A/S | 103420 | NKA-059887 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-21 | 2025-10-03 | 2025-10-03 | Own with Digging | 2025-03-26 |  |  |  |  | 2025-07-07 |  | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting for pricing to make an offer to GC SE | 2299 | ALD AUTOMOTIVE A/S | 104678 | NKA-059289 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 |  |  | Change | 2025-03-07 | [10 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed |  | 6500 | Amgros I/S | 104799-016 | C34301-1134736-01 | 104799-016-001 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 | 2025-05-28 | Own OnNet |  |  |  | 2025-05-19 |  | 2025-04-09 | 2025-05-09 | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed |  | 176 | Amgros I/S | 104799-016 | C34301-1134737-01 | 104799-016-002 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 | 2025-05-28 | Own OnNet |  |  |  | 2025-05-21 |  | 2025-04-09 | 2025-05-09 | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed |  | 1408 | Amgros I/S | 104799-016 | C34301-1134738-01 | 104799-016-003 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 | 2025-05-28 | Own OnNet |  |  |  | 2025-05-21 |  | 2025-04-09 | 2025-05-09 | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 13740.4 | Ap Pension Livsforsikringsaktieselskab | 97681 | NBM-057059 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-11-04 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Fiber ordered at 3rd party -awaiting delivery date | 1505 | Associated Danish Ports A/S | 102713 | NKA-060419 |  | Kristijan Krsteski | Public DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-04-29 |  | 2025-04-22 11:47:00.000 | 2025-05-09 | [7 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Fiber ordered at 3rd party -awaiting delivery date | 387.5 | Associated Danish Ports A/S | 102713 | NMA-060420 |  | Kristijan Krsteski | Public DK | In Process | 2025-04-22 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Fiber ordered at 3rd party -awaiting delivery date | 387.5 | Associated Danish Ports A/S | 102713 | NSW-060421 |  | Kristijan Krsteski | Public DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 7. Service activation | 1.2 Customer not reachable / unresponsive | Implementing and testing with the customer have been hard to kodinate due to the status on the ordre. | 0 | Associated Danish Ports A/S | 93020 | NSW-055598 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2024-07-16 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 5050 | B4restore A/S | 100991-073 | C30955-1136310-01 | 100991-073-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-04-16 |  |  | Own OnNet | [5 empty] | 2025-07-17 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Waiting for customer get back about dates for SW after freeze period | 1725 | Banedanmark | 103135 | NKA-020463 |  | Morten Skytte | Public DK | In Process | 2025-03-17 | 2025-05-28 | 2025-05-28 | Change | 2017-05-16 | 2017-07-25 08:42:00.000 | 2017-07-28 15:22:00.000 |  |  | 2017-08-11 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Shift in vendor after site survey | 945 | Banedanmark | 103381 | NKA-059935 |  | Morten Skytte | Public DK | In Process | 2025-03-25 | 2025-07-27 | 2025-07-27 | 3rd Party | [7 empty] | 2025-07-27 | 2025-07-27 |  |  | New Sales | BO
[5 empty] | 1050 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 101218 | NKA-030336 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-01-23 |  |  | Change
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | FPM - Ny fiber. | 525 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 101218 | NKA-058586 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-01-23 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-01-30 | 2025-04-04 13:07:00.000 | 2025-04-22 14:00:00.000 | 2025-05-16 |  | 2025-04-04 | 2025-05-02 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 0 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 101218 | NML-030337 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-01-23 |  |  | Change
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | FPM - Ny fiber. | 525 | BDO STATSAUTORISERET REVISIONSAKTIESELSKAB | 101218 | NML-058587 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-01-23 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-30 |  |  | 2025-05-16 |  |  | 2025-05-02 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track; awaiting input from Fibia | 1250 | BELFOR Denmark A/S | 104945 | NKA-060415 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-25 |  |  | 2025-06-06 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track; awaiting input from Fibia | 375 | BELFOR Denmark A/S | 104945 | NSW-060416 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-06-06 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track; awaiting input from Fibia | 1250 | BELFOR Denmark A/S | 105008 | NKA-060417 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-04-23 | [6 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track; awaiting input from Fibia | 375 | BELFOR Denmark A/S | 105008 | NSW-060418 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-07-11 | 2025-07-11 | Own OnNet | [7 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
[5 empty] | 784.5 | Better Energy Management A/S | 105316 | NKA-060469 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-25 |  |  | Own OnNet | 2025-04-25 | 2025-05-01 12:07:00.000 | 2025-05-05 10:13:00.000 | 2025-05-23 |  | 2025-06-13 | 2025-05-12 |  |  |  |  | New Sales | BO
[5 empty] | 784.5 | Better Energy Management A/S | 105316 | NML-060470 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-25 |  |  | 3rd Party | 2025-04-25 |  |  | 2025-05-23 |  | 2025-06-13 | 2025-05-12 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Ordre skal først levers 3/10-2025 | 725 | Billigblomst Adm. A/S | 91356 | NKA-053364 |  | Merete Helme | Enterprise DK | In Process | 2024-02-19 | 2025-10-03 | 2025-10-03 | 3rd Party | [7 empty] | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 725 | Billigblomst Adm. A/S | 91356 | NKA-053382 |  | Merete Helme | Enterprise DK | In Process | 2024-02-19 | 2025-06-06 | 2025-06-06 | 3rd Party |  |  |  | 2025-05-30 |  | 2025-06-06 | 2025-04-09 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Ordre skal først leveres 3/10-2025 | 725 | Billigblomst Adm. A/S | 91356 | NML-053365 |  | Merete Helme | Enterprise DK | In Process | 2024-02-19 | 2025-10-03 | 2025-10-03 | 3rd Party | [7 empty] | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 725 | Billigblomst Adm. A/S | 91356 | NML-053383 |  | Merete Helme | Enterprise DK | In Process | 2024-02-19 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-01 |  |  | 2025-05-30 |  |  | 2025-04-09 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, SW 13/5 | 1000 | Billund Kommune | 102199 | NKA-009209 |  | Eva Eisner | Public DK | In Process | 2025-02-18 | 2025-05-16 | 2025-05-16 | Change |  | 2023-03-14 08:52:00.000 | 2023-03-14 08:52:00.000 | 2025-05-13 |  |  | 2025-05-13 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, SW 13/5 | 450 | Billund Kommune | 102199 | NKA-009222 |  | Eva Eisner | Public DK | In Process | 2025-02-18 | 2025-05-16 | 2025-05-16 | Change |  | 2023-03-14 09:28:00.000 | 2023-03-14 09:28:00.000 | 2025-05-13 |  |  | 2025-05-12 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, SW 14/5 | 450 | Billund Kommune | 102199 | NKA-031743 |  | Eva Eisner | Public DK | In Process | 2025-02-18 | 2025-05-16 | 2025-05-16 | Change |  | 2023-03-14 08:14:00.000 | 2023-03-14 08:14:00.000 | 2025-05-14 |  |  | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, SW 14/5 | 600 | Billund Kommune | 102199 | NKA-031744 |  | Eva Eisner | Public DK | In Process | 2025-02-18 | 2025-05-16 | 2025-05-16 | Change |  |  |  | 2025-05-14 |  |  | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
[5 empty] | 1025 | Brøndby Kommune Rådhuset | 100084 | NSF-060740 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | [6 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
[5 empty] | 1275 | Brøndby Kommune Rådhuset | 100084 | NSF-060741 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | [6 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
[5 empty] | 1525 | Brøndby Kommune Rådhuset | 100084 | NSF-060742 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | [6 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | -4168.6167 | Brønderslev Kommune | 100557-003 | F30256-1136218-01 | 100557-003-001 | Shazia Mobin | Public DK | In Process | 2025-04-14 | 2025-06-13 |  | Change |  |  |  | 2025-06-06 |  | 2025-07-07 |  |  | 2025-06-13 | 2025-06-13 |  | Change | AX
[5 empty] | 1050 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135627-01 | 106556-011-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 | 2025-06-20 | Own with Digging |  |  |  | 2025-06-13 |  | 2025-06-17 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[5 empty] | 0 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135628-01 | 106556-011-002 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-17 |  |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[5 empty] | 0 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135630-01 | 106556-011-004 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-17 |  |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[5 empty] | 0 | Coloplast A/S | 100575-033 | C30278-1132145-01 | 100575-033-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-10-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2024-11-27 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 1.Order entry and validation | 3.1 Third party vendor delay | This is OpenNet vendor - Problems with BO mapping, i cant chose the correct SSID | 417.5 | COOP DANMARK A/S | 104731 | NKA-060339 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 1.Order entry and validation | 3.1 Third party vendor delay | This is OpenNet vendor - Problems with BO mapping, i cant chose the correct SSID | 417.5 | COOP DANMARK A/S | 104731 | NML-060340 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Problems with moving CPE |  | COOP DANMARK A/S | 104776 | NKA-017579 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-28 |  |  | Change | 2017-01-26 | 2017-02-22 13:00:00.000 | 2017-01-24 08:20:00.000 | [8 empty] | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Problems with moving CPE |  | COOP DANMARK A/S | 105012 | NML-018730 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 | 2025-06-06 | 2025-06-06 | Change | [6 empty] | 2025-05-01 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | On track | 417.5 | COOP DANMARK A/S | 105064 | NKA-060297 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-14 |  |  | 2025-05-30 |  | 2025-05-26 | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | On track | 417.5 | COOP DANMARK A/S | 105064 | NML-060298 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-14 |  |  | 2025-05-30 |  |  | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[6 empty] | COOP DANMARK A/S | 105537 | NBM-052043 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-08 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 110.61 | COOP DANMARK A/S | 105572 | NBM-051854 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-08 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 475 | COOP DANMARK A/S | 105582 | NKA-018460 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-08 | 2025-05-16 | 2025-05-16 | Change | 2017-01-27 | [5 empty] | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
[5 empty] | 475 | COOP DANMARK A/S | 105582 | NML-018461 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-08 | 2025-05-16 | 2025-05-16 | Change | [6 empty] | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
[5 empty] | 0 | COOP DANMARK A/S | 93108 | NBM-052208 |  | Gunvor Pagh | Enterprise DK | In Process | 2023-12-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need confirmation from Peter Friis that it is done |  | COOP DANMARK A/S | 97456 | NKA-041909 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-07-02 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 1480 | Dalgas a/s | 103582 | NKA-037393 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-09 |  |  | Change | 2025-05-12 |  |  | 2025-05-12 |  | 2025-07-21 | [5 empty] | Change | BO
[5 empty] | 4879.75 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132546-01 | 107531-002-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | 3rd Party | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 2682 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132548-01 | 107531-002-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | 3rd Party | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 0 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132550-01 | 107531-002-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | Own OnNet | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 0 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132551-01 | 107531-002-006 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | Own OnNet | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 14157 | DAN`X A/S | 92961 | NBM-051845 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2023-12-14 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 11956.7 | DAN`X A/S | 92961 | NBM-051846 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2023-12-14 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 0 | DAN`X A/S | 92963 | NKA-033906 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-23 | 2025-05-23 | Change | 2024-02-26 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 0 | DAN`X A/S | 92963 | NKA-033907 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-23 | 2025-05-23 | Change | 2021-04-06 | 2021-04-08 14:00:00.000 | 2021-05-20 16:23:00.000 |  |  | 2021-06-08 |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 1634 | DAN`X A/S | 92963 | NKA-051475 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-02-26 | 2024-06-27 14:59:00.000 | 2024-05-21 11:18:00.000 | 2024-05-27 |  |  | 2025-03-19 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 1634 | DAN`X A/S | 92963 | NKA-051476 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-02-27 | 2024-06-27 15:00:00.000 | 2024-05-23 10:09:00.000 | 2024-05-27 |  |  | 2025-03-19 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 6. Cabling splicing and installation | 2203.2 | DAN`X A/S | 92963 | NRS-051477 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-16 | 2025-05-16 | Own OnNet |  |  |  | 2024-05-29 |  |  | 2023-12-13 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | -9403.94 | DAN`X A/S | 98820 | NBM-051845 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-30 | Change | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
[5 empty] | -7203.64 | DAN`X A/S | 98820 | NBM-051846 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-30 | Change | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 1.Order entry and validation | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer vendor - er blevet rykket for | 977.5 | Danepork A/S | 103326 | NKA-059736 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-12 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 1.Order entry and validation | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer vendor - er blevet rykket for | 977.5 | Danepork A/S | 103326 | NML-059737 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-12 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | -0.87333 | Dan-Foam ApS | 102892-008 | C32553-1135648-01 | 102892-008-001 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-23 | 2025-05-02 | Change |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-23 | 2025-05-23 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 518.2 | Dan-Foam ApS | 102892-008 | C32553-1135649-01 | 102892-008-002 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-23 | 2025-05-02 | Change |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-23 | 2025-05-23 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | Dan-Foam ApS | 102892-008 | C32553-1135650-01 | 102892-008-003 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-23 | 2025-05-02 | Own OnNet |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 2012 | Danica Ejendomme P/S | 88343 | NKA-048437 |  | Jan Dibbern | Enterprise DK | In Process | 2023-06-16 | 2025-06-30 | 2025-06-30 | Own OnNet | 2023-05-16 | 2023-06-27 13:24:00.000 | 2023-06-27 13:25:00.000 |  |  | 2023-06-29 | 2023-06-28 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[5 empty] | 2012 | Danica Ejendomme P/S | 88343 | NKA-048438 |  | Jan Dibbern | Enterprise DK | In Process | 2023-06-16 | 2025-06-30 | 2025-06-30 | Own with Digging | 2023-06-16 | 2024-06-07 12:33:00.000 | 2024-06-07 12:33:00.000 |  |  | 2025-06-30 | 2023-06-28 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 350 | Danmarks Meteorologiske Institut | 102835 | NKA-059003 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-19 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-24 |  |  | 2025-06-13 |  | 2025-06-03 | 2025-05-13 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 821 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129804-01 | 100489-187-001 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-25 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-25 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 85 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129806-01 | 100489-187-003 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 94 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129808-01 | 100489-187-005 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 85 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129810-01 | 100489-187-007 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 146 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129812-01 | 100489-187-009 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 638 | Danmarks Tekniske Universitet | 100489-188 | F30176-1130153-01 | 100489-188-001 | Michael Kronbach Leth | Public DK | In Process | 2024-07-23 | 2025-06-30 | 2025-04-25 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-10-07 |  | 2025-04-25 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 629 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130598-01 | 100489-189-001 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 92 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130600-01 | 100489-189-003 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 96 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130602-01 | 100489-189-005 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own OnNet |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 85 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130604-01 | 100489-189-007 | Michael Kronbach Leth | Public DK | Created | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 163 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130606-01 | 100489-189-009 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 117 | Danmarks Tekniske Universitet | 100489-192 | F30176-1134864-01 | 100489-192-001 | Michael Kronbach Leth | Public DK | Created | 2025-02-22 | 2025-06-30 |  | Own OnNet | [5 empty] | 2025-05-16 |  |  | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. | 283 | Danmarks Tekniske Universitet | 100489-195 | F30176-1135247-01 | 100489-195-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-12 | 2025-06-30 |  | Own OnNet | [5 empty] | 2025-06-01 |  |  | 2025-06-30 | 2025-06-30 |  | New Sales | AX
[5 empty] | 188 | Danmarks Tekniske Universitet | 100489-196 | F30176-1136654-01 | 100489-196-001 | Michael Kronbach Leth | Public DK | In Process | 2025-04-30 | 2025-06-30 | 2025-06-30 | Own with Digging |  |  |  | 2025-06-27 |  | 2025-07-17 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
[5 empty] | 475 | Danpilot Svendborg | 104609 | NKA-060072 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-05-05 |  |  | 2025-07-25 |  |  |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Pending on OpenNet tool fix | 540 | DANSK AVIS OMDELING A/S | 101097 | NKA-058161 |  | Martin Rasmussen | Enterprise DK | In Process | 2024-12-27 | 2025-05-30 | 2025-04-11 | 3rd Party | [7 empty] | 2025-04-11 | 2025-04-11 | 2025-05-30 |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Pending on OpenNet tool fix | 540 | DANSK AVIS OMDELING A/S | 101097 | NML-058162 |  | Martin Rasmussen | Enterprise DK | In Process | 2024-12-27 | 2025-05-30 | 2025-04-11 | 3rd Party | 2025-01-23 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-05-30 |  | New Sales | BO
[5 empty] | 2495 | DANSK AVIS OMDELING A/S | 103525 | NKA-060488 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 2495 | DANSK AVIS OMDELING A/S | 103525 | NKA-060489 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1995 | DANSK AVIS OMDELING A/S | 103525 | NKA-060490 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1995 | DANSK AVIS OMDELING A/S | 103525 | NKA-060491 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060492 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-08 |  |  |  |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[5 empty] | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060493 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-08 |  |  |  |  | 2025-07-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[5 empty] | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060494 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-08 | 2025-05-09 13:15:00.000 | 2025-05-13 10:13:00.000 | 2025-06-06 |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060495 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-08 | 2025-05-09 13:17:00.000 | 2025-05-13 10:13:00.000 | 2025-06-06 |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060496 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060497 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060498 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060499 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060500 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
[5 empty] | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060501 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own with Digging | [6 empty] | 2025-04-28 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Delivery is in Norway. Deliveries abroad can take much longer than domestec deliveries. | 2472.5 | Dansk Brand- og sikringsteknisk Institut | 102685 | NKA-058841 |  | Peter Madsen | Enterprise DK | In Process | 2025-02-10 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-03-13 |  |  |  |  | 2025-03-28 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | This is the "B-end" for above circuit(NKA-058841). It's a "EPL" solution(point-2-point). There is no work needed, other than configuration, for NOC-997185, but it can't be done until the "A-end" connection has been delivered. |  | Dansk Brand- og sikringsteknisk Institut | 102685 | NOC-997185 |  | Peter Madsen | Enterprise DK | In Process | 2025-02-10 | 2025-07-11 | 2025-07-11 | Change | 2021-02-25 | [6 empty] | 2025-07-11 | 2025-07-11 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Order is on track | 4275 | Dansk Cater A/S | 101461-008 | F31427-1136260-01 | 101461-008-001 | Cecilie Heidner Nielsen | Enterprise DK | In Process | 2025-04-15 | 2025-05-28 | 2025-08-28 | Own with Digging |  |  |  | 2025-05-28 |  | 2025-07-06 |  | 2025-08-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Order is on track | 4575 | Dansk Cater A/S | 101461-008 | F31427-1136262-01 | 101461-008-003 | Cecilie Heidner Nielsen | Enterprise DK | In Process | 2025-04-15 | 2025-05-28 | 2025-08-28 | Own with Digging |  |  |  | 2025-05-28 |  | 2025-07-06 |  | 2025-08-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Pending delivery/sign off. | 2091 | Dansk Retursystem A/S | 100785 | NKA-057824 |  | Peter Madsen | Enterprise DK | In Process | 2024-12-10 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-12-13 | 2025-04-09 08:10:00.000 | 2025-04-11 10:06:00.000 |  |  | 2025-03-14 |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Pending that the customers' building is ready for delivery. It's a new site being constructed. Won't be ready for delivery until at least august/september. | 2091 | Dansk Retursystem A/S | 100785 | NKA-057825 |  | Peter Madsen | Enterprise DK | In Process | 2024-12-10 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-12-13 |  |  |  |  | 2025-03-14 |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet | 4500 | Danske Commodities A/S | 101109-042 | F31073-1125802-01 | 101109-042-001 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet | 4600 | Danske Commodities A/S | 101109-042 | F31073-1125804-01 | 101109-042-003 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet | 3900 | Danske Commodities A/S | 101109-042 | F31073-1125806-01 | 101109-042-005 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet | 4000 | Danske Commodities A/S | 101109-042 | F31073-1125808-01 | 101109-042-007 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Order is on track | 1600 | Danske Commodities A/S | 101109-053 | C31073-1136532-01 | 101109-053-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-27 | 2025-07-01 | 2025-07-01 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-07-17 |  | 2025-07-01 | 2025-07-01 | 2025-07-01 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Order is on track | 0 | Danske Commodities A/S | 101109-053 | C31073-1136533-01 | 101109-053-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-27 | 2025-07-01 |  | Own OnNet | [5 empty] | 2025-07-17 |  |  | 2025-07-01 | 2025-07-01 |  | New Sales | AX
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | On track | 1495 | Danske Olieberedskabslagre | 100670 | NDD-058082 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | Own OnNet | [7 empty] | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | On track | 1495 | Danske Olieberedskabslagre | 100670 | NDD-058083 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | Own OnNet | [7 empty] | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting for KAM and Carsten Jørgensen | 837 | Danske Olieberedskabslagre | 100670 | NKA-058049 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting for KAM and Carsten Jørgensen | 837 | Danske Olieberedskabslagre | 100670 | NKA-058057 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NKA-058061 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-04-11 | 2025-04-24 10:01:00.000 | 2025-05-02 09:56:00.000 | 2025-05-16 |  | 2025-05-16 |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NKA-058063 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-04-16 | 2025-04-24 10:20:00.000 | 2025-05-12 23:44:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-04-09 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | 837 | Danske Olieberedskabslagre | 100670 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | Own OnNet
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NML-058048 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NML-058056 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NML-058060 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | 3rd Party |  |  | 2025-04-25 08:31:00.000 | 2025-05-16 |  |  |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 837 | Danske Olieberedskabslagre | 100670 | NML-058062 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-01-20 | 2025-04-24 10:20:00.000 | 2025-04-25 09:46:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-04-09 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | 837 | Danske Olieberedskabslagre | 100670 | NML-058074 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | -777 | Danske Olieberedskabslagre | 103254 | NKA-058049 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | -777 | Danske Olieberedskabslagre | 103254 | NKA-058057 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | -777 | Danske Olieberedskabslagre | 103254 | NKA-058061 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 | 2025-05-16 | 2025-05-16 | Change | 2025-04-11 | 2025-04-24 10:01:00.000 | 2025-05-02 09:56:00.000 |  |  | 2025-05-16 | 2025-04-28 | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | -777 | Danske Olieberedskabslagre | 103254 | NKA-058063 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 | 2025-05-16 | 2025-05-16 | Change | 2025-04-16 | 2025-04-24 10:20:00.000 | 2025-05-12 23:44:00.000 | 2025-05-16 |  | 2025-05-16 |  | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | -1439 | Danske Olieberedskabslagre | 103254 | NKA-058069 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change | 2025-01-17 | 2025-01-21 11:47:00.000 | 2025-02-21 10:12:00.000 |  |  | 2025-03-17 | 2025-04-09 |  |  |  |  | Change | BO
[5 empty] | 60 | Danske Olieberedskabslagre | 103254 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 955 | Danske Olieberedskabslagre | 103254 | NKA-059983 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 955 | Danske Olieberedskabslagre | 103254 | NML-059982 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | Danske Olieberedskabslagre | 105234 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-16 |  |  | Change
[5 empty] | 787 | Danske Olieberedskabslagre | 105246 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-15 |  |  | Change
[5 empty] | 787 | Danske Olieberedskabslagre | 105246 | NML-058074 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-15 |  |  | Change
|  | 6. Cabling splicing and installation |  | On track | 680 | Deichmann Sko AB | 97337 | NKA-055297 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | 3rd Party | 2024-07-17 |  |  |  |  | 2025-01-31 | 2024-07-17 | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 680 | Deichmann Sko AB | 97337 | NKA-055333 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | 2024-07-17 |  |  |  |  | 2024-06-20 | 2024-07-17 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann Sko AB | 97337 | NMA-055299 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | 3rd Party | [7 empty] | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann Sko AB | 97337 | NMA-055335 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann Sko AB | 97337 | NSW-055298 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | Own OnNet | [7 empty] | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann Sko AB | 97337 | NSW-055334 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055384 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own with Digging | 2024-11-11 | 2025-05-13 12:53:00.000 |  | 2025-06-20 |  | 2025-04-25 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055408 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-28 | 2024-11-11 14:04:00.000 | 2024-11-11 14:04:00.000 | 2025-05-30 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055426 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-11-11 | 2024-12-15 21:07:00.000 | 2024-12-18 08:15:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055429 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2024-11-11 | 2025-01-28 09:09:00.000 | 2025-04-14 12:10:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055435 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-11-11 | 2025-01-28 10:18:00.000 | 2025-05-08 13:02:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 720 | Deichmann-Sko ApS | 97347 | NKA-055447 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own with Digging | 2024-11-11 | 2024-11-12 16:57:00.000 | 2025-05-12 08:23:00.000 | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055385 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055409 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055421 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-16 | 2025-05-16 | 3rd Party | [6 empty] | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055427 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055430 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055436 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NMA-055448 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055386 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055410 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055422 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-16 | 2025-05-16 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055428 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-23 | 2025-05-23 | Own OnNet | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055431 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055437 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 50 | Deichmann-Sko ApS | 97347 | NSW-055449 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 900 | DGI | 103177 | NKA-059646 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-06 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-03-07 |  |  | 2025-05-12 |  | 2025-05-09 |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Pending delivery/sign off. | 4620 | DI | 102543 | NKA-060057 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-28 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-31 | 2025-04-30 09:51:00.000 | 2025-05-07 09:17:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Pending delivery/sign off. | 4620 | DI | 102543 | NKA-060058 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-28 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-31 | 2025-04-30 09:52:00.000 | 2025-05-07 09:17:00.000 | 2025-05-23 |  | 2025-06-13 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Pending GC Norway. On track | 900 | Diningsix A/S | 104919 | NKA-060447 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-23 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | On track | 625 | DLF Seeds A/S | 102480 | NKA-059765 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-13 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-17 | [6 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | On track | 625 | DLF Seeds A/S | 102480 | NML-059766 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-13 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-17 | [6 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 2821 | Dovista A/S | 103016 | NII-060186 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 2821 | Dovista A/S | 103016 | NII-060187 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5956 | Dovista A/S | 103016 | NII-060188 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5956 | Dovista A/S | 103016 | NII-060189 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-12 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5655 | Dovista A/S | 103016 | NII-060190 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5655 | Dovista A/S | 103016 | NII-060191 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5581 | Dovista A/S | 103016 | NII-060192 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5581 | Dovista A/S | 103016 | NII-060193 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 3428 | Dovista A/S | 103016 | NII-060194 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 3428 | Dovista A/S | 103016 | NII-060195 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 3361.5 | Dovista A/S | 103016 | NII-060196 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 3361.5 | Dovista A/S | 103016 | NII-060197 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5581 | Dovista A/S | 103016 | NII-060198 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 5581 | Dovista A/S | 103016 | NII-060199 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 4149 | Dovista A/S | 104664 | NII-060200 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-21 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.4 Pending equipment/product to be ready | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. | 4149 | Dovista A/S | 104664 | NII-060201 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-21 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
[5 empty] | 0 | DSV A/S | 100789-076 | C30752-1120913-01 | 100789-076-001 | Kasper Bruun Nielsen | Enterprise DK | In Process | 2023-06-27 |  |  | Own OnNet | [5 empty] | 2023-07-24 | [5 empty] | New Sales | AX
[5 empty] | 1600 | DSV A/S | 100789-085 | C30752-1131765-01 | 100789-085-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-10-21 | 2025-05-21 | 2025-05-09 | Own with Digging |  |  |  | 2025-05-02 |  | 2025-01-07 | 2025-03-11 | 2025-05-09 | 2025-05-21 | 2025-05-21 |  | New Sales | AX
[5 empty] | 1600 | DSV A/S | 100789-085 | C30752-1131767-01 | 100789-085-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-10-21 | 2025-05-21 | 2025-05-09 | Own with Digging |  |  |  | 2025-05-02 |  | 2025-01-07 | 2025-03-11 | 2025-05-09 | 2025-05-21 | 2025-05-21 |  | New Sales | AX
[5 empty] | 900 | DSV A/S | 100789-085 | C30752-1131769-01 | 100789-085-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-10-21 | 2025-05-21 | 2025-04-11 | Own with Digging |  |  |  | 2025-04-04 |  | 2025-01-07 | 2025-05-02 | 2025-04-11 | 2025-05-21 | 2025-05-21 |  | New Sales | AX
[5 empty] | 96 | DSV A/S | 100789-085 | C30752-1131770-01 | 100789-085-006 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-10-21 | 2025-05-21 | 2025-04-11 | Own OnNet |  |  |  | 2025-04-04 |  | 2025-01-07 | 2025-03-11 | 2025-04-11 | 2025-05-21 | 2025-05-21 |  | New Sales | AX
|  | 2. Delivery planning | 3.1 Third party vendor delay | Wrong information from Sales | 1050 | DSV A/S | 100789-088 | C30752-1136045-01 | 100789-088-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-07 | 2025-06-20 | 2025-06-20 | Own OnNet |  |  |  | 2025-06-13 |  | 2025-06-27 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
|  | 8. Ready for service | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Awaiting provisioning for RFS approval | 60 | DSV A/S | 100789-088 | C30752-1136046-01 | 100789-088-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-07 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-27 |  |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[5 empty] | 670 | Elis Danmark A/S | 102414 | NKA-060542 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 585 | Elis Danmark A/S | 102414 | NKA-060544 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Own with Digging | [11 empty] | New Sales | BO
[5 empty] | 670 | Elis Danmark A/S | 102414 | NML-060543 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 585 | Elis Danmark A/S | 102414 | NML-060545 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | -122.8 | Elis Danmark A/S | 102414 | NSW-044170 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044175 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044178 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044181 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044183 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044186 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044189 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044195 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044197 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044203 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044206 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -101.2 | Elis Danmark A/S | 102414 | NSW-044209 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044212 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044215 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044218 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044221 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-044226 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 850 | Elis Danmark A/S | 102414 | NSW-044229 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -90 | Elis Danmark A/S | 102414 | NSW-046860 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 470 | Elis Danmark A/S | 102414 | NSW-060546 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not started | 1320 | ENTERTAINMENT TRADING A/S | 105207 | NKA-060412 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-05-14 |  |  | 2025-06-13 |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not started | 387.5 | ENTERTAINMENT TRADING A/S | 105207 | NMA-060414 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not started | 387.5 | ENTERTAINMENT TRADING A/S | 105207 | NSW-060413 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Ordre skal først leveres ultimo december | 999 | European Energy A/S | 103432 | NKA-059755 |  | Merete Helme | Enterprise DK | In Process | 2025-03-12 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 999 | European Energy A/S | 97899 | NKA-055965 |  | Merete Helme | Enterprise DK | In Process | 2024-08-27 | 2025-05-28 | 2025-05-28 | 3rd Party | 2024-09-02 | [5 empty] | 2025-03-06 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Service Window needs to be planned | 1650 | Fiftytwo A/S | 96513 | NKA-055062 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-06-26 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-07-08 | [5 empty] | 2024-09-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Service Window needs to be planned | 1650 | Fiftytwo A/S | 96513 | NKA-055063 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-06-26 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-07-08 | [5 empty] | 2024-09-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 697.5 | FLAMMEN A/S | 102960 | NKA-060444 |  | Merete Helme | Enterprise DK | In Process | 2025-04-23 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-01 |  |  | 2025-07-04 |  | 2025-07-18 | 2025-05-07 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 697.5 | FLAMMEN A/S | 102960 | NML-060445 |  | Merete Helme | Enterprise DK | In Process | 2025-04-23 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-01 |  |  | 2025-07-04 |  | 2025-07-18 | 2025-05-07 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg | 1495 | Fleggaard It ApS | 93857 | NKA-054774 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-31 | 2025-05-31 | Own with Digging | 2024-11-13 | [6 empty] | 2025-05-31 | 2025-05-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg | 1295 | Fleggaard It ApS | 93857 | NKA-054775 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-31 | 2025-05-31 | Own OnNet | 2024-06-19 | 2024-06-26 11:38:00.000 | 2024-07-02 10:03:00.000 | 2024-07-31 |  |  |  | 2025-05-31 | 2025-05-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg | 1495 | Fleggaard It ApS | 93857 | NKA-054776 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-31 | 2025-05-31 | Own with Digging | 2024-11-13 | [6 empty] | 2025-05-31 | 2025-05-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 2037 | FLSMIDTH A/S | 96792 | NKA-058793 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-06 | 2025-07-18 | 2025-07-18 | Own with Digging | 2025-02-07 |  |  |  |  | 2025-05-02 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 2037 | FLSMIDTH A/S | 96792 | NKA-058794 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-06 | 2025-07-18 | 2025-07-18 | Own with Digging | 2025-02-07 |  |  |  |  | 2025-05-02 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | Need clarification on configuration in data center. | 1586 | FOA Fag og Arbejde | 103456 | NKA-059764 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-13 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 8. Ready for service | 8. Ready for service | 8. Ready for service | 4130 | FOA Fag og Arbejde | 98150 | NKA-059241 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own OnNet | 2025-03-10 |  |  |  |  | 2025-05-16 | [5 empty] | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Reliant on line 249 | -1846.86 | FOA Fag og Arbejde | 98150 | NOC-997378 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Change |  | 2018-01-04 15:18:00.000 | 2018-01-04 15:18:00.000 | [8 empty] | Change | BO
|  | 2. Delivery planning | 2.5 Internal or external data/documentation incomplete/ incorrect | Needed to obtain correct location for Dark Fiber from customer | 1775 | FOA Fag og Arbejde | 98150 | NSF-059243 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own with Digging | 2025-03-10 | 2025-05-07 07:36:00.000 |  |  |  | 2025-05-16 | 2025-03-03 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.5 Internal or external data/documentation incomplete/ incorrect | Needed to obtain correct location for Dark Fiber from customer | 1775 | FOA Fag og Arbejde | 98150 | NSF-059244 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own with Digging | 2025-03-10 | 2025-05-07 07:37:00.000 |  |  |  | 2025-05-16 | 2025-03-03 |  |  |  |  | New Sales | BO
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 101523 | NKA-058262 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | 3rd Party
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 101523 | NKA-058263 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | 3rd Party
[6 empty] | Forsvaret og Forsvarsministeriets styrelser | 101766 | NKA-058262 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | Change
[6 empty] | Forsvaret og Forsvarsministeriets styrelser | 101766 | NKA-058263 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | Change
[5 empty] | 925 | Forsvaret og Forsvarsministeriets styrelser | 102351 | NKA-058631 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-28 |  |  | 3rd Party
[5 empty] | 925 | Forsvaret og Forsvarsministeriets styrelser | 102351 | NKA-058632 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-28 |  |  | 3rd Party
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 104956 | NKA-060250 |  | Eva Eisner | Public DK | In Process | 2025-04-03 |  |  | 3rd Party
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000272 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000273 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000301 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000478 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000479 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000480 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 720 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000481 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 350 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000486 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 800 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000487 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 800 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000488 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 350 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000489 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 720 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000490 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 3125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-000492 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 500 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-001984 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-001985 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 720 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-001999 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002000 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002008 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 500 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002010 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002020 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002024 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002027 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 500 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002028 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002029 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 870 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002030 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002332 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002334 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002335 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002336 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002337 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002338 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002339 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 800 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002340 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 800 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002341 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002342 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002343 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002344 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002345 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002346 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002347 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002348 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002349 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002350 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 970 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002351 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002352 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 1045 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002353 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002354 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002355 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002356 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002357 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002358 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002360 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 1045 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002361 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002363 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002364 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002366 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002367 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002368 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002369 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002370 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 775 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002371 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002372 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002373 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002374 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002375 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 775 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002378 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002380 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002381 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002382 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002383 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002384 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 400 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002387 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002390 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 25 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002391 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002392 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002394 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002396 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002397 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002400 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002401 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002402 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002403 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002405 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002406 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002407 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002408 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002409 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002410 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002411 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002413 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002417 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002418 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002419 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002420 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002421 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002422 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 775 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002423 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002425 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002426 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 500 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002822 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 25 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002823 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 25 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-002825 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003088 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003089 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003090 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003091 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003092 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003093 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 350 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003402 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003988 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-003989 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-004189 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-004437 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-004840 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-004841 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-005309 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 350 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-005743 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-006172 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-006515 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-006776 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 500 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-006799 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-007252 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 400 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-007285 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009270 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 945 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009283 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 945 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009284 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009287 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009288 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009361 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009402 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009403 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009404 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 2475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009506 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009544 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009590 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-009763 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010190 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010348 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010610 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010618 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010724 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-010961 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011442 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011444 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011445 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011547 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 945 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011837 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 945 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011838 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011869 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011886 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-011887 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-013694 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-013695 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-014551 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-014552 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 775 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-015331 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 2475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-015332 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 845 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-015935 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-016151 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-016152 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-016862 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-017109 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019612 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019613 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019614 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019616 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019617 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019618 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019619 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-019620 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-020213 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 750 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-022844 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-023016 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-023017 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-025857 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 775 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-026122 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 550 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-027068 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-027284 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-028671 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-028760 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-029008 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 4125 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-029492 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-029888 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030143 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030280 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030292 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 675 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030331 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030414 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030574 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-030575 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-031153 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 525 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-031175 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 925 | Forsvaret og Forsvarsministeriets styrelser | 82959 | NKA-031984 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-28 |  |  | Change
[5 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 91996 | NKA-002013 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-22 |  |  | Change
[5 empty] | 7100 | Foss Analytical A/S | 98346 | NKA-056204 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-09-12 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-09-23 | 2024-11-25 13:35:00.000 | 2024-12-12 13:09:00.000 | 2025-03-19 |  | 2025-03-28 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 7100 | Foss Analytical A/S | 98346 | NKA-056205 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-09-12 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-09-23 | 2024-11-25 13:35:00.000 | 2024-12-12 13:09:00.000 | 2025-03-19 |  | 2025-03-28 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 1195 | FRELSENS HÆR SOCIALTJENESTEN | 103003 | NKA-060669 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 3995 | Frode Laursen A/S | 105079 | NKA-060620 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. | 4500 | Frode Laursen A/S | 89081 | NKA-023538 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2018-03-07 |  |  |  |  | 2018-06-29 |  | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. | 2500 | Frode Laursen A/S | 89081 | NKA-033837 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2021-03-25 | [5 empty] | 2025-04-03 | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. | 6000 | Frode Laursen A/S | 89081 | NOC-998343 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2014-03-12 | [6 empty] | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. | 4000 | Frode Laursen A/S | 89081 | NOC-998373 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1760 | GENERAL LOGISTICS SYSTEMS DENMARK A/S | 103151 | NKA-059759 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-12 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-17 | 2025-04-04 12:25:00.000 | 2025-04-24 10:10:00.000 | 2025-06-20 |  |  | 2025-04-29 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035592 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035593 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-28 13:42:00.000 | 2021-11-10 14:51:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035594 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035595 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 08:21:00.000 | 2021-10-26 08:21:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035596 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 08:21:00.000 | 2021-10-26 08:22:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035599 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035600 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035601 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035602 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035603 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-07 11:18:00.000 | 2021-07-01 10:16:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035604 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 12:09:00.000 | 2021-07-01 10:11:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035605 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-25 15:37:00.000 | 2021-10-25 15:40:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035606 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035607 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035608 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035609 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-08 13:39:00.000 | 2021-10-08 13:39:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035610 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035611 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035612 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035613 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035614 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035615 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035616 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035617 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035618 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035620 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-08 13:13:00.000 | 2021-10-08 13:13:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035622 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035625 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035626 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035627 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035628 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 09:35:00.000 | 2021-10-26 09:35:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035631 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-27 13:32:00.000 | 2021-10-27 13:32:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035632 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035633 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035634 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035635 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035636 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-28 09:22:00.000 | 2021-07-01 10:30:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035637 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035638 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-28 11:19:00.000 | 2021-10-28 11:19:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035640 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035641 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035642 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035644 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-18 10:33:00.000 | 2021-10-18 10:33:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035645 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-27 12:00:00.000 | 2021-10-27 12:00:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035646 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-27 13:28:00.000 | 2021-10-27 13:28:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035647 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035648 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035649 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035650 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035651 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035652 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035653 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035654 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035655 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-09-28 08:45:00.000 | 2021-09-28 11:23:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035656 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035658 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035659 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035660 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035661 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035662 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-01 11:15:00.000 | 2021-11-01 11:15:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035663 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035664 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [6 empty] | 2025-05-09 | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035665 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035666 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035667 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035668 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035669 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035670 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035671 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035672 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035674 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035676 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035678 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035679 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035680 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-01 09:47:00.000 | 2021-11-01 09:47:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035681 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035682 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035683 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035685 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035686 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035687 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035688 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035690 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035691 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035692 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035694 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035695 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035696 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035697 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035699 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [6 empty] | 2025-05-09 | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035700 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035701 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-01 09:20:00.000 | 2021-07-01 10:27:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035702 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035703 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035704 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035705 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035706 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035707 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035708 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035710 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035711 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035712 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035713 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035714 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035715 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035716 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035718 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  |  | 2021-07-02 08:10:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035719 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035720 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035721 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035722 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035723 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-27 09:00:00.000 | 2021-10-27 09:01:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035724 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035725 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-29 09:33:00.000 | 2021-10-29 09:34:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035726 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035727 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035728 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035729 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 13:26:00.000 | 2021-10-26 15:22:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035730 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 13:37:00.000 | 2021-10-26 14:28:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035731 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035732 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 12:58:00.000 | [5 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035733 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035736 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-25 10:19:00.000 | 2021-10-25 10:19:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035737 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-26 11:22:00.000 | 2021-10-29 10:58:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035739 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035740 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035741 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035742 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035743 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035745 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035747 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035748 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035751 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035752 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035753 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035758 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035759 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035760 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-29 12:27:00.000 | 2021-10-29 12:27:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035766 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035768 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035770 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035771 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035776 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-10-28 10:50:00.000 | 2021-10-28 10:50:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035778 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035779 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035782 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035785 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035786 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035787 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035792 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035793 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-17 08:35:00.000 | 2021-11-17 08:36:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035794 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035796 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2021-07-16 | 2021-11-09 08:17:00.000 | 2021-11-09 08:17:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035797 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2021-07-16 | 2021-11-09 08:20:00.000 | 2021-11-09 08:20:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035798 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-037694 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-038185 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2021-11-10 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-043334 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2022-07-12 |  |  |  |  | 2022-10-14 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-043926 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2022-09-23 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | GENTOFTE KOMMUNE | 102771 | NKA-050668 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2023-11-20 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | The Technical part is not agreed on yet (Netteam) | 6048.86 | Give Uddannelsescenter | 102537 | NBM-058822 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-02-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-21 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | The Technical part is not agreed on yet (Netteam) | 1887.84 | Give Uddannelsescenter | 102537 | NBM-058823 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-02-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-21 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | The Technical part is not agreed on yet (Netteam) | 2257.71 | Give Uddannelsescenter | 102537 | NBM-058824 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-02-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-21 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | The Technical part is not agreed on yet (Netteam) | 1680.02 | Give Uddannelsescenter | 104905 | NBM-060251 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | 3. Part og Kunde havde en misforståelse af leverance dato. | 550 | Glostrup Kommune | 100034 | NKA-056919 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | 3rd Party | 2024-11-18 |  |  |  |  | 2025-01-31 |  | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | 3. Part og Kunde havde en misforståelse af leverance dato. | 227.5 | Glostrup Kommune | 100034 | NMA-056921 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | 3rd Party | 2024-11-18 |  |  |  |  | 2025-01-31 |  | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | 3. Part og Kunde havde en misforståelse af leverance dato. | 227.5 | Glostrup Kommune | 100034 | NSW-056920 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | Own OnNet | [7 empty] | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
[6 empty] | Glostrup Kommune | 105649 | NKA-041535 |  | Morten Skytte | Public DK | In Process | 2025-05-09 | 2025-07-01 | 2025-07-01 | Change | 2022-06-09 | [6 empty] | 2025-07-01 | 2025-07-01 |  |  | Change | BO
|  | 5. Configuration |  | Awating configuration | 25 | Guldborgsund Kommune | 105041 | NKA-033744 |  | Morten Skytte | Public DK | In Process | 2025-04-10 | 2025-06-30 | 2025-06-30 | Change | 2021-03-15 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 2. Delivery planning | 3.2 Third party resource constraint | On track | 300 | Guldborgsund Kommune | 105144 | NKA-060502 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-28 |  |  | 2025-06-17 |  | 2025-06-17 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[5 empty] | 300 | Guldborgsund Kommune | 105648 | NKA-060720 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-13 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 300 | Guldborgsund Kommune | 105648 | NKA-060721 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-13 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Hard to make appointment with end customer for CPE installation | 950 | Haderslev kommune | 89321 | NKA-050356 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-02 |  |  | 2025-04-30 |  | 2025-02-24 | 2025-02-27 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050357 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | No link from 3.part when trying to migrate in SW - new to be schuled | 1400 | Haderslev kommune | 89321 | NKA-050369 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-09 | 2025-04-25 12:17:00.000 | 2025-04-25 12:17:00.000 | 2025-04-23 |  | 2025-02-25 | 2025-01-17 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Hard to make appointment with end customer for CPE installation | 1400 | Haderslev kommune | 89321 | NKA-050376 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-02 |  |  | 2025-04-30 |  | 2025-03-07 | 2025-02-28 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050381 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050382 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050383 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050384 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050385 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050386 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050387 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050388 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050389 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050390 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050395 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % | 475 | Haderslev kommune | 89321 | NKA-050396 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050350 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-05-28 | 2025-05-28 | Change | 2024-07-18 |  |  |  |  | 2024-08-28 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050355 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050356 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-02 |  |  |  |  | 2025-02-24 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050357 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050369 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-09 | 2025-04-25 12:17:00.000 | 2025-04-25 12:17:00.000 |  |  | 2025-02-25 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050374 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050376 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-02 |  |  |  |  | 2025-03-07 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050377 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050381 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050382 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050383 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050384 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050385 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050386 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050387 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050388 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050389 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050390 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050395 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050396 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off | 40 | Haderslev kommune | 89440 | NKA-050397 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 1050 | Halberg A/S | 105673 | NKA-060682 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 3.1 Third party vendor delay | On track - part of the total Harboe Solution | 0 | Harboes Bryggeri A/S | 102376 | NCI-058640 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-01-28 |  |  | Own OnNet | [6 empty] | 2025-02-11 |  |  |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Third party vendor delay | On track - part of the total Harboe Solution | 0 | Harboes Bryggeri A/S | 102376 | NSW-058639 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-01-28 |  |  | Own OnNet | [6 empty] | 2025-02-11 |  |  |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Long lead time in Germany op to 26 weeks ordred 13-01-2025 | 4950 | Harboes Bryggeri A/S | 98586 | NKA-056499 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own with Digging | 2025-01-13 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Germany vendor wants 45.000 euro to compelete the installation, and that is more the expected. Therefore Carsten Jørgensen is helping with an alternative, but germany third party vendor is moving slow | 7600 | Harboes Bryggeri A/S | 98586 | NKA-056501 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own with Digging | 2025-01-13 | [10 empty] | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow but because Dargun is not ready the customer is not in a hurry | 1450 | Harboes Bryggeri A/S | 98586 | NKA-056503 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-11-27 |  |  | 2025-02-11 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow but because Dargun is not ready the customer is not in a hurry | 2095 | Harboes Bryggeri A/S | 98586 | NKA-056505 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-11-27 |  |  | 2025-02-14 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Long lead time in Germany op to 26 weeks ordred 13-01-2025 | 1370 | Harboes Bryggeri A/S | 98586 | NSW-056498 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Germany vendor wants 45.000 euro to compelete the installation, and that is more the expected. Therefore Carsten Jørgensen is helping with an alternative, but germany third party vendor is moving slow | 1680 | Harboes Bryggeri A/S | 98586 | NSW-056500 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow but because Dargun is not ready the customer is not in a hurry | 840 | Harboes Bryggeri A/S | 98586 | NSW-056502 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow but because Dargun is not ready the customer is not in a hurry | 2670 | Harboes Bryggeri A/S | 98586 | NSW-056504 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 7. Service activation | 2.1 Order forgotten, but back on track to be processed | Handed over from Enterprice were ther warent made a status since | 900 | Hempel Fonden | 101434 | NKA-058108 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-01-02 | 2025-01-07 11:58:00.000 | 2025-01-10 09:55:00.000 |  |  | 2025-03-07 | 2025-01-31 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 7. Service activation | 2.1 Order forgotten, but back on track to be processed | Handed over from Enterprice were ther warent made a status since | 200 | Hempel Fonden | 101434 | NMA-058110 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | 3rd Party | [6 empty] | 2025-02-07 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 7. Service activation | 2.1 Order forgotten, but back on track to be processed | Handed over from Enterprice were ther warent made a status since | 200 | Hempel Fonden | 101434 | NSW-058109 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-02-07 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 7. Service activation | 2.5 Internal or external data/documentation incomplete/ incorrect | Fejl i BO ordre. |  | Herningsholm Erhvervsskole & Gymnasier S/I | 102088 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2025-02-12 |  |  | Change |  | 2023-10-24 13:56:00.000 | 2023-10-24 13:56:00.000 |  |  |  | 2025-05-01 |  |  |  |  | Change | BO
|  | 7. Service activation | 2.5 Internal or external data/documentation incomplete/ incorrect | Fejl i BO ordre. |  | Herningsholm Erhvervsskole & Gymnasier S/I | 102088 | NKA-055508 |  | Michael Kronbach Leth | Public DK | In Process | 2025-02-12 | 2025-05-28 | 2025-05-28 | Change | 2024-07-10 | 2024-07-17 10:57:00.000 | 2024-07-18 08:57:00.000 |  |  | 2024-08-30 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track |  | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 |  |  | Change |  | 2023-10-24 13:56:00.000 | 2023-10-24 13:56:00.000 | [8 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 720 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-042377 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 |  |  | Change | 2022-05-02 |  | 2022-06-01 09:42:00.000 |  |  | 2022-09-14 | [5 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060067 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Own OnNet | 2025-04-15 | 2025-05-06 14:35:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060068 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-04-15 | 2025-05-06 14:47:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060069 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 |  |  | Own with Digging | 2025-04-15 | 2025-05-09 07:21:00.000 |  | 2025-06-20 |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | Afventer SW med kunden i Juli måned. | 6000 | Herningsholm Erhvervsskole & Gymnasier S/I | 88766 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2023-09-11 | 2025-07-30 | 2025-07-30 | Change |  |  |  | 2024-03-14 |  |  |  | 2025-07-30 | 2025-07-30 |  |  | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Pending on OpenNet tool fix | 850 | Hi Five A/S | 104285 | NKA-059846 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 8. Ready for service |  | Pending on OpenNet tool fix | 3238.5 | Hillerød Kommune | 104814 | NDD-060179 |  | Morten Skytte | Public DK | In Process | 2025-03-31 | 2025-05-15 | 2025-05-15 | Own OnNet |  |  |  | 2025-04-28 |  |  | 2025-05-13 | 2025-05-15 | 2025-05-15 |  |  | New Sales | BO
|  | 5. Configuration |  | Information just recieved 30.04.25 | 3238.5 | Hillerød Kommune | 104814 | NKA-060178 |  | Morten Skytte | Public DK | In Process | 2025-03-31 | 2025-05-15 | 2025-05-15 | Own OnNet | 2025-04-03 | 2025-04-23 17:13:00.000 | 2025-04-23 18:28:00.000 | 2025-04-28 |  | 2025-04-30 | 2025-05-13 | 2025-05-15 | 2025-05-15 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Vendor shift after site survey | 1725 | Hjørring Gymnasium og HF-Kursus | 101158 | NKA-006159 |  | Morten Skytte | Public DK | In Process | 2024-12-03 | 2025-07-27 | 2025-07-27 | Change | 2025-02-18 | 2025-02-25 07:50:00.000 |  | 2025-06-27 |  |  |  | 2025-07-27 | 2025-07-27 |  |  | Change | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | This is DDoS protection. Pending that the fiber circuit, that this DDoS protection needs to protect, will be converted with 3rd party vendor. It's a conversion another department/person(Morten Skytte) will handle. | 5995 | HKScan Denmark A/S | 102177 | NDD-059699 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | This is DDoS protection. Pending that the fiber circuit, that this DDoS protection needs to protect, will be converted with 3rd party vendor. It's a conversion another department/person(Morten Skytte) will handle. | 5995 | HKScan Denmark A/S | 102177 | NDD-059700 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 8. Ready for service |  | Delivered and signed off 29/04-2025 | 1495 | HKScan Denmark A/S | 102177 | NDD-059703 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-04-29 | 2025-06-20 | 2025-06-20 |  | 2025-04-29 00:00:00.000 | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | This is DDoS protection. Pending delivery of the fiber(20/06-2025), that this DDoS protection needs to protect. | 1495 | HKScan Denmark A/S | 102177 | NDD-059704 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-04-29 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | -61.64 | HKScan Denmark A/S | 102177 | NKA-051377 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-05-28 | 2025-05-28 | Change |  |  |  | 2025-05-26 |  | 2025-05-26 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 20/06 | 1450 | HKScan Denmark A/S | 102177 | NKA-059698 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-21 | 2025-04-08 13:32:00.000 | 2025-05-13 10:06:00.000 | 2025-06-13 |  |  |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | -1480.8 | HKScan Denmark A/S | 102177 | NOC-996874 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-05-28 | 2025-05-28 | Change |  |  |  | 2025-05-26 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | 3rd party vendor has to "convert" this circuit from current POI to new POI due to ordered service speed of 10 Gbps. It's booked for 05/05, and then we have to configure our part | 0 | Hoffmann A/S | 103075 | NOC-995822 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-07-04 | 2025-07-04 | Change |  | 2016-09-14 14:21:00.000 | 2016-09-14 14:21:00.000 |  |  |  |  | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Pending the conversion of abovecircuit(NOC-995822) before we can work on this circuit(Redundant solution). | 0 | Hoffmann A/S | 103075 | NOC-995895 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-07-04 | 2025-07-04 | Change | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | No link when doing SW week 18 | 400 | Horsens kommune | 100303 | NKA-057346 |  | Morten Skytte | Public DK | In Process | 2024-11-13 | 2025-05-16 | 2025-05-16 | 3rd Party |  |  |  | 2025-04-10 |  |  |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | No link when doing SW week 18 | 325 | Horsens kommune | 100303 | NSW-057347 |  | Morten Skytte | Public DK | In Process | 2024-11-13 | 2025-05-16 | 2025-05-16 | Own OnNet | [7 empty] | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | No link when doing SW week 18 |  | Horsens kommune | 100321 | NKA-057346 |  | Morten Skytte | Public DK | In Process | 2024-11-06 |  |  | Change | [11 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060203 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 |  |  | Own with Digging | 2025-05-06 | 2025-05-09 12:39:00.000 |  | 2025-07-04 |  | 2025-07-18 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060204 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-24 |  |  | 2025-07-25 |  | 2025-07-18 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060205 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 08:00:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060206 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-24 | 2025-04-29 08:38:00.000 | 2025-05-07 12:47:00.000 | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060207 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 09:30:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060208 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-24 | 2025-04-29 08:59:00.000 | 2025-05-07 12:29:00.000 | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 5723 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060209 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 |  |  | Own OnNet | 2025-04-24 |  |  |  |  | 2025-07-18 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 5723 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060210 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 |  |  | Own OnNet | 2025-04-24 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 299.5 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060212 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1360 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060213 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 09:57:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1500 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060214 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 08:41:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 1660 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060215 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-25 | 2025-07-25 | Own OnNet | 2025-04-24 | 2025-05-05 07:45:00.000 | 2025-05-14 14:50:00.000 | 2025-07-18 |  | 2025-07-18 |  | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. | 299.5 | HUSCOMPAGNIET HOLDING A/S | 103188 | NML-060211 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 1250 | HUSCOMPAGNIET HOLDING A/S | 105286 | NKA-060559 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-01 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048925 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048931 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2024-07-02 |  | 2024-08-13 09:05:00.000 |  |  | 2024-09-13 | [5 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048933 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048935 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048937 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048939 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | [11 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-048947 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-053054 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change |  | 2024-05-28 14:34:00.000 | 2024-05-08 14:29:00.000 | [8 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-053055 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change |  | 2024-06-19 13:46:00.000 | 2024-06-19 13:46:00.000 | [8 empty] | Change | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Afventer bekræftelse på deres nye MPLS Ark. |  | I/S VESTFORBRÆNDING | 103060 | NKA-056750 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2024-10-11 |  |  |  |  | 2024-12-20 | [5 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104556 | NKA-060023 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-04 |  |  |  |  | 2025-06-13 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 252.5 | I/S VESTFORBRÆNDING | 104556 | NKA-060025 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104556 | NKA-060027 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104556 | NML-060024 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | [5 empty] | 2025-06-13 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104556 | NML-060026 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104556 | NML-060028 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060375 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 475 | I/S VESTFORBRÆNDING | 104579 | NKA-060377 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | Own OnNet | 2025-04-15 | 2025-05-09 12:39:00.000 | 2025-05-14 08:46:00.000 | 2025-05-30 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060378 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060380 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060382 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060384 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060376 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060379 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | [5 empty] | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060381 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060383 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer klarmelding fra TDC | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060385 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer datoer fra FPM | 475 | I/S VESTFORBRÆNDING | 88172 | NKA-048922 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-03-12 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer dato fra 3.part | 252.5 | I/S VESTFORBRÆNDING | 88172 | NKA-048939 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-07-31 | 2025-07-31 | 3rd Party | [7 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer dato fra 3.part | 252.5 | I/S VESTFORBRÆNDING | 88172 | NKA-048943 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-05-28 | 2025-05-28 | 3rd Party | 2023-11-09 |  |  | 2025-05-23 |  |  | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer dato fra 3.part | 252.5 | I/S VESTFORBRÆNDING | 88172 | NML-048940 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-07-31 | 2025-07-31 | 3rd Party | 2023-11-06 | [6 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer dato fra 3.part | 252.5 | I/S VESTFORBRÆNDING | 88172 | NML-048944 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-05-28 | 2025-05-28 | 3rd Party | 2023-11-09 |  |  | 2025-05-23 |  |  | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 93.75 | INFRASTRUKTURSELSKABET LJ A/S | 107101-006 | F36205-1130134-01 | 107101-006-001 | Mette Vinther | Public DK | In Process | 2024-07-23 | 2025-08-29 | 2025-08-29 | Own OnNet |  |  |  | 2025-08-22 |  | 2024-09-10 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | New Sales | AX
[5 empty] | 350 | It-Forsyningen I/S | 105498 | NKA-046566 |  | Morten Skytte | Public DK | In Process | 2025-05-09 |  |  | Change | 2023-02-10 | 2023-04-25 15:45:00.000 | 2023-04-25 15:45:00.000 | [8 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Delay GC Norway | 1038 | Jem & Fix A/S | 100796 | NKA-057361 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-11-13 | 2025-05-23 | 2025-05-23 | 3rd Party | 2024-11-14 |  |  |  |  | 2025-01-31 | 2025-02-02 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Delay GC Norway | 1038 | Jem & Fix A/S | 101288 | NKA-058314 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-01-10 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-01-13 |  |  |  |  | 2025-02-04 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | On track | 850 | Jem & Fix A/S | 103386 | NKA-059840 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 | 2025-08-01 | 2025-08-01 | Own with Digging | 2025-03-26 | 2025-03-27 10:43:00.000 | 2025-05-13 08:47:00.000 | 2025-06-13 |  | 2025-08-01 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Jem & Fix A/S | 103386 | NKA-059841 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Jem & Fix A/S | 104367 | NKA-059866 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-20 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-09 |  |  |  |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Jem & Fix A/S | 105311 | NKA-060462 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-24 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Jem & Fix A/S | 105311 | NKA-060463 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Jem & Fix A/S | 105311 | NKA-060464 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-24 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 850 | Jem & Fix A/S | 88683 | NKA-048998 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-04-22 | 2025-04-24 12:14:00.000 | 2025-05-02 08:05:00.000 | 2025-06-06 |  | 2025-07-11 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[5 empty] | 850 | Jem & Fix A/S | 88683 | NKA-049011 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-07-18 | 2025-07-18 | Own OnNet | [7 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
[5 empty] | 850 | Jem & Fix A/S | 88683 | NKA-049014 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-05-06 | 2025-05-08 11:36:00.000 |  | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | 850 | Jem & Fix A/S | 88683 | NKA-049085 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-07-18 | 2025-07-18 | Own OnNet | [7 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 850 | Jem & Fix A/S | 88683 | NKA-049100 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | 3rd Party | 2024-12-20 |  |  | 2025-05-23 |  | 2025-06-13 | 2025-05-05 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 850 | Jem & Fix A/S | 88683 | NKA-049106 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-12-20 | 2025-01-17 09:30:00.000 | 2025-03-18 12:38:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 850 | Jem & Fix A/S | 88683 | NKA-049113 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-01-21 | 2025-02-25 06:48:00.000 | 2025-03-18 10:12:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 0 | Jem & Fix A/S | 97729 | NKA-049100 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-07-19 | 2025-06-13 | 2025-06-13 | Change | 2024-12-20 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | Change | BO
[5 empty] | 0 | Jem & Fix A/S | 97729 | NKA-049113 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-07-19 | 2025-06-13 | 2025-06-13 | Change | 2025-01-21 | 2025-02-25 06:48:00.000 | 2025-03-18 10:12:00.000 |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | Change | BO
[5 empty] | 1650 | Johs. Rasmussen, Svebølle A/S | 102816 | NKA-060581 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-05 |  |  | 2025-07-04 |  | 2025-07-04 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
[5 empty] | 200 | Johs. Rasmussen, Svebølle A/S | 102816 | NML-060580 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-06-06 | 2025-06-06 | 3rd Party |  |  |  | 2025-06-04 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | -285.8 | Johs. Rasmussen, Svebølle A/S | 102816 | NOC-997751 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-06-06 | 2025-06-06 | Change | 2016-10-06 |  |  | 2025-06-04 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | Change | BO
[5 empty] | 5450 | Jysk A/S | 107550-009 | C36587-1135566-01 | 107550-009-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-06-13 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | 5934 | Jysk A/S | 107550-009 | C36587-1135568-01 | 107550-009-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-06-13 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 5. Configuration | 2.1 Order forgotten, but back on track to be processed | Old BTO order taken over from other segment. Needs technical clarification and clarification with sales. Involved team changed multiple times in both sales and delivery. | 1308 | Jysk CTS A/S | 89637 | NKA-049663 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-08-22 | 2025-06-13 | 2025-06-13 | Own OnNet | 2023-09-08 | [5 empty] | 2025-01-28 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[5 empty] | 599.94 | Jyske Bank A/S | 101491-013 | B31457-1136860-01 | 101491-013-001 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Change | [5 empty] | 2025-09-16 | [5 empty] | Change | AX
[5 empty] | 0 | Jyske Bank A/S | 101491-013 | B31457-1136861-01 | 101491-013-002 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Change | [5 empty] | 2025-09-16 | [5 empty] | Change | AX
[5 empty] | 0 | Jyske Bank A/S | 101491-013 | B31457-1136862-01 | 101491-013-003 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Change | [5 empty] | 2025-09-16 | [5 empty] | Change | AX
[5 empty] | 0 | Jyske Bank A/S | 101491-013 | B31457-1136863-01 | 101491-013-004 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Change | [5 empty] | 2025-09-16 | [5 empty] | Change | AX
[5 empty] | -160.0133 | Jyske Bank A/S | 101491-013 | C31457-1136865-01 | 101491-013-006 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Change | [5 empty] | 2025-09-16 | [5 empty] | Change | AX
[5 empty] | 60 | Jyske Bank A/S | 101491-013 | C31457-1136866-01 | 101491-013-007 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 |  |  | Own OnNet | [5 empty] | 2025-09-16 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 550 | Kalundborg kommune | 93742 | NKA-023151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-17 |  |  | Change | 2018-02-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001355 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001357 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-21 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001358 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-10 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001361 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001362 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-09-04 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001364 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001365 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001368 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-10-14 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001369 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001370 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-20 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001371 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001372 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-08-31 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001374 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001375 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001376 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001377 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-001378 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-07 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-004657 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change |  |  |  | 2025-03-03 | [7 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-004681 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-09-25 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-005732 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-10-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-005733 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-10-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-007073 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-03-06 |  |  |  |  | 2014-04-22 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-008423 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-06-16 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-008678 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-07-14 |  |  |  |  | 2014-09-08 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-015322 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-07-08 |  |  |  |  | 2016-09-02 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-015571 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:21:00.000 | 2016-08-04 16:21:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-015572 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:22:00.000 | 2016-08-04 16:22:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-015573 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:22:00.000 | 2016-08-04 16:22:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-016769 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-12-06 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-019741 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-020063 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 | 2025-06-30 | 2025-06-30 | Change | 2017-04-03 |  |  | 2025-03-31 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-021079 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-07-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-021361 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-08-25 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-021785 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-09-26 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-022148 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-10-30 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-022164 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-10-30 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-022346 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-11-14 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 25 | Kalundborg kommune | 94451 | NKA-022777 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-05 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-022923 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-19 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-022946 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-19 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-023066 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-01 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-023116 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-023151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-023194 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-16 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-024172 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-04-06 |  |  |  |  | 2018-06-08 | 2024-10-24 |  |  |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-027189 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-03-06 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-028218 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-07-16 | 2019-10-01 08:52:00.000 | 2019-10-01 08:52:00.000 | [8 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-028441 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-08-09 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-034959 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 | 2025-07-31 | 2025-07-31 | Change | 2021-06-08 | [6 empty] | 2025-07-31 | 2025-07-31 |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-034973 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2021-06-17 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 650 | Kalundborg kommune | 94451 | NKA-044605 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2022-10-18 |  |  | 2025-03-03 | [7 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 950 | Kalundborg kommune | 96656 | NKA-004657 |  | Michael Kronbach Leth | Public DK | In Process | 2024-05-29 |  |  | Change | [11 empty] | Change | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | On track | 2500 | Kilroy International A/S | 96128 | NKA-058039 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet |  |  |  | 2025-04-25 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | On track | 2500 | Kilroy International A/S | 96128 | NKA-058040 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet |  |  |  | 2025-04-25 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 30/05 | 1760 | Kk Wind Solutions A/S | 103535 | NKA-060226 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-02 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-07 | 2025-04-08 09:15:00.000 | 2025-05-02 09:09:00.000 | 2025-05-23 |  | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 560 | Kolding Kommune Rådhuset | 82944 | NKA-003429 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-27 |  |  | Change
|  | 7. Service activation | 3.1 Third party vendor delay | Waiting for installation from GC NO | -641.03 | KPMG ACOR TAX PARTNERSELSKAB | 90629 | NKA-029266 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-11-06 | 2025-06-13 | 2025-06-13 | Change | 2019-11-28 |  |  |  |  | 2020-01-17 |  | 2025-06-13 | 2025-06-13 |  | 2024-03-13 00:00:00.000 | Change | BO
|  | 7. Service activation | 3.1 Third party vendor delay | Waiting for installation from GC NO | 3366 | KPMG ACOR TAX PARTNERSELSKAB | 90629 | NKA-050904 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-11-06 | 2025-06-13 | 2025-06-13 | 3rd Party | 2023-11-16 | [6 empty] | 2025-06-13 | 2025-06-13 |  | 2024-03-13 00:00:00.000 | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Order is just a "add-on" of BGP mechanism. It's related to order ID 98424(the fiber order). |  | Kromann Reumert | 94179 | NKA-056733 |  | Peter Madsen | Enterprise DK | In Process | 2024-11-27 | 2025-07-04 | 2025-07-04 | Change | 2025-01-06 | 2025-02-20 09:54:00.000 | 2025-02-20 09:54:00.000 |  |  | 2025-06-30 |  | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Order is just a "add-on" of BGP mechanism. It's related to order ID 98424(the fiber order). |  | Kromann Reumert | 94179 | NKA-056734 |  | Peter Madsen | Enterprise DK | In Process | 2024-11-27 | 2025-07-04 | 2025-07-04 | Change | 2025-01-06 | 2025-03-27 12:59:00.000 | 2025-03-27 12:59:00.000 |  |  | 2025-06-30 |  | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | DDoS Protection order. It's dependent on delivery of the fiber on the same project ID. | 522 | Kromann Reumert | 98424 | NDD-056737 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | DDoS Protection order. It's dependent on delivery of the fiber on the same project ID. | 522 | Kromann Reumert | 98424 | NDD-056738 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 04/07 | 2720 | Kromann Reumert | 98424 | NKA-056733 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-01-06 | 2025-02-20 09:54:00.000 | 2025-02-20 09:54:00.000 | 2025-06-27 |  | 2025-06-30 | 2025-04-01 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 04/07 | 2720 | Kromann Reumert | 98424 | NKA-056734 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-01-06 | 2025-03-27 12:59:00.000 | 2025-03-27 12:59:00.000 | 2025-06-27 |  | 2025-06-30 | 2025-04-01 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 11732.5 | Københavns Kommune | 101858 | NDD-058420 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet |  |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 11732.5 | Københavns Kommune | 101858 | NDD-058422 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet |  |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 11732.5 | Københavns Kommune | 101858 | NKA-058419 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 11732.5 | Københavns Kommune | 101858 | NKA-058421 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 12015 | Københavns Kommune | 101858 | NKA-058423 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 12015 | Københavns Kommune | 101858 | NKA-058424 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 4140 | Københavns Kommune | 101858 | NKA-058425 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution | 4140 | Københavns Kommune | 101858 | NKA-058426 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1070 | Københavns Kommune | 101913 | NKA-058550 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 | 2025-06-30 | 2025-06-30 | Own OnNet | 2025-03-05 | 2025-04-11 08:11:00.000 | 2025-04-28 08:07:00.000 | 2025-05-09 |  | 2025-05-09 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 415 | Københavns Kommune | 102441 | NKA-059158 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-27 | 2025-05-28 | 2025-05-16 | Own with Digging | 2025-02-28 | 2025-04-03 08:56:00.000 | 2025-04-22 10:14:00.000 | 2025-05-23 |  | 2025-05-09 | 2025-04-24 | 2025-05-16 | 2025-05-16 | 2025-05-28 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 490 | Københavns Kommune | 105122 | NKA-060367 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-07-02 | 2025-07-02 | 3rd Party | 2025-04-15 |  |  | 2025-06-27 |  |  | 2025-05-07 | 2025-07-02 | 2025-07-02 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 490 | Københavns Kommune | 105194 | NKA-060435 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-22 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-04-22 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 960 | Københavns Kommune | 105737 | NKA-023580 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-13 | 2025-05-20 | 2025-05-20 | Change | 2018-03-08 | 2018-03-26 07:42:00.000 | 2018-03-26 07:43:00.000 |  |  | 2018-06-11 |  | 2025-05-20 | 2025-05-20 |  |  | Change | BO
[5 empty] | 550 | Københavns Kommune | 84112 | NKA-045993 |  | Michael Kronbach Leth | Public DK | In Process | 2022-12-02 | 2025-05-28 | 2025-05-28 | 3rd Party | 2022-12-06 |  |  | 2025-05-23 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055121 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-01-22 |  |  |  |  | 2025-04-04 | 2025-03-24 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055125 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-12-03 |  |  |  |  | 2025-02-14 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055126 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-12-03 | 2025-04-23 09:33:00.000 | 2025-04-28 13:20:00.000 | 2025-05-16 |  | 2025-02-14 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055128 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2024-12-03 |  |  |  |  | 2025-02-14 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055134 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-12-12 | 2025-05-01 08:40:00.000 | 2025-05-05 09:54:00.000 | 2025-05-23 |  | 2025-02-28 | 2025-05-12 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055135 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-04-23 17:32:00.000 | 2025-04-25 13:05:00.000 | 2025-05-16 |  | 2025-04-26 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055137 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-23 09:49:00.000 | 2025-04-25 14:07:00.000 | 2025-05-16 |  | 2025-04-25 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055138 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-02-14 | 2025-04-23 09:51:00.000 | 2025-04-25 14:22:00.000 | 2025-06-06 |  | 2025-04-25 | 2025-05-08 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055143 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-05-01 07:45:00.000 | 2025-05-05 12:11:00.000 | 2025-05-23 |  | 2025-04-25 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055144 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055145 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055146 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-29 |  |  |  |  | 2025-04-04 | 2025-03-24 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055147 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-29 |  |  |  |  | 2025-04-04 | 2025-03-21 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055148 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-22 |  |  |  |  | 2025-04-04 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055149 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055150 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055153 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-22 |  |  |  |  | 2025-04-04 | 2025-03-24 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055156 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-10 08:31:00.000 | 2025-04-22 15:08:00.000 | 2025-05-09 |  | 2025-04-25 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055159 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055160 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055161 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055165 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055168 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | [5 empty] | 2025-04-18 | 2025-05-01 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055170 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-05-01 08:48:00.000 | 2025-05-05 13:10:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055172 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055173 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-03-18 11:37:00.000 | 2025-03-28 13:48:00.000 |  |  | 2025-04-25 | 2025-04-02 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055174 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-05-02 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055175 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-02-21 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055176 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-02 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055177 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-05-01 08:57:00.000 | 2025-05-06 08:24:00.000 | 2025-05-23 |  | 2025-04-25 | 2025-05-12 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055178 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-02-24 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055179 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055181 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-02-14 | 2025-05-08 12:36:00.000 | 2025-05-13 09:28:00.000 | 2025-05-30 |  | 2025-04-25 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055182 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-02-14 | 2025-05-08 12:52:00.000 | 2025-05-13 10:18:00.000 | 2025-05-30 |  | 2025-04-25 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055184 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. | 1270 | Københavns Kommune | 97026 | NKA-055185 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-01 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055187 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055188 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-11 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055189 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055191 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-07 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055193 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-25 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055194 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 1270 | Københavns Kommune | 97026 | NKA-055195 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055196 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-05-01 08:02:00.000 | 2025-05-06 11:16:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055197 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-02 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055198 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055199 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-14 | 2025-04-23 16:13:00.000 | 2025-04-28 10:40:00.000 |  |  | 2025-04-25 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055201 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055202 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-11 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055203 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-15 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055204 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055206 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-30 12:39:00.000 | 2025-05-13 10:55:00.000 | 2025-05-30 |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055207 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2024-12-12 |  |  |  |  | 2025-02-28 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055208 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-15 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055212 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-02 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055215 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-15 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055216 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055217 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055218 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-10 08:20:00.000 | 2025-04-15 14:04:00.000 |  |  | 2025-04-25 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055219 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-25 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055220 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-10 08:28:00.000 | 2025-04-22 13:53:00.000 |  |  | 2025-04-25 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055221 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055222 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055224 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-30 09:31:00.000 | 2025-05-07 10:05:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055225 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-23 09:43:00.000 | 2025-04-28 12:28:00.000 |  |  | 2025-04-25 | 2025-05-08 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055226 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-19 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055227 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055228 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-15 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055229 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055230 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055232 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055233 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055234 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-14 | 2025-04-23 16:22:00.000 | 2025-04-24 09:50:00.000 |  |  | 2025-04-25 | 2025-05-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055239 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-01 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 1270 | Københavns Kommune | 97026 | NKA-055240 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2024-08-21 12:07:00.000 | 2025-02-23 21:16:00.000 | 2025-05-30 |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 12450 | Københavns Kommune | 97026 | NKA-055243 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2024-08-19 | 2024-08-21 12:06:00.000 | 2024-08-27 13:02:00.000 | 2024-10-15 |  | 2024-09-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 12450 | Københavns Kommune | 97026 | NKA-055244 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2024-08-19 | 2024-08-21 12:11:00.000 | 2024-08-27 13:02:00.000 | 2024-10-15 |  | 2024-09-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 12300 | Københavns Kommune | 97026 | NKA-055245 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2024-08-19 | 2024-08-21 12:07:00.000 | 2024-08-27 13:04:00.000 | 2024-10-22 |  | 2024-09-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer datoer, svar på gravetilladelser og installation | 12300 | Københavns Kommune | 97026 | NKA-055246 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2024-08-19 | 2024-08-21 12:09:00.000 | 2024-08-27 13:04:00.000 | 2024-10-22 |  | 2024-09-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 288.56 | Lagkagehuset A/S | 105224 | NBM-060528 |  | Flemming Skovdal | Enterprise DK | In Process | 2025-04-29 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | -528 | LEGO System A/S | 101442-031 | C31408-1131198-01 | 101442-031-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-09-19 | 2025-06-06 |  | Change | [5 empty] | 2024-11-25 |  |  | 2025-06-06 | 2025-06-06 |  | Change | AX
[5 empty] | 1100 | LEGO System A/S | 101442-033 | C31408-1133379-01 | 101442-033-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-16 | 2025-06-06 |  | Own with Digging | [5 empty] | 2025-02-26 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 176 | LEGO System A/S | 101442-033 | C31408-1133380-01 | 101442-033-002 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-16 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-02-26 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 50 | LEGO System A/S | 101442-033 | C31408-1133382-01 | 101442-033-004 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-16 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-02-26 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 1100 | LEGO System A/S | 101442-033 | C31408-1133383-01 | 101442-033-005 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-16 | 2025-06-06 |  | Own with Digging | [5 empty] | 2025-02-26 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 50 | LEGO System A/S | 101442-033 | C31408-1133385-01 | 101442-033-007 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-16 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-02-26 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102732 | NKA-058938 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-03 |  |  | 2025-05-09 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102732 | NKA-058939 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-03 |  |  | 2025-05-09 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 1750 | Lidl Danmark K/S | 102865 | NGF-059283 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-05 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-04-24 | [5 empty] | 2025-03-05 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 1815 | Lidl Danmark K/S | 102937 | NDD-059641 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059307 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-04-16 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059308 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059309 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059310 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059311 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059312 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059313 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059314 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059315 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059316 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059317 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059318 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059319 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059320 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059321 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059322 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059323 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059324 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059325 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059326 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059327 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059328 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059329 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059330 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059331 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059332 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059333 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-22 | 2025-04-22 14:12:00.000 | 2025-04-23 18:04:00.000 | 2025-05-16 |  |  | 2025-05-05 | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059334 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-22 | 2025-04-22 14:11:00.000 | 2025-04-23 18:05:00.000 | 2025-05-16 |  |  |  | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059335 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059336 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059337 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-16 | 2025-05-16 | 3rd Party | [7 empty] | 2025-05-16 | 2025-05-16 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059338 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059339 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [10 empty] | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059340 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059341 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-04-22 | 2025-04-25 07:21:00.000 | 2025-05-08 10:57:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059342 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-22 | 2025-04-25 07:20:00.000 | 2025-05-08 11:08:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059343 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059344 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059345 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 | [6 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059346 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 | [6 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059347 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059348 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059349 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-28 13:25:00.000 | 2025-05-01 11:13:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059350 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-28 13:25:00.000 | 2025-05-01 11:13:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059351 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059352 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059353 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-05-12 10:09:00.000 |  | 2025-06-20 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059354 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-05-12 10:09:00.000 |  | 2025-06-20 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059355 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059356 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059357 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059358 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059359 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-21 | 2025-05-05 09:58:00.000 | 2025-05-06 09:46:00.000 | 2025-05-16 |  | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059360 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-21 | 2025-05-05 09:57:00.000 | 2025-05-06 09:48:00.000 | 2025-05-16 |  | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059361 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059362 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059363 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-03-27 08:54:00.000 | 2025-04-15 13:20:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059364 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-03-27 08:56:00.000 | 2025-04-15 13:37:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059365 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059366 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059367 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059368 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059369 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059370 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059371 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-04-14 19:52:00.000 | 2025-04-30 13:41:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059372 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-14 19:50:00.000 | 2025-04-30 13:42:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059373 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059374 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059375 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059376 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059377 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 |  |  |  |  | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059378 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 |  |  |  |  | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059379 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059380 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059381 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059382 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059383 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059384 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059385 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059386 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059387 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059388 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059389 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059390 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059391 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059392 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059393 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059394 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059395 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-07 14:17:00.000 | 2025-04-09 10:12:00.000 | 2025-05-05 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059396 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-15 | 2025-04-07 14:17:00.000 | 2025-04-09 10:05:00.000 | 2025-05-05 |  |  | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059397 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059398 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059399 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059400 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059401 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059402 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059403 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059404 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059405 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059406 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059407 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059408 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059409 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059410 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059411 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059412 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059413 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059414 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059415 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059416 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059417 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059418 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059419 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059420 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059421 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059422 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059423 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059424 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059425 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-05 14:20:00.000 | 2025-05-23 |  | 2025-05-23 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059426 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-06 07:46:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059427 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059428 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059429 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059430 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059431 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059432 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059433 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059434 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059435 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059436 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059437 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059438 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059439 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059440 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059441 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059442 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059443 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059444 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059445 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059446 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059447 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059448 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059449 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-04-10 | 2025-04-11 11:33:00.000 |  | 2025-08-08 |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059450 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-04-10 | 2025-04-11 11:32:00.000 |  | 2025-08-04 |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059451 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059452 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059453 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-30 | 2025-05-12 12:38:00.000 | 2025-05-14 08:50:00.000 | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059454 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-04-30 | 2025-05-12 12:37:00.000 | 2025-05-14 08:51:00.000 | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059455 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059456 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059457 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059458 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059459 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059460 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059461 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059462 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059463 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059464 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059465 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059466 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059467 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059468 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059469 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-07 14:41:00.000 | 2025-04-07 14:41:00.000 | 2025-05-13 |  | 2025-05-23 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059470 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-07 14:41:00.000 | 2025-04-07 14:42:00.000 | 2025-05-13 |  | 2025-05-23 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059471 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059472 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059473 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-14 18:41:00.000 | 2025-05-01 07:28:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059474 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-04-14 18:42:00.000 | 2025-05-01 07:29:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059475 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059476 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059477 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  | 2025-04-09 08:38:00.000 |  |  |  |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059478 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  | 2025-04-09 08:37:00.000 |  |  |  |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059479 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059480 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059481 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059482 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059483 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059484 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059485 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059486 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059487 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-03-24 | 2025-05-12 09:07:00.000 |  | 2025-06-20 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059488 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-03-24 | 2025-05-12 09:06:00.000 |  | 2025-06-20 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059489 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059490 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059491 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059492 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059493 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059494 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059495 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-04-29 14:46:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059496 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-04-29 14:46:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059497 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059498 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059499 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059500 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059501 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059502 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059503 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059504 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059505 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059506 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059507 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059508 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059509 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059510 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059511 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059512 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059513 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059514 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059515 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059516 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059517 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059518 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059519 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-04-09 09:52:00.000 | 2025-04-24 08:29:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059520 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-09 09:53:00.000 | 2025-04-24 08:28:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059521 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party |  |  |  | 2025-05-14 |  |  |  | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059522 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party |  |  |  | 2025-05-13 |  |  |  | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059523 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059524 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059525 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059526 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059527 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059528 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059529 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059530 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059531 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059532 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059533 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059534 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059535 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party |  |  |  | 2025-05-14 |  |  |  | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059536 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party |  |  |  | 2025-05-14 |  |  |  | 2025-05-23 | 2025-05-23 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059537 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059538 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059539 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059540 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059541 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-03-21 | 2025-05-12 12:10:00.000 |  | 2025-06-27 |  | 2025-05-30 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059542 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-03-21 | 2025-05-12 12:11:00.000 |  | 2025-06-27 |  | 2025-05-30 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059543 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059544 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059545 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059546 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059547 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059548 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059549 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059550 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059551 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059552 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059553 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059554 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059555 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059556 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059557 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059558 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059559 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059560 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059561 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059562 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059563 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059564 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059565 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059566 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059567 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059568 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059569 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-21 | 2025-04-14 20:39:00.000 | 2025-04-30 12:40:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059570 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-14 | 2025-04-14 20:41:00.000 | 2025-04-30 12:41:00.000 | 2025-05-23 |  |  |  | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059571 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059572 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059573 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-28 | 2025-04-30 10:19:00.000 |  | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059574 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-04-28 | 2025-04-30 10:20:00.000 |  | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059575 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059576 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059577 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059578 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059579 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059580 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059581 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059582 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059583 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-05-14 08:49:00.000 |  | 2025-06-27 |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059584 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-05-14 08:49:00.000 |  | 2025-06-27 |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059585 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059586 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059587 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-04-09 11:44:00.000 | 2025-04-24 13:04:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059588 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-09 11:45:00.000 | 2025-04-24 13:04:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059589 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059590 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059591 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-04-30 10:51:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059592 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-04-30 10:51:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059593 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059594 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059595 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059596 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059597 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party |  |  | 2025-04-30 10:26:00.000 |  |  |  |  | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059598 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059599 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059600 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059601 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059602 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059603 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-24 | 2025-05-01 09:47:00.000 | 2025-05-06 10:15:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059604 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-24 | 2025-05-01 09:48:00.000 | 2025-05-06 10:16:00.000 | 2025-05-23 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059605 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059606 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059607 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-24 | 2025-04-28 12:49:00.000 | 2025-05-01 13:48:00.000 | 2025-05-23 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059608 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-24 | 2025-04-28 12:48:00.000 | 2025-05-01 13:49:00.000 | 2025-05-23 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059609 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059610 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059611 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059612 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059613 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-05-06 10:35:00.000 |  | 2025-06-13 |  | 2025-05-23 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059614 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-05-06 10:36:00.000 |  | 2025-06-13 |  | 2025-05-23 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059617 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059618 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059619 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059620 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059621 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059622 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059623 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059624 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059625 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059626 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059627 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059628 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059629 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059630 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 850 | Lidl Danmark K/S | 102937 | NKA-059631 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 800 | Lidl Danmark K/S | 102937 | NKA-059632 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 1800 | Lidl Danmark K/S | 102937 | NKA-059635 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-11 | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | 2025-05-02 |  |  |  | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | PMO | 1800 | Lidl Danmark K/S | 102937 | NKA-059636 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | Own OnNet |  | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | 2025-05-02 |  |  |  | 2025-05-23 | 2025-05-23 |  | 2025-05-02 00:00:00.000 | New Sales | BO
[5 empty] | 850 | Lidl Danmark K/S | 105410 | NKA-060548 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party |  |  | 2025-05-01 07:40:00.000 | [8 empty] | New Sales | BO
[5 empty] | 800 | Lidl Danmark K/S | 105410 | NKA-060549 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | On Track | On Track | On Track | 1355 | Light Brick A/S | 105384 | NKA-044433 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-04-28 |  |  | Change | 2022-08-05 | 2022-08-12 08:24:00.000 | 2022-08-12 08:23:00.000 |  |  |  | 2025-04-29 |  |  |  |  | Change | BO
[5 empty] | 1250 | Lokaltog A/S | 101174-010 | C31138-1130914-01 | 101174-010-001 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-23 | 2025-05-23 | Own with Digging |  |  |  | 2025-05-23 |  | 2024-11-07 | 2025-02-17 | 2025-05-23 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 1400 | Lokaltog A/S | 101174-010 | C31138-1130918-01 | 101174-010-005 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-23 | 2025-05-23 | Own with Digging |  |  |  | 2025-05-23 |  | 2024-11-07 |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 0 | Lokaltog A/S | 101174-010 | C31138-1130920-01 | 101174-010-007 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-23 | 2025-05-23 | Own OnNet |  |  |  | 2025-05-23 |  | 2024-11-07 |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 0 | Lokaltog A/S | 101174-010 | C31138-1130921-01 | 101174-010-008 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-23 | 2025-05-23 | Own OnNet |  |  |  | 2025-05-23 |  | 2024-11-07 |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1395 | Lundsøe Køl & Frys A/S | 104921 | NKA-060342 |  | Line Skov | Enterprise DK | In Process | 2025-04-10 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-11 | 2025-04-14 10:32:00.000 | 2025-04-29 11:17:00.000 | 2025-05-23 |  | 2025-06-06 | 2025-04-30 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 2835 | MAERSK A/S | 107525-005 | C36565-1135209-01 | 107525-005-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-11 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-06-11 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 4200 | MAERSK A/S | 107525-005 | C36565-1135211-01 | 107525-005-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-11 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-06-11 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1000 | Meyers A/S | 105620 | NKA-060667 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 06/06 | 2140 | Molslinjen A/S | 104668 | NKA-059995 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-26 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-28 | 2025-04-24 09:08:00.000 | 2025-05-07 13:14:00.000 | 2025-05-30 |  | 2025-05-30 | 2025-05-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 1452 | Munck Havne & Anlæg A/S | 104526 | NKA-060249 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-03 |  |  | 3rd Party | 2025-04-10 |  |  | 2025-07-18 |  | 2025-07-11 | 2025-04-23 |  |  |  |  | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Not Complete ordre i BO | -982.5 | Næstved Kommune | 79364 | NKA-006801 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-05-30 | 2025-05-30 | Change | 2014-01-22 |  |  |  |  | 2014-03-07 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Not Complete ordre i BO | -982.5 | Næstved Kommune | 79364 | NKA-007204 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-05-30 | 2025-05-30 | Change | 2014-03-24 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Not Complete ordre i BO | 650 | Næstved Kommune | 79364 | NSW-041184 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Not Complete ordre i BO | 650 | Næstved Kommune | 79364 | NSW-041185 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1237 | Nagel Danmark A/S | 98152 | NKA-056844 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-10-18 | 2025-06-13 | 2025-06-13 | Own OnNet | 2024-11-01 | 2025-04-08 13:27:00.000 | 2025-05-09 10:22:00.000 | 2025-06-06 |  | 2025-01-17 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1237 | Nagel Danmark A/S | 98152 | NKA-056845 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-10-18 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-11-01 | 2025-04-08 13:29:00.000 | 2025-05-09 11:51:00.000 | 2025-06-06 |  | 2025-01-17 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136120-01 | 103690-003-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136122-01 | 103690-003-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136124-01 | 103690-003-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own with Digging | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136126-01 | 103690-003-007 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136128-01 | 103690-003-009 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 1255 | Naviair | 103690-003 | C33271-1136130-01 | 103690-003-011 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Order is on track | 1700 | NCC Danmark A/S | 101119-042 | C31083-1135942-01 | 101119-042-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-03 | 2025-07-18 |  | 3rd Party | [5 empty] | 2025-06-26 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 9. Documentation and vendor invoice | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting redoc from provisioning | 0 | NCC Danmark A/S | 101119-042 | C31083-1135943-01 | 101119-042-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-03 | 2025-07-18 |  | Own OnNet | [5 empty] | 2025-06-26 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
[5 empty] | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133207-01 | 101045-063-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133208-01 | 101045-063-002 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own OnNet | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | 5850 | Nets Danmark A/S | 101045-063 | C31009-1133210-01 | 101045-063-004 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | 5850 | Nets Danmark A/S | 101045-063 | C31009-1133211-01 | 101045-063-005 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133213-01 | 101045-063-007 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133215-01 | 101045-063-009 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own OnNet | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
[5 empty] | -276.7733 | Nets Danmark A/S | 101045-064 | C31009-1133291-01 | 101045-064-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-10 | 2025-06-06 |  | Change | [5 empty] | 2025-02-26 | 2025-01-31 |  | 2025-06-06 | 2025-06-06 |  | Change | AX
[5 empty] | -206.7167 | Nets Danmark A/S | 101045-064 | C31009-1133293-01 | 101045-064-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-10 | 2025-06-06 |  | Change | [5 empty] | 2025-02-26 | 2025-01-31 |  | 2025-06-06 | 2025-06-06 |  | Change | AX
[5 empty] | -206.7167 | Nets Danmark A/S | 101045-064 | C31009-1133295-01 | 101045-064-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-10 | 2025-06-06 |  | Change | [5 empty] | 2025-02-26 | 2025-01-31 |  | 2025-06-06 | 2025-06-06 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Kunden ønsker denne haste leveret | 4900 | NIC. CHRISTIANSEN GRUPPEN A/S | 106520-010 | C35716-1135836-01 | 106520-010-001 | Michael Kronbach Leth | Enterprise DK | In Process | 2025-03-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-06-04 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Lav prioritet hos kunden | 4900 | NIC. CHRISTIANSEN GRUPPEN A/S | 106520-010 | C35716-1135838-01 | 106520-010-003 | Michael Kronbach Leth | Enterprise DK | In Process | 2025-03-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-06-04 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 3025 | NIRAS A/S | 100351 | NKA-057331 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-11-12 | 2025-06-27 | 2025-06-27 | Own with Digging | 2024-02-13 | 2025-02-20 09:56:00.000 | 2025-02-20 09:56:00.000 | 2025-06-27 |  | 2024-11-14 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[5 empty] | 3025 | NIRAS A/S | 100351 | NKA-057332 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-11-12 | 2025-06-27 | 2025-06-27 | Own with Digging | 2024-11-13 | 2025-03-27 11:46:00.000 | 2025-03-27 11:46:00.000 | 2025-06-27 |  | 2024-02-14 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[5 empty] | 1500 | Norconsult Danmark A/S | 102343 | NOC-997145 |  | Peter Madsen | Enterprise DK | In Process | 2025-02-24 | 2025-05-28 | 2025-05-28 | Change | 2020-12-07 | [6 empty] | 2025-05-28 | 2025-05-28 |  |  | Change | BO
[5 empty] | 400 | Norddjurs Kommune | 77244 | NKA-022194 |  | Morten Skytte | Public DK | In Process | 2021-12-28 |  |  | Change
|  | 7. Service activation |  | Awating SW error correction | 3149.11 | Norddjurs Kommune | 77244 | NKA-022216 |  | Morten Skytte | Public DK | In Process | 2021-12-28 | 2025-05-16 | 2025-03-28 | Change | 2017-10-23 | 2017-12-04 15:58:00.000 | 2017-12-04 15:58:00.000 |  |  |  | 2024-09-20 | 2025-03-28 | 2025-03-28 | 2025-05-16 | 2025-02-28 00:00:00.000 | Change | BO
|  | 7. Service activation |  | Awating SW error correction | -3400 | Norddjurs Kommune | 77244 | NKA-022217 |  | Morten Skytte | Public DK | In Process | 2021-12-28 | 2025-05-16 | 2025-03-28 | Change | 2017-10-23 | 2018-01-02 09:41:00.000 | 2018-01-02 09:41:00.000 |  |  |  | 2024-09-20 | 2025-03-28 | 2025-03-28 | 2025-05-16 |  | Change | BO
|  | 7. Service activation |  | Awating SW error correction | 457.5 | Norddjurs Kommune | 77244 | NKA-027063 |  | Morten Skytte | Public DK | In Process | 2021-12-28 | 2025-05-23 | 2024-12-06 | Change | 2019-03-07 |  |  | 2024-03-06 |  |  |  | 2024-12-06 | 2024-12-06 | 2025-05-23 |  | Change | BO
[5 empty] | 325 | Norddjurs Kommune | 77244 | NSW-039758 |  | Morten Skytte | Public DK | In Process | 2021-12-28 |  |  | Own OnNet
|  | 7. Service activation |  | Awating SW error correction | 455 | Norddjurs Kommune | 77244 | NSW-039804 |  | Morten Skytte | Public DK | In Process | 2021-12-28 | 2025-05-23 | 2024-12-06 | Own OnNet | [7 empty] | 2024-12-06 | 2024-12-06 | 2025-05-23 |  | New Sales | BO
|  | 7. Service activation |  | Awating SW error correction | 30 | Norddjurs Kommune | 87005 | NMA-047419 |  | Morten Skytte | Public DK | In Process | 2023-03-30 | 2025-05-23 | 2024-12-02 | 3rd Party | [7 empty] | 2024-12-02 | 2024-12-02 | 2025-05-23 |  | New Sales | BO
[5 empty] | -19882.52 | Nordstern ApS | 104653 | NBM-057421 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-05-05 | 2025-05-23 | 2025-05-23 | Change | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | Change | BO
[5 empty] | 765 | Normal A/S | 105629 | NKA-060630 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-07 |  |  | Own with Digging | 2025-05-07 |  |  |  |  | 2025-06-18 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues |  | 1050 | NOVO NORDISK A/S | 100573 | NDD-057468 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-21 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues |  | 1050 | NOVO NORDISK A/S | 100573 | NKA-057467 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-21 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-046207 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2022-12-22 | 2023-01-06 07:39:00.000 | 2023-01-06 07:40:00.000 | [8 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-046208 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2022-12-22 | 2023-01-06 07:41:00.000 | 2023-01-06 07:41:00.000 | [8 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-046263 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-01-02 | 2023-01-12 09:34:00.000 | 2023-01-12 09:34:00.000 |  |  | 2023-02-10 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-046264 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-01-02 | 2023-01-17 13:07:00.000 | 2023-01-17 13:07:00.000 |  |  | 2023-03-03 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-047446 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-04-03 | 2023-06-23 14:32:00.000 | 2023-06-23 14:32:00.000 | [8 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-047447 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-04-03 | 2023-06-23 14:32:00.000 | 2023-06-23 14:32:00.000 | [8 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-047864 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-04-27 | 2023-08-30 10:47:00.000 | 2023-08-30 10:47:00.000 |  |  | 2023-06-30 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-047865 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-04-27 |  |  |  |  | 2023-06-30 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-051434 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-12-12 | 2023-12-19 08:49:00.000 | 2023-12-19 08:50:00.000 | [8 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-051435 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2023-12-12 |  |  |  |  | 2024-02-09 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-052794 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-01-12 | 2024-03-26 10:10:00.000 | 2024-03-26 10:10:00.000 |  |  | 2024-05-31 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-052796 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-01-17 | 2024-03-26 10:11:00.000 | 2024-03-26 10:11:00.000 |  |  | 2024-05-24 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053331 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-02-16 | 2024-03-01 11:06:00.000 | 2024-03-01 11:06:00.000 |  |  | 2024-03-15 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053332 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-02-16 | 2024-03-11 10:16:00.000 | 2024-03-11 10:17:00.000 |  |  | 2024-04-26 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053336 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-02-16 | 2024-05-23 08:10:00.000 | 2024-05-23 08:10:00.000 |  |  | 2024-05-31 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053337 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-02-16 | 2024-05-23 08:11:00.000 | 2024-05-23 08:11:00.000 |  |  | 2024-05-31 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053465 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-03-04 | 2024-03-19 10:53:00.000 | 2024-03-19 10:53:00.000 |  |  | 2024-04-12 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053467 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-03-04 | 2024-03-19 10:52:00.000 | 2024-03-19 10:52:00.000 |  |  | 2024-04-12 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053469 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-03-04 | 2024-03-18 12:06:00.000 |  |  |  | 2024-03-27 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-053470 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-03-04 | 2024-03-18 12:06:00.000 |  |  |  | 2024-03-27 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-054177 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-04-24 | 2024-06-03 10:37:00.000 | 2024-06-07 09:17:00.000 |  |  | 2024-07-05 | [5 empty] | Change | BO
[6 empty] | NOVO NORDISK A/S | 102134 | NKA-054178 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-01-30 |  |  | Change | 2024-04-24 | 2024-06-03 10:39:00.000 | 2024-06-27 13:41:00.000 |  |  | 2024-07-05 | [5 empty] | Change | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 102632 | NDD-059037 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2025-06-06 |  |  |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 102632 | NDD-059038 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2025-06-06 |  |  |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 102632 | NKA-059035 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2025-03-03 | 2025-04-07 14:45:00.000 |  | 2025-06-06 |  | 2025-06-13 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 102632 | NKA-059036 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2025-03-03 | 2025-05-01 12:37:00.000 |  | 2025-06-06 |  | 2025-09-05 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059181 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:35:00.000 | 2025-04-02 10:36:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059182 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:59:00.000 | 2025-04-02 10:59:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059183 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:36:00.000 | 2025-04-02 10:36:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059184 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:00:00.000 | 2025-04-02 11:00:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059185 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:37:00.000 | 2025-04-02 10:37:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059186 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:00:00.000 | 2025-04-02 11:00:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059187 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:38:00.000 | 2025-04-02 10:38:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059188 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:01:00.000 | 2025-04-02 11:01:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059189 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:38:00.000 | 2025-04-02 10:39:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059190 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:02:00.000 | 2025-04-02 11:02:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059191 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:39:00.000 | 2025-04-02 10:39:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059192 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:34:00.000 | 2025-04-02 11:34:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059193 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:41:00.000 | 2025-04-02 10:41:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059194 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:28:00.000 | 2025-04-02 13:29:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059195 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:41:00.000 | 2025-04-02 10:42:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059196 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:29:00.000 | 2025-04-02 13:29:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059197 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:42:00.000 | 2025-04-02 10:43:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059198 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:30:00.000 | 2025-04-02 13:30:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059199 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:43:00.000 | 2025-04-02 10:43:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059200 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:30:00.000 | 2025-04-02 13:30:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059201 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:44:00.000 | 2025-04-02 10:45:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059202 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:31:00.000 | 2025-04-02 13:31:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059203 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:49:00.000 | 2025-04-02 10:50:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059204 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:32:00.000 | 2025-04-02 13:32:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059205 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:50:00.000 | 2025-04-02 10:50:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059206 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:33:00.000 | 2025-04-02 13:33:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059207 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:51:00.000 | 2025-04-02 10:51:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059208 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:33:00.000 | 2025-04-02 13:34:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059209 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:51:00.000 | 2025-04-02 10:52:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059210 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:34:00.000 | 2025-04-02 13:35:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059211 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:52:00.000 | 2025-04-02 10:52:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059212 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:35:00.000 | 2025-04-02 13:35:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059213 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:53:00.000 | 2025-04-02 10:53:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059214 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:41:00.000 | 2025-04-02 13:42:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059215 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:56:00.000 | 2025-04-02 10:56:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 450 | NOVO NORDISK A/S | 102754 | NSF-059216 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-03 | 2025-04-02 13:42:00.000 | 2025-04-02 13:42:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 103433 | NDD-059734 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-03-12 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 103433 | NDD-059735 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-03-12 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 103433 | NKA-059732 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-03-12 |  |  | Own with Digging | 2025-03-17 | [10 empty] | New Sales | BO
[5 empty] | 4525 | NOVO NORDISK A/S | 103433 | NKA-059733 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-03-12 |  |  | Own with Digging | 2025-03-17 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 4308 | NOVO NORDISK A/S | 104162-014 | F33710-1123338-01 | 104162-014-012 | Henrik Møller Fyhn | Enterprise DK | In Process | 2023-10-18 | 2025-06-26 | 2025-01-06 | Own OnNet |  |  |  | 2024-06-07 |  | 2023-11-24 |  | 2025-01-06 | 2025-06-26 | 2025-06-26 |  | New Sales | AX
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 4550 | NOVO NORDISK A/S | 95116 | NDD-053971 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-04-05 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2024-05-22 |  |  | 2024-05-29 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 4550 | NOVO NORDISK A/S | 95116 | NKA-053970 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-04-05 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-04-09 | 2024-05-28 14:41:00.000 | 2024-04-15 13:22:00.000 | 2024-05-22 |  | 2024-05-03 | 2024-05-29 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 0 | NOVO NORDISK A/S | 96292 | NDD-051424 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Change | [6 empty] | 2025-02-24 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 500 | NOVO NORDISK A/S | 96292 | NDD-057882 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Own OnNet | [6 empty] | 2025-02-25 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 0 | NOVO NORDISK A/S | 96292 | NKA-051423 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Change | 2023-12-13 | 2024-03-22 07:55:00.000 | 2024-03-22 07:55:00.000 |  |  | 2024-04-26 |  | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 1895 | NOVO NORDISK A/S | 96292 | NKA-057881 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Own with Digging | 2024-12-19 | 2025-05-09 07:21:00.000 | 2025-05-12 10:22:00.000 | 2025-05-30 |  | 2025-02-28 | 2025-05-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 2000 | NOVO NORDISK A/S | 96443 | NDD-054872 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  | 2025-02-05 00:00:00.000 | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 2000 | NOVO NORDISK A/S | 96443 | NDD-054873 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 7100 | NOVO NORDISK A/S | 96443 | NKA-054870 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2024-06-28 | 2024-09-04 11:04:00.000 | 2024-09-04 11:04:00.000 | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  | 2025-02-05 00:00:00.000 | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 7100 | NOVO NORDISK A/S | 96443 | NKA-054871 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2024-06-28 | 2024-09-04 11:03:00.000 | 2024-09-04 11:03:00.000 | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 1185 | NOVO NORDISK A/S | 98339 | NKA-056001 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-08-29 | 2025-06-06 | 2025-06-06 | 3rd Party | 2024-09-13 |  |  |  |  | 2024-12-13 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 4550 | NOVO NORDISK A/S | 98917 | NDD-057021 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own OnNet |  |  |  | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 4550 | NOVO NORDISK A/S | 98917 | NDD-057022 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own OnNet |  |  |  | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 4550 | NOVO NORDISK A/S | 98917 | NKA-057019 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-11-06 | 2024-11-13 15:44:00.000 | 2024-11-15 13:15:00.000 | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready |  | 4550 | NOVO NORDISK A/S | 98917 | NKA-057020 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-11-06 | 2024-11-13 15:44:00.000 | 2024-11-19 09:55:00.000 | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1596 | Novozymes A/S | 103672-023 | F33253-1136084-01 | 103672-023-001 | Shazia Mobin | Enterprise DK | Created | 2025-04-08 | 2025-07-04 |  | Own with Digging | [5 empty] | 2025-06-29 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 2047 | Novozymes A/S | 103672-023 | F33253-1136086-01 | 103672-023-003 | Shazia Mobin | Enterprise DK | Created | 2025-04-08 | 2025-07-04 |  | Own with Digging | [5 empty] | 2025-06-29 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | On Track | On Track | On Track | 329.5 | Nymølle Stenindustrier A/S | 102906 | NKA-059045 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-21 |  |  | Own OnNet | 2025-03-03 |  |  |  |  | 2025-05-02 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | On Track | On Track | On Track | 329.5 | Nymølle Stenindustrier A/S | 102906 | NML-059044 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-21 |  |  | 3rd Party | [5 empty] | 2025-05-02 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060274 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | Own OnNet | 2025-05-14 |  |  |  |  | 2025-12-01 |  | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060276 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060278 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060280 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-08 | 2025-05-02 13:30:00.000 | 2025-05-14 09:02:00.000 | 2025-06-06 |  | 2025-05-30 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060282 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060284 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-04-08 | 2025-05-14 13:57:00.000 |  | 2025-06-13 |  | 2025-05-30 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060286 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060288 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060290 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060292 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060294 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060275 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | 3rd Party | [7 empty] | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060277 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060279 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060281 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  |  | 2025-06-06 |  |  |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060283 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060285 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  |  | 2025-06-13 |  |  |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060287 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060289 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060291 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060293 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060295 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | -1091.3833 | Region Midtjylland | 100464-018 | C30130-1136192-01 | 100464-018-003 | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-05-28 |  | Change | [5 empty] | 2025-07-02 |  |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 0 | Region Midtjylland | 100464-018 | F30130-1136190-01 | 100464-018-001 | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | Change |  |  |  | 2025-05-23 |  | 2025-07-02 |  | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 4750 | Region Sjælland | 92989 | NGF-052964 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-22 | 2025-06-30 | 2025-06-30 | Own with Digging | 2024-11-25 | 2025-01-10 12:15:00.000 | 2025-01-24 09:45:00.000 |  |  | 2025-02-07 | 2024-01-22 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[5 empty] | 29500 | Region Syddanmark | 100730-063 | C30693-1109649-01 | 100730-063-001 | Michael Kronbach Leth | Public DK | In Process | 2022-02-15 | 2025-08-22 |  | Own with Digging | [5 empty] | 2022-10-01 |  |  | 2025-08-22 | 2025-08-22 |  | New Sales | AX
[5 empty] | 29500 | Region Syddanmark | 100730-063 | C30693-1109650-01 | 100730-063-002 | Michael Kronbach Leth | Public DK | In Process | 2022-02-15 | 2025-06-13 |  | Own with Digging | [5 empty] | 2022-10-01 |  |  | 2025-06-13 | 2025-06-13 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 8490 | Region Syddanmark | 100730-079 | C30693-1134744-01 | 100730-079-001 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 |  | Change | [5 empty] | 2025-05-05 | 2025-04-14 |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 8490 | Region Syddanmark | 100730-079 | C30693-1134746-01 | 100730-079-003 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 |  | Change | [5 empty] | 2025-05-05 | 2025-04-14 |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 332 | Region Syddanmark | 105413 | NKA-060524 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-29 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-29 |  |  | 2025-06-20 |  | 2025-06-11 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136336-01 | 105762-006-001 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136337-01 | 105762-006-002 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136338-01 | 105762-006-003 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136339-01 | 105762-006-004 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136340-01 | 105762-006-005 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136341-01 | 105762-006-006 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136342-01 | 105762-006-007 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136343-01 | 105762-006-008 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136344-01 | 105762-006-009 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136345-01 | 105762-006-010 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136346-01 | 105762-006-011 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136347-01 | 105762-006-012 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136348-01 | 105762-006-013 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136349-01 | 105762-006-014 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136350-01 | 105762-006-015 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136351-01 | 105762-006-016 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136352-01 | 105762-006-017 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136353-01 | 105762-006-018 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136354-01 | 105762-006-019 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | BTO solution | 0 | Rigspolitiet | 105762-006 | C35135-1136355-01 | 105762-006-020 | Michael Kronbach Leth | Public DK | Created | 2025-04-22 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-05-07 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 3350 | Roskilde Kommune | 102148 | NKA-001880 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 |  |  | Change | 2025-05-02 | 2025-05-02 13:40:00.000 | 2025-05-07 10:20:00.000 | 2025-05-23 |  | 2025-05-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 3200 | Roskilde Kommune | 102148 | NKA-019998 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 |  |  | Change | 2017-03-23 | 2017-05-02 11:25:00.000 | 2017-05-02 11:25:00.000 | [8 empty] | Change | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060649 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060650 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060651 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060652 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060653 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060654 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 1199 | Røverkøb A/S | 105266 | NKA-060655 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-05-09 | [6 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060656 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060657 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060658 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060659 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060660 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060661 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060662 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060663 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060664 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060665 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[5 empty] | 669 | Røverkøb A/S | 105266 | NKA-060666 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | Samsøe & Samsøe Whole Sale ApS | 105439 | NKA-043240 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2025-04-29 | 2025-05-28 | 2025-05-28 | Change | 2022-08-23 | 2022-10-14 07:26:00.000 |  | 2025-05-23 |  | 2022-10-07 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Awaits permit from building owner | 6710 | Samsøe & Samsøe Whole Sale ApS | 80781 | NKA-042995 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2022-06-07 | 2025-12-31 | 2025-12-31 | 3rd Party | 2022-10-03 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Scafold is blocking the entrance to the shop | 5050 | Samsøe & Samsøe Whole Sale ApS | 97292 | NKA-055088 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2024-06-26 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-02-19 |  |  |  |  | 2024-12-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Awaits permit from building owner | 4125 | Samsøe & Samsøe Whole Sale ApS | 97335 | NKA-055099 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2024-06-26 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-06-24 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 1850 | Schou Company A/S | 106496-012 | C35697-1136317-01 | 106496-012-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 | 2025-07-18 |  | Own with Digging | [5 empty] | 2025-07-09 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 60 | Schou Company A/S | 106496-012 | C35697-1136318-01 | 106496-012-002 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 | 2025-07-18 |  | Own OnNet | [5 empty] | 2025-07-09 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 1850 | Schou Company A/S | 106496-012 | C35697-1136320-01 | 106496-012-004 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 | 2025-07-18 |  | Own with Digging | [5 empty] | 2025-07-09 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning | 750 | SDI Media A/S | 93136 | NKA-052897 |  | Merete Helme | Enterprise DK | In Process | 2024-01-15 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-01-16 | 2024-01-18 09:32:00.000 | 2024-01-18 09:39:00.000 | 2024-03-15 |  | 2024-02-09 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | OpenNet had internal Delay - refused to inform reason. | 2600 | Semco Maritime A/S | 101823 | NKA-058912 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-13 |  |  | 3rd Party | 2025-02-13 |  |  | 2025-06-06 |  | 2025-05-27 | 2025-03-24 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | OpenNet had internal Delay - refused to inform reason. | 1950 | Semco Maritime A/S | 93328 | NKA-056039 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-08 |  |  | 2025-06-06 |  | 2025-03-13 | 2025-04-25 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Can't get proper information from customer | 1100 | Semco Maritime A/S | 93328 | NKA-056041 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | Own with Digging | 2025-02-10 | 2025-02-11 11:46:00.000 | 2025-03-05 14:21:00.000 |  |  | 2025-05-09 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Can't get proper information from customer | 1500 | Semco Maritime A/S | 93328 | NKA-056043 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | Own with Digging | 2025-02-10 | 2025-02-11 11:46:00.000 | 2025-03-05 14:47:00.000 |  |  | 2025-05-09 | 2025-03-14 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Miscommunication delaying delivery | 4400 | Semco Maritime A/S | 93328 | NKA-056051 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | Cancelled | Cancelled | Cancelled | 3080 | Semco Maritime A/S | 93328 | NKA-056053 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | Site survey passed on 16/04 | 3080 | Semco Maritime A/S | 93328 | NKA-056054 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | On Track | On Track | 3080 | Semco Maritime A/S | 93328 | NKA-056055 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 2375 | Skanderborg Kommune | 100219 | NKA-057799 |  | Michael Kronbach Leth | Public DK | In Process | 2024-12-10 | 2025-06-02 | 2025-06-02 | Own OnNet | 2024-12-16 |  |  | 2025-05-09 |  | 2025-09-01 |  | 2025-06-02 | 2025-06-02 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 2375 | Skanderborg Kommune | 100962 | NKA-057798 |  | Michael Kronbach Leth | Public DK | In Process | 2024-12-10 | 2025-09-01 | 2025-09-01 | Own OnNet | [5 empty] | 2025-09-01 |  | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
[5 empty] | 11130 | Sluseholmen 7 A/S | 97750 | NBM-055817 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-08-14 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
[5 empty] | 1675 | Sluseholmen 7 A/S | 97750 | NBM-055818 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-08-14 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 1428 | Sol og Strand Feriehusudlejning A/S | 104666 | NKA-060243 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-03 |  |  | 3rd Party | 2025-05-06 |  |  |  |  | 2025-08-15 | [5 empty] | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 275 | Sol og Strand Feriehusudlejning A/S | 104666 | NMA-060242 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-03 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 275 | Sol og Strand Feriehusudlejning A/S | 104666 | NSW-060241 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-03 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 1350 | Sol og Strand Feriehusudlejning A/S | 104712 | NKA-060021 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 |  |  | 3rd Party | 2025-05-13 |  |  | 2025-06-20 |  | 2025-06-10 | [5 empty] | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 275 | Sol og Strand Feriehusudlejning A/S | 104712 | NMA-060020 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  |  | 2.3 Internal resource constraints (e.g., no one to work on the order) | Pending handover from local delivery (Project reassigned to Christoffer Møller) | 275 | Sol og Strand Feriehusudlejning A/S | 104712 | NSW-060019 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 1350 | SOLAR A/S | 103691 | NKA-059916 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-04-14 10:10:00.000 | 2025-05-05 13:11:00.000 | 2025-05-30 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 710 | SOLAR A/S | 103691 | NSW-059917 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 0 | Spar Nord Bank A/S | 100525-117 | F30221-1136761-01 | 100525-117-001 | Camilla Olesen | Enterprise DK | Created | 2025-05-07 | 2025-07-31 |  | Change | [5 empty] | 2025-07-21 |  |  | 2025-07-31 | 2025-07-31 |  | Change | AX
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | Pending installation 7/5/25 | 1773 | Staten og Kommunernes Indkøbsservice A/S | 103085 | NBM-059303 |  | Kristijan Krsteski | Public DK | In Process | 2025-03-06 | 2025-05-16 | 2025-05-16 | 3rd Party |  |  |  | 2025-05-09 |  | 2025-05-16 | 2025-04-02 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 845 | Statens IT | 102515 | NKA-058786 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-05 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-06 | 2025-03-17 11:17:00.000 | 2025-03-17 11:17:00.000 | 2025-06-13 |  |  | 2025-05-07 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 845 | Statens IT | 102921 | NKA-060364 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-08-06 | 2025-08-06 | 3rd Party |  |  |  | 2025-08-01 |  |  |  | 2025-08-06 | 2025-08-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaits confirmation on loaction and SFP module | 3125 | Statens IT | 102971 | NKA-059157 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-04-24 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 845 | Statens IT | 103149 | NKA-059898 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-24 | 2025-06-11 | 2025-06-11 | 3rd Party | 2025-04-15 |  |  | 2025-06-06 |  | 2025-05-27 |  | 2025-06-11 | 2025-06-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 7237.5 | Statens IT | 103184 | NGF-060061 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 7237.5 | Statens IT | 103184 | NGF-060062 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 2325 | Statens IT | 103184 | NGF-060063 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 7650 | Statens IT | 103184 | NGF-060064 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 7650 | Statens IT | 103184 | NGF-060065 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 3150 | Statens IT | 103184 | NGF-060066 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 1589.75 | Statens IT | 103184 | NSF-060059 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution | 1589.75 | Statens IT | 103184 | NSF-060060 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Customer just approved new solution | 0 | Statens IT | 103385 | NKA-057946 |  | Morten Skytte | Public DK | In Process | 2025-03-14 | 2025-06-13 | 2025-06-13 | Change | 2024-12-20 | 2025-02-07 13:04:00.000 | 2025-02-14 13:47:00.000 | 2025-03-21 |  | 2025-03-04 |  | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Customer just approved new solution | 3125 | Statens IT | 103385 | NKA-059775 |  | Morten Skytte | Public DK | In Process | 2025-03-14 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-03-14 | 2025-04-25 10:52:00.000 | 2025-05-09 14:13:00.000 | 2025-06-06 |  |  | 2025-05-13 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 845 | Statens IT | 104610 | NKA-059970 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-25 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-03-26 | 2025-04-02 11:12:00.000 |  | 2025-07-04 |  | 2025-07-11 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 845 | Statens IT | 104656 | NKA-059925 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-25 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-26 |  |  | 2025-06-13 |  | 2025-06-10 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Awating date from 3. part | 845 | Statens IT | 104926 | NKA-060252 |  | Morten Skytte | Public DK | In Process | 2025-04-03 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Awating date from 3. part | 290 | Statens IT | 104926 | NMA-060254 |  | Morten Skytte | Public DK | In Process | 2025-04-03 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Awating date from 3. part | 290 | Statens IT | 104926 | NSW-060253 |  | Morten Skytte | Public DK | In Process | 2025-04-03 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | On track | 845 | Statens IT | 105148 | NKA-060366 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-04-15 |  |  | 2025-06-10 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[5 empty] | 350 | Statens IT | 105711 | NKA-060693 |  | Morten Skytte | Public DK | In Process | 2025-05-12 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 720 | Statens IT | 85895 | NKA-006121 |  | Bonnie Jensen | Public DK | In Process | 2023-02-14 |  |  | Change
[6 empty] | Statens IT | 86807 | NKA-000777 |  | Morten Skytte | Public DK | In Process | 2024-01-04 |  |  | Change
[5 empty] | 945 | Statens IT | 86807 | NKA-052754 |  | Morten Skytte | Public DK | In Process | 2024-01-04 |  |  | Own OnNet
[5 empty] | 925 | Statens IT | 87327 | NKA-000521 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 845 | Statens IT | 87327 | NKA-001316 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 845 | Statens IT | 87327 | NKA-008572 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 920 | Statens IT | 87327 | NKA-012063 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 845 | Statens IT | 87327 | NKA-022293 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 845 | Statens IT | 87327 | NKA-035134 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[5 empty] | 845 | Statens IT | 90910 | NKA-011368 |  | Bonnie Jensen | Public DK | In Process | 2023-10-02 |  |  | Change
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer status og datoer fra 3.part | 450 | Stevns Kommune | 98576 | NKA-056300 |  | Michael Kronbach Leth | Public DK | In Process | 2024-09-19 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-09-30 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer status og datoer fra 3.part | 325 | Stevns Kommune | 98576 | NSW-056301 |  | Michael Kronbach Leth | Public DK | In Process | 2024-09-19 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Afventer leveringsdato fra 3. part | 150 | Styrelsen for It og Læring | 102893 | NKA-059069 |  | Eva Eisner | Public DK | In Process | 2025-02-25 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-20 |  |  | 2025-05-16 |  | 2025-05-13 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 9693 | Sund & Bælt Holding A/S | 82790 | NKA-041907 |  | Oliver Mariager | Public DK | In Process | 2023-02-08 |  |  | Change
[5 empty] | 1907.4 | Sund & Bælt Holding A/S | 82790 | NKA-046742 |  | Oliver Mariager | Public DK | In Process | 2023-02-08 |  |  | Own with Digging
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Just startet | 3079 | Sydbank A/S | 104165-012 | C33713-1136323-01 | 104165-012-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 |  |  | 3rd Party | [5 empty] | 2025-07-09 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | Just startet | 3079 | Sydbank A/S | 104165-012 | C33713-1136325-01 | 104165-012-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 |  |  | 3rd Party | [5 empty] | 2025-07-09 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 8500 | Syddansk Erhvervsskole | 103009 | NDD-059299 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-06 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 8500 | Syddansk Erhvervsskole | 103009 | NKA-059298 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-06 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-03-07 |  | 2025-03-06 09:46:00.000 |  |  | 2025-05-20 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer leveringsdato | 1625 | Syddansk Erhvervsskole | 105422 | NKA-060523 |  | Eva Eisner | Public DK | In Process | 2025-04-29 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-29 | 2025-04-30 10:15:00.000 | 2025-04-30 10:15:00.000 | 2025-06-13 |  | 2025-06-20 | 2025-05-12 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1990 | Syddansk Universitet (university Of Southern Denmark) | 100964-007 | F30928-1135939-01 | 100964-007-001 | Shazia Mobin | Public DK | In Process | 2025-04-03 | 2025-06-06 | 2025-05-30 | Own with Digging |  |  |  | 2025-05-30 |  | 2025-06-25 |  | 2025-05-30 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[5 empty] | 4000 | Syddansk Universitet (university Of Southern Denmark) | 100964-008 | F30928-1136815-01 | 100964-008-001 | Michael Kronbach Leth | Public DK | Created | 2025-05-09 |  |  | Own with Digging | [5 empty] | 2025-07-31 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 9588 | Søstrene Grenes Import A/S | 100998-028 | C30962-1135204-01 | 100998-028-001 | Michael Kronbach Leth | Enterprise DK | Created | 2025-03-11 | 2025-08-29 |  | 3rd Party | [5 empty] | 2025-06-02 |  |  | 2025-08-29 | 2025-08-29 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde | 9762 | Søstrene Grenes Import A/S | 100998-028 | C30962-1135206-01 | 100998-028-003 | Michael Kronbach Leth | Enterprise DK | Created | 2025-03-11 | 2025-08-29 |  | 3rd Party | [5 empty] | 2025-06-02 |  |  | 2025-08-29 | 2025-08-29 |  | New Sales | AX
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | The order is non-standard as submitted. Need additional info | 6250 | Søstrene Grenes Import A/S | 104957 | NKA-060429 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-04-22 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | The order is non-standard as submitted. Need additional info | 750 | Søstrene Grenes Import A/S | 104957 | NKA-060430 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-04-22 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-04-23 |  |  |  |  | 2025-06-27 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 1450 | T HANSEN GRUPPEN A/S | 103415 | NKA-059743 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-01 | 2025-04-10 11:00:00.000 | 2025-05-05 14:44:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 425 | T HANSEN GRUPPEN A/S | 103415 | NMA-059745 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | 3rd Party | [5 empty] | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 2300 | T HANSEN GRUPPEN A/S | 103415 | NSF-059746 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-01 | 2025-04-10 10:49:00.000 | 2025-05-07 10:42:00.000 | 2025-05-30 |  | 2025-05-02 | 2025-03-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 425 | T HANSEN GRUPPEN A/S | 103415 | NSW-059744 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 750 | T HANSEN GRUPPEN A/S | 103609 | NKA-059877 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | Own with Digging | 2025-03-25 |  |  |  |  | 2025-10-24 |  | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 162.5 | T HANSEN GRUPPEN A/S | 103609 | NMA-059879 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | 3rd Party | 2025-03-25 | [6 empty] | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 162.5 | T HANSEN GRUPPEN A/S | 103609 | NSW-059878 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | Own OnNet | [7 empty] | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | On track | 750 | T HANSEN GRUPPEN A/S | 104364 | NKA-059880 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-03-28 14:30:00.000 | 2025-04-30 11:01:00.000 | 2025-05-23 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 162.5 | T HANSEN GRUPPEN A/S | 104364 | NMA-059882 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 162.5 | T HANSEN GRUPPEN A/S | 104364 | NSW-059881 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | Waiting for installation and fiber from GC SE | 1400 | T HANSEN GRUPPEN A/S | 104366 | NKA-059870 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-27 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | Waiting for installation and fiber from GC SE | 275 | T HANSEN GRUPPEN A/S | 104366 | NMA-059872 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-27 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | Waiting for installation and fiber from GC SE | 275 | T HANSEN GRUPPEN A/S | 104366 | NSW-059871 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | Own OnNet | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 3850 | T HANSEN GRUPPEN A/S | 104597 | NKA-060269 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-06 | [5 empty] | New Sales | BO
[5 empty] | 3850 | T HANSEN GRUPPEN A/S | 104597 | NKA-060270 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-30 | [5 empty] | New Sales | BO
[5 empty] | 537.5 | T HANSEN GRUPPEN A/S | 104597 | NMA-060272 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-23 | [5 empty] | New Sales | BO
[5 empty] | 537.5 | T HANSEN GRUPPEN A/S | 104597 | NSW-060271 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 895 | T HANSEN GRUPPEN A/S | 104597 | NSW-060273 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
[6 empty] | T HANSEN GRUPPEN A/S | 105628 | NSW-060605 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-07 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 1500 | TCM Operations A/S | 102940 | NKA-036523 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | 2021-08-23 | 2021-08-27 11:31:00.000 |  |  |  | 2021-10-07 | [5 empty] | Change | BO
[5 empty] | 350 | TCM Operations A/S | 102940 | NSW-036545 |  | Kristijan Krsteski | Enterprise DK | In Process | 2025-04-30 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 845 | Techcollege | 105617 | NKA-060635 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 3.3 Other installation obstacles and infratructure issues | Waiting for backbone upgrade and new JDSU test | 13500 | Techcollege | 91284 | NKA-001435 |  | Jane Birgitte Høgaard | Public DK | In Process | 2024-01-30 | 2025-06-30 | 2025-06-30 | Change | 2024-02-28 | 2024-03-01 09:04:00.000 | 2024-03-04 15:38:00.000 | 2024-12-09 |  | 2024-05-03 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 8. Ready for service | 3.3 Other installation obstacles and infratructure issues | Waiting for backbone upgrade and new JDSU test | 13500 | Techcollege | 91284 | NKA-020212 |  | Jane Birgitte Høgaard | Public DK | In Process | 2024-01-30 | 2025-06-30 | 2025-06-30 | Change | 2017-04-18 | 2017-08-17 14:00:00.000 | 2017-08-17 14:00:00.000 | 2024-12-09 |  | 2017-10-31 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
[5 empty] | -0.0066667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135708-01 | 107596-003-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.0066667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135709-01 | 107596-003-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135710-01 | 107596-003-003 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.96667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135711-01 | 107596-003-004 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.11 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135712-01 | 107596-003-005 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135713-01 | 107596-003-006 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.19667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135714-01 | 107596-003-007 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.3 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135715-01 | 107596-003-008 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135716-01 | 107596-003-009 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.72333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135718-01 | 107596-003-011 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.46 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135719-01 | 107596-003-012 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135720-01 | 107596-003-013 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135722-01 | 107596-003-015 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135723-01 | 107596-003-016 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.41333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135725-01 | 107596-003-018 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135727-01 | 107596-003-020 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135728-01 | 107596-003-021 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135729-01 | 107596-003-022 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135731-01 | 107596-003-024 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135732-01 | 107596-003-025 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.11333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135734-01 | 107596-003-027 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.61667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135735-01 | 107596-003-028 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135736-01 | 107596-003-029 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | -0.1 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135738-01 | 107596-003-031 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | -0.52 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135739-01 | 107596-003-032 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135740-01 | 107596-003-033 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135742-01 | 107596-003-035 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 800 | Thisted Kommune | 103133 | NKA-060244 |  | Eva Eisner | Public DK | In Process | 2025-04-03 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-07 | 2025-04-08 11:56:00.000 | 2025-04-24 13:53:00.000 | 2025-05-14 |  | 2025-06-18 | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 227.5 | Thisted Kommune | 103133 | NMA-060246 |  | Eva Eisner | Public DK | In Process | 2025-04-03 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-07 |  |  |  |  | 2025-06-18 | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 227.5 | Thisted Kommune | 103133 | NSW-060245 |  | Eva Eisner | Public DK | In Process | 2025-04-03 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 2100 | Thornico IT A/S | 101568-032 | C31534-1135228-01 | 101568-032-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-02 | 2025-05-07 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 2100 | Thornico IT A/S | 101568-032 | C31534-1135230-01 | 101568-032-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | 3rd Party | [5 empty] | 2025-06-02 | 2025-05-07 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 2300 | Thornico IT A/S | 101568-032 | C31534-1135232-01 | 101568-032-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | 3rd Party | [5 empty] | 2025-06-02 | 2025-05-08 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 2300 | Thornico IT A/S | 101568-032 | C31534-1135234-01 | 101568-032-007 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own with Digging | [5 empty] | 2025-06-02 | 2025-05-10 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 3200 | Thornico IT A/S | 101568-032 | C31534-1135236-01 | 101568-032-009 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | 3rd Party | [5 empty] | 2025-06-02 | 2025-05-10 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 3200 | Thornico IT A/S | 101568-032 | C31534-1135238-01 | 101568-032-011 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | 3rd Party | [5 empty] | 2025-06-02 | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 1300 | Thornico IT A/S | 101568-032 | C31534-1135240-01 | 101568-032-013 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own with Digging | [5 empty] | 2025-06-02 | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 0 | Thornico IT A/S | 101568-032 | C31534-1135241-01 | 101568-032-014 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-02 | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 2625 | Thornico IT A/S | 101568-032 | C31534-1135243-01 | 101568-032-016 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-06-20 | 2025-06-20 | 3rd Party |  |  |  | 2025-06-18 |  | 2025-06-02 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[5 empty] | 0 | Thornico IT A/S | 101568-032 | C31534-1135245-01 | 101568-032-018 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-02 | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 0 | Thornico IT A/S | 101568-032 | C31534-1135246-01 | 101568-032-019 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-02 | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Waiting for rack info from the customer | 4320 | Topsoe A/S | 100779 | NKA-057949 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-18 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-01-06 |  |  |  |  | 2025-02-28 | 2025-02-20 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | TV2¦DANMARK | 100514-117 | B30208-1136216-01 | 100514-117-001 | Shazia Mobin | Public DK | In Process | 2025-04-14 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2025-05-23 |  | 2025-08-18 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | On Track | On Track | On Track |  | twoday Danmark A/S | 101493 | NKA-055475 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-12-11 |  |  | Change | 2024-07-04 | 2024-08-20 15:44:00.000 | 2024-08-20 15:44:00.000 | 2025-05-07 |  | 2024-08-30 | [5 empty] | Change | BO
|  | 3. Installation preparation and digging order |  | On track | 1450 | twoday Danmark A/S | 90369 | NKA-055478 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-06-28 | 2025-09-05 | 2025-09-05 | Own OnNet | 2024-07-04 | 2024-10-02 13:48:00.000 | 2024-10-02 13:48:00.000 | 2025-08-29 |  | 2025-03-01 | 2024-10-14 | 2025-09-05 | 2025-09-05 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Awating 3 part to fix error | 892 | Tønder Kommune | 102621 | NKA-058895 |  | Morten Skytte | Public DK | In Process | 2025-02-12 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-16 |  |  | 2025-04-25 |  | 2025-04-25 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 895 | Tønder Kommune | 97010 | NKA-055059 |  | Morten Skytte | Public DK | In Process | 2024-06-25 |  |  | Own OnNet
[5 empty] | 895 | Tønder Kommune | 97010 | NKA-055060 |  | Morten Skytte | Public DK | In Process | 2024-06-25 |  |  | Own OnNet
[5 empty] | -436.69 | Unisport A/S | 105569 | NBM-041174 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-05-13 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 30/05 | 1660 | United Petfood Denmark A/S | 104742 | NKA-060256 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-03 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-07 | 2025-04-08 09:17:00.000 | 2025-04-29 11:09:00.000 | 2025-05-23 |  | 2025-06-06 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.2 Customer not reachable / unresponsive |  | 5100 | Urban Partners A/S | 101892 | NII-058952 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 |  |  | Own OnNet | [6 empty] | 2025-02-17 |  |  |  |  | New Sales | BO
|  | On Track | On Track | On Track | 2200 | Urban Partners A/S | 101892 | NII-058953 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 |  |  | 3rd Party | [6 empty] | 2025-02-17 |  |  |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1 Third party vendor delay | Difficulties | 4600 | Urban Partners A/S | 102056 | NII-058975 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 |  |  | 3rd Party | [6 empty] | 2025-02-17 |  |  |  |  | New Sales | BO
|  | On Track |  |  | 1600 | Urban Partners A/S | 102056 | NKA-058974 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-03-07 |  |  |  |  | 2025-04-11 |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 20/06 | 1399 | Vattenfall Vindkraft A/S | 103303 | NKA-059771 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-13 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-24 |  |  | 2025-06-13 |  | 2025-06-03 | 2025-05-14 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 812.25 | Vejle Kommune | 100606-089 | C30318-1135745-01 | 100606-089-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-30 | 2025-11-07 |  | Own OnNet | [5 empty] | 2025-06-16 |  |  | 2025-11-07 | 2025-11-07 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 100 | Vejle Kommune | 100606-089 | C30318-1135746-01 | 100606-089-002 | Michael Kronbach Leth | Public DK | Created | 2025-03-30 | 2025-11-07 |  | Own OnNet | [5 empty] | 2025-06-16 |  |  | 2025-11-07 | 2025-11-07 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 812.25 | Vejle Kommune | 100606-090 | C30318-1135825-01 | 100606-090-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-16 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 0 | Vejle Kommune | 100606-090 | C30318-1135826-01 | 100606-090-002 | Michael Kronbach Leth | Public DK | Created | 2025-03-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-06-16 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 2265 | Vejle Kommune | 100606-093 | C30318-1128873-02 | 100606-093-007 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Opgradering | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 2265 | Vejle Kommune | 100606-093 | C30318-1128876-02 | 100606-093-008 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Opgradering | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 163.5 | Vejle Kommune | 100606-093 | C30318-1136287-01 | 100606-093-001 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change |  |  |  | 2025-05-12 |  | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 163.5 | Vejle Kommune | 100606-093 | C30318-1136288-01 | 100606-093-002 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 | 2025-06-27 |  | Change | [5 empty] | 2025-07-07 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 163.5 | Vejle Kommune | 100606-093 | C30318-1136289-01 | 100606-093-003 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change |  |  |  | 2025-05-12 |  | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 163.5 | Vejle Kommune | 100606-093 | C30318-1136290-01 | 100606-093-004 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 0 | Vejle Kommune | 100606-093 | C30318-1136291-01 | 100606-093-005 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Own OnNet | [5 empty] | 2025-07-07 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 0 | Vejle Kommune | 100606-093 | C30318-1136292-01 | 100606-093-006 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Own OnNet | [5 empty] | 2025-07-07 | [5 empty] | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 600 | Vesthimmerlands Kommune | 104738 | NKA-060022 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  |  | 2025-07-11 |  | 2025-07-03 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 30 | Vesthimmerlands Kommune | 104740 | NKA-060022 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-07-18 | 2025-07-18 | Change | 2025-04-24 |  |  |  |  | 2025-07-03 |  | 2025-07-18 | 2025-07-18 |  |  | Change | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Waiting for Opennet | 600 | Vesthimmerlands Kommune | 105255 | NKA-060401 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-16 | 2025-07-23 | 2025-07-23 | 3rd Party | 2025-05-06 |  |  | 2025-07-18 |  | 2025-07-15 |  | 2025-07-23 | 2025-07-23 |  |  | New Sales | BO
|  |  |  | Part of migration project | 400.95 | Viborg Kommune | 103119 | NKA-059264 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 400.95 | Viborg Kommune | 103119 | NKA-059265 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 400.95 | Viborg Kommune | 103119 | NKA-059266 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 400.95 | Viborg Kommune | 103119 | NKA-059267 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | Own OnNet | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 400.95 | Viborg Kommune | 103119 | NKA-059268 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 546.75 | Viborg Kommune | 103119 | NKA-059269 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | Own OnNet |  |  |  | 2025-06-17 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
[5 empty] | 2300 | Wismo Group A/S | 101534-018 | C31500-1133908-01 | 101534-018-015 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 50 | Wismo Group A/S | 101534-018 | C31500-1133909-01 | 101534-018-016 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 2300 | Wismo Group A/S | 101534-018 | C31500-1133911-01 | 101534-018-018 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 50 | Wismo Group A/S | 101534-018 | C31500-1133912-01 | 101534-018-019 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 0 | Wismo Group A/S | 101534-018 | C31500-1133913-01 | 101534-018-020 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 1700 | Wismo Group A/S | 101534-018 | C31500-1133914-01 | 101534-018-021 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 50 | Wismo Group A/S | 101534-018 | C31500-1133915-01 | 101534-018-022 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 1700 | Wismo Group A/S | 101534-018 | C31500-1133917-01 | 101534-018-024 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 50 | Wismo Group A/S | 101534-018 | C31500-1133918-01 | 101534-018-025 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 0 | Wismo Group A/S | 101534-018 | C31500-1133919-01 | 101534-018-026 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 4. Final design | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) | -3458.02 | ZeroNorth A/S | 101796 | NBM-040748 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-05-30 | 2025-05-30 | Change | 2025-03-10 |  |  |  |  | 2025-04-30 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 4. Final design | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) | 126.66 | ZeroNorth A/S | 101796 | NBM-047894 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-05-30 | 2025-05-30 | Change | 2025-03-10 |  |  |  |  | 2025-04-30 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 4. Final design | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) | 4718 | ZeroNorth A/S | 101796 | NBM-058731 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-10 |  |  |  |  | 2025-04-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Awating GC to establies new line | 2851.86 | Øresunds Internationale Skole S/I | 100271 | NKA-011021 |  | Morten Skytte | Public DK | In Process | 2024-11-29 |  |  | Change |  | 2021-01-27 09:41:00.000 | 2021-01-27 12:39:00.000 | [8 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | 3. party have trouble | 176 | Ørsted Services A/S | 101383-036 | C31349-1134123-01 | 101383-036-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-21 | 2025-05-16 |  | Own OnNet | [5 empty] | 2025-04-15 |  |  | 2025-05-16 | 2025-05-16 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 16/05 | 3000 | A/B Lindegården | 103580 | NKA-059824 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-20 | 2025-04-04 12:40:00.000 | 2025-04-22 09:31:00.000 | 2025-05-16 |  | 2025-05-09 | 2025-04-22 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 600 | Aarhus Motion | 105070 | NBM-060351 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 900 | Aarhus Motion | 105070 | NKA-060348 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-14 | 2025-04-25 10:07:00.000 | 2025-05-09 08:51:00.000 | 2025-05-30 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | Aarhus Motion | 105070 | NMA-060350 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | Aarhus Motion | 105070 | NSW-060349 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-05-05 |  |  | 2025-05-28 |  | 2025-05-16 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060388 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-15 |  |  | 2025-05-28 |  | 2025-06-13 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1195 | ABCforsikringsagentur A/S | 105230 | NKA-060386 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-16 | 2025-05-05 16:44:00.000 | 2025-05-05 15:08:00.000 | 2025-05-23 |  | 2025-06-13 | 2025-05-13 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | -1050.89 | ABCforsikringsagentur A/S | 105465 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-05-28 | 2025-05-28 | Change | 2025-05-05 |  |  | 2025-05-28 |  | 2025-05-16 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | Change | BO
[5 empty] | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NKA-060181 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | 2025-04-07 | 2025-04-23 15:01:00.000 |  | 2025-06-20 |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NML-060182 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | 2025-04-07 |  |  | 2025-06-20 |  | 2025-06-27 | [5 empty] | New Sales | BO
|  | 9. Documentation and vendor invoice | Other (incl. termination, on hold etc.) | This line is delivered - but there is an eror in BO order, but it should have been completed. Dont understand why it is on the list? | 121.38 | ALFABO | 74844 | NKA-036952 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2021-09-07 |  |  | 3rd Party | 2021-09-24 |  |  |  |  | 2021-10-04 | 2021-09-24 |  |  |  | 2023-04-24 00:00:00.000 | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1350 | Al-Irchad Skolen | 102553 | NBM-059109 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 899 | Al-Irchad Skolen | 102553 | NKA-059110 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-13 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | Al-Irchad Skolen | 102553 | NMA-059107 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-31 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | Al-Irchad Skolen | 102553 | NSW-059108 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 23/05 | 1055 | Andersen-Andersen ApS | 103536 | NKA-059830 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-20 | 2025-04-28 14:40:00.000 | 2025-05-02 10:30:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-05-14 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 2500 | Archon DK ApS | 105548 | NBM-060607 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-06 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 1395 | Archon DK ApS | 105548 | NKA-060608 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-05-06 | 2025-05-12 11:59:00.000 | 2025-05-13 08:51:00.000 | 2025-05-30 |  | 2025-05-30 | 2025-05-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 945 | AS3 A/S | 103392 | NKA-060343 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-04-10 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-14 | 2025-04-21 12:02:00.000 | 2025-04-29 14:02:00.000 | 2025-05-23 |  | 2025-06-06 | 2025-04-29 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 697.5 | BESS Frederiksværk I ApS | 101911 | NKA-058435 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 |  |  | 3rd Party | [6 empty] | 2025-01-23 |  |  |  |  | New Sales | BO
|  | On Track | On Track | On Track | 697.5 | BESS Frederiksværk I ApS | 101911 | NML-058436 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 |  |  | 3rd Party | [6 empty] | 2025-01-23 |  |  |  |  | New Sales | BO
[5 empty] | 1186 | Best Ejendomme A/S | 105526 | NKA-060558 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-05-02 |  |  |  |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | On Track | 2.1 Order forgotten, but back on track to be processed | Received delivery from Enterprise without handover - pending investigation with Solution Engineer to find out where this was left, so we can start it up again | 520 | BHS Logistics A/S | 79039 | NSW-041031 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | On Track | 2.1 Order forgotten, but back on track to be processed | Received delivery from Enterprise without handover - pending investigation with Solution Engineer to find out where this was left, so we can start it up again | 520 | BHS Logistics A/S | 79039 | NSW-041032 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 06/06 | 665.5 | Bluebyte ApS | 103578 | NKA-059827 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-20 | 2025-04-04 07:37:00.000 | 2025-04-28 14:37:00.000 | 2025-05-28 |  |  | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 06/06 | 665.5 | Bluebyte ApS | 103578 | NML-059828 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-20 |  |  | 2025-05-28 |  |  | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127937-01 | 105961-007-011 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet | [5 empty] | 2024-07-08 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127938-01 | 105961-007-012 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet | [5 empty] | 2024-07-08 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127948-01 | 105961-007-022 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet | [5 empty] | 2024-07-08 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 2500 | BONE CONSULT A/S | 105961-007 | C35256-1127950-01 | 105961-007-024 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet | [5 empty] | 2024-07-08 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127952-01 | 105961-007-026 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2024-05-14 | 2025-05-28 |  | Own OnNet | [5 empty] | 2024-07-08 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 96 | BONE CONSULT A/S | 105961-008 | C35256-1135227-01 | 105961-008-001 | Camilla Villumsen Kaimer | SMB Portfolio DK | In Process | 2025-03-12 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaiting SW execution | -1321.62 | BRUUN & STENGADE A/S | 101934 | NKA-016343 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Change | 2016-10-25 | 2016-11-21 13:52:00.000 | 2016-11-21 13:52:00.000 | 2025-05-09 |  | 2017-01-30 | 2025-05-09 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 800 | BRUUN & STENGADE A/S | 101934 | NKA-060091 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-05-12 13:13:00.000 |  | 2025-06-13 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | BRUUN & STENGADE A/S | 101934 | NMA-060093 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-10 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaiting SW execution | 200 | BRUUN & STENGADE A/S | 101934 | NMA-060095 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-12 | 2025-05-12 | 3rd Party | 2025-04-10 |  |  |  |  | 2025-06-06 | 2025-05-09 | 2025-05-12 | 2025-05-12 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 200 | BRUUN & STENGADE A/S | 101934 | NSW-060092 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaiting SW execution | 200 | BRUUN & STENGADE A/S | 101934 | NSW-060094 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-12 | 2025-05-12 | Own OnNet | [6 empty] | 2025-05-09 | 2025-05-12 | 2025-05-12 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | -312.71 | BSC Drift ApS | 104739 | NKA-028998 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Change | 2019-10-18 | 2019-10-28 11:15:00.000 | 2019-10-29 07:50:00.000 |  |  | 2019-12-17 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | 230 | BSC Drift ApS | 104739 | NMA-060117 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-06 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | 230 | BSC Drift ApS | 104739 | NSW-060118 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [6 empty] | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 895 | Bysted & Partners ApS | 103106 | NKA-060120 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-09 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 150 | Bysted & Partners ApS | 103106 | NMA-060122 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 150 | Bysted & Partners ApS | 103106 | NSW-060121 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 30/05 | 1315 | Copenhagen Bamboo ApS | 101143 | NKA-057576 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-26 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-12-06 | 2025-04-03 13:06:00.000 | 2025-04-23 09:56:00.000 | 2025-05-16 |  | 2025-03-07 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 1388.81 | Copenhagen Coffee Lab Holding ApS | 105359 | NBM-060697 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 860 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060694 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-13 | 2025-05-14 12:02:00.000 | 2025-05-14 10:33:00.000 | 2025-05-30 |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 760 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060698 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060696 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060700 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060695 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060699 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 23/05 | 1095 | Danexplore ApS | 103312 | NKA-059888 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-21 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-24 | 2025-03-31 10:40:00.000 | 2025-04-24 14:57:00.000 | 2025-05-23 |  |  | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 895 | Dansk Vegetarisk Forening (DVF) | 103541 | NKA-060076 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-09 | 2025-05-13 10:33:00.000 |  | 2025-06-13 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NMA-060078 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Awaiting Fiber PM - Delivery proceeding as planned | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NSW-060077 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.2 Customer not reachable / unresponsive | Wating for the buildingowner to accept the design plan | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056366 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-05-30 | 2025-01-10 | Own with Digging | 2024-10-15 |  |  |  |  | 2025-01-10 |  | 2025-01-10 | 2025-01-10 | 2025-05-30 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056374 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-05-30 | 2025-05-30 | 3rd Party |  |  |  | 2025-05-30 |  |  | 2025-05-06 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1700 | DANSKE KONCEPT RESTAURANTER A/S | 98680 | NKA-056601 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-10-03 | 2025-06-06 | 2025-06-06 | Own with Digging | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | On Track | 2.1 Order forgotten, but back on track to be processed | This order was forgotten in delivery prior to handover to SmartConnect |  | Danske Shoppingcentre P/S | 100107 | NSW-037789 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-10-17 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 1391 | Den selvejende institution Friplejehjemmet Alba Marie | 103605 | NKA-060268 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-08 | 2025-05-01 10:53:00.000 | 2025-05-07 10:47:00.000 | 2025-05-30 |  | 2025-07-18 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | -180.9967 | DIS Sølvgade A/S | 103176-004 | C32793-1136828-01 | 103176-004-001 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Change | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | Change | AX
[5 empty] | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136829-01 | 103176-004-002 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136830-01 | 103176-004-003 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136831-01 | 103176-004-004 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 3624 | DIS Sølvgade A/S | 103176-004 | C32793-1136833-01 | 103176-004-006 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own with Digging | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136834-01 | 103176-004-007 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[5 empty] | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136835-01 | 103176-004-008 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Originally delayed by customer. Now back in production | 981 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 102945 | NKA-059059 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-25 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-03 | 2025-05-07 07:53:00.000 | 2025-05-11 00:35:00.000 | 2025-05-21 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Originally delayed by customer. Now back in production | 981 | Dornan Engineering, Filial Af Dornan Engineering Limited, Irland | 102945 | NML-059058 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-25 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-03 |  | 2025-05-08 14:06:00.000 | 2025-05-21 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned | 1350 | E45 ApS | 102578 | NBM-059780 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-14 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-03-19 |  |  | 2025-05-12 |  | 2025-05-01 | 2025-04-25 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | 2643 | Ecm Industries A/S | 94182 | NKA-053149 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-02-06 | 2025-08-08 | 2025-08-08 | 3rd Party | 2024-07-25 | [6 empty] | 2025-08-08 | 2025-08-08 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned | 3569 | Ejendomsanpartsselskabet MT 04 | 91727 | NBM-060202 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-02 |  |  | 2025-05-23 |  | 2025-05-02 | 2025-05-13 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned | -929.74 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | Change | 2016-08-03 | 2016-07-11 11:49:00.000 | 2016-07-08 12:28:00.000 | 2025-05-19 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned | -248.28 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-23 | 2025-05-23 | Change | 2016-08-03 | 2016-07-11 11:52:00.000 | 2016-07-08 12:29:00.000 | 2025-05-19 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | On Track | On Track | On Track | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059940 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet | [7 empty] | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059941 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet | [7 empty] | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 584 | Ejendomsselskabet Søkvæsthuset ApS | 103477 | NDD-059942 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet | [7 empty] | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 20/06 | 995 | Ejerforeningen Beddingen | 103697 | NKA-059848 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-27 |  |  | 2025-06-20 |  | 2025-06-10 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | 1416 | Eurographic Group A/S | 102676 | NKA-059039 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-05 | 2025-03-18 09:18:00.000 | 2025-03-20 13:38:00.000 | 2025-04-07 |  |  | 2025-04-03 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | 612 | Eurographic Group A/S | 102676 | NMA-059041 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning | 612 | Eurographic Group A/S | 102676 | NSW-059040 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-23 | 2025-05-23 | Own OnNet | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 3.3 Other installation obstacles and infratructure issues | Postponing installation due to lack of clarification in the sales phase. Technical clarification and errors in physical installation. | 3870.05 | Flyers ApS | 102767 | NBM-058991 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-19 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-02-25 |  |  | 2025-05-09 |  | 2025-04-25 | 2025-02-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 775 | FUEGO ApS | 98741 | NBM-058935 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-03-06 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 1000 | FUEGO ApS | 98741 | NKA-058932 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-27 | 2025-06-27 | Own with Digging |  |  |  | 2025-06-17 |  | 2025-05-30 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 100 | FUEGO ApS | 98741 | NMA-058934 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 100 | FUEGO ApS | 98741 | NSW-058933 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[6 empty] | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136868-01 | 106418-746-001 | Camilla Olesen | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet | [5 empty] | 2025-08-13 | [5 empty] | New Sales | AX
[6 empty] | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136871-01 | 106418-746-004 | Camilla Olesen | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own with Digging | [5 empty] | 2025-08-13 | [5 empty] | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1592.7 | Go Autonomous ApS | 101916 | NBM-060238 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-08 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1592.71 | Go Autonomous ApS | 101916 | NBM-060240 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1400 | Go Autonomous ApS | 101916 | NKA-060237 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-07 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1400 | Go Autonomous ApS | 101916 | NKA-060239 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-07 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 100 | H. DAUGAARD A/S | 106840-006 | C35985-1126258-01 | 106840-006-001 | Henrik Møller Fyhn | SMB Portfolio DK | In Process | 2024-03-06 | 2025-06-06 | 2024-12-13 | Change |  |  |  | 2024-12-06 |  | 2024-05-23 | 2024-07-10 | 2024-12-13 | 2025-06-06 | 2025-06-06 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1495 | H.C. Andersens Flyttefirma A/S | 104913 | NKA-060080 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-08 | 2025-04-24 13:54:00.000 | 2025-05-08 12:58:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 230 | H.C. Andersens Flyttefirma A/S | 104913 | NMA-060082 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-06 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 230 | H.C. Andersens Flyttefirma A/S | 104913 | NSW-060081 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | On track - in production at 3. party | 1140 | Hoffmann Professional A/S | 105172 | NKA-060438 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-04-30 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | On track - in production at 3. party | 230 | Hoffmann Professional A/S | 105172 | NMA-060439 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | On track - in production at 3. party | 230 | Hoffmann Professional A/S | 105172 | NSW-060440 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 9. Documentation and vendor invoice | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Peding Sales, and finilaizing of installation (Netteam) Handed over to Martin Ramsussen. | 14438.31 | I/S Ugebladsdistribution | 98963 | NBM-056549 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2024-09-30 | 2025-06-27 | 2025-06-27 | 3rd Party | 2024-10-31 |  |  |  |  | 2025-03-31 | 2025-05-07 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 102436 | NKA-058723 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-01-31 | 2025-05-16 | 2025-05-16 | 3rd Party | [5 empty] | 2025-05-16 | 2025-04-24 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 1629 | Imerco A/S | 102528 | NKA-058919 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-13 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-07 |  |  | 2025-05-30 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 103032 | NKA-059128 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-26 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-02-27 | 2025-04-10 12:14:00.000 | 2025-04-15 14:51:00.000 | 2025-05-23 |  | 2025-05-23 | 2025-04-23 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 103032 | NKA-059137 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-26 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-03-07 |  |  | 2025-05-16 |  | 2025-05-13 | 2025-04-28 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 103321 | NKA-060453 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-04-24 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-04-24 | 2025-05-01 07:59:00.000 | 2025-04-29 13:03:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 979 | Imerco A/S | 93095 | NKA-052427 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-04-15 | 2025-04-16 12:53:00.000 | 2025-05-05 13:13:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Wating for 3. party to confirm the ordre | 979 | Imerco A/S | 93095 | NKA-052428 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-07-18 | 2025-07-18 | 3rd Party |  |  | 2024-01-03 07:45:00.000 |  |  |  | 2025-05-02 | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Wating for 3. party to confirm the deliverydate | 979 | Imerco A/S | 93095 | NKA-052430 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Wating for 3. party to confirm the deliverydate | 979 | Imerco A/S | 93095 | NKA-052431 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  | 2024-01-27 18:31:00.000 |  |  |  | 2025-05-02 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design |  | On track | 979 | Imerco A/S | 93095 | NKA-052432 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-22 |  |  | 2025-06-13 |  | 2025-06-03 | 2025-04-29 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  | On track | 979 | Imerco A/S | 93095 | NKA-052436 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-23 | 2025-05-23 | 3rd Party |  |  |  | 2025-05-16 |  |  | 2025-03-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1 Third party vendor delay | Pending on OpenNet tool fix | 979 | Imerco A/S | 93095 | NKA-052440 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1 Third party vendor delay | Pending on OpenNet tool fix | 979 | Imerco A/S | 93095 | NKA-052441 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 93095 | NKA-052451 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-10 |  |  | 2025-05-23 |  | 2025-05-16 | 2025-05-05 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 979 | Imerco A/S | 93095 | NKA-052452 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-02-19 | 2025-05-01 12:22:00.000 | 2025-05-05 08:16:00.000 | 2025-05-23 |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.4 Pending equipment/product to be ready | Pending on OpenNet tool fix | 979 | Imerco A/S | 93095 | NKA-052454 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 795 | Immudex ApS | 102843 | NDD-059971 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet | [7 empty] | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | On Track | On Track | On Track | 795 | Immudex ApS | 102843 | NDD-059972 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-20 | 2025-05-20 | Own OnNet | [7 empty] | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
[5 empty] | 1185 | Inco Svendborg Slagtehus A/S | 105563 | NKA-060611 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-05-06 |  |  | 2025-06-20 |  | 2025-07-25 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 695 | India Royale ApS | 104999 | NKA-060320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-14 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 150 | India Royale ApS | 104999 | NMA-060322 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 150 | India Royale ApS | 104999 | NSW-060321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaiting SW/Installation execution | 2440 | Intech | 103238 | NBM-060096 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-02 |  |  | 2025-05-09 |  | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaiting SW/Installation execution | -2416.06 | Intech | 103238 | NOC-997264 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | Change |  |  |  | 2025-05-09 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
[5 empty] | 995 | i-team Danmark ApS | 105696 | NKA-060722 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 150 | i-team Danmark ApS | 105696 | NMA-060723 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 150 | i-team Danmark ApS | 105696 | NSW-060724 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[5 empty] | 1395 | Kontorfællesskabet Wilders Plads ApS | 105521 | NKA-060646 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-08 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-09 |  |  |  |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 400 | Labelless Media ApS | 101484 | NBM-058251 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-01-07 |  |  | 2025-05-09 |  | 2025-02-28 | 2025-04-15 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | Labelless Media ApS | 101484 | NMA-058253 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-01-07 |  |  |  |  | 2025-02-28 | 2025-04-29 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | Labelless Media ApS | 101484 | NSW-058252 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-07 | 2025-05-16 | 2025-05-16 | Own OnNet | [6 empty] | 2025-04-29 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 0 | Labelless Media ApS | 102390 | NKA-058250 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-01-30 | 2025-05-16 | 2025-05-16 | Change | 2025-01-07 | 2025-01-27 06:47:00.000 |  | 2025-05-09 |  | 2025-02-28 |  | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 1395 | LaundryHouse ApS | 100684 | NKA-058086 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-01-03 | 2025-01-18 10:08:00.000 | 2025-01-29 12:22:00.000 | 2025-05-16 |  | 2025-03-21 | 2025-03-18 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | LaundryHouse ApS | 100684 | NMA-058088 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | 3rd Party | [6 empty] | 2025-03-18 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | LaundryHouse ApS | 100684 | NSW-058087 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-12-20 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-03-18 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 1487.98 | LE-Fix Clothing ApS | 105193 | NBM-060392 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-15 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-15 |  |  | 2025-05-16 |  | 2025-05-23 | 2025-04-15 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 1595 | Legendary Gaming Group ApS | 105322 | NKA-060450 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-23 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-23 | 2025-04-29 08:07:00.000 | 2025-04-28 13:27:00.000 | 2025-05-16 |  | 2025-06-13 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 895 | Limitless Reality ApS | 103229 | NKA-059986 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-03-27 | 2025-04-30 09:24:00.000 | 2025-05-02 13:07:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-05-08 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | 829.13 | Lise Frandsen ApS | 105407 | NBM-060606 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-08 |  |  | 2025-05-28 |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 83.12 | Lise Frandsen ApS | 105407 | NKA-025349 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Change |  |  |  | 2025-05-28 |  | 2025-05-28 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 2120 | Lokal Forsikring G/S | 91200 | NKA-052835 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-23 10:01:00.000 | 2024-02-23 10:01:00.000 |  |  |  |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 2120 | Lokal Forsikring G/S | 91200 | NKA-052836 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own with Digging | 2024-01-25 | 2024-02-23 10:01:00.000 | 2024-02-23 10:01:00.000 |  |  | 2024-03-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052837 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party | 2024-01-25 |  | 2025-05-12 12:52:00.000 |  |  | 2024-03-20 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052838 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-01-26 13:32:00.000 | 2024-01-26 13:32:00.000 | 2024-03-07 |  | 2024-02-16 | 2024-07-15 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052839 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-03-11 | 2024-03-20 11:12:00.000 | 2024-03-20 11:14:00.000 |  |  | 2024-05-24 | 2025-02-21 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052840 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-19 07:45:00.000 | 2024-02-19 07:45:00.000 |  |  | 2024-03-22 | 2025-02-18 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052841 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052842 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | 3rd Party | 2024-01-25 |  | 2025-05-12 12:48:00.000 |  |  |  | 2025-03-24 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052843 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party | 2024-01-25 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 970 | Lokal Forsikring G/S | 91200 | NKA-052844 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-28 07:25:00.000 | 2024-02-28 07:25:00.000 | 2024-03-18 |  | 2024-03-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 825 | Lokal Forsikring G/S | 91200 | NSW-052845 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 825 | Lokal Forsikring G/S | 91200 | NSW-052846 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052847 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052848 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052849 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052850 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052851 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052852 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | Own OnNet | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052853 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 530 | Lokal Forsikring G/S | 91200 | NSW-052854 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052845 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052847 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052848 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052849 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052850 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052851 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052852 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052853 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  |  | 1.1 Waiting on customer confirmation or input | Planning Installation & Service Window - Expected completed Q3 | 390 | Lokal Forsikring G/S | 98237 | NSW-052854 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 662 | Lomax A/S | 102189 | NBM-059710 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 950 | Lomax A/S | 102189 | NBM-059711 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 950 | Lomax A/S | 102189 | NBM-059712 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 4. Final design | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 2580.06 | Lomax A/S | 102189 | NBM-059713 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 4. Final design | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 2747.5 | Lomax A/S | 102189 | NKA-059706 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | 2025-03-11 | 2025-03-17 10:21:00.000 | 2025-03-31 14:14:00.000 | 2025-05-01 |  | 2025-05-02 | 2025-04-09 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 4. Final design | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 2747.5 | Lomax A/S | 102189 | NKA-059707 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | 2025-03-11 | 2025-03-17 10:21:00.000 | 2025-03-31 14:15:00.000 | 2025-05-01 |  | 2025-05-02 | 2025-04-09 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 4. Final design | 3.3 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange | 2550 | Lomax A/S | 102189 | NKA-059709 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 |  |  | 3rd Party | 2025-03-12 |  |  | 2025-05-07 |  | 2025-04-10 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1245 | LUTHERSK MISSIONSFORENING | 102804 | NKA-059162 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-03-19 | 2025-04-29 11:04:00.000 | 2025-05-13 14:28:00.000 | 2025-06-06 |  | 2025-06-06 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 225 | LUTHERSK MISSIONSFORENING | 102804 | NMA-059163 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-05-01 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 225 | LUTHERSK MISSIONSFORENING | 102804 | NSW-059164 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 600 | Macarons Design I/S | 103494 | NBM-059950 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party |  |  |  | 2025-05-30 |  | 2025-06-20 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 995 | Macarons Design I/S | 103494 | NKA-059947 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-04-01 | 2025-04-10 08:03:00.000 | 2025-04-29 10:56:00.000 | 2025-05-23 |  | 2025-06-20 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | Macarons Design I/S | 103494 | NMA-059948 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-06-20 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awating installation - The delivery is proceeding as planned | 200 | Macarons Design I/S | 103494 | NSW-059949 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 895 | Mano Event ApS | 100141 | NKA-059654 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-13 | 2025-04-10 06:58:00.000 | 2025-05-01 14:02:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 150 | Mano Event ApS | 100141 | NMA-059656 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-25 |  |  |  |  | 2025-05-30 | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 150 | Mano Event ApS | 100141 | NSW-059655 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | Own OnNet | [6 empty] | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 895 | Møbelkompagniet ApS | 104652 | NKA-060045 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-03 | 2025-05-07 10:21:00.000 |  | 2025-06-20 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 577.5 | Møbelkompagniet ApS | 104652 | NKA-060048 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-03 |  |  | 2025-06-06 |  | 2025-06-27 | 2025-04-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 180 | Møbelkompagniet ApS | 104652 | NMA-060047 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 577.5 | Møbelkompagniet ApS | 104652 | NML-060049 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-03 |  |  | 2025-06-06 |  |  | 2025-04-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | On track | 180 | Møbelkompagniet ApS | 104652 | NSW-060046 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 600 | NGZC ApS | 105044 | NBM-060260 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-04 |  |  | 2025-05-23 |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1600 | NGZC ApS | 105044 | NKA-060257 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-04 | 2025-05-01 14:14:00.000 | 2025-05-02 09:16:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-05-14 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 200 | NGZC ApS | 105044 | NMA-060259 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-04 |  |  |  |  | 2025-05-23 | 2025-05-14 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 200 | NGZC ApS | 105044 | NSW-060258 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 1095 | Norrlyst ApS | 104558 | NKA-059937 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-02 | 2025-04-25 09:26:00.000 | 2025-05-05 10:12:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 180 | Norrlyst ApS | 104558 | NMA-059939 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-05 |  |  |  |  | 2025-05-30 | 2025-05-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned | 180 | Norrlyst ApS | 104558 | NSW-059938 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed | Awaiting production at 3. party | 1149 | NOVARAM ApS | 100681 | NKA-059024 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-09-02 | 2025-05-02 | 3rd Party | 2025-04-23 |  |  | 2025-06-27 |  |  | 2025-02-26 | 2025-05-02 | 2025-05-02 | 2025-09-02 |  | New Sales | BO
[5 empty] | 350 | Ok A.M.B.A. | 102967 | NBM-060644 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 1050 | Ok A.M.B.A. | 102967 | NKA-060641 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet | [5 empty] | 2025-07-04 | [5 empty] | New Sales | BO
[5 empty] | 0 | Ok A.M.B.A. | 102967 | NMA-060643 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 0 | Ok A.M.B.A. | 102967 | NSW-060642 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1095 | Optinor ApS | 103352 | NKA-060551 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | Own with Digging | 2025-05-01 |  |  |  |  | 2025-07-11 | [5 empty] | New Sales | BO
[5 empty] | 200 | Optinor ApS | 103352 | NMA-060553 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 200 | Optinor ApS | 103352 | NSW-060552 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | Data center lacks capacity/need to Confirm ME Trunks | 2968 | Perspektiva IT ApS | 100657 | NKA-059019 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-02-20 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-20 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.3 Other installation obstacles and infratructure issues | Data center lacks capacity/need to Confirm ME Trunks | 2968 | Perspektiva IT ApS | 100657 | NKA-059020 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-02-20 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-20 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 20/06 | 1095 | Psykologhuset Trekanten ApS | 104667 | NKA-059980 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-27 | 2025-04-22 14:10:00.000 | 2025-05-08 10:31:00.000 | 2025-05-23 |  | 2025-06-13 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not started | 1410 | Radiant ApS | 105341 | NBM-060525 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-05-01 |  |  |  |  | 2025-06-20 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not started | 1195 | Radiant ApS | 105341 | NKA-060526 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-05-02 | 2025-05-05 14:18:00.000 | 2025-05-08 12:18:00.000 | 2025-05-30 |  | 2025-06-20 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | OH - Afventer kundes tilbagemelding omkring renoveret bygning | 1695 | Raw Power Games ApS | 97083 | NKA-055484 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-07-01 | 2025-06-13 | 2025-06-13 | 3rd Party | 2024-08-27 |  |  | 2025-06-06 |  |  | 2025-05-13 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On-track | 700 | salting & dyrby ApS | 104811 | NKA-060426 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-04-23 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On-track | 700 | salting & dyrby ApS | 104811 | NML-060427 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-23 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Confirmed delivery date: 02/05 | 1944 | Skousen NO | 100710 | NKA-057251 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-08 | 2025-05-28 | 2025-04-25 | 3rd Party | [5 empty] | 2025-05-01 | 2025-02-13 | 2025-04-25 | 2025-04-25 | 2025-05-28 | 2025-04-08 00:00:00.000 | New Sales | BO
[5 empty] | 1355 | Stavnskær Fragt A/S | 105016 | NKA-060603 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-07-25 | 2025-07-25 | Own OnNet | 2025-05-06 | 2025-05-07 12:27:00.000 | 2025-05-14 14:42:00.000 | 2025-06-06 |  | 2025-07-25 |  | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
[5 empty] | 4051 | STRATU ApS | 106547-008 | F35739-1136632-01 | 106547-008-001 | Cecilie Heidner Nielsen | SMB Portfolio DK | Created | 2025-04-30 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-07-22 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 0 | SYGEFORSIKRINGEN "DANMARK" GS | 101102 | NKA-057300 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-05 | 2025-05-30 | 2025-05-30 | Change | 2024-11-22 | 2024-12-09 09:09:00.000 | 2024-12-11 10:48:00.000 |  |  | 2025-01-31 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 101558 | NKA-057969 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-12-18 | 2024-12-19 08:22:00.000 | 2024-12-27 12:32:00.000 | 2025-01-31 |  |  | 2025-01-21 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 101558 | NML-057970 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-12-18 |  |  | 2025-01-31 |  |  | 2025-01-21 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | -23427 | SYGEFORSIKRINGEN "DANMARK" GS | 101606 | NBM-057308 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-12-19 | 2025-05-30 | 2025-05-30 | Change | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer |  | SYGEFORSIKRINGEN "DANMARK" GS | 102563 | NKA-057295 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-02-10 | 2025-05-30 | 2025-05-30 | Change | 2024-11-22 | 2024-12-13 13:31:00.000 | 2024-12-18 06:49:00.000 | 2025-04-04 |  | 2025-01-31 |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057301 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057302 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2577.88 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057303 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2411.24 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057304 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2096.58 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057305 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 2411.24 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057306 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 3325.92 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057307 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 24779 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NBM-057308 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057285 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-11-22 | 2024-11-26 14:58:00.000 | 2024-12-12 10:41:00.000 | 2025-02-25 |  | 2025-01-31 | 2025-01-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057287 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-29 |  |  | 2025-01-15 |  |  | 2025-01-03 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057289 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-11-22 | 2024-12-03 11:53:00.000 | 2024-12-11 13:01:00.000 | 2025-01-07 |  | 2025-01-10 | 2025-01-03 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057291 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-11-22 | 2024-12-08 23:23:00.000 | 2024-12-13 08:46:00.000 | 2025-01-20 |  | 2025-01-31 | 2025-01-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057293 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-02-28 |  |  | 2025-01-30 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057295 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-11-22 | 2024-12-13 13:31:00.000 | 2024-12-18 06:49:00.000 | 2025-01-31 |  | 2025-01-31 | 2025-01-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 1945 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057299 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-11-22 | 2024-12-06 09:03:00.000 | 2024-12-11 10:48:00.000 | 2025-01-30 |  | 2025-01-31 | 2025-01-30 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 1945 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NKA-057300 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | Own with Digging | 2024-11-22 | 2024-12-09 09:09:00.000 | 2024-12-11 10:48:00.000 | 2025-01-30 |  | 2025-01-31 | 2025-01-30 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057286 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-02-25 |  |  | 2025-01-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057288 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-29 |  |  | 2025-01-15 |  |  | 2025-01-03 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057290 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-01-07 |  |  | 2025-01-03 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057292 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-01-20 |  |  | 2025-01-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057294 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-02-28 |  |  | 2025-01-30 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | On track - Waiting on when the customer is ready to take the solution in use. We are first allowed to invoice the customer when the whole solution is taken in use. This is the agreement between Sales and the customer | 622.5 | SYGEFORSIKRINGEN "DANMARK" GS | 96115 | NML-057296 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-11-11 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-11-22 |  |  | 2025-01-31 |  |  | 2025-01-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 695 | Taconic Biosciences A/S | 104948 | NCI-060727 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1700 | Taconic Biosciences A/S | 104948 | NKA-060725 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1700 | Taconic Biosciences A/S | 104948 | NML-060726 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting customer accepting cost of internal cabling | 1595 | Trescal A/S | 95792 | NKA-056532 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-09-30 | 2026-04-25 | 2026-04-25 | 3rd Party | 2024-10-18 |  |  |  |  | 2025-01-10 | 2025-03-14 | 2026-04-25 | 2026-04-25 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting customer accepting cost of internal cabling | 1595 | Trescal A/S | 95792 | NKA-056533 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-09-30 | 2026-04-25 | 2026-04-25 | 3rd Party | 2024-10-10 |  |  |  |  | 2025-01-10 | 2025-03-14 | 2026-04-25 | 2026-04-25 |  |  | New Sales | BO
[5 empty] | 1242 | Vækst+ ApS | 104703 | NKA-059996 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-08 | 2025-04-09 09:05:00.000 | 2025-05-08 07:27:00.000 | 2025-05-23 |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Hanaded over from local deliver - Delivery not startede | 895 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NKA-059149 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 |  |  | Own OnNet | 2025-03-20 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Hanaded over from local deliver - Delivery not startede | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NMA-059151 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | 3rd Party | [7 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Hanaded over from local deliver - Delivery not startede | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NSW-059150 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | Own OnNet | [7 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 1095 | WOBA ApS | 104677 | NKA-059976 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet | 2025-04-07 | 2025-04-07 10:48:00.000 | 2025-04-24 08:08:00.000 |  |  | 2025-06-06 |  | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 180 | WOBA ApS | 104677 | NMA-059977 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | 3rd Party | 2025-04-07 |  |  |  |  | 2025-06-06 |  | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting Fiber PM - Delivery proceeding as planned | 180 | WOBA ApS | 104677 | NSW-059978 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
[5 empty] | -312.19 | Voldgiftsinstituttet | 105411 | NKA-030523 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Change | 2020-05-06 | 2020-05-12 14:32:00.000 | 2020-08-03 10:18:00.000 |  |  | 2020-06-24 |  | 2025-06-20 | 2025-06-20 |  |  | Change | BO
[5 empty] | 200 | Voldgiftsinstituttet | 105411 | NMA-060616 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-05-12 |  |  |  |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | 200 | Voldgiftsinstituttet | 105411 | NSW-060617 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | 995 | Wolt Services Danmark ApS | 105303 | NKA-060446 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-23 |  |  | Own OnNet | 2025-04-24 |  |  |  |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.2 Third party resource constraint | On track | 597.5 | ADDvision ApS | 102224 | NKA-059275 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-27 | 2025-05-27 | 3rd Party | 2025-03-06 |  |  | 2025-05-23 |  |  | 2025-03-13 | 2025-05-27 | 2025-05-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 597.5 | ADDvision ApS | 102224 | NKA-059277 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-06 | 2025-04-02 09:46:00.000 | 2025-04-10 10:52:00.000 | 2025-05-15 |  | 2025-05-09 | 2025-04-16 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.2 Third party resource constraint | Follows projektID 102224 | 597.5 | ADDvision ApS | 102224 | NML-059276 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-27 | 2025-05-27 | 3rd Party | 2025-03-06 |  |  | 2025-05-23 |  |  | 2025-03-13 | 2025-05-27 | 2025-05-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Follows projektID 102224 | 597.5 | ADDvision ApS | 102224 | NML-059278 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-06 |  |  | 2025-05-15 |  |  | 2025-04-16 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | -4.2 | A-One Solutions ApS | 101317 | NKA-044529 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2024-12-03 |  |  | Change | 2022-09-15 | 2022-12-30 11:10:00.000 | 2022-12-30 11:10:00.000 | [8 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 597.5 | Basic & More A/S | 103579 | NKA-059849 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-22 09:22:00.000 | 2025-04-28 14:22:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 597.5 | Basic & More A/S | 103579 | NML-059850 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-24 |  |  | 2025-05-16 |  | 2025-05-16 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[5 empty] | 597.5 | Basic & More A/S | 105734 | NKA-060730 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 597.5 | Basic & More A/S | 105734 | NML-060731 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 9. Documentation and vendor invoice |  | Klarmeldt d. 30-06-23 | 995 | Beat A/S | 81373 | NKA-043321 |  | Oliver Mariager | SMB Portfolio DK | RFS | 2022-06-30 | 2023-06-30 |  | Own OnNet
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1255 | BONE CONSULT A/S | 103330 | NKA-059806 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-17 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-19 | 2025-03-20 15:34:00.000 | 2025-04-23 09:55:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1255 | BONE CONSULT A/S | 103330 | NKA-059807 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-17 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-19 | 2025-03-20 15:34:00.000 | 2025-04-23 10:53:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, afventer SIM-kort info, herefter konfig | 1095 | ByFrame ApS | 103557 | NKA-059960 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-27 | 2025-04-30 08:10:00.000 | 2025-05-02 12:20:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, afventer SIM-kort info, herefter konfig | 200 | ByFrame ApS | 103557 | NMA-059961 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-05-16 | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track, afventer SIM-kort info, herefter konfig | 200 | ByFrame ApS | 103557 | NSW-059962 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-05-05 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1360 | Christiansen & Essenbæk A/S | 103186 | NKA-059642 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-06 | 2025-05-16 | 2025-05-16 | Own with Digging | 2025-03-11 | 2025-03-12 09:41:00.000 | 2025-04-14 12:23:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-04-07 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Dalsten Tandlægecenter ApS | 104897 | NKA-060056 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-28 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-07 | 2025-04-15 08:17:00.000 | 2025-04-25 13:17:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-04-28 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  |  |  | Part of migration project | 2200 | DANSK CAMPING UNION | 102100 | NKA-058445 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-01-17 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  | 2025-06-19 |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 2100 | DANSK CAMPING UNION | 102499 | NKA-058785 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-02-05 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 2100 | DANSK CAMPING UNION | 103124 | NKA-059177 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-01 | 2025-07-01 | 3rd Party | 2025-03-03 |  |  | 2025-06-04 |  | 2025-06-04 |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Afventer leveringsdato fra 3. part - intern flytning |  | Dansk Miljørådgivning A/S (DMR Geoteknik, DMR Skimmel & DMR Arbejdsmiljø) | 103430 | NKA-014092 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-11 |  |  | Change | 2016-03-30 |  |  |  |  | 2016-06-15 | 2025-04-10 |  |  |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1135 | Estatetool A/S | 103694 | NKA-059853 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-24 | 2025-04-22 10:54:00.000 | 2025-04-28 13:27:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 230 | Estatetool A/S | 103694 | NMA-059855 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-24 |  |  |  |  | 2025-05-16 | 2025-05-01 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 230 | Estatetool A/S | 103694 | NSW-059854 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-05-01 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Afventer leveringsdato fra 3. part | 300 | Faxe Kommune - IT-afdelingen | 103174 | NKA-059900 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-24 | 2025-05-26 | 2025-05-26 | 3rd Party | 2025-03-24 |  |  | 2025-05-20 |  |  | 2025-04-15 | 2025-05-26 | 2025-05-26 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  |  | 475 | Forsvarsministeriets Ejendomsstyrelse | 103026 | NKA-059934 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-25 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-04 | 2025-04-30 12:51:00.000 |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Afventer leveringsdato fra 3.part | 845 | Forsvarsministeriets Ejendomsstyrelse | 103320 | NKA-060338 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-04-10 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-04-22 |  | 2025-04-11 07:29:00.000 |  |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-008760 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-008823 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-008845 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1000 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009439 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009550 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009551 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009560 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009561 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-009562 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1850 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-013948 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015284 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015285 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015286 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015287 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015288 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015289 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015290 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015291 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015292 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015293 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015294 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015295 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015296 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015297 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015299 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015300 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015303 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015304 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015305 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015306 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015307 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015713 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-015714 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016468 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016472 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016474 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016475 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016477 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016480 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016481 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016483 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016484 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016485 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016487 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016488 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016489 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016490 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016785 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016833 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-016834 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020397 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020398 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020399 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020400 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020401 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020402 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020403 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020404 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020405 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020406 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020407 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020408 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020409 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020410 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020696 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020737 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020738 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-020841 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-021096 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 475 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-021240 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-021440 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 475 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-022407 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-022410 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-022437 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 475 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-022806 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-025641 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-025642 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-026207 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 525 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-026311 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-026312 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-026337 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-026338 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-028136 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-028324 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-028971 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-029256 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 1350 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-030226 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-031895 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-031896 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-034678 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-034801 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-035210 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 950 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-035346 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
[5 empty] | 475 | Forsvarsministeriets Ejendomsstyrelse | 82918 | NKA-037210 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2022-09-27 |  |  | Change
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1395 | Ganni A/S | 100380 | NKA-057854 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-05-21 | 2025-05-09 | Own with Digging | 2024-12-17 | 2025-03-14 13:21:00.000 | 2025-04-08 09:49:00.000 | 2025-05-14 |  | 2025-05-02 | 2025-04-16 | 2025-05-09 | 2025-05-09 | 2025-05-21 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1395 | Ganni A/S | 100380 | NKA-057855 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-05-21 | 2025-05-09 | Own with Digging | 2024-12-17 | 2025-03-14 13:21:00.000 | 2025-04-08 09:50:00.000 | 2025-05-14 |  | 2025-05-02 | 2025-04-16 | 2025-05-09 | 2025-05-09 | 2025-05-21 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 2500 | Ganni A/S | 100380 | NKA-057859 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-12-13 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Other installation obstacles and infratructure issues | Awaits power supply in the shop | 4600 | Ganni A/S | 102217 | NKA-058736 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-02-03 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-02-05 | [6 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | Hansens Gamle Familiehave ApS | 95669 | NKA-059070 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-02-25 | 2025-05-23 | 2025-05-23 | Own with Digging | 2025-03-04 | 2025-04-01 10:34:00.000 | 2025-04-23 09:58:00.000 | 2025-05-16 |  |  | 2025-04-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 597.5 | Hildebrandt & Brandi Danmark A/S | 103074 | NKA-059851 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-03-27 | 2025-04-03 08:49:00.000 | 2025-04-07 10:20:00.000 | 2025-06-27 |  | 2025-05-16 | 2025-04-08 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 597.5 | Hildebrandt & Brandi Danmark A/S | 103074 | NML-059852 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-03-27 |  |  | 2025-06-27 |  | 2025-05-16 | 2025-04-08 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | on track | 1310 | Hudklinik v/Henrik Rask Kralund | 103099 | NKA-060073 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-08 |  |  | 2025-06-20 |  | 2025-06-11 | 2025-05-01 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | I/S Lægerne Sønderhøj | 102968 | NKA-059245 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-03 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-06 | 2025-03-12 09:53:00.000 | 2025-04-30 09:21:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-05 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1195 | Impero A/S | 103196 | NKA-059273 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-23 | 2025-05-16 | Own OnNet | 2025-03-07 | 2025-03-28 13:34:00.000 | 2025-04-03 08:57:00.000 | 2025-05-16 |  | 2025-04-25 | 2025-04-08 | 2025-05-16 | 2025-05-16 | 2025-05-23 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer leveringsdato | 597.5 | Koppers Denmark ApS | 101089 | NKA-059858 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-03-27 |  |  |  |  | 2025-05-16 | 2025-04-04 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 2.3 Internal resource constraints (e.g., no one to work on the order) | Fast track, NML er sendt til billing | 597.5 | Koppers Denmark ApS | 101089 | NML-059859 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-05-16 | 2025-04-04 | 2025-12-31 | 2025-12-31 |  | 2025-04-22 00:00:00.000 | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Waiting for an installation date | 1895 | Lelectric A/S | 102363 | NKA-060451 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-04-23 | 2025-07-09 | 2025-07-09 | 3rd Party | 2025-04-28 |  |  | 2025-07-04 |  |  | 2025-05-05 | 2025-07-09 | 2025-07-09 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | New order - awaits delivery date | 2255 | Moldow A/S | 105337 | NKA-060471 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-04-25 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-01 |  |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
[5 empty] | 1495 | Møgelhøj Arkitekter P/S | 102749 | NKA-058872 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-02-11 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-02-17 |  |  | 2025-06-13 |  | 2025-04-16 | 2025-02-26 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Stille awating final date for delivery | 1300 | Naturstyrelsen | 100652 | NKA-057903 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-12-16 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-03-05 |  |  | 2025-07-11 |  | 2025-04-24 | 2025-03-18 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Confirmed delivery | 1300 | Naturstyrelsen | 100652 | NKA-057905 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-12-16 | 2025-06-29 | 2025-06-29 | 3rd Party | 2025-03-05 |  |  | 2025-08-25 |  | 2025-04-23 | 2025-03-25 | 2025-06-29 | 2025-06-29 |  |  | New Sales | BO
|  |  |  | Part of migration project | 0 | Nr. Snede Fængsel | 103616 | NKA-004029 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change |  |  |  | 2025-06-04 | [7 empty] | Change | BO
|  |  |  | Part of migration project | 0 | Nr. Snede Fængsel | 103616 | NKA-005319 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change |  |  |  | 2025-06-10 |  | 2025-06-10 | [5 empty] | Change | BO
|  | 4. Final design | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Peter Skafte ApS | 104549 | NKA-059979 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-01 | 2025-04-30 07:41:00.000 | 2025-05-07 10:44:00.000 | 2025-05-23 |  | 2025-05-23 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | On Track |  | Part of migration project | 1555 | Region Nordjylland | 103176 | NKA-059644 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-11 |  | 2025-03-06 15:51:00.000 |  |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | On Track |  | Part of migration project | 1555 | Region Nordjylland | 103176 | NML-059645 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 622.5 | Riel Sikring ApS | 101555 | NKA-057864 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-16 |  |  | 2025-05-23 |  | 2025-06-30 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. | 622.5 | Riel Sikring ApS | 101555 | NML-057865 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-09 |  |  | 2025-05-23 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer leveringsdato | 895 | Selmatec A/S | 102792 | NKA-059836 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-20 | 2025-05-12 08:15:00.000 | 2025-05-09 08:27:00.000 | 2025-05-23 |  | 2025-06-06 | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer leveringsdato | 200 | Selmatec A/S | 102792 | NMA-059838 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-20 |  |  |  |  | 2025-06-06 | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer leveringsdato | 200 | Selmatec A/S | 102792 | NSW-059837 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-28 | 2025-05-28 | Own OnNet | [6 empty] | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Deleyed due to local restriction on site | 1100 | Skive Kommune | 94395 | NKA-054245 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-04-29 | 2025-07-07 | 2025-07-07 | 3rd Party | 2024-06-07 |  |  | 2025-06-30 |  | 2024-08-15 | 2024-07-01 | 2025-07-07 | 2025-07-07 |  |  | New Sales | BO
|  | 5. Configuration | 1.2 Customer not reachable / unresponsive | Afventer ok fra kunden på fast strrøm | 845 | Statens Museum For Kunst | 102147 | NKA-058894 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-02-12 | 2025-05-16 | 2025-05-16 | 3rd Party | 2025-02-25 | 2025-02-25 14:33:00.000 | 2025-02-13 09:07:00.000 |  |  |  |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 845 | Statens Museum For Kunst | 103393 | NKA-059791 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-17 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-18 | 2025-03-20 12:08:00.000 | 2025-03-31 11:22:00.000 | 2025-05-16 |  | 2025-05-09 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 103416 | NKA-059719 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-11 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-04-07 |  |  | 2025-06-27 |  | 2025-06-19 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060326 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060327 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060328 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060329 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060330 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060331 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060332 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 105145 | NKA-060333 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-23 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 98971 | NKA-056784 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-10-14 |  |  | 3rd Party | 2024-11-05 |  |  | 2024-12-16 |  | 2025-01-15 | [5 empty] | New Sales | BO
|  |  |  | Part of migration project | 0 | Telenor A/S | 99904 | NKA-056783 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-10-14 |  |  | 3rd Party | 2024-11-05 |  |  | 2024-12-16 |  | 2025-01-15 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | The Marketing Guy ApS | 103086 | NKA-059816 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-18 | 2025-05-20 | 2025-05-20 | Own OnNet | 2025-03-19 | 2025-04-08 12:26:00.000 | 2025-04-24 14:41:00.000 | 2025-05-16 |  |  | 2025-04-25 | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | Unicontrol ApS | 102597 | NKA-059967 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | Own OnNet | 2025-03-27 | 2025-03-28 07:11:00.000 |  | 2025-07-25 |  | 2025-05-16 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Unicontrol ApS | 102597 | NMA-059968 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-05-16 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Unicontrol ApS | 102597 | NSW-059969 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | Own OnNet | [7 empty] | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[5 empty] | 1200 | VICURAS DK A/S | 105621 | NKA-060728 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet | 2025-05-14 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Længere dialog mellem udlejer, kunde og 3. part | 1278 | 101 Copenhagen ApS | 102707 | NKA-059028 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-07 |  |  | 2025-06-06 |  | 2025-05-16 | 2025-04-15 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Længere dialog mellem udlejer, kunde og 3. part | 255 | 101 Copenhagen ApS | 102707 | NMA-059030 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-07 |  |  |  |  | 2025-05-16 | 2025-04-15 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Third party vendor delay | Længere dialog mellem udlejer, kunde og 3. part | 255 | 101 Copenhagen ApS | 102707 | NSW-059029 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | Own OnNet | [6 empty] | 2025-04-15 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) |  | 1495 | Abstracta Interiør A/S | 105245 | NKA-060441 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-23 |  |  | Own OnNet | 2025-04-23 |  |  |  |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 574.5 | ADDvision ApS | 101976 | NKA-060219 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-02 | 2025-05-01 12:34:00.000 | 2025-05-05 12:56:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-04-04 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 574.5 | ADDvision ApS | 101976 | NML-060220 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-02 |  |  | 2025-05-23 |  | 2025-05-30 | 2025-04-04 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | ADDvision ApS | 102766 | NKA-031201 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-12 | 2025-07-18 | 2025-07-18 | Change | 2025-02-21 |  |  | 2025-07-18 |  | 2025-03-28 | 2025-03-26 | 2025-07-18 | 2025-07-18 |  |  | Change | BO
[5 empty] | 597.5 | ADDvision ApS | 103431 | NKA-060621 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 |  |  | Own OnNet | 2025-05-08 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 597.5 | ADDvision ApS | 103431 | NML-060622 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 |  |  | 3rd Party | 2025-05-08 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 547.5 | ADDvision ApS | 105459 | NKA-060584 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-05-05 | 2025-05-13 13:22:00.000 |  | 2025-06-13 |  | 2025-06-20 | 2025-05-05 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | 547.5 | ADDvision ApS | 105459 | NML-060585 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-05-05 |  |  | 2025-06-13 |  | 2025-06-20 | 2025-05-05 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 996 | Adminia ApS | 105363 | NKA-060472 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 |  |  | Own with Digging | 2025-04-28 |  |  |  |  | 2025-07-11 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 200 | Adminia ApS | 105363 | NMA-060473 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 |  |  | 3rd Party | 2025-04-28 |  |  |  |  | 2025-07-11 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 200 | Adminia ApS | 105363 | NSW-060474 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1659 | Advokaterne i Rosenborggade I/S | 105327 | NKA-060686 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet | 2025-05-13 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer Netplan, så prov | 950 | Aktieselskabet Bremen | 102096 | NKA-059178 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-03-13 | 2025-04-15 14:07:00.000 | 2025-05-02 11:52:00.000 | 2025-05-23 |  | 2025-06-06 | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer Netplan, så prov | 950 | Aktieselskabet Bremen | 102096 | NML-059179 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-13 |  |  | 2025-05-23 |  | 2025-06-06 | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1195 | Allunite A/S | 102186 | NKA-058503 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-02-03 | 2025-04-28 10:08:00.000 | 2025-05-12 10:50:00.000 | 2025-06-06 |  | 2025-04-16 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058504 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-14 |  |  |  |  | 2025-04-04 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058516 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-03 |  |  |  |  | 2025-03-21 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058517 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-03 |  |  |  |  | 2025-03-21 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058520 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-02-03 |  |  |  |  | 2025-04-16 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058523 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-03 | 2025-03-03 15:12:00.000 | 2025-03-07 13:24:00.000 |  |  | 2025-03-21 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer godkendelse fra bygningsejer | 1195 | Allunite A/S | 102186 | NKA-058524 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-02-06 | 2025-02-28 14:04:00.000 | 2025-03-18 08:27:00.000 | 2025-05-23 |  | 2025-03-28 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | afventer installation | 4000 | Alphadyne Asset Management (Europe) A/S | 102644 | NKA-059831 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer COLT i UK | 4000 | Alphadyne Asset Management (Europe) A/S | 102644 | NKA-059834 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-04-09 | 2025-04-14 12:15:00.000 | 2025-04-22 14:20:00.000 | 2025-05-12 |  | 2025-06-06 |  | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Afventer prov for håndtering af IPv6 adresser | 0 | Anchor Lab K/S | 103946 | NKA-032881 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-20 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 895 | Andersen-Andersen ApS | 105420 | NKA-060619 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 |  |  | Own OnNet | 2025-05-08 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design | 795 | Apel Fine Jewellery | 102850 | NKA-059168 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-03-13 | 2025-05-09 08:39:00.000 |  | 2025-07-04 |  | 2025-06-06 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design | 150 | Apel Fine Jewellery | 102850 | NMA-059170 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design | 150 | Apel Fine Jewellery | 102850 | NSW-059169 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | Own OnNet | [7 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer venfor | 622.5 | ARC Nordic A/S | 104918 | NKA-060521 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-25 | 2025-07-25 | 3rd Party | 2025-05-07 |  |  | 2025-07-18 |  | 2025-07-04 |  | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer venfor | 622.5 | ARC Nordic A/S | 104918 | NML-060522 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-25 | 2025-07-25 | 3rd Party | 2025-05-07 |  |  | 2025-07-18 |  | 2025-07-04 |  | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
[5 empty] | 1295 | Arpe & Kjeldsholm A/S | 105688 | NKA-060707 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-05-13 | 2025-05-14 09:19:00.000 |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 695 | Bagt ApS | 102606 | NKA-060099 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-07 | 2025-05-08 07:57:00.000 | 2025-05-08 07:57:00.000 | 2025-05-23 |  | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | Bagt ApS | 102606 | NKA-060102 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own with Digging | 2025-04-07 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | Bagt ApS | 102606 | NKA-060105 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own with Digging | [5 empty] | 2025-07-04 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 1350 | Bagt ApS | 102606 | NKA-060108 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party |  |  |  | 2025-06-13 |  | 2025-07-04 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 1350 | Bagt ApS | 102606 | NKA-060111 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-07 |  |  | 2025-06-20 |  | 2025-07-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 1350 | Bagt ApS | 102606 | NKA-060114 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-07 |  |  | 2025-06-20 |  | 2025-07-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NMA-060101 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | 3rd Party | [5 empty] | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NMA-060104 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | 2025-04-07 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NMA-060107 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | [5 empty] | 2025-07-04 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NMA-060110 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | [5 empty] | 2025-07-04 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NMA-060113 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | 2025-04-07 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NMA-060116 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | 2025-04-07 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NSW-060100 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NSW-060103 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Bagt ApS | 102606 | NSW-060106 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NSW-060109 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NSW-060112 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready | On track | 150 | Bagt ApS | 102606 | NSW-060115 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 995 | BEGRAVELSESFORRETNINGEN DEN SIDSTEREJSE V/SOLVEJG RITZAU | 105398 | NKA-060598 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 |  |  | Own with Digging | 2025-05-08 |  |  |  |  | 2025-08-31 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1795 | Begroni ApS | 103050 | NKA-060520 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-29 | 2025-05-13 10:11:00.000 | 2025-05-13 10:12:00.000 | 2025-05-23 |  | 2025-06-20 | 2025-05-13 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra kunden omkring SV | -100 | Bionordika Denmark A/S | 104650 | NKA-025618 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | Change | 2018-09-12 | 2018-10-04 10:21:00.000 | 2018-10-05 11:30:00.000 | 2025-05-22 |  | 2018-12-05 |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra kunden omkring SV | 230 | Bionordika Denmark A/S | 104650 | NMA-059963 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | 3rd Party | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra kunden omkring SV | 230 | Bionordika Denmark A/S | 104650 | NSW-059964 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-23 | 2025-05-23 | Own OnNet | [7 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | Afventer svar fra kunden på info omkring DC/Rack | 1099 | Blueprint | 100868 | NKA-057898 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-13 |  |  | Own OnNet | 2025-05-08 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1550 | Bolig Buddy ApS | 98852 | NKA-056432 |  | Line Skov | SMB Portfolio DK | In Process | 2024-09-24 | 2025-05-23 | 2025-05-16 | Own with Digging | 2025-01-30 | 2025-04-01 09:35:00.000 | 2025-04-15 10:06:00.000 | 2025-05-16 |  | 2025-05-16 | 2025-04-07 | 2025-05-16 | 2025-05-16 | 2025-05-23 |  | New Sales | BO
[5 empty] | 1100 | Boligforeningen Grønløkken | 107620-002 | C36637-1136771-01 | 107620-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-06-27 |  | Own with Digging | [5 empty] | 2025-06-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 0 | Boligforeningen Grønløkken | 107620-002 | C36637-1136772-01 | 107620-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-06-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installation | 1395 | Bomae ApS | 105415 | NKA-060529 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-30 | 2025-05-12 10:24:00.000 | 2025-05-01 14:52:00.000 | 2025-05-30 |  | 2025-05-28 | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Britt Sisseck | 97827 | NKA-060422 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet | 2025-04-25 |  |  |  |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Britt Sisseck | 97827 | NMA-060424 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-04-25 |  |  |  |  | 2025-06-13 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Britt Sisseck | 97827 | NSW-060423 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1900 | C.F. Møller Norge AS | 105249 | NKA-060465 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-24 |  |  | 3rd Party | 2025-04-28 |  |  |  |  | 2025-07-18 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installation | 2200 | Cadesign base A/S | 101983 | NKA-060123 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-07 | 2025-04-10 08:36:00.000 | 2025-04-29 09:11:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-04-30 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1371 | Cadesign base A/S | 102065-030 | C32152-1135219-01 | 102065-030-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-05-30 |  | Own with Digging | [5 empty] | 2025-05-30 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | Cadesign base A/S | 102065-030 | C32152-1135220-01 | 102065-030-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-05-30 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | -0.55333 | Cadesign base A/S | 102065-030 | C32152-1135221-01 | 102065-030-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-05-30 |  | Change | [5 empty] | 2025-05-30 |  |  | 2025-05-30 | 2025-05-30 |  | Change | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installation | 849.93 | Cadesign base A/S | 104899 | NKA-060054 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-02 | 2025-04-03 09:32:00.000 | 2025-04-07 09:00:00.000 | 2025-06-13 |  | 2025-06-06 | 2025-04-09 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installation | 849.93 | Cadesign base A/S | 104899 | NML-060055 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-28 |  |  | 2025-06-13 |  | 2025-06-06 | 2025-04-09 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra TK | 1495 | Cematech ApS | 102720 | NDD-059955 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra TK | 1295 | Cematech ApS | 102720 | NKA-059954 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer svar fra TK | 200 | Cematech ApS | 102720 | NML-059956 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning | 1196 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NKA-052598 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-05-23 | 2025-05-23 | Own with Digging | 2023-05-22 | 2024-06-19 13:54:00.000 | 2024-06-19 13:55:00.000 |  |  |  | 2024-04-22 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning | 199.5 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NMA-052599 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-05-23 | 2025-05-23 | 3rd Party | 2023-12-22 | [5 empty] | 2024-04-22 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Zen omlægning | 199.5 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NSW-052600 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2024-04-22 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1895 | Chatservice ApS | 105285 | NKA-060436 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-22 | 2025-05-08 15:44:00.000 | 2025-05-13 08:09:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer Netplan | 1495 | CIC Operations Odense ApS | 98795 | NKA-057086 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-11-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2024-11-13 | 2025-04-04 09:58:00.000 | 2025-05-02 11:09:00.000 | 2025-06-13 |  | 2025-01-31 | 2025-05-06 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Waiting for Fiber PM to start the project | 1245 | Citrusmedia ApS | 105037 | NKA-060263 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-04-04 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-04 | 2025-05-02 13:47:00.000 | 2025-05-05 10:24:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-05-06 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | Have a meeting with customer in week 19 | 2500 | Compugroup Medical Denmark A/S | 101944-014 | C32025-1134067-01 | 101944-014-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-17 | 2025-05-30 | 2025-03-14 | Change |  |  |  | 2025-03-14 |  | 2025-04-09 | 2025-03-05 | 2025-03-14 | 2025-05-30 | 2025-05-30 |  | Change | AX
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | Have a meeting with customer in week 19 | 2900 | Compugroup Medical Denmark A/S | 101944-014 | C32025-1134069-01 | 101944-014-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-17 | 2025-05-30 | 2025-03-14 | Change |  |  |  | 2025-03-14 |  | 2025-04-09 | 2025-03-05 | 2025-03-14 | 2025-05-30 | 2025-05-30 |  | Change | AX
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 794 | ConXus A/S | 105120 | NKA-060402 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-16 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-22 | 2025-04-23 12:00:00.000 | 2025-04-24 09:32:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-05-08 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | ConXus A/S | 105120 | NMA-060404 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-16 |  |  | 3rd Party | [5 empty] | 2025-05-23 | 2025-05-08 |  |  |  |  | New Sales | BO
|  | 5. Configuration |  | On track | 150 | ConXus A/S | 105120 | NSW-060403 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-16 |  |  | Own OnNet | [6 empty] | 2025-05-08 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Har afventet 3P - Er klar til os nu, skal blot finde dato | 997.5 | Danibo ApS | 97085 | NKA-054814 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-06-17 | 2025-05-30 | 2025-05-30 | 3rd Party |  |  |  | 2024-12-12 |  |  |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Har afventet 3P - Er klar til os nu, skal blot finde dato | 997.5 | Danibo ApS | 97085 | NML-054815 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-06-17 | 2025-05-30 | 2025-05-30 | 3rd Party |  |  |  | 2024-12-12 |  |  |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Dan-Revision Taastrup ApS | 104848 | NKA-060222 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 |  |  | Own with Digging | 2025-04-07 |  |  |  |  | 2025-09-22 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Dan-Revision Taastrup ApS | 104848 | NML-060221 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 |  |  | 3rd Party | 2025-04-07 |  |  |  |  | 2025-04-22 | [5 empty] | New Sales | BO
[5 empty] | -1439.2667 | Dansk Arbejdsgiverforening | 100862-014 | C30825-1136598-01 | 100862-014-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2025-04-29 | 2025-05-23 |  | Change | [5 empty] | 2025-07-21 |  |  | 2025-05-23 | 2025-05-23 |  | Change | AX
[5 empty] | 2500 | Dansk Arbejdsgiverforening | 100862-014 | C30825-1136599-01 | 100862-014-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-07-21 |  |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 134 | Dansk Arbejdsgiverforening | 100862-014 | C30825-1136600-01 | 100862-014-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-07-21 |  |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Dansk It | 105023 | NKA-060359 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-14 | 2025-05-06 14:17:00.000 | 2025-05-14 13:22:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Dansk It | 105023 | NML-060360 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[5 empty] | 995 | Dansk Turbo Teknik A/S | 105272 | NKA-060668 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-13 |  |  |  |  | 2025-08-01 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | -774.9 | Danske Advokater | 103584 | NKA-005674 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-02 | 2025-05-28 | 2025-05-28 | Change | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer Netplan | 1260 | Danske Advokater | 103584 | NKA-060224 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-02 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-04-23 15:09:00.000 | 2025-05-07 15:29:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  | -2900.95 | Dayforce A/S | 102950 | NKA-025351 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Afventer kunden, skal finde dato for SV | -1666.06 | Dayforce A/S | 102950 | NKA-032475 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Change | 2020-11-25 | 2021-02-02 11:17:00.000 | 2021-02-02 11:17:00.000 | [8 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | Afventer design | 1326 | Dentorium ApS | 103142 | NKA-059860 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-28 |  |  |  |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 1994 | Dignity - Dansk Institut Mod Tortur | 102249 | NKA-058696 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-30 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-17 | 2025-03-03 07:35:00.000 | 2025-03-12 14:47:00.000 |  |  | 2025-04-11 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | SV skal sættes op | 2050 | DKI Management A/S | 101227 | NKA-058380 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-01-23 | 2025-01-27 14:20:00.000 | 2025-01-29 10:27:00.000 | 2025-03-27 |  | 2025-03-14 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | SV skal sættes op | 2050 | DKI Management A/S | 101227 | NKA-058381 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-01-23 | 2025-01-27 14:21:00.000 | 2025-01-29 12:36:00.000 | 2025-03-27 |  | 2025-03-14 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | SV skal sættes op | 2400 | DKI Management A/S | 101227 | NKA-058382 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-01-23 | 2025-01-27 14:22:00.000 | 2025-01-29 13:09:00.000 | 2025-03-27 |  | 2025-03-14 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Arrange service Windoew with customer | -468.61 | ed A/S | 96319 | NKA-028814 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2024-10-09 | 2025-05-16 | 2025-05-16 | Change | 2019-10-23 |  |  | 2025-05-14 |  |  |  | 2025-05-16 | 2025-05-16 |  |  | Change | BO
[5 empty] | -2218 | Edora A/S | 105533 | NKA-049932 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-07 | 2025-05-16 | 2025-05-16 | Change | 2023-10-02 | 2023-10-11 08:21:00.000 | 2023-10-11 08:21:00.000 |  |  | 2023-12-15 |  | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Third party vendor delay | Afventer TDC klarmelder | 1395 | Ejendomsselskabet Lyngby Hovedgade 78 ApS | 99947 | NKA-056809 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-10-15 | 2025-05-30 | 2025-05-30 | 3rd Party | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | SV skal sættes op | 1195 | EKHO EKHO | 101232 | NKA-025721 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-12-05 | 2025-05-23 | 2025-05-23 | Change | 2018-09-26 |  |  | 2025-05-21 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | SV skal sættes op | 200 | EKHO EKHO | 101232 | NML-057697 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-12-05 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-03 |  |  |  |  | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | -1268.61 | Event Space ApS | 103077 | NKA-036803 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-12 |  |  | Change | 2021-09-14 | 2021-10-05 13:52:00.000 | 2021-08-31 14:08:00.000 |  |  | 2021-11-16 | [5 empty] | Change | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 213.27 | Event Space ApS | 103077 | NKA-036804 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-12 |  |  | Change | 2021-09-14 | 2021-10-05 13:49:00.000 | 2021-08-31 14:12:00.000 |  |  | 2021-11-16 | [5 empty] | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Mangler config på 4G delen | -250.62 | Executive Cognito A/S | 102304 | NKA-034187 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-31 |  |  | Change | 2021-04-19 |  |  | 2025-04-07 | [7 empty] | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Mangler config på 4G delen | 200 | Executive Cognito A/S | 102304 | NML-058724 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-31 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 995 | exs nordic A/S | 105610 | NKA-060648 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-12 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE for patchning | 1500 | FAB:IT ApS | 107317-002 | C36378-1125451-01 | 107317-002-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-05-30 |  | Own OnNet | [5 empty] | 2024-04-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE for patchning | 0 | FAB:IT ApS | 107317-002 | C36378-1125453-01 | 107317-002-003 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-05-30 |  | Own OnNet | [5 empty] | 2024-04-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE for patchning | 2000 | FAB:IT ApS | 107317-002 | C36378-1125454-01 | 107317-002-004 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-05-30 |  | Own OnNet | [5 empty] | 2024-04-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE for patchning | 0 | FAB:IT ApS | 107317-002 | C36378-1125456-01 | 107317-002-006 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-05-30 |  | Own OnNet | [5 empty] | 2024-04-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE for patchning | 2000 | FAB:IT ApS | 107317-002 | C36378-1125457-01 | 107317-002-007 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-05-30 |  | Own OnNet | [5 empty] | 2024-04-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 1200 | Fænøsundlægerne I/S | 104846 | NKA-060261 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-08 | 2025-05-02 08:48:00.000 | 2025-05-12 09:13:00.000 | 2025-06-20 |  | 2025-06-06 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[5 empty] | 1495 | FEC Taby Ab | 107397-003 | C36447-1136725-01 | 107397-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-08-15 |  | Own OnNet | [5 empty] | 2025-07-21 |  |  | 2025-08-15 | 2025-08-15 |  | New Sales | AX
[5 empty] | 0 | FEC Taby Ab | 107397-003 | C36447-1136726-01 | 107397-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-08-15 |  | Own OnNet | [5 empty] | 2025-07-21 |  |  | 2025-08-15 | 2025-08-15 |  | New Sales | AX
[5 empty] | 1495 | Fiberline Building Profiles A/S | 105577 | NKA-060610 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-05-05 | 2025-05-07 15:14:00.000 | 2025-05-08 13:51:00.000 | 2025-05-23 |  | 2025-05-23 | 2025-05-13 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | Filmkontakt Nord. Fonden For Nordiske Kort- og Dokumentarfilm | 105343 | NKA-057312 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-24 | 2025-05-30 | 2025-05-30 | Change | 2024-11-21 | 2024-12-06 10:55:00.000 | 2024-12-10 10:51:00.000 | 2025-05-23 |  | 2025-01-10 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Waiting for 3 party | 977.3533 | Finans Danmark | 103973-004 | C33538-1134609-01 | 103973-004-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-06 | 2025-05-30 | 2025-05-30 | Change |  |  |  | 2025-05-26 |  | 2025-04-29 | 2025-04-09 | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | Change | AX
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Waiting for 3 party | -2285.79 | Finans Danmark | 103973-004 | C33538-1134611-01 | 103973-004-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-06 | 2025-05-30 | 2025-05-30 | Change |  |  |  | 2025-05-26 |  | 2025-04-29 | 2025-04-09 | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | Change | AX
[5 empty] | 3000 | FINN FROGNE A/S | 106740-008 | C35898-1136681-01 | 106740-008-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 3000 | FINN FROGNE A/S | 106740-008 | C35898-1136682-01 | 106740-008-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 50 | FINN FROGNE A/S | 106740-008 | C35898-1136684-01 | 106740-008-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 50 | FINN FROGNE A/S | 106740-008 | C35898-1136685-01 | 106740-008-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 60 | FINN FROGNE A/S | 106740-008 | C35898-1136686-01 | 106740-008-006 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 60 | FINN FROGNE A/S | 106740-008 | C35898-1136687-01 | 106740-008-007 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[5 empty] | 176 | FINN FROGNE A/S | 106740-008 | C35898-1136688-01 | 106740-008-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-06-25 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 1395 | Fjord Rådgivende Ingeniører A/S | 102594 | NKA-059957 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-15 | 2025-08-15 | Own OnNet | 2025-05-13 |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
[5 empty] | 1695 | Flexdanmark | 102845-005 | C32515-1136586-01 | 102845-005-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Own with Digging | [5 empty] | 2025-07-21 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[5 empty] | 0 | Flexdanmark | 102845-005 | C32515-1136587-01 | 102845-005-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Change | [5 empty] | 2025-07-21 |  |  | 2025-05-28 | 2025-05-28 |  | Change | AX
[5 empty] | 100 | Flexdanmark | 102845-005 | C32515-1136588-01 | 102845-005-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Change | [5 empty] | 2025-07-21 |  |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | Mangler blot installation | 2500 | Fonden for Herning Isstadion | 101024 | NKA-059152 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-03-13 | 2025-03-25 10:37:00.000 | 2025-04-14 14:10:00.000 | 2025-05-09 |  | 2025-05-09 | 2025-04-29 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need a FE and a service window | 3600 | Fonden Wonderful Copenhagen | 107556-002 | C36592-1133981-01 | 107556-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-10 | 2025-05-23 | 2025-04-04 | Own with Digging |  |  |  | 2025-04-04 |  | 2025-04-02 |  | 2025-04-04 | 2025-05-23 | 2025-05-23 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer Netplan | 1510 | Fondsmæglerselskabet Marselis A/S | 104901 | NKA-060079 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-09 | 2025-04-30 14:25:00.000 | 2025-05-08 12:20:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-13 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[5 empty] | 1116.9 | Foreningshuset Sundholm8 | 84553 | NKA-046136 |  | Lars Gottschalck | SMB Portfolio DK | RFS | 2022-12-14 | 2023-04-12 |  | Own OnNet
[5 empty] | 2550 | Forum Cph ApS | 107618-002 | C36635-1136705-01 | 107618-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-06 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-30 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | 60 | Forum Cph ApS | 107618-002 | C36635-1136706-01 | 107618-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-06 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-30 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | 9200 | Forum Cph ApS | 107618-002 | C36635-1136708-01 | 107618-002-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-06 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-30 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | 60 | Forum Cph ApS | 107618-002 | C36635-1136710-01 | 107618-002-006 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-06 | 2025-05-30 | 2025-05-30 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-30 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | 895 | Frederiksborggade Øjenklinik v/Hanne Göte | 105705 | NKA-060708 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 |  |  | Own OnNet | 2025-05-13 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 984 | Fresh Out The Oven ApS | 103173 | NKA-059994 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-28 | 2025-05-02 11:46:00.000 |  | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 697.5 | Frøslev Træ A/S | 103631 | NKA-059903 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party | 2025-05-06 |  |  | 2025-06-27 |  | 2025-06-17 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NKA-059905 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NKA-059907 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NKA-059909 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 697.5 | Frøslev Træ A/S | 103631 | NKA-059911 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-11 | 2025-04-30 09:54:00.000 | 2025-05-06 13:55:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 697.5 | Frøslev Træ A/S | 103631 | NML-059904 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party |  |  |  | 2025-06-27 | [7 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NML-059906 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NML-059908 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 597.5 | Frøslev Træ A/S | 103631 | NML-059910 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Afventer opennet | 697.5 | Frøslev Træ A/S | 103631 | NML-059912 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-11 |  |  | 2025-05-30 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[5 empty] | -210.23 | Fsb I Gladsaxe | 105176 | NKA-040724 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Change | 2022-03-07 | 2022-04-12 12:57:00.000 | 2022-03-02 10:38:00.000 |  |  | 2022-05-25 | [5 empty] | Change | BO
[5 empty] | 200 | Fsb I Gladsaxe | 105176 | NMA-040726 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Change | [11 empty] | Change | BO
[5 empty] | -292.71 | Fsb I Gladsaxe | 105176 | NSW-040725 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer afvikling af SV den 15/5 | 734.1 | GORM x ENVISION A/S | 103391 | NKA-050671 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-18 | 2025-05-16 | 2025-05-16 | Change | 2023-10-17 | 2023-10-23 12:12:00.000 | 2023-10-26 10:37:00.000 | 2025-05-15 |  | 2023-12-15 |  | 2025-05-16 | 2025-05-16 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer afvikling af SV den 15/5 | 2210 | GORM x ENVISION A/S | 103391 | NKA-059820 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-18 | 2025-06-27 | 2025-06-27 | Own OnNet | 2024-03-26 | 2025-04-23 09:27:00.000 | 2025-04-30 07:40:00.000 | 2025-06-27 |  | 2025-05-16 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Skal først leveres til oktober | 949 | GREEN STORAGE A/S | 95021 | NKA-054920 |  | Line Skov | SMB Portfolio DK | In Process | 2024-06-24 | 2025-10-01 | 2025-10-01 | 3rd Party | [7 empty] | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer installationsuge | 1295 | Gustaf Fagerberg A/S | 102958 | NKA-060519 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-28 | 2025-08-15 | 2025-08-15 | Own OnNet | 2024-04-30 |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
[5 empty] | 1100 | H. BAASCH EJENDOMME ApS | 107614-002 | C36634-1136549-01 | 107614-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-20 |  |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
[5 empty] | 0 | H. BAASCH EJENDOMME ApS | 107614-002 | C36634-1136550-01 | 107614-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-23 |  | Own OnNet | [5 empty] | 2025-06-20 |  |  | 2025-05-23 | 2025-05-23 |  | New Sales | AX
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - service vindue | 714.9 | H+ A/S | 105390 | NKA-035285 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Change | 2021-06-16 | 2021-11-10 15:08:00.000 | 2021-11-10 15:08:00.000 |  |  | 2021-12-01 | [5 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer afvikling af servicevindue | -578.59 | H9 ApS | 98474 | NKA-021308 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-10-18 | 2025-05-23 | 2025-05-23 | Change | 2024-04-29 |  |  | 2025-05-21 |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer afvikling af servicevindue | 200 | H9 ApS | 98474 | NML-056835 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-10-18 | 2025-05-23 | 2025-05-23 | 3rd Party | [5 empty] | 2025-05-16 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | 1495 | Hallerupnet ApS | 103076 | NDD-059810 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | 1497.87 | Hallerupnet ApS | 103076 | NKA-043808 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change | 2022-09-05 | [10 empty] | Change | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | 1888.5 | Hallerupnet ApS | 103076 | NKA-059809 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | 1000 | Hallerupnet ApS | 103076 | NKA-059811 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet | 2025-04-11 |  |  |  |  | 2025-06-06 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | -2141.4 | Hallerupnet ApS | 103076 | NRS-043807 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | AFventer intern/ekstern afklaring omkring nogle ting vedr. DC | 1888.5 | Hallerupnet ApS | 103076 | NRS-059808 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning - afventer afvikling | 2000 | Heimstaden Flintholm Kollegiet ApS | 94367 | NKA-053529 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-03-01 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-03-05 | 2024-03-06 09:30:00.000 | 2024-03-06 09:31:00.000 |  |  | 2024-05-03 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Got new dates from Fiber PM | 1865 | Hesehus A/S | 104734-010 | C34237-1134236-01 | 104734-010-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2025-01-27 | 2025-05-28 | 2025-05-16 | Own OnNet |  |  |  | 2025-05-09 |  | 2025-04-15 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Got new dates from Fiber PM | 842 | Hesehus A/S | 104734-010 | C34237-1134237-01 | 104734-010-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-27 | 2025-05-28 | 2025-05-02 | Own OnNet |  |  |  | 2025-04-25 |  | 2025-04-15 |  | 2025-05-02 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Got new dates from Fiber PM | 228 | Hesehus A/S | 104734-010 | C34237-1134238-01 | 104734-010-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-27 | 2025-05-28 | 2025-05-02 | Own OnNet |  |  |  | 2025-04-25 |  | 2025-04-15 |  | 2025-05-02 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Holst-Group ApS | 104453 | NKA-059874 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-31 | 2025-05-02 07:14:00.000 | 2025-05-05 09:38:00.000 | 2025-05-23 |  | 2025-05-23 | 2025-05-07 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Holst-Group ApS | 104453 | NMA-059876 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-31 |  |  |  |  | 2025-05-16 | 2025-05-07 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Holst-Group ApS | 104453 | NSW-059875 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-05-28 | 2025-05-28 | Own OnNet | [6 empty] | 2025-05-07 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1395 | Holtec Automatic A/S | 100768 | NKA-058900 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-12 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-03-19 |  |  | 2025-05-23 |  | 2025-04-29 | 2025-04-11 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Hudklinikken Helsingør I/S | 103481 | NKA-060089 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-01 | 2025-04-15 09:41:00.000 | 2025-04-28 08:01:00.000 | 2025-05-16 |  | 2025-05-30 | 2025-04-28 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 622.5 | Hudklinikken Helsingør I/S | 103481 | NML-060090 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-04-01 |  |  | 2025-05-16 |  | 2025-04-15 | 2025-04-28 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 749 | Infolink ApS | 102404 | NKA-060218 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-04-02 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-04-02 | 2025-04-04 10:23:00.000 | 2025-04-28 12:12:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-04-30 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Afventer - muligvis ny vendor | 995 | Institutionen Thomas P.Hejles Ungdomshus | 105308 | NKA-060437 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet | 2025-04-23 |  |  |  |  | 2025-06-13 | [5 empty] | New Sales | BO
[5 empty] | -523.7133 | Intecredo International ApS | 104899-009 | C34376-1136842-01 | 104899-009-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change | [5 empty] | 2025-07-03 |  |  | 2025-08-01 | 2025-08-01 |  | Change | AX
[5 empty] | 1033.6567 | Intecredo International ApS | 104899-009 | C34376-1136843-01 | 104899-009-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change | [5 empty] | 2025-07-03 |  |  | 2025-08-01 | 2025-08-01 |  | Change | AX
[5 empty] | -505.0633 | Intecredo International ApS | 104899-009 | C34376-1136844-01 | 104899-009-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change | [5 empty] | 2025-07-03 |  |  | 2025-08-01 | 2025-08-01 |  | Change | AX
[5 empty] | -1084.9 | Intecredo International ApS | 104899-009 | C34376-1136848-01 | 104899-009-007 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change | [5 empty] | 2025-07-03 |  |  | 2025-08-01 | 2025-08-01 |  | Change | AX
[5 empty] | 0 | Intecredo International ApS | 104899-009 | C34376-1136849-01 | 104899-009-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Own OnNet | [5 empty] | 2025-07-03 |  |  | 2025-08-01 | 2025-08-01 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 995 | IntraVAT ApS | 100480 | NKA-057080 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-05 | 2025-05-23 | 2025-05-23 | 3rd Party | 2024-12-03 |  |  |  |  | 2025-02-28 | 2025-02-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 150 | IntraVAT ApS | 100480 | NMA-057082 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-05 | 2025-05-23 | 2025-05-23 | 3rd Party | 2024-12-03 |  |  |  |  | 2025-02-28 | 2025-02-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | On track | 150 | IntraVAT ApS | 100480 | NSW-057081 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-05 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-02-25 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1495 | Ismageriet ApS | 104409-004 | C33943-1134819-01 | 104409-004-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-19 | 2025-05-30 | 2025-05-16 | Own OnNet |  |  |  | 2025-05-09 |  | 2025-05-14 | 2025-04-02 | 2025-05-16 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | Ismageriet ApS | 104409-004 | C33943-1134820-01 | 104409-004-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-19 | 2025-05-30 | 2025-05-16 | Own OnNet |  |  |  | 2025-05-09 |  | 2025-05-14 |  | 2025-05-16 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Provisioning awaits info from custormer | 2460 | IT Forum Gruppen A/S | 102529 | NKA-058983 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-18 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-21 | 2025-03-25 10:45:00.000 | 2025-03-25 10:46:00.000 |  |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Provisioning awaits info from custormer | 2460 | IT Forum Gruppen A/S | 102529 | NKA-058984 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-18 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-21 | 2025-03-25 10:46:00.000 | 2025-03-25 10:55:00.000 |  |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Delivery late August | 1324 | IT Forum Gruppen A/S | 102686 | NKA-059689 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
[5 empty] | -4800.92 | Jelling Familie Camping ApS | 105442 | NKA-028737 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-06 | 2025-06-06 | Change | 2019-10-15 |  |  | 2025-05-16 |  | 2019-11-26 |  | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 3. Installation preparation and digging order | Other (incl. termination, on hold etc.) | Waiting for a delivery date | 0 | Jeudan A/S | 105215 | NKA-060361 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-11 |  |  | Own OnNet | 2025-04-22 |  |  |  |  | 2025-06-06 | [5 empty] | New Sales | BO
[6 empty] | Jeudan A/S | 105609 | NKA-025629 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 | 2025-05-19 | 2025-05-19 | Change | 2018-09-14 | 2018-09-26 11:39:00.000 | 2018-09-27 09:03:00.000 |  |  | 2018-10-26 |  | 2025-05-19 | 2025-05-19 |  |  | Change | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold etc.) | On track | 1895 | Keepers ApS | 102583 | NKA-059116 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-03 | 2025-06-03 | Own OnNet | 2025-03-03 | 2025-03-19 13:20:00.000 | 2025-04-10 10:51:00.000 | 2025-05-19 |  | 2024-04-25 |  | 2025-06-03 | 2025-06-03 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Waiting for 3 party | 2495 | Keepers ApS | 102668 | NKA-059862 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed | On track | 1095 | Kirkebjerg Køreskole ApS | 85903 | NKA-046870 |  | Line Skov | SMB Portfolio DK | In Process | 2023-02-16 | 2025-07-04 | 2025-07-04 | Own with Digging | 2023-02-17 | 2025-05-07 14:09:00.000 |  | 2025-06-27 |  | 2023-05-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Skal aftales SV for | 847.5 | Kjærgaard A/S | 93908 | NKA-053097 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-02-01 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-02-09 | 2024-02-22 14:28:00.000 | 2024-02-16 11:04:00.000 | 2024-02-27 |  | 2024-03-08 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Skal aftales SV for | 847.5 | Kjærgaard A/S | 93908 | NML-053098 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-02-01 | 2025-05-23 | 2025-05-23 | 3rd Party |  |  |  | 2024-02-27 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 899 | Klc Erhverv København ApS | 104717 | NKA-060316 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-08 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-09 | 2025-05-07 12:46:00.000 | 2025-05-12 09:06:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  |  |  | RFS 2022 | 443.688 | Klimadan A/S | 101027-003 | C30991-1111651-01 | 101027-003-001 | Shazia Mobin | SMB Portfolio DK | RFS | 2022-05-06 | 2022-06-29 | 2022-06-29 | Change
[5 empty] | 955 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NKA-060626 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | Own OnNet | 2025-05-09 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
[5 empty] | 200 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NMA-060627 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | 3rd Party | 2025-05-09 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
[5 empty] | 200 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NSW-060628 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold etc.) | New order - awaits delivery date | 1695 | Konsulent Bjarne Aalbæk | 105153 | NKA-060443 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-23 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-01 |  |  | 2025-07-11 |  | 2025-06-25 | 2025-05-07 | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 2000 | Krogstrup ApS | 103606 | NKA-060357 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-04-14 |  |  | 2025-06-27 |  | 2025-07-11 | 2025-04-29 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1299 | Kuube Denmark ApS | 102144 | NKA-058447 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-02-10 |  |  | 2025-05-30 |  | 2025-05-09 | 2025-04-29 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Kuube Denmark ApS | 102144 | NMA-058448 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-05-09 | 3rd Party | 2025-02-10 |  |  |  |  | 2025-05-09 | 2025-04-29 | 2025-05-09 | 2025-05-09 | 2025-06-06 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Kuube Denmark ApS | 102144 | NSW-058449 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-05-09 | Own OnNet | [6 empty] | 2025-04-29 | 2025-05-09 | 2025-05-09 | 2025-06-06 |  | New Sales | BO
[5 empty] | 622.5 | Læge Torben Larsen | 105483 | NKA-060582 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-05 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 622.5 | Læge Torben Larsen | 105483 | NML-060583 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party | 2025-05-05 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | ontrack | 912 | Landinspektørfirmaet Hyldegaard P/S | 102373 | NKA-059249 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-04 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-03-13 | 2025-04-29 12:59:00.000 | 2025-05-02 08:37:00.000 | 2025-05-16 |  | 2025-05-09 | 2025-05-02 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
[5 empty] | 1700 | LEMAN A/S | 105301 | NKA-060555 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-05-02 | 2025-05-06 14:33:00.000 |  | 2025-06-20 |  | 2025-07-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Lokalbolig Hvidovre ApS | 103266 | NKA-059865 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-28 | 2025-05-02 10:47:00.000 |  | 2025-06-13 |  | 2025-05-16 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Lokalbolig Hvidovre ApS | 103266 | NMA-059864 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-28 |  |  |  |  | 2025-05-16 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 200 | Lokalbolig Hvidovre ApS | 103266 | NSW-059863 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer SV dato | 1345 | Ls Montage ApS | 100378 | NKA-056963 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-10-29 | 2025-07-04 | 2025-05-23 | 3rd Party | 2025-05-06 |  |  | 2025-06-27 |  | 2025-06-17 |  | 2025-05-23 | 2025-05-23 | 2025-07-04 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1445 | Lyngby Låse & Alarm ApS | 103576 | NKA-059812 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-17 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-03-18 | 2025-04-23 08:37:00.000 | 2025-04-28 09:45:00.000 | 2025-05-16 |  | 2024-04-25 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 952 | MOBILXPERTEN ApS | 103839 | NKA-060352 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-10 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-04-14 | 2025-05-09 12:53:00.000 |  | 2025-07-04 |  | 2025-07-11 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
[5 empty] | 625 | MOBILXPERTEN ApS | 105536 | NKA-060684 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own with Digging | 2025-05-13 |  |  |  |  | 2025-08-08 | [5 empty] | New Sales | BO
[5 empty] | 625 | MOBILXPERTEN ApS | 105536 | NML-060685 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | 3rd Party | [5 empty] | 2025-08-08 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | afventer COLT svar | 3660 | Mos Mosh A/S | 103236 | NKA-060075 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party | 2025-04-09 | [10 empty] | New Sales | BO
[5 empty] | 995 | Move Innovation ApS | 102737 | NKA-060683 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet | [5 empty] | 2025-07-04 | [5 empty] | New Sales | BO
[5 empty] | 1595 | N3 ApS | 103317 | NKA-060527 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-04-30 |  |  |  |  | 2025-06-20 | [5 empty] | New Sales | BO
[5 empty] | 622.5 | Najell Denmark ApS | 105329 | NKA-060534 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-05-02 | 2025-05-13 13:00:00.000 |  | 2025-06-13 |  | 2025-06-20 | [5 empty] | New Sales | BO
[5 empty] | 622.5 | Najell Denmark ApS | 105329 | NML-060535 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 |  |  | 3rd Party | 2025-05-02 |  |  | 2025-06-13 |  | 2025-06-20 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer SV dato | -181.16 | Natus Medical Denmark ApS | 101313 | NKA-019996 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-04-25 | Change | 2017-03-24 | 2017-04-20 14:57:00.000 | 2017-04-24 10:14:00.000 |  |  | 2017-06-16 |  | 2025-04-25 | 2025-04-25 | 2025-05-30 |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer SV dato | 1495 | Natus Medical Denmark ApS | 101313 | NKA-057962 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-18 | 2025-05-30 | 2025-04-04 | Own with Digging | 2025-01-10 | 2025-02-26 12:38:00.000 | 2025-02-27 15:16:00.000 | 2025-03-07 |  |  |  | 2025-04-04 | 2025-04-04 | 2025-05-30 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | Noteless AS | 105323 | NKA-060475 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-25 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-28 | 2025-04-28 14:35:00.000 | 2025-04-29 15:03:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-09 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 225 | Noteless AS | 105323 | NMA-060477 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-25 |  |  | 3rd Party | 2025-04-28 |  |  |  |  | 2025-06-06 | 2025-05-09 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 225 | Noteless AS | 105323 | NSW-060476 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-25 |  |  | Own OnNet | [6 empty] | 2025-05-09 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Waiting for 3 party | 2100 | Ntrakker AB | 106002-016 | C35287-1136087-01 | 106002-016-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-08 | 2025-07-11 |  | 3rd Party | [5 empty] | 2025-06-27 |  |  | 2025-07-11 | 2025-07-11 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 3.2 Third party resource constraint | Waiting for 3 party | 60 | Ntrakker AB | 106002-016 | C35287-1136088-01 | 106002-016-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-08 | 2025-07-11 |  | Own OnNet | [5 empty] | 2025-06-27 |  |  | 2025-07-11 | 2025-07-11 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 3313 | NØRGÅRD MIKKELSEN REKLAMEBUREAU A/S | 102585 | NKA-059894 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-21 | 2025-07-15 | 2025-07-15 | Own with Digging | 2025-03-31 | 2025-04-04 08:57:00.000 |  | 2025-06-20 |  | 2024-06-27 |  | 2025-07-15 | 2025-07-15 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.2 Customer not reachable / unresponsive | Rebooked for week 21 postponed as customer pours floor | 1778 | Oreco A/S | 103235 | NKA-059760 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-13 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-19 | 2025-04-03 09:38:00.000 | 2025-04-03 09:39:00.000 | 2025-05-23 |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[5 empty] | 647.5 | Our Units ApS | 104852 | NKA-060530 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-04-30 |  |  |  |  | 2025-06-20 | [5 empty] | New Sales | BO
[5 empty] | 647.5 | Our Units ApS | 104852 | NML-060531 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | 3rd Party | 2025-04-30 |  |  |  |  | 2025-06-20 | [5 empty] | New Sales | BO
[5 empty] | 1400 | Oustrupgård Agro ApS | 97994 | NKA-056743 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-10-10 | 2025-06-13 | 2025-06-13 | 3rd Party | 2024-10-18 |  |  |  |  | 2025-01-10 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | on track | 895 | Owayy ApS | 103102 | NKA-059174 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-13 | 2025-04-09 08:34:00.000 | 2025-04-11 12:06:00.000 | 2025-05-16 |  | 2025-05-09 | 2025-05-02 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | on track | 200 | Owayy ApS | 103102 | NMA-059175 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-23 | 2025-05-23 | 3rd Party | [6 empty] | 2025-05-02 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | on track | 200 | Owayy ApS | 103102 | NSW-059176 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-05-02 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | on track | 1295 | P+p Arkitekter A/S | 103316 | NKA-059901 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-27 | 2025-04-01 12:32:00.000 | 2025-04-24 06:48:00.000 | 2025-05-16 |  | 2025-05-23 | 2025-04-29 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
[6 empty] | Penta Advokater A/S | 105456 | NKA-013625 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-30 |  |  | Change | 2024-04-12 | [5 empty] | 2025-05-01 |  |  |  |  | Change | BO
[5 empty] | 1841 | Penta Advokater A/S | 105457 | NKA-060629 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-07 |  |  | Own OnNet | 2025-05-08 |  |  |  |  | 2025-11-01 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1300 | Planet2030 | 98496 | NKA-058679 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-29 | 2025-05-23 | 2025-05-16 | Own with Digging | 2025-02-11 | 2025-04-01 09:18:00.000 | 2025-04-15 10:02:00.000 | 2025-05-16 |  | 2025-05-02 | 2025-04-16 | 2025-05-16 | 2025-05-16 | 2025-05-23 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Planet2030 | 98496 | NMA-058681 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-29 | 2025-05-23 | 2025-05-16 | 3rd Party | 2025-04-22 |  |  |  |  | 2025-05-16 | 2025-04-16 | 2025-05-16 | 2025-05-16 | 2025-05-23 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Planet2030 | 98496 | NSW-058680 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-29 | 2025-05-23 | 2025-05-16 | Own OnNet | [6 empty] | 2025-04-16 | 2025-05-16 | 2025-05-16 | 2025-05-23 |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning | 897.5 | Polaris Management A/S | 94828 | NKA-054033 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-04-12 | 2025-05-23 | 2025-05-23 | Own OnNet | 2024-04-29 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning | 897.5 | Polaris Management A/S | 94828 | NML-054034 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-04-12 | 2025-05-23 | 2025-05-23 | 3rd Party | 2024-04-29 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Pompette ApS | 105163 | NKA-060334 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-05-08 13:23:00.000 | 2025-05-12 10:03:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Pompette ApS | 105163 | NMA-060336 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 |  |  | 3rd Party | 2025-04-10 |  |  |  |  | 2025-06-06 | 2025-05-13 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 150 | Pompette ApS | 105163 | NSW-060335 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [6 empty] | 2025-05-13 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | PROCOPA IT ApS | 105881-080 | C35226-1135895-01 | 105881-080-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-01 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-05-23 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 995 | PROCOPA IT ApS | 105881-081 | C35226-1135920-01 | 105881-081-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-02 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-05-27 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
[5 empty] | -231.9567 | PROCOPA IT ApS | 105881-082 | C35226-1136819-01 | 105881-082-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-12 | 2025-07-04 |  | Change | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | Change | AX
[5 empty] | 795 | PROJECT OPEN ApS | 107619-003 | C36636-1136796-01 | 107619-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet | [5 empty] | 2025-06-27 | [5 empty] | New Sales | AX
[5 empty] | 96 | PROJECT OPEN ApS | 107619-003 | C36636-1136797-01 | 107619-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet | [5 empty] | 2025-06-27 | [5 empty] | New Sales | AX
[5 empty] | 0 | PROJECT OPEN ApS | 107619-003 | C36636-1136798-01 | 107619-003-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet | [5 empty] | 2025-06-27 | [5 empty] | New Sales | AX
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | SV skal sættes op | 31.53 | Pålsson Arkitekter A/S | 105003 | NKA-040572 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-07 |  |  | Change | 2022-02-23 | 2022-03-10 10:11:00.000 | 2022-02-16 19:53:00.000 |  |  | 2022-03-31 | [5 empty] | Change | BO
[5 empty] | 895 | RareWine ApS | 104737 | NKA-060533 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-05-02 | 2025-05-05 12:59:00.000 | 2025-05-14 10:56:00.000 | 2025-06-06 |  | 2025-06-20 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato fra kunden for SV | -0.62 | Rasmussen Skilte ApS | 102434 | NKA-036506 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | Change | 2021-07-27 | 2021-08-26 19:05:00.000 |  |  |  | 2021-10-04 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato fra kunden for SV | 200 | Rasmussen Skilte ApS | 102434 | NMA-058842 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato fra kunden for SV | 200 | Rasmussen Skilte ApS | 102434 | NSW-058843 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1195 | RIGHT PEOPLE GROUP ApS | 107438-003 | C36481-1135502-01 | 107438-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-21 | 2025-06-13 | 2025-06-13 | Own with Digging |  |  |  | 2025-06-06 |  | 2025-06-12 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 0 | RIGHT PEOPLE GROUP ApS | 107438-003 | C36481-1135503-01 | 107438-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-21 | 2025-06-13 | 2025-06-13 | Own OnNet |  |  |  | 2025-06-13 |  | 2025-06-12 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 497.5 | Riverty Services Denmark A/S | 104661 | NKA-060039 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-03 | 2025-04-10 12:12:00.000 | 2025-05-12 07:43:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 497.5 | Riverty Services Denmark A/S | 104661 | NML-060040 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-30 |  |  | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | On track | 2600 | Rosendahl Design Group A/S | 102302 | NKA-058845 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | 3rd Party | 2025-03-27 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | On track | 1095 | Saint Revision ApS | 103138 | NKA-059253 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-04 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-12 | 2025-04-30 10:46:00.000 | 2025-05-08 15:11:00.000 | 2025-05-23 |  | 2025-05-02 | 2025-05-09 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | On track | 200 | Saint Revision ApS | 103138 | NMA-059254 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-04 |  |  | 3rd Party | [5 empty] | 2025-05-28 | 2025-05-09 |  |  |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | On track | 200 | Saint Revision ApS | 103138 | NSW-059255 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-04 |  |  | Own OnNet | [6 empty] | 2025-05-09 |  |  |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | -1099.31 | Sephora Danmark ApS | 100014 | NKA-038507 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change | [11 empty] | Change | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | -1099.31 | Sephora Danmark ApS | 100014 | NKA-038509 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change | [11 empty] | Change | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | 876.52 | Sephora Danmark ApS | 100014 | NML-038508 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change | [11 empty] | Change | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | 876.52 | Sephora Danmark ApS | 100014 | NML-038510 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change | [11 empty] | Change | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | -199.31 | Sephora Danmark ApS | 100017 | NKA-037347 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change | 2021-10-05 | [10 empty] | Change | BO
|  | 1.Order entry and validation | 2.5 Internal or external data/documentation incomplete/ incorrect | Koordinater forkerte, 3P vil ik udføre de er rigtig - sendt retur til salg | 100 | Sephora Danmark ApS | 100017 | NML-057260 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | The customer has not responded regarding the date for the inspection. | 1399 | Sharp Business Systems Danmark A/S | 103117 | NKA-060180 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-01 | 2025-05-13 13:14:00.000 | 2025-05-13 13:30:00.000 | 2025-05-30 |  | 2025-05-30 | 2025-05-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1245 | Simons Padel Club ApS | 102857 | NKA-058992 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-02-19 | 2025-05-16 | 2025-05-16 | Own OnNet | 2025-02-24 | 2025-04-09 12:32:00.000 | 2025-04-28 12:26:00.000 | 2025-05-16 |  | 2025-04-18 | 2025-04-30 | 2025-05-16 | 2025-05-16 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer design | 852 | Sleep in Heaven ApS | 103041 | NKA-059821 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-27 | 2025-05-01 10:57:00.000 | 2025-05-06 08:35:00.000 | 2025-05-23 |  | 2025-05-23 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer design | 852 | Sleep in Heaven ApS | 103041 | NKA-059822 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-27 | 2025-05-01 10:37:00.000 | 2025-05-06 10:12:00.000 | 2025-05-23 |  | 2025-05-23 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | afvneter installation and prov | 2.4 Pending equipment/product to be ready | afvneter installation and prov | 895 | Smiley Fitness ApS | 103111 | NKA-059171 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-13 | 2025-04-24 10:35:00.000 | 2025-05-06 13:34:00.000 |  |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready | afvneter installation and prov | 200 | Smiley Fitness ApS | 103111 | NMA-059172 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready | afvneter installation and prov | 200 | Smiley Fitness ApS | 103111 | NSW-059173 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.3 Other installation obstacles and infratructure issues | Waiting for an installation date | 895 | Sofigate ApS | 105312 | NKA-060442 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-23 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-24 | 2025-04-28 15:13:00.000 | 2025-04-28 10:11:00.000 | 2025-06-06 |  |  | 2025-05-12 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[5 empty] | 1245 | Space Composite Structures DENMARK APS | 100398 | NKA-060586 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-05 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | -435.9 | Space gaming ApS | 101332 | NKA-030643 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Change | 2020-05-29 | 2020-06-08 14:22:00.000 | 2020-07-09 13:47:00.000 |  |  | 2020-07-27 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 250 | Space gaming ApS | 101332 | NMA-057699 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 250 | Space gaming ApS | 101332 | NSW-057698 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 1421 | Strøm Hansen A/S | 105440 | NKA-060597 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-05-05 | 2025-05-06 07:38:00.000 | 2025-05-09 10:48:00.000 | 2025-05-30 |  | 2025-06-20 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Suaning Import | 102078 | NKA-058362 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-02-12 |  |  | 2025-05-16 |  |  | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 149.5 | Suaning Import | 102078 | NMA-058364 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-02-12 | [5 empty] | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 149.5 | Suaning Import | 102078 | NSW-058363 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | Own OnNet | [6 empty] | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1395 | Subit ApS | 105278 | NKA-060408 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-16 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-22 | 2025-04-22 12:29:00.000 | 2025-04-25 10:34:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 500 | Sulzer Pumps Denmark A/S | 102723 | NDD-059659 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | -3267.91 | Sulzer Pumps Denmark A/S | 102723 | NKA-035286 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 |  |  | Change | 2021-06-16 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kunde svar omkring dato for SV | 200 | Sulzer Pumps Denmark A/S | 102723 | NML-059658 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 |  |  | 3rd Party | [11 empty] | New Sales | BO
[5 empty] | 1595 | SVEJSECENTER REHERMANN A/S | 105514 | NKA-042793 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-23 | 2025-05-23 | Change | 2022-06-03 | 2022-12-29 14:38:00.000 | 2022-12-29 14:38:00.000 | 2025-05-22 |  |  |  | 2025-05-23 | 2025-05-23 |  |  | Change | BO
[5 empty] | 200 | SVEJSECENTER REHERMANN A/S | 105514 | NML-060596 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-05-07 | [6 empty] | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | ontrack | 447.5 | Tandlægeselskabet Klinik for Kæbekirurgi I/S | 104593 | NKA-059932 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-02 | 2025-04-24 07:24:00.000 | 2025-04-30 11:22:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-01 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | ontrack | 447.5 | Tandlægeselskabet Klinik for Kæbekirurgi I/S | 104593 | NML-059933 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-02 |  |  | 2025-05-23 |  | 2025-05-30 | 2025-05-01 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready | afventer design | 1095 | Tariq ApS | 103139 | NKA-059682 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-10 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-14 | 2025-05-01 13:20:00.000 | 2025-05-06 11:15:00.000 | 2025-05-23 |  | 2025-05-09 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 550 | Td-K A/S | 101714-006 | C31680-1135555-01 | 101714-006-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-25 | 2025-05-16 | 2025-05-16 | Own OnNet |  |  |  | 2025-05-09 |  | 2025-06-16 |  | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 550 | Td-K A/S | 101714-006 | C31680-1135556-01 | 101714-006-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-25 | 2025-05-16 | 2025-05-16 | Own OnNet |  |  |  | 2025-05-09 |  | 2025-06-16 |  | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | New Sales | AX
|  | 2. Delivery planning | 3.1 Third party vendor delay | afventer tdc | 700 | Tegnestuen Vandkunsten A/S | 101036 | NKA-057597 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-28 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-10 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | afventer tdc | 700 | Tegnestuen Vandkunsten A/S | 101036 | NML-057598 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-28 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-10 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | Telebesparelse ApS | 105083 | NKA-060317 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-10 | 2025-05-12 15:23:00.000 | 2025-05-14 13:59:00.000 | 2025-06-13 |  | 2025-06-06 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | Telebesparelse ApS | 105083 | NKA-060318 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own with Digging | 2025-04-10 |  |  |  |  | 2025-07-04 | [5 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1095 | Telebesparelse ApS | 105083 | NKA-060319 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [5 empty] | 2025-06-06 | [5 empty] | New Sales | BO
[6 empty] | Telecom X ApS | 105378 | NKA-034507 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 |  |  | Change | 2021-05-03 | 2021-05-04 10:45:00.000 | 2021-06-17 10:15:00.000 |  |  | 2021-06-24 | [5 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaits FiberPM | 1317 | Temashop ApS | 98382 | NKA-056221 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-13 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-10-04 | 2025-05-05 12:38:00.000 | 2025-05-14 13:15:00.000 | 2025-06-06 |  | 2024-12-20 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaits FiberPM | 1317 | Temashop ApS | 98382 | NML-056222 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-13 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  |  | 2025-06-06 |  |  |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer kundes svar på SV dato | 1295 | The Company Group A/S | 102438 | NKA-059007 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-20 | 2025-05-23 | 2025-05-23 | Own OnNet | 2025-03-27 |  |  |  |  | 2025-05-23 |  | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready | Ontrack | 2200 | Topsil Globalwafers A/S | 103231 | NKA-059922 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-02 |  |  |  |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready | ontrack | -763.73 | Topsil Globalwafers A/S | 103231 | NOC-995820 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Change | [11 empty] | Change | BO
[5 empty] | 1295 | Totalklima ApS | 105380 | NKA-060532 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet | 2025-04-30 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 995 | Truckplanner A/S | 105461 | NKA-060623 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-06 |  |  | Own OnNet | 2025-05-07 | 2025-05-13 08:27:00.000 | 2025-05-14 07:43:00.000 | 2025-05-16 |  |  | 2025-05-13 |  |  |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready | ontrack | 1495 | Tømrermester Jim Jensen A/S | 102182 | NKA-058670 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-29 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-02-10 | 2025-02-14 13:12:00.000 | 2025-02-20 10:55:00.000 | 2025-05-30 |  | 2025-04-11 | 2025-03-03 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato for SV, aftales med kunden | -427.32 | Væxthuset 3 ApS | 101127 | NKA-010325 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Change | 2015-03-11 | [10 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato for SV, aftales med kunden | 165 | Væxthuset 3 ApS | 101127 | NMA-057713 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | afventer dato for SV, aftales med kunden | 165 | Væxthuset 3 ApS | 101127 | NSW-057712 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 4. Final design | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1160 | Vamdrup Fjernvarme A m b A | 105019 | NKA-060255 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-03 | 2025-07-11 | 2025-07-11 | Own OnNet | 2025-04-10 | 2025-04-11 08:19:00.000 | 2025-05-05 12:19:00.000 | 2025-06-27 |  | 2025-06-06 | 2025-05-06 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 2500 | Wennick Enterprise A/S | 103127 | NKA-059797 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-17 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-18 | 2025-04-25 08:23:00.000 | 2025-05-07 10:51:00.000 | 2025-05-16 |  | 2025-06-06 | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaits scheduling service window | 3111 | Veo Technologies ApS | 102743 | NDD-059652 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaits scheduling service window | -3051.47 | Veo Technologies ApS | 102743 | NKA-035994 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-28 | 2025-05-28 | Change | 2021-09-10 | 2021-10-25 17:34:00.000 | 2021-07-12 07:47:00.000 |  |  | 2021-11-04 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed | Ordren skulle have været reverted i februar - reverted 30-04-2025 og bestilt på ny | 895 | Verdens Skove, Århus | 102530 | NKA-058987 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-18 | 2025-06-27 | 2025-05-16 | 3rd Party | 2025-04-30 |  |  | 2025-05-09 |  | 2025-06-27 |  | 2025-05-16 | 2025-05-16 | 2025-06-27 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - skal først leveres 1. august | 2095 | Vest Energi ApS | 105347 | NKA-060508 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-25 | 2025-07-25 | Own OnNet | 2025-04-29 | 2025-04-30 10:23:00.000 | 2025-05-06 12:52:00.000 | 2025-07-18 |  | 2025-07-25 | 2025-05-09 | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Servicevindue skal aftales | 1495 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NDD-056466 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 | 2025-05-28 | 2025-05-28 | Own OnNet | 2024-12-04 | [6 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Servicevindue skal aftales | -1065.86 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NKA-030930 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 | 2025-05-28 | 2025-05-28 | Change | 2020-06-26 | 2020-08-28 09:14:00.000 | 2020-06-25 11:22:00.000 |  |  | 2020-09-11 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Servicevindue skal aftales | 57.89 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NRK-030931 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 | 2025-05-28 | 2025-05-28 | Change | 2020-06-25 | 2020-09-14 13:09:00.000 | 2020-09-14 13:09:00.000 |  |  | 2020-09-11 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 895 | Vurderingsmægler ApS | 105158 | NKA-060325 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-10 | 2025-05-08 14:01:00.000 | 2025-05-13 14:55:00.000 | 2025-06-06 |  | 2025-06-06 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | afventer design | 2595 | Zauner Anlagentechnik GmbH | 101608 | NKA-058379 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-15 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-01-15 | 2025-05-07 07:57:00.000 | 2025-05-09 10:48:00.000 | 2025-05-21 |  | 2025-03-07 | 2025-05-12 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 8. Ready for service |  | Done | 1400 | Zebnet ApS | 98482 | NKA-056423 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 | 2025-05-30 | 2025-05-30 | 3rd Party | 2024-10-01 |  |  | 2024-12-04 |  | 2024-12-04 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 8. Ready for service |  | Done | 1400 | Zebnet ApS | 98482 | NML-056424 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 | 2025-05-30 | 2025-05-30 | 3rd Party |  |  |  | 2024-12-04 |  |  |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Opennet fejl | 200 | Zebnet ApS | 98482 | NML-056428 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Third party vendor delay | Opennet fejl | -1710.58 | Zebnet ApS | 98482 | NOC-995967 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 |  |  | Change |  |  |  | 2025-04-29 |  | 2024-08-13 | [5 empty] | Change | BO
[5 empty] | 4095 | ZTLment ApS | 105695 | NKA-060681 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet | 2025-05-12 | 2025-05-12 15:29:00.000 | 2025-05-14 06:52:00.000 |  |  | 2025-06-13 | [5 empty] | New Sales | BO
[5 empty] | 855 | Zurface A/S | 104749 | NDD-060570 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | [11 empty] | New Sales | BO
[5 empty] | 855 | Zurface A/S | 104749 | NKA-060569 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party | 2025-05-08 |  |  |  |  | 2025-08-01 | [5 empty] | New Sales | BO
[5 empty] | 1100 | Zurface A/S | 104749 | NKA-060571 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-08 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 299.5 | Zurface A/S | 104749 | NKA-060573 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-14 | [10 empty] | New Sales | BO
[5 empty] | 299.5 | Zurface A/S | 104749 | NKA-060575 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-14 | [10 empty] | New Sales | BO
[5 empty] | 1100 | Zurface A/S | 104749 | NKA-060576 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet | 2025-05-08 |  |  |  |  | 2025-06-27 | [5 empty] | New Sales | BO
[5 empty] | 1250 | Zurface A/S | 104749 | NKA-060577 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party | 2025-05-08 |  |  |  |  | 2025-08-01 | [5 empty] | New Sales | BO
[5 empty] | 299.5 | Zurface A/S | 104749 | NML-060572 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party | 2025-05-14 | [10 empty] | New Sales | BO
[5 empty] | 299.5 | Zurface A/S | 104749 | NML-060574 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party | 2025-05-14 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track | 1495 | Ølsnedkeren ApS | 102565 | NKA-059914 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-27 |  |  | 2025-06-13 |  | 2025-06-13 | 2025-04-28 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO