## Export
Focus Enterprise | # | EXPIDITE | Delta MRC | Customer name | SalesProjectID_ContractNumber | ServiceID_Crid | Project ID AX | Delivery Project Manager | Segment Red. | Project Stage | Dateofcreation_ContractApproved | Committed RFS | Customer AgreedRFS/ConfirmedDeliveryDate | DELIVERYCATEGORY
0 | 1 | 0 | 1278 | 101 Copenhagen ApS | 102707 | NKA-059028 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 255 | 101 Copenhagen ApS | 102707 | NMA-059030 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 255 | 101 Copenhagen ApS | 102707 | NSW-059029 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-21 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 1495 | Abstracta Interiør A/S | 105245 | NKA-060441 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-23 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 |  | ADDvision ApS | 102766 | NKA-031201 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-12 | 2025-07-18 | 2025-07-18 | Change
0 | 1 | 0 | 597.5 | ADDvision ApS | 103431 | NKA-060621 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 597.5 | ADDvision ApS | 103431 | NML-060622 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 547.5 | ADDvision ApS | 105459 | NKA-060584 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 547.5 | ADDvision ApS | 105459 | NML-060585 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 5495 | ADDvision ApS | 105719 | NKA-058980 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-22 |  |  | Change
0 | 1 | 0 | 996 | Adminia ApS | 105363 | NKA-060472 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 200 | Adminia ApS | 105363 | NMA-060473 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 200 | Adminia ApS | 105363 | NSW-060474 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-25 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 1659 | Advokaterne i Rosenborggade I/S | 105327 | NKA-060686 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet
0 | 1 | 0 | 950 | Aktieselskabet Bremen | 102096 | NKA-059178 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-06-20 | 2025-06-20 | Own with Digging
0 | 1 | 0 | 950 | Aktieselskabet Bremen | 102096 | NML-059179 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058503 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-13 | 2025-06-13 | Own with Digging
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058504 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-08-01 | 2025-08-01 | Own OnNet
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058516 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058517 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-08-29 | 2025-08-29 | Own OnNet
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058520 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-08-01 | 2025-08-01 | Own with Digging
0 | 1 | 0 | 1195 | Allunite A/S | 102186 | NKA-058523 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-21 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1195 | Allunite A/S | 102764 | NKA-059666 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-03-07 |  |  | Own OnNet
0 | 1 | 0 | 1195 | Allunite A/S | 102764 | NKA-059667 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-03-07 |  |  | Own with Digging
0 | 1 | 0 | 1460 | Alpha Solutions A/S | 103412 | NKA-060743 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 4000 | Alphadyne Asset Management (Europe) A/S | 102644 | NKA-059831 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 |  |  | 3rd Party
0 | 1 | 0 | 4000 | Alphadyne Asset Management (Europe) A/S | 102644 | NKA-059834 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1095 | Alumichem A/S | 105803 | NKA-060897 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Own OnNet
0 | 1 | 0 | 1095 | Alumichem A/S | 105803 | NKA-060898 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Own OnNet
0 | 1 | 0 | 1095 | Alveus Therapeutics ApS | 105827 | NKA-060821 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-19 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 0 | Anchor Lab K/S | 103946 | NKA-032881 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-20 |  |  | Change
0 | 1 | 0 | 246.34 | Andelsboligforeningen Hvidovrevang | 96524 | NKA-023023 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-06-03 |  |  | Change
0 | 1 | 0 | 895 | Andersen-Andersen ApS | 105420 | NKA-060619 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 795 | Apel Fine Jewellery | 102850 | NKA-059168 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 150 | Apel Fine Jewellery | 102850 | NMA-059170 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | 3rd Party
0 | 1 | 0 | 150 | Apel Fine Jewellery | 102850 | NSW-059169 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-11 | 2025-07-11 | Own OnNet
0 | 1 | 0 | 622.5 | ARC Nordic A/S | 104918 | NKA-060521 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 622.5 | ARC Nordic A/S | 104918 | NML-060522 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 1295 | Arpe & Kjeldsholm A/S | 105688 | NKA-060707 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 1145 | Asador ApS | 98811 | NKA-056527 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-09-30 |  |  | Own with Digging
0 | 1 | 0 | 150 | Asador ApS | 98811 | NMA-056529 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-09-30 |  |  | 3rd Party
0 | 1 | 0 | 150 | Asador ApS | 98811 | NSW-056528 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-09-30 |  |  | Own OnNet
0 | 1 | 0 | 995 | Bagt ApS | 102606 | NKA-060102 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 995 | Bagt ApS | 102606 | NKA-060105 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 1350 | Bagt ApS | 102606 | NKA-060108 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 1350 | Bagt ApS | 102606 | NKA-060111 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 1350 | Bagt ApS | 102606 | NKA-060114 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NMA-060104 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NMA-060107 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NMA-060110 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NMA-060113 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NMA-060116 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NSW-060103 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NSW-060106 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NSW-060109 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NSW-060112 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 | 150 | Bagt ApS | 102606 | NSW-060115 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-31 |  |  | Own OnNet
0 | 1 | 0 |  | Bauer Media ApS | 105736 | NKA-035834 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-16 |  |  | Change
0 | 1 | 0 | 995 | BEGRAVELSESFORRETNINGEN DEN SIDSTEREJSE V/SOLVEJG RITZAU | 105398 | NKA-060598 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-05 |  |  | Own with Digging
0 | 1 | 0 | 1495 | Begroni ApS | 105973 | NKA-060879 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-26 |  |  | Own OnNet
0 | 1 | 0 | 2595 | Bilfinger Life Science GmbH | 105678 | NKA-060871 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 1711 | Blue Ocean Robotics ApS | 105746 | NKA-060761 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1099 | Blueprint | 100868 | NKA-057898 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-13 |  |  | Own OnNet
0 | 1 | 0 | 1050 | Boldlight ApS | 98505 | NKA-056602 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-10-03 |  |  | Own with Digging
0 | 1 | 0 | 1100 | Boligforeningen Grønløkken | 107620-002 | C36637-1136771-01 | 107620-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-06-27 |  | Own with Digging
0 | 1 | 0 | 0 | Boligforeningen Grønløkken | 107620-002 | C36637-1136772-01 | 107620-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 522 | Boligselskabet Lejerbo | 101264-028 | C31228-1136880-01 | 101264-028-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 1914 | Boligselskabet Lejerbo | 101264-028 | C31228-1136881-01 | 101264-028-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 2342 | Boligselskabet Lejerbo | 101264-028 | C31228-1136882-01 | 101264-028-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own with Digging
0 | 1 | 0 | 2181 | Boligselskabet Lejerbo | 101264-028 | C31228-1136883-01 | 101264-028-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 0 | Boligselskabet Lejerbo | 101264-028 | C31228-1136884-01 | 101264-028-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 0 | Boligselskabet Lejerbo | 101264-028 | C31228-1136886-01 | 101264-028-007 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 0 | Boligselskabet Lejerbo | 101264-028 | C31228-1136887-01 | 101264-028-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 |  |  | Own OnNet
0 | 1 | 0 | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127937-01 | 105961-007-011 | Shazia Mobin | SMB Portfolio DK | Created | 2024-05-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127938-01 | 105961-007-012 | Shazia Mobin | SMB Portfolio DK | Created | 2024-05-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 1250 | BONE CONSULT A/S | 105961-007 | C35256-1127948-01 | 105961-007-022 | Shazia Mobin | SMB Portfolio DK | Created | 2024-05-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 2500 | BONE CONSULT A/S | 105961-007 | C35256-1127950-01 | 105961-007-024 | Shazia Mobin | SMB Portfolio DK | Created | 2024-05-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 0 | BONE CONSULT A/S | 105961-007 | C35256-1127952-01 | 105961-007-026 | Shazia Mobin | SMB Portfolio DK | Created | 2024-05-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 96 | BONE CONSULT A/S | 105961-008 | C35256-1135227-01 | 105961-008-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-12 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 622.5 | Borgernær Psykiatri Danmark P/S | 105656 | NKA-060762 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 622.5 | Borgernær Psykiatri Danmark P/S | 105656 | NML-060763 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 895 | Britt Sisseck | 97827 | NKA-060422 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 150 | Britt Sisseck | 97827 | NMA-060424 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 150 | Britt Sisseck | 97827 | NSW-060423 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1950 | BRUGG Denmark A/S | 88356 | NKA-048369 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-06-13 |  |  | 3rd Party
0 | 1 | 0 | 150 | BRUGG Denmark A/S | 88356 | NMA-048371 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-06-13 |  |  | 3rd Party
0 | 1 | 0 | 150 | BRUGG Denmark A/S | 88356 | NSW-048370 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-06-13 |  |  | Own OnNet
0 | 1 | 0 | 1100 | C.F. Møller Danmark A/S | 101354 | NML-058029 |  | Lars Gottschalck | SMB Portfolio DK | Closed | 2024-12-19 | 2025-03-28 | 2025-03-28 | 3rd Party
0 | 1 | 0 | 1900 | C.F. Møller Norge AS | 105249 | NKA-060465 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-24 | 2025-05-28 | 2025-05-28 | 3rd Party
0 | 1 | 0 | 1371 | Cadesign base A/S | 102065-030 | C32152-1135219-01 | 102065-030-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-06-06 |  | Own with Digging
0 | 1 | 0 | 0 | Cadesign base A/S | 102065-030 | C32152-1135220-01 | 102065-030-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | -0.55333 | Cadesign base A/S | 102065-030 | C32152-1135221-01 | 102065-030-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-03-11 | 2025-06-06 | 2025-06-06 | Change
0 | 1 | 0 | 849.93 | Cadesign base A/S | 104899 | NKA-060054 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 849.93 | Cadesign base A/S | 104899 | NML-060055 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 1595 | Cafe Under uret ApS | 105870 | NKA-058713 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Change
0 | 1 | 0 | 1375 | CEGO A/S | 106646-005 | C35824-1136898-01 | 106646-005-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136899-01 | 106646-005-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 100 | CEGO A/S | 106646-005 | C35824-1136900-01 | 106646-005-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 1455 | CEGO A/S | 106646-005 | C35824-1136902-01 | 106646-005-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136903-01 | 106646-005-006 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 1375 | CEGO A/S | 106646-005 | C35824-1136905-01 | 106646-005-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136906-01 | 106646-005-009 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 100 | CEGO A/S | 106646-005 | C35824-1136907-01 | 106646-005-010 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 1375 | CEGO A/S | 106646-005 | C35824-1136909-01 | 106646-005-012 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136910-01 | 106646-005-013 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 100 | CEGO A/S | 106646-005 | C35824-1136911-01 | 106646-005-014 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 1455 | CEGO A/S | 106646-005 | C35824-1136913-01 | 106646-005-016 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136914-01 | 106646-005-017 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 1455 | CEGO A/S | 106646-005 | C35824-1136916-01 | 106646-005-019 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 345 | CEGO A/S | 106646-005 | C35824-1136917-01 | 106646-005-020 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 15 | CEGO A/S | 106646-005 | C35824-1136919-01 | 106646-005-022 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 128 | CEGO A/S | 106646-005 | C35824-1136920-01 | 106646-005-023 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 128 | CEGO A/S | 106646-005 | C35824-1136921-01 | 106646-005-024 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 0 | CEGO A/S | 106646-005 | C35824-1136922-01 | 106646-005-025 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 0 | CEGO A/S | 106646-005 | C35824-1136923-01 | 106646-005-026 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 0 | CEGO A/S | 106646-005 | C35824-1136924-01 | 106646-005-027 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 128 | CEGO A/S | 106646-005 | C35824-1136925-01 | 106646-005-028 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-14 | 2025-07-04 |  | Own OnNet
0 | 1 | 0 | 1495 | Cematech ApS | 102720 | NDD-059955 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | Own OnNet
0 | 1 | 0 | 1295 | Cematech ApS | 102720 | NKA-059954 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | Own OnNet
0 | 1 | 0 | 200 | Cematech ApS | 102720 | NML-059956 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-25 |  |  | 3rd Party
0 | 1 | 0 | 1196 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NKA-052598 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 199.5 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NMA-052599 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 199.5 | CENTERFORENINGEN RO´S TORV F.M.B.A. | 93246 | NSW-052600 |  | Merete Helme | SMB Portfolio DK | In Process | 2023-12-22 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1895 | Chatservice ApS | 105285 | NKA-060436 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 1495 | CIC Operations Odense ApS | 98795 | NKA-057086 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-11-06 | 2025-06-20 | 2025-06-20 | Own with Digging
0 | 1 | 0 | 1782 | Cim Industrial Systems A/S | 105797 | NKA-060770 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-15 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 2500 | Compugroup Medical Denmark A/S | 101944-014 | C32025-1134067-01 | 101944-014-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-17 | 2025-05-30 | 2025-03-14 | Change
0 | 1 | 0 | 2900 | Compugroup Medical Denmark A/S | 101944-014 | C32025-1134069-01 | 101944-014-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-17 | 2025-05-30 | 2025-03-14 | Change
0 | 1 | 0 | 1810 | Conaxess Trade Denmark A/S | 105335 | NKA-060765 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 |  |  | 3rd Party
0 | 1 | 0 | 995 | Coresearch Vision A/S | 102345 | NKA-058613 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-24 |  |  | Own with Digging
0 | 1 | 0 | 200 | Coresearch Vision A/S | 102345 | NMA-058614 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-24 |  |  | 3rd Party
0 | 1 | 0 | 200 | Coresearch Vision A/S | 102345 | NSW-058615 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-24 |  |  | Own OnNet
0 | 1 | 0 | 1056 | CR ELECTRIC A/S | 101169 | NKA-059161 |  | Line Skov | SMB Portfolio DK | On Hold | 2025-02-27 | 2025-05-16 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 1056 | CR ELECTRIC A/S | 101169 | NML-059160 |  | Line Skov | SMB Portfolio DK | On Hold | 2025-02-27 | 2025-05-16 | 2025-05-16 | 3rd Party
0 | 1 | 0 | -200.68 | CR Electric J/F A/S | 103319 | NKA-040072 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-03-24 | 2025-04-25 | 2025-04-25 | Change
0 | 1 | 0 | 200 | CR Electric J/F A/S | 103319 | NML-059920 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-03-24 | 2025-04-25 | 2025-04-25 | 3rd Party
0 | 1 | 0 | 622.5 | Dan-Revision Taastrup ApS | 104848 | NKA-060222 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 |  |  | Own with Digging
0 | 1 | 0 | 622.5 | Dan-Revision Taastrup ApS | 104848 | NML-060221 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-02 |  |  | 3rd Party
0 | 1 | 0 | 1095 | Dansende Dynamisk Verden Skole | 88738 | NKA-049176 |  | Line Skov | SMB Portfolio DK | On Hold | 2023-07-06 |  |  | Own with Digging
0 | 1 | 0 | 895 | Dansk Internet og computer | 102175 | NKA-058564 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-01-22 |  |  | Own OnNet
0 | 1 | 0 |  | Dansk Internet og computer | 102550 | NKA-058564 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-02-04 |  |  | Change
0 | 1 | 0 | 100 | Dansk Internet og computer | 102550 | NML-058762 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-02-04 |  |  | 3rd Party
0 | 1 | 0 | 622.5 | Dansk It | 105023 | NKA-060359 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 622.5 | Dansk It | 105023 | NML-060360 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 995 | Dansk Turbo Teknik A/S | 105272 | NKA-060668 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own with Digging
0 | 1 | 0 | -774.9 | Danske Advokater | 103584 | NKA-005674 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-02 | 2025-06-04 | 2025-06-04 | Change
0 | 1 | 0 | 1260 | Danske Advokater | 103584 | NKA-060224 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-02 | 2025-06-03 | 2025-06-03 | Own OnNet
0 | 1 | 0 | -2900.95 | Dayforce A/S | 102950 | NKA-025351 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Change
0 | 1 | 0 | -1666.06 | Dayforce A/S | 102950 | NKA-032475 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Change
0 | 1 | 0 | 1326 | Dentorium ApS | 103142 | NKA-059860 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own with Digging
0 | 1 | 0 | 1994 | Dignity - Dansk Institut Mod Tortur | 102249 | NKA-058696 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-30 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 2050 | DKI MANAGEMENT A/S | 101227 | NKA-058380 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 2050 | DKI MANAGEMENT A/S | 101227 | NKA-058381 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 2400 | DKI MANAGEMENT A/S | 101227 | NKA-058382 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-01-15 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1155 | Dollarstore ApS | 105770 | NKA-060766 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 995 | Ecotree International ApS | 105782 | NKA-060788 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-16 |  |  | Own OnNet
0 | 1 | 0 | 797.5 | Emineral A/S | 105749 | NKA-060767 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 797.5 | Emineral A/S | 105749 | NML-060768 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 0 | Erenfred Pedersen A/S | 89487 | NKA-006114 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Change
0 | 1 | 0 | 0 | Erenfred Pedersen A/S | 89487 | NKA-006116 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Change
0 | 1 | 0 | 995 | Erenfred Pedersen A/S | 89487 | NKA-051331 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Own OnNet
0 | 1 | 0 | 495 | Erenfred Pedersen A/S | 89487 | NMA-051334 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | 3rd Party
0 | 1 | 0 | 370 | Erenfred Pedersen A/S | 89487 | NSW-051330 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Own OnNet
0 | 1 | 0 | 840 | Erenfred Pedersen A/S | 89487 | NSW-051332 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Own OnNet
0 | 1 | 0 | 495 | Erenfred Pedersen A/S | 89487 | NSW-051333 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-11-30 |  |  | Own OnNet
0 | 1 | 0 | -1268.61 | Event Space ApS | 103077 | NKA-036803 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-12 |  |  | Change
0 | 1 | 0 | 213.27 | Event Space ApS | 103077 | NKA-036804 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-12 |  |  | Change
0 | 1 | 0 | -250.62 | Executive Cognito A/S | 102304 | NKA-034187 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-31 |  |  | Change
0 | 1 | 0 | 200 | Executive Cognito A/S | 102304 | NML-058724 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-01-31 |  |  | 3rd Party
0 | 1 | 0 | 995 | exs nordic A/S | 105610 | NKA-060648 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 1500 | FAB:IT ApS | 107317-002 | C36378-1125451-01 | 107317-002-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 0 | FAB:IT ApS | 107317-002 | C36378-1125453-01 | 107317-002-003 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 2000 | FAB:IT ApS | 107317-002 | C36378-1125454-01 | 107317-002-004 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 0 | FAB:IT ApS | 107317-002 | C36378-1125456-01 | 107317-002-006 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 2000 | FAB:IT ApS | 107317-002 | C36378-1125457-01 | 107317-002-007 | Shazia Mobin | SMB Portfolio DK | In Process | 2024-02-14 | 2025-06-27 |  | Own OnNet
0 | 1 | 0 | 1200 | Fænøsundlægerne I/S | 104846 | NKA-060261 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 1495 | FEC Taby Ab | 107397-003 | C36447-1136725-01 | 107397-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-08-15 |  | Own OnNet
0 | 1 | 0 | 0 | FEC Taby Ab | 107397-003 | C36447-1136726-01 | 107397-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-07 | 2025-08-15 |  | Own OnNet
0 | 1 | 0 | 977.3533 | Finans Danmark | 103973-004 | C33538-1134609-01 | 103973-004-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-06 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | -2285.79 | Finans Danmark | 103973-004 | C33538-1134611-01 | 103973-004-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-06 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | 3000 | FINN FROGNE A/S | 106740-008 | C35898-1136681-01 | 106740-008-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 3000 | FINN FROGNE A/S | 106740-008 | C35898-1136682-01 | 106740-008-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 50 | FINN FROGNE A/S | 106740-008 | C35898-1136684-01 | 106740-008-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 50 | FINN FROGNE A/S | 106740-008 | C35898-1136685-01 | 106740-008-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 60 | FINN FROGNE A/S | 106740-008 | C35898-1136686-01 | 106740-008-006 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 60 | FINN FROGNE A/S | 106740-008 | C35898-1136687-01 | 106740-008-007 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 176 | FINN FROGNE A/S | 106740-008 | C35898-1136688-01 | 106740-008-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1395 | Fjord Rådgivende Ingeniører A/S | 102594 | NKA-059957 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-15 | 2025-08-15 | Own OnNet
0 | 1 | 1 | 1695 | Flexdanmark | 102845-005 | C32515-1136586-01 | 102845-005-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Own with Digging
0 | 1 | 1 | 0 | Flexdanmark | 102845-005 | C32515-1136587-01 | 102845-005-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Change
0 | 1 | 1 | 100 | Flexdanmark | 102845-005 | C32515-1136588-01 | 102845-005-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-29 | 2025-05-28 |  | Change
0 | 1 | 0 | 1295 | Floating Power Plant A/S | 105835 | NKA-060824 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-19 |  |  | Own OnNet
0 | 1 | 0 | 1510 | Fondsmæglerselskabet Marselis A/S | 104901 | NKA-060079 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 1116.9 | Foreningshuset Sundholm8 | 84553 | NKA-046136 |  | Lars Gottschalck | SMB Portfolio DK | RFS | 2022-12-14 | 2023-04-12 |  | Own OnNet
0 | 1 | 0 | 895 | Frederiksborggade Øjenklinik v/Hanne Göte | 105705 | NKA-060708 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 |  |  | Own OnNet
0 | 1 | 0 | 984 | Fresh Out The Oven ApS | 103173 | NKA-059994 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-20 | 2025-06-20 | Own with Digging
0 | 1 | 0 | 697.5 | Frøslev Træ A/S | 103631 | NKA-059903 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NKA-059905 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NKA-059907 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NKA-059909 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Own OnNet
0 | 1 | 0 | 697.5 | Frøslev Træ A/S | 103631 | NKA-059911 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 697.5 | Frøslev Træ A/S | 103631 | NML-059904 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NML-059906 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NML-059908 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party
0 | 1 | 0 | 597.5 | Frøslev Træ A/S | 103631 | NML-059910 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 |  |  | 3rd Party
0 | 1 | 0 | 697.5 | Frøslev Træ A/S | 103631 | NML-059912 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 1295 | Fødevarebanken | 95488 | NKA-054290 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-05-02 |  |  | 3rd Party
0 | 1 | 0 | 200 | Fødevarebanken | 95488 | NMA-054292 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-05-02 |  |  | 3rd Party
0 | 1 | 0 | 200 | Fødevarebanken | 95488 | NSW-054291 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-05-02 |  |  | Own OnNet
0 | 1 | 0 | 814.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057987 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 |  |  | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057989 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057991 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057993 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057995 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057997 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NKA-057999 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | Own OnNet
0 | 1 | 0 | 814.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057988 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 |  |  | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057990 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057992 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057994 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057996 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-057998 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 664.5 | Gloube ApS Grønningen 5 kld. 1270 København.K | 100504 | NML-058000 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-12-19 | 2025-02-28 | 2025-02-28 | 3rd Party
0 | 1 | 0 | 2210 | GORM x ENVISION A/S | 103391 | NKA-059820 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-18 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1295 | Grazper Technologies ApS | 107630-003 | C36646-1136970-01 | 107630-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-21 | 2025-07-11 | 2025-07-11 | Own OnNet
0 | 1 | 0 | 0 | Grazper Technologies ApS | 107630-003 | C36646-1136971-01 | 107630-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-21 | 2025-07-11 | 2025-07-11 | Own OnNet
0 | 1 | 0 | 0 | Grazper Technologies ApS | 107630-003 | C36646-1136974-01 | 107630-003-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-21 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 949 | GREEN STORAGE A/S | 95021 | NKA-054920 |  | Line Skov | SMB Portfolio DK | In Process | 2024-06-24 | 2025-10-01 | 2025-10-01 | 3rd Party
0 | 1 | 0 | 1395 | Green Therma ApS | 105987 | NKA-060900 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Own OnNet
0 | 1 | 0 | 1300 | GROH Engineering A/S | 105801 | NKA-060887 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-26 |  |  | Own OnNet
0 | 1 | 0 | 1295 | Gustaf Fagerberg A/S | 102958 | NKA-060519 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-28 | 2025-08-15 | 2025-08-15 | Own OnNet
0 | 1 | 0 | 714.9 | H+ A/S | 105390 | NKA-035285 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Change
0 | 1 | 0 | 1495 | Hallerupnet ApS | 103076 | NDD-059810 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet
0 | 1 | 0 | 1497.87 | Hallerupnet ApS | 103076 | NKA-043808 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change
0 | 1 | 0 | 1888.5 | Hallerupnet ApS | 103076 | NKA-059809 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet
0 | 1 | 0 | 1000 | Hallerupnet ApS | 103076 | NKA-059811 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet
0 | 1 | 0 | -2141.4 | Hallerupnet ApS | 103076 | NRS-043807 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change
0 | 1 | 0 | 1888.5 | Hallerupnet ApS | 103076 | NRS-059808 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Own OnNet
0 | 1 | 0 | 1695 | Hedema A/S | 105888 | NKA-060842 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-21 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 2000 | Heimstaden Flintholm Kollegiet ApS | 94367 | NKA-053529 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-03-01 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1865 | Hesehus A/S | 104734-010 | C34237-1134236-01 | 104734-010-001 | Shazia Mobin | SMB Portfolio DK | In Process | 2025-01-27 | 2025-05-28 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 842 | Hesehus A/S | 104734-010 | C34237-1134237-01 | 104734-010-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-27 | 2025-05-28 | 2025-05-02 | Own OnNet
0 | 1 | 0 | 228 | Hesehus A/S | 104734-010 | C34237-1134238-01 | 104734-010-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-01-27 | 2025-05-28 | 2025-05-02 | Own OnNet
0 | 1 | 0 | 1395 | Holtec Automatic A/S | 100768 | NKA-058900 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-12 | 2025-08-01 | 2025-08-01 | 3rd Party
0 | 1 | 0 | 895 | Impact People ApS | 95699 | NKA-055092 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-06-26 |  |  | Own OnNet
0 | 1 | 0 | 200 | Impact People ApS | 95699 | NMA-055090 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-06-26 |  |  | 3rd Party
0 | 1 | 0 | 200 | Impact People ApS | 95699 | NSW-055091 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-06-26 |  |  | Own OnNet
0 | 1 | 0 | 749 | Infolink ApS | 105611 | NKA-060865 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-22 |  |  | Own OnNet
0 | 1 | 0 | 995 | Institutionen Thomas P.Hejles Ungdomshus | 105308 | NKA-060437 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | -523.7133 | Intecredo International ApS | 104899-009 | C34376-1136842-01 | 104899-009-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change
0 | 1 | 0 | 1033.6567 | Intecredo International ApS | 104899-009 | C34376-1136843-01 | 104899-009-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change
0 | 1 | 0 | -505.0633 | Intecredo International ApS | 104899-009 | C34376-1136844-01 | 104899-009-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change
0 | 1 | 0 | -1084.9 | Intecredo International ApS | 104899-009 | C34376-1136848-01 | 104899-009-007 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Change
0 | 1 | 0 | 0 | Intecredo International ApS | 104899-009 | C34376-1136849-01 | 104899-009-008 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-13 | 2025-08-01 |  | Own OnNet
0 | 1 | 0 | 1495 | Ismageriet ApS | 104409-004 | C33943-1134819-01 | 104409-004-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-19 | 2025-05-30 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 0 | Ismageriet ApS | 104409-004 | C33943-1134820-01 | 104409-004-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-02-19 | 2025-05-30 | 2025-05-16 | Own OnNet
0 | 1 | 0 | 2460 | IT Forum Gruppen A/S | 102529 | NKA-058983 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-18 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 2460 | IT Forum Gruppen A/S | 102529 | NKA-058984 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-02-18 | 2025-05-28 | 2025-05-28 | Own OnNet
0 | 1 | 0 | 1324 | IT Forum Gruppen A/S | 102686 | NKA-059689 |  | Merete Helme | SMB Portfolio DK | On Hold | 2025-03-10 |  |  | Own OnNet
0 | 1 | 0 | 945 | Itino A/S | 105361 | NKA-060899 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Own OnNet
0 | 1 | 0 | 0 | Jeudan A/S | 105215 | NKA-060361 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-11 |  |  | Own OnNet
0 | 1 | 0 | 2495 | Keepers ApS | 102668 | NKA-059862 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 1095 | Kibodan A/S | 105720 | NKA-060834 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-21 |  |  | Own OnNet
0 | 1 | 0 | 1095 | Kirkebjerg Køreskole ApS | 85903 | NKA-046870 |  | Line Skov | SMB Portfolio DK | In Process | 2023-02-16 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 1095 | Kjærgaard A/S | 105283 | NKA-060851 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-22 |  |  | 3rd Party
0 | 1 | 0 | 847.5 | Kjærgaard A/S | 93908 | NKA-053097 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-02-01 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 847.5 | Kjærgaard A/S | 93908 | NML-053098 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-02-01 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 897.5 | Klarlund A/S | 94538 | NML-053417 |  | Merete Helme | SMB Portfolio DK | Closed | 2024-02-22 |  |  | 3rd Party
0 | 1 | 0 | 443.688 | Klimadan A/S | 101027-003 | C30991-1111651-01 | 101027-003-001 | Shazia Mobin | SMB Portfolio DK | RFS | 2022-05-06 | 2022-06-29 | 2022-06-29 | Change
0 | 1 | 0 | 955 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NKA-060626 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | Own OnNet
0 | 1 | 0 | 200 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NMA-060627 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | 3rd Party
0 | 1 | 0 | 200 | Koldby Optik, Østerbrogade 108 ApS | 105223 | NSW-060628 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-05-07 |  |  | Own OnNet
0 | 1 | 0 | 1695 | Konsulent Bjarne Aalbæk | 105153 | NKA-060443 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-23 | 2025-07-18 | 2025-07-18 | 3rd Party
0 | 1 | 0 | 2000 | Krogstrup ApS | 103606 | NKA-060357 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-11 | 2025-07-04 | 2025-07-04 | 3rd Party
0 | 1 | 0 | -442.92 | Krøyer Pedersen | 103353 | NKA-016171 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-03-26 |  |  | Change
0 | 1 | 0 | -572.58 | Krøyer Pedersen | 103353 | NOC-996528 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-03-26 |  |  | Change
0 | 1 | 0 | 1299 | Kuube Denmark ApS | 102144 | NKA-058447 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 150 | Kuube Denmark ApS | 102144 | NMA-058448 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-05-09 | 3rd Party
0 | 1 | 0 | 150 | Kuube Denmark ApS | 102144 | NSW-058449 |  | Line Skov | SMB Portfolio DK | In Process | 2025-01-17 | 2025-06-06 | 2025-05-09 | Own OnNet
0 | 1 | 0 | 622.5 | Læge Torben Larsen | 105483 | NKA-060582 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet
0 | 1 | 0 | 622.5 | Læge Torben Larsen | 105483 | NML-060583 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party
0 | 1 | 0 | 895 | Langebæk Lægehus, Alment Praktiserende Læger ApS | 105962 | NKA-060872 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 1700 | LEMAN A/S | 105301 | NKA-060555 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 895 | Lokalbolig Hvidovre ApS | 103266 | NKA-059865 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own with Digging
0 | 1 | 0 | 200 | Lokalbolig Hvidovre ApS | 103266 | NMA-059864 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 200 | Lokalbolig Hvidovre ApS | 103266 | NSW-059863 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-20 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 1345 | Ls Montage ApS | 100378 | NKA-056963 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-10-29 | 2025-07-04 | 2025-05-23 | 3rd Party
0 | 1 | 0 | 1095 | Lucky Joe ApS | 105975 | NKA-060895 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-27 |  |  | Own with Digging
0 | 1 | 0 | 1195 | Merco Print A/S | 98053 | NKA-055857 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-08-20 |  |  | 3rd Party
0 | 1 | 0 | 952 | MOBILXPERTEN ApS | 103839 | NKA-060352 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-10 | 2025-07-11 | 2025-07-11 | Own with Digging
0 | 1 | 0 | 625 | MOBILXPERTEN ApS | 105536 | NKA-060684 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own with Digging
0 | 1 | 0 | 625 | MOBILXPERTEN ApS | 105536 | NML-060685 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | 3rd Party
0 | 1 | 0 | 895 | Moderliv ApS | 98648 | NKA-056194 |  | Line Skov | SMB Portfolio DK | On Hold | 2024-09-11 |  |  | Own OnNet
0 | 1 | 0 | 3660 | Mos Mosh A/S | 103236 | NKA-060075 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-31 |  |  | 3rd Party
0 | 1 | 0 | 995 | Move Innovation ApS | 102737 | NKA-060683 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet
0 | 1 | 0 | 795 | N/F OLIOLI ApS | 96973 | NKA-054715 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-06-11 |  |  | Own with Digging
0 | 1 | 0 | 1595 | N3 ApS | 103317 | NKA-060527 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet
0 | 1 | 0 | 1055 | N'age ApS | 105353 | NKA-060776 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-16 |  |  | Own with Digging
0 | 1 | 0 | 1055 | N'age ApS | 105353 | NKA-060777 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-16 | 2025-07-04 | 2025-07-04 | Own OnNet
0 | 1 | 0 | 622.5 | Najell Denmark ApS | 105329 | NKA-060534 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 622.5 | Najell Denmark ApS | 105329 | NML-060535 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | -181.16 | Natus Medical Denmark ApS | 101313 | NKA-019996 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-18 | 2025-06-20 | 2025-04-25 | Change
0 | 1 | 0 | 1495 | Natus Medical Denmark ApS | 101313 | NKA-057962 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-18 | 2025-06-20 | 2025-04-04 | Own with Digging
0 | 1 | 0 | 995 | Nordic Skin College ApS | 98839 | NKA-057261 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-11-08 |  |  | Own with Digging
0 | 1 | 0 | 2100 | Ntrakker AB | 106002-016 | C35287-1136087-01 | 106002-016-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-08 | 2025-07-11 |  | 3rd Party
0 | 1 | 0 | 60 | Ntrakker AB | 106002-016 | C35287-1136088-01 | 106002-016-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-08 | 2025-07-11 |  | Own OnNet
0 | 1 | 0 | 3313 | NØRGÅRD MIKKELSEN REKLAMEBUREAU A/S | 102585 | NKA-059894 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-21 | 2025-07-15 | 2025-07-15 | Own with Digging
0 | 1 | 0 | 1395 | Odense Hostel ApS | 94167 | NKA-053114 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2024-02-02 |  |  | 3rd Party
0 | 1 | 0 | 1778 | Oreco A/S | 103235 | NKA-059760 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-13 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 647.5 | Our Units ApS | 104852 | NKA-060530 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | Own OnNet
0 | 1 | 0 | 647.5 | Our Units ApS | 104852 | NML-060531 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 |  |  | 3rd Party
0 | 1 | 0 | 1400 | Oustrupgård Agro ApS | 97994 | NKA-056743 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-10-10 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 955 | Padel Club Randers ApS | 82901 | NML-045041 |  | Merete Helme | SMB Portfolio DK | Closed | 2022-09-30 |  |  | 3rd Party
0 | 1 | 0 |  | Penta Advokater A/S | 105456 | NKA-013625 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-30 |  |  | Change
0 | 1 | 0 | 1841 | Penta Advokater A/S | 105457 | NKA-060629 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-07 | 2025-10-24 | 2025-10-24 | Own OnNet
0 | 1 | 0 | 2968 | Perspektiva IT ApS | 100657 | NKA-059019 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-20 | 2025-06-27 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 2968 | Perspektiva IT ApS | 100657 | NKA-059020 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-20 | 2025-06-27 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 1755 | PM-SOLUTIONS APS | 105767 | NKA-060790 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-16 | 2025-06-27 | 2025-06-27 | Own with Digging
0 | 1 | 0 | 897.5 | Polaris Management A/S | 94828 | NKA-054033 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-04-12 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 897.5 | Polaris Management A/S | 94828 | NML-054034 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-04-12 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 895 | Pompette ApS | 105163 | NKA-060334 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 150 | Pompette ApS | 105163 | NMA-060336 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-06 | 2025-06-06 | 3rd Party
0 | 1 | 0 | 150 | Pompette ApS | 105163 | NSW-060335 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-06 | 2025-06-06 | Own OnNet
0 | 1 | 0 | 1095 | PROCOPA IT ApS | 105881-070 | C35226-1129814-01 | 105881-070-001 | Shazia Mobin | SMB Portfolio DK | On Hold | 2024-07-09 | 2024-08-30 |  | Own OnNet
0 | 1 | 0 | 1195 | PROCOPA IT ApS | 105881-070 | C35226-1129816-01 | 105881-070-003 | Shazia Mobin | SMB Portfolio DK | On Hold | 2024-07-09 | 2024-08-30 |  | Own OnNet
0 | 1 | 0 | 995 | PROCOPA IT ApS | 105881-080 | C35226-1135895-01 | 105881-080-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-01 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | 995 | PROCOPA IT ApS | 105881-081 | C35226-1135920-01 | 105881-081-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-04-02 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | -231.9567 | PROCOPA IT ApS | 105881-082 | C35226-1136819-01 | 105881-082-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-12 | 2025-07-04 |  | Change
0 | 1 | 0 | 795 | PROJECT OPEN ApS | 107619-003 | C36636-1136796-01 | 107619-003-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 96 | PROJECT OPEN ApS | 107619-003 | C36636-1136797-01 | 107619-003-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 0 | PROJECT OPEN ApS | 107619-003 | C36636-1136798-01 | 107619-003-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-08 |  |  | Own OnNet
0 | 1 | 0 | 32 | PST V/SØREN THESTRUP | 105523-004 | C34941-1115124-01 | 105523-004-001 | Shazia Mobin | SMB Portfolio DK | On Hold | 2022-10-14 |  |  | Own OnNet
0 | 1 | 0 | 31.53 | Pålsson Arkitekter A/S | 105003 | NKA-040572 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-07 | 2025-05-30 | 2025-05-30 | Change
0 | 1 | 0 | 1195 | RackPeople ApS | 105593 | NKA-026942 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-21 | 2025-06-20 | 2025-06-20 | Change
0 | 1 | 0 | 200 | RackPeople ApS | 105593 | NML-060841 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-21 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 1095 | Ramudden Danmark A/S | 91154 | NKA-050744 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-10-23 |  |  | 3rd Party
0 | 1 | 0 | 1095 | Ramudden Danmark A/S | 91154 | NKA-050745 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2023-10-23 | 2025-05-09 | 2025-05-09 | Own OnNet
0 | 1 | 0 | 895 | RareWine ApS | 104737 | NKA-060533 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | -0.62 | Rasmussen Skilte ApS | 102434 | NKA-036506 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | Change
0 | 1 | 0 | 200 | Rasmussen Skilte ApS | 102434 | NMA-058842 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | 3rd Party
0 | 1 | 0 | 200 | Rasmussen Skilte ApS | 102434 | NSW-058843 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | Own OnNet
0 | 1 | 0 | 497.5 | Riverty Services Denmark A/S | 104661 | NKA-060039 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 497.5 | Riverty Services Denmark A/S | 104661 | NML-060040 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 2600 | Rosendahl Design Group A/S | 102302 | NKA-058845 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-10 |  |  | 3rd Party
0 | 1 | 0 | 4200 | Secure Data Center ApS | 102109 | NKA-058647 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-28 |  |  | Own OnNet
0 | 1 | 0 | 2100 | Secure Data Center ApS | 102109 | NKA-058648 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-28 |  |  | Own OnNet
0 | 1 | 0 | 2100 | Secure Data Center ApS | 102109 | NKA-058649 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-28 |  |  | Own OnNet
0 | 1 | 0 | 4200 | Secure Data Center ApS | 102109 | NKA-058650 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-01-28 |  |  | Own OnNet
0 | 1 | 0 | 1595 | Sentry Technologies ApS | 105697 | NKA-060764 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-15 |  |  | Own OnNet
0 | 1 | 0 | -1099.31 | Sephora Danmark ApS | 100014 | NKA-038507 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change
0 | 1 | 0 | -1099.31 | Sephora Danmark ApS | 100014 | NKA-038509 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change
0 | 1 | 0 | 876.52 | Sephora Danmark ApS | 100014 | NML-038508 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change
0 | 1 | 0 | 876.52 | Sephora Danmark ApS | 100014 | NML-038510 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change
0 | 1 | 0 | -199.31 | Sephora Danmark ApS | 100017 | NKA-037347 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | Change
0 | 1 | 0 | 100 | Sephora Danmark ApS | 100017 | NML-057260 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-08 |  |  | 3rd Party
0 | 1 | 0 | 1399 | Sharp Business Systems Danmark A/S | 103117 | NKA-060180 |  | Shazia Mobin | SMB Portfolio DK | In Process | 2025-03-31 | 2025-05-30 | 2025-05-30 | Own OnNet
0 | 1 | 0 | -1135.34 | Sirius Advokater I/S | 101069 | NKA-025416 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-20 |  |  | Change
0 | 1 | 0 | 300 | Sirius Advokater I/S | 101069 | NML-060828 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-20 |  |  | 3rd Party
0 | 1 | 0 | 1295 | Skypuzzler ApS | 105744 | NKA-060769 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-15 |  |  | Own with Digging
0 | 1 | 0 | 852 | Sleep in Heaven ApS | 103041 | NKA-059821 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 852 | Sleep in Heaven ApS | 103041 | NKA-059822 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 895 | Smiley Fitness ApS | 103111 | NKA-059171 |  | Christoffer Møller Andersen | SMB Portfolio DK | On Hold | 2025-02-28 |  |  | Own OnNet
0 | 1 | 0 | 200 | Smiley Fitness ApS | 103111 | NMA-059172 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 |  |  | 3rd Party
0 | 1 | 0 | 200 | Smiley Fitness ApS | 103111 | NSW-059173 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-28 |  |  | Own OnNet
0 | 1 | 0 | 1095 | Småskolen Søgårdhus | 100552 | NKA-057704 |  | Merete Helme | SMB Portfolio DK | On Hold | 2024-12-05 |  |  | 3rd Party
0 | 1 | 0 | 200 | Småskolen Søgårdhus | 100552 | NMA-057706 |  | Merete Helme | SMB Portfolio DK | On Hold | 2024-12-05 |  |  | 3rd Party
0 | 1 | 0 | 200 | Småskolen Søgårdhus | 100552 | NSW-057705 |  | Merete Helme | SMB Portfolio DK | On Hold | 2024-12-05 |  |  | Own OnNet
0 | 1 | 0 | 895 | Sofigate ApS | 105312 | NKA-060442 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-04-23 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 1245 | Space Composite Structures DENMARK APS | 100398 | NKA-060586 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | -435.9 | Space gaming ApS | 101332 | NKA-030643 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Change
0 | 1 | 0 | 250 | Space gaming ApS | 101332 | NMA-057699 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | 3rd Party
0 | 1 | 0 | 250 | Space gaming ApS | 101332 | NSW-057698 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Own OnNet
0 | 1 | 0 | 150 | Sparholt VVS ApS | 98945 | NMA-056613 |  | Merete Helme | SMB Portfolio DK | Closed | 2024-10-03 |  |  | 3rd Party
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | B36652-1137048-01 | 107635-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | B36652-1137049-01 | 107635-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | B36652-1137050-01 | 107635-002-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | B36652-1137051-01 | 107635-002-004 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | C36652-1137052-01 | 107635-002-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 0 | Sparta Atletik og Løb ApS | 107635-002 | C36652-1137053-01 | 107635-002-006 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 |  |  | Own OnNet
0 | 1 | 0 | 500 | Sulzer Pumps Denmark A/S | 102723 | NDD-059659 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 |  |  | Own OnNet
0 | 1 | 0 | -3267.91 | Sulzer Pumps Denmark A/S | 102723 | NKA-035286 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-27 | 2025-06-27 | Change
0 | 1 | 0 | 200 | Sulzer Pumps Denmark A/S | 102723 | NML-059658 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-27 | 2025-06-27 | 3rd Party
0 | 1 | 0 | 700 | Tegnestuen Vandkunsten A/S | 101036 | NKA-057597 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-28 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 700 | Tegnestuen Vandkunsten A/S | 101036 | NML-057598 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-11-28 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 1095 | Telebesparelse ApS | 105083 | NKA-060317 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-20 | 2025-06-20 | Own OnNet
0 | 1 | 0 | 1095 | Telebesparelse ApS | 105083 | NKA-060318 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-07-04 | 2025-07-04 | Own with Digging
0 | 1 | 0 | 1095 | Telebesparelse ApS | 105083 | NKA-060319 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet
0 | 1 | 0 | 849 | Telebesparelse ApS | 98634 | NKA-056439 |  | Merete Helme | SMB Portfolio DK | On Hold | 2024-09-24 |  |  | Own with Digging
0 | 1 | 0 |  | Telecom X ApS | 105378 | NKA-034507 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-12 | 2025-06-13 | 2025-06-13 | Change
0 | 1 | 0 | 1317 | Temashop ApS | 98382 | NKA-056221 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-13 | 2025-06-13 | 2025-06-13 | Own with Digging
0 | 1 | 0 | 1317 | Temashop ApS | 98382 | NML-056222 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-13 | 2025-06-13 | 2025-06-13 | 3rd Party
0 | 1 | 0 | 1295 | The Company Group A/S | 102438 | NKA-059007 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2025-02-20 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1559 | Titan Containers A/S | 100984 | NKA-060848 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-21 | 2025-08-22 | 2025-08-22 | 3rd Party
0 | 1 | 0 | 2200 | Topsil Globalwafers A/S | 103231 | NKA-059922 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 | 2025-07-11 | 2025-06-27 | Own with Digging
0 | 1 | 0 | -763.73 | Topsil Globalwafers A/S | 103231 | NOC-995820 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 |  |  | Change
0 | 1 | 0 | 1295 | Totalklima ApS | 105380 | NKA-060532 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | -427.32 | Væxthuset 3 ApS | 101127 | NKA-010325 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 | 2025-05-28 | 2025-05-28 | Change
0 | 1 | 0 | 165 | Væxthuset 3 ApS | 101127 | NMA-057713 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | 3rd Party
0 | 1 | 0 | 165 | Væxthuset 3 ApS | 101127 | NSW-057712 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-12-05 |  |  | Own OnNet
0 | 1 | 0 | 1160 | Vamdrup Fjernvarme A m b A | 105019 | NKA-060255 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-03 | 2025-07-11 | 2025-07-11 | Own OnNet
0 | 1 | 0 | 3111 | Veo Technologies ApS | 102743 | NDD-059652 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-16 | 2025-06-16 | Own OnNet
0 | 1 | 0 | -3051.47 | Veo Technologies ApS | 102743 | NKA-035994 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-27 | 2025-06-27 | Change
0 | 1 | 0 | 895 | Verdens Skove, Århus | 102530 | NKA-058987 |  | Line Skov | SMB Portfolio DK | In Process | 2025-02-18 | 2025-06-27 | 2025-05-16 | 3rd Party
0 | 1 | 0 | 2095 | Vest Energi ApS | 105347 | NKA-060508 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-28 | 2025-07-25 | 2025-07-25 | Own OnNet
0 | 1 | 0 | 1495 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NDD-056466 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 |  |  | Own OnNet
0 | 1 | 0 | -1065.86 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NKA-030930 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 |  |  | Change
0 | 1 | 0 | 57.89 | Vilhelm Lauritzen Arkitekter A/S | 97191 | NRK-030931 |  | Merete Helme | SMB Portfolio DK | In Process | 2024-09-25 |  |  | Change
0 | 1 | 0 | 895 | Vurderingsmægler ApS | 105158 | NKA-060325 |  | Line Skov | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 200 | Zebnet ApS | 98482 | NML-056428 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 |  |  | 3rd Party
0 | 1 | 0 | -1710.58 | Zebnet ApS | 98482 | NOC-995967 |  | Christoffer Møller Andersen | SMB Portfolio DK | In Process | 2024-09-24 |  |  | Change
0 | 1 | 0 | 4095 | ZTLment ApS | 105695 | NKA-060681 |  | Line Skov | SMB Portfolio DK | In Process | 2025-05-09 |  |  | Own OnNet
0 | 1 | 0 | 855 | Zurface A/S | 104749 | NDD-060570 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-07-25 | 2025-07-25 | Own OnNet
0 | 1 | 0 | 855 | Zurface A/S | 104749 | NKA-060569 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-07-25 | 2025-07-25 | 3rd Party
0 | 1 | 0 | 1100 | Zurface A/S | 104749 | NKA-060571 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet
0 | 1 | 0 | 299.5 | Zurface A/S | 104749 | NKA-060573 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet
0 | 1 | 0 | 299.5 | Zurface A/S | 104749 | NKA-060575 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | Own OnNet
0 | 1 | 0 | 1100 | Zurface A/S | 104749 | NKA-060576 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-06-27 | 2025-06-27 | Own OnNet
0 | 1 | 0 | 1250 | Zurface A/S | 104749 | NKA-060577 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 | 2025-07-25 | 2025-07-25 | 3rd Party
0 | 1 | 0 | 299.5 | Zurface A/S | 104749 | NML-060572 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party
0 | 1 | 0 | 299.5 | Zurface A/S | 104749 | NML-060574 |  | Merete Helme | SMB Portfolio DK | In Process | 2025-05-02 |  |  | 3rd Party
0 | 1 | 0 | 1495 | Ølsnedkeren ApS | 102565 | NKA-059914 |  | Line Skov | SMB Portfolio DK | In Process | 2025-03-24 | 2025-06-20 | 2025-06-20 | 3rd Party
0 | 1 | 0 | 0 | Ønskeskyen ApS | 107636-002 | C36654-1137057-01 | 107636-002-001 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 | 2025-06-13 | 2025-06-13 | Change
0 | 1 | 0 | 0 | Ønskeskyen ApS | 107636-002 | C36654-1137058-01 | 107636-002-002 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 | 2025-06-13 | 2025-06-13 | Change
0 | 1 | 0 | 60 | Ønskeskyen ApS | 107636-002 | C36654-1137059-01 | 107636-002-003 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 | 2025-06-13 | 2025-06-13 | Own OnNet
0 | 1 | 0 | 0 | Ønskeskyen ApS | 107636-002 | C36654-1137061-01 | 107636-002-005 | Shazia Mobin | SMB Portfolio DK | Created | 2025-05-23 | 2025-06-13 | 2025-06-13 | Own OnNet
Total | 425 | 1 | 336675.2813
Applied filters: Actual RFS is (Blank) Delivery Project Manager is not (Blank) #Booked is not blank Department is SMB Delivery DK Std. Delivery is STD. Delivery Segment Red. is SMB Portfolio DK Project Stage is not (Blank), Cancelled, Terminated, or Finished Customer name is not GlobalConnect A/S