## Sheet1
Latest backlog update: | Unnamed: 1 | Input: Which delivery step is the order in? (Drop down list) | Input: What is the status of the order? (Drop down list) | (Optional) Input: Comment | (Optional) Input: Comment.1 | Delta MRC | Customer name | SalesProjectID_ContractNumber | ServiceID_Crid | Project ID AX | Delivery Project Manager | Segment Red. | Project Stage | Dateofcreation_ContractApproved | Committed RFS | Customer AgreedRFS/ConfirmedDeliveryDate | DELIVERYCATEGORY | Date signed | Planning complete date | Design complete date | Correct RFS | Actual RFS | Expected RFS | Deliveryconfirmationdate_Configsignoffdate | Customer Agreed RFS | CUSTOMERCONFIRMEDDELIVERYDATE | CUSTOMERDEFERREDDELIVERYDATE | ReadyForBilling | ProjectTypeValue | SOURCE
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer design (var i tvivl om kolonne D er sat rigtig) |  | 947.5 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 102301 | NKA-059687 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-10 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-03-14 |  |  |  |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | SVdato - 27/05/2025 |  | 947.5 | A.P. Møller og Hustru Chastine Mc-Kinney Møllers Fond Til Almene Formaal | 102301 | NML-059688 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-10 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-14 |  |  |  |  | 2025-05-09 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | On track |  | 560 | Aabenraa Kommune | 103678 | NKA-060363 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-25 | 2025-06-25 | 3rd Party | 2025-04-25 |  |  | 2025-06-20 |  | 2025-06-10 | 2025-05-14 | 2025-06-25 | 2025-06-25 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | Follows projektID 103678 |  | 30 | Aabenraa Kommune | 103680 | NKA-060363 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-25 | 2025-06-25 | Change | 2025-04-25 |  |  |  |  | 2025-06-10 |  | 2025-06-25 | 2025-06-25 |  |  | Change | BO
[6 empty] | 30 | Aabenraa Kommune | 105970 | NKA-055946 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-26 |  |  | Change | 2024-08-27 |  |  |  |  | 2024-09-12 | [5 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Ordering issues |  | 845 | Aarhus Business College | 101953 | NKA-058344 |  | Morten Skytte | Public DK | In Process | 2025-01-13 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-03-21 |  |  | 2025-06-06 |  | 2025-05-30 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Waiting for date from 3. part |  | 845 | Aarhus Business College | 102560 | NKA-058767 |  | Morten Skytte | Public DK | In Process | 2025-02-04 | 2025-06-29 | 2025-06-29 | 3rd Party | [7 empty] | 2025-06-29 | 2025-06-29 |  |  | New Sales | BO
[6 empty] | 7625 | Aarhus Business College | 105408 | NKA-006093 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | 2017-10-18 | 2017-10-18 14:06:00.000 | 2017-10-18 14:06:00.000 | [8 empty] | Change | BO
[6 empty] | 6000 | Aarhus Business College | 105408 | NKA-010029 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 7000 | Aarhus Business College | 105408 | NKA-053439 |  | Morten Skytte | Public DK | In Process | 2025-05-06 |  |  | Change | 2024-03-27 | 2024-04-15 12:08:00.000 | 2024-04-09 11:18:00.000 | [8 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 1210 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060636 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-09 | 2025-05-20 08:02:00.000 | 2025-05-20 12:30:00.000 | 2025-06-27 |  | 2025-06-27 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 1210 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060637 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-09 | 2025-05-20 08:03:00.000 | 2025-05-20 12:31:00.000 | 2025-06-27 |  | 2025-06-27 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 860 | Aarhus Kommune - Filmby Aarhus | 103444 | NKA-060638 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-09 | 2025-05-20 08:00:00.000 | 2025-05-20 12:32:00.000 | 2025-06-27 |  | 2025-06-27 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060126 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own with Digging | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060127 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060128 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060129 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060130 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060131 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party |  |  | 2025-04-02 08:21:00.000 |  |  |  |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060132 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060133 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party |  |  | 2025-04-02 08:22:00.000 |  |  |  |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060134 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060135 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060136 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060137 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060138 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060139 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060140 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1095 | Abc Lavpris Hovedkontor | 102649 | NKA-060141 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1725 | Abc Lavpris Hovedkontor | 102649 | NKA-060172 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 1725 | Abc Lavpris Hovedkontor | 102649 | NKA-060173 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060124 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060142 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060144 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060146 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060148 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060150 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060152 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060154 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060156 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060158 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060160 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060162 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060164 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060166 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060168 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NMA-060170 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | 3rd Party | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060125 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060143 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060145 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060147 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060149 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060151 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060153 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060155 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060157 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060159 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060161 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060163 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060165 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060167 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060169 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | We have just recived equitment today, and waiting on konfig to be done |  | 282.5 | Abc Lavpris Hovedkontor | 102649 | NSW-060171 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | GC solution engineer has a technical meeting with the customer on which solution they prefer in regards to schwiching from old solution to the new solution |  | 700 | Abc Lavpris Hovedkontor | 102649 | NSW-060174 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | GC solution engineer has a technical meeting with the customer on which solution they prefer in regards to schwiching from old solution to the new solution |  | 700 | Abc Lavpris Hovedkontor | 102649 | NSW-060175 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-31 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 4282 | ABENA A/S | 103420 | NKA-059887 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-21 | 2025-10-03 | 2025-10-03 | Own with Digging | 2025-03-26 |  |  |  |  | 2025-07-07 |  | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting for pricing to make an offer to GC SE |  | 2299 | ALD AUTOMOTIVE A/S | 104678 | NKA-059289 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 |  |  | Change | 2025-03-07 | [10 empty] | Change | BO
|  | 1.9 PMO delivery planning | 2.4 Pending equipment/product to be ready for installations |  |  | 13740.4 | Ap Pension Livsforsikringsaktieselskab | 97681 | NBM-057059 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-11-04 | 2025-09-30 | 2025-09-30 | Own OnNet | [7 empty] | 2025-09-30 | 2025-09-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | Overleveret til Natascha |  | 1505 | Associated Danish Ports A/S | 102713 | NKA-060419 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-04-29 |  | 2025-04-22 11:47:00.000 | 2025-06-06 | [7 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | Overleveret til Natascha |  | 387.5 | Associated Danish Ports A/S | 102713 | NMA-060420 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-04-22 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | Overleveret til Natascha |  | 387.5 | Associated Danish Ports A/S | 102713 | NSW-060421 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.2 Customer not reachable / unresponsive | Implementing and testing with the customer have been hard to kodinate due to the status on the ordre. |  | 0 | Associated Danish Ports A/S | 93020 | NSW-055598 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2024-07-16 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 5050 | B4restore A/S | 100991-073 | C30955-1136310-01 | 100991-073-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-04-16 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-07-17 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Waiting for customer get back about dates for SW after freeze period |  | 1725 | Banedanmark | 103135 | NKA-020463 |  | Morten Skytte | Public DK | In Process | 2025-03-17 | 2025-05-28 | 2025-05-28 | Change | 2017-05-16 | 2017-07-25 08:42:00.000 | 2017-07-28 15:22:00.000 |  |  | 2017-08-11 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Shift in vendor after site survey |  | 945 | Banedanmark | 103381 | NKA-059935 |  | Morten Skytte | Public DK | In Process | 2025-03-25 | 2025-07-27 | 2025-07-27 | 3rd Party | [7 empty] | 2025-07-27 | 2025-07-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track; awaiting input from Fibia |  | 1250 | BELFOR Denmark A/S | 104945 | NKA-060415 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-25 |  |  | 2025-06-06 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track; awaiting delivery from Fibia |  | 375 | BELFOR Denmark A/S | 104945 | NSW-060416 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-06-06 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track; awaiting delivery from Fibia |  | 1250 | BELFOR Denmark A/S | 105008 | NKA-060417 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-04-23 | [6 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track; awaiting delivery from Fibia |  | 375 | BELFOR Denmark A/S | 105008 | NSW-060418 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-22 | 2025-07-11 | 2025-07-11 | Own OnNet | [7 empty] | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 1025 | Brøndby Kommune Rådhuset | 100084 | NSF-060740 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | 2025-05-19 | [5 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 1275 | Brøndby Kommune Rådhuset | 100084 | NSF-060741 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | 2025-05-19 | [5 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 1525 | Brøndby Kommune Rådhuset | 100084 | NSF-060742 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-14 |  |  | Own with Digging | 2025-05-19 | [5 empty] | 2025-05-14 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | -4168.6167 | Brønderslev Kommune | 100557-003 | F30256-1136218-01 | 100557-003-001 | Shazia Mobin | Public DK | In Process | 2025-04-14 | 2025-06-13 |  | Change |  |  |  | 2025-06-06 |  | 2025-07-07 |  |  | 2025-06-13 | 2025-06-13 |  | Change | AX
[7 empty] | Carglass A/S | 105822 | NBM-060003 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-23 |  |  | Change | [11 empty] | Change | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 1050 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135627-01 | 106556-011-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 | 2025-06-20 | Own with Digging |  |  |  | 2025-06-13 |  | 2025-06-17 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 0 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135628-01 | 106556-011-002 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-17 |  |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 0 | CHANGE OF SCANDINAVIA RETAIL A/S | 106556-011 | C35749-1135630-01 | 106556-011-004 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-17 |  |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[6 empty] | 3970 | Cimbria A/S | 105712 | NKA-060864 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-22 |  |  | 3rd Party |  |  | 2025-05-23 06:48:00.000 | [8 empty] | New Sales | BO
[6 empty] | 1962 | Cimbria A/S | 105712 | NOC-997893 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-22 |  |  | Change | [11 empty] | Change | BO
|  | 5. Configuration | Other (incl. termination, on hold, unassigned statuses etc.) | Is being done by technology |  | 0 | Coloplast A/S | 100575-033 | C30278-1132145-01 | 100575-033-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-10-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2024-11-27 |  |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting on Pre-sales GC - to find me a new vendor |  | 417.5 | COOP DANMARK A/S | 104731 | NKA-060339 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting on Pre-sales GC - to find me a new vendor |  | 417.5 | COOP DANMARK A/S | 104731 | NML-060340 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Problems with moving CPE and fiber - waiting on a delivery date |  |  | COOP DANMARK A/S | 104776 | NKA-017579 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-03-28 |  |  | Change | 2017-01-26 | 2017-02-22 13:00:00.000 | 2017-01-24 08:20:00.000 | [8 empty] | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Problems with moving CPE and fiber - waiting on a delivery date |  |  | COOP DANMARK A/S | 105012 | NML-018730 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-10 | 2025-06-06 | 2025-06-06 | Change | [6 empty] | 2025-05-01 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Waiting on thired party to complete the installation |  | 417.5 | COOP DANMARK A/S | 105064 | NKA-060297 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-07 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-14 |  |  | 2025-05-30 |  | 2025-05-26 | 2025-04-16 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Waiting on thired party to complete the installation |  | 417.5 | COOP DANMARK A/S | 105064 | NML-060298 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-04-07 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-14 |  |  | 2025-05-30 |  |  | 2025-04-16 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Need to find technician to install the switch |  | 110.61 | COOP DANMARK A/S | 105572 | NBM-051854 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-08 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 110.61 | COOP DANMARK A/S | 105760 | NBM-052166 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-15 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 110.61 | COOP DANMARK A/S | 105761 | NBM-052560 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-15 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 766.41 | COOP DANMARK A/S | 105766 | NBM-060772 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | [11 empty] | New Sales | BO
[7 empty] | COOP DANMARK A/S | 105808 | NBM-052509 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-21 |  |  | Change | [11 empty] | Change | BO
[7 empty] | COOP DANMARK A/S | 105808 | NKA-018027 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-05-21 |  |  | Change | 2017-01-30 | [10 empty] | Change | BO
[6 empty] | 0 | COOP DANMARK A/S | 93108 | NBM-052208 |  | Gunvor Pagh | Enterprise DK | In Process | 2023-12-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Need confirmation from Peter Friis that it is done |  |  | COOP DANMARK A/S | 97456 | NKA-041909 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-07-02 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 1480 | Dalgas a/s | 103582 | NKA-037393 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-09 |  |  | Change | 2025-05-12 |  |  | 2025-05-12 |  | 2025-07-21 | [5 empty] | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | 3P is waiting for their 3P |  | 4879.75 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132546-01 | 107531-002-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | 3rd Party | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | 3P is waiting for their 3P |  | 2682 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132548-01 | 107531-002-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | 3rd Party | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | 3P is waiting for their 3P |  | 0 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132550-01 | 107531-002-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | Own OnNet | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | 3P is waiting for their 3P |  | 0 | DAMCO Poland sp. z o.o. | 107531-002 | C36570-1132551-01 | 107531-002-006 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-11-21 | 2025-07-04 |  | Own OnNet | [5 empty] | 2024-12-24 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
[6 empty] | 630 | DAN`X A/S | 105716 | NMA-060747 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-05-15 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 630 | DAN`X A/S | 105716 | NSW-060746 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | 2.6 Order in queue: Being processed | Servicevindue den 24.05 |  | 14157 | DAN`X A/S | 92961 | NBM-051845 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2023-12-14 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | 2.6 Order in queue: Being processed | Servicevindue den 24.05 |  | 11956.7 | DAN`X A/S | 92961 | NBM-051846 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2023-12-14 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | 6. Cabling splicing and installation |  | 0 | DAN`X A/S | 92963 | NKA-033906 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-27 | 2025-05-27 | Change | 2021-04-06 | 2021-04-08 14:00:00.000 | 2021-05-20 16:22:00.000 |  |  | 2021-06-08 |  | 2025-05-27 | 2025-05-27 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | 6. Cabling splicing and installation |  | 0 | DAN`X A/S | 92963 | NKA-033907 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-27 | 2025-05-27 | Change | 2021-04-06 | 2021-04-08 14:00:00.000 | 2021-05-20 16:23:00.000 |  |  | 2021-06-08 |  | 2025-05-27 | 2025-05-27 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | 6. Cabling splicing and installation |  | 1634 | DAN`X A/S | 92963 | NKA-051475 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-02-26 | 2024-06-27 14:59:00.000 | 2024-05-21 11:18:00.000 | 2024-05-27 |  |  | 2025-03-19 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | 6. Cabling splicing and installation |  | 1634 | DAN`X A/S | 92963 | NKA-051476 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-30 | 2025-05-30 | Own OnNet | 2024-02-27 | 2024-06-27 15:00:00.000 | 2024-05-23 10:09:00.000 | 2024-05-27 |  |  | 2025-03-19 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | 6. Cabling splicing and installation |  | 2203.2 | DAN`X A/S | 92963 | NRS-051477 |  | Andrew David Lindsey | Enterprise DK | In Process | 2023-12-13 | 2025-05-27 | 2025-05-27 | Own OnNet |  |  |  | 2024-05-29 |  |  | 2023-12-13 | 2025-05-27 | 2025-05-27 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | 2.6 Order in queue: Being processed | Servicevindue den 24.05 |  | -9403.94 | DAN`X A/S | 98820 | NBM-051845 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-30 | Change | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 1.9 PMO delivery planning | 2.6 Order in queue: Being processed | Servicevindue den 24.05 |  | -7203.64 | DAN`X A/S | 98820 | NBM-051846 |  | Julie Lillethorup Kierkegaard | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-30 | Change | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 2. Delivery planning | 3.1.1 Pending external 3rd party: Open-Net | Afventer Opennet |  | 977.5 | Danepork A/S | 103326 | NKA-059736 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-12 |  |  | 3rd Party | 2025-05-19 |  |  | 2025-07-04 |  | 2025-06-30 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1.1 Pending external 3rd party: Open-Net | Afventer Opennet |  | 977.5 | Danepork A/S | 103326 | NML-059737 |  | Christoffer Møller Andersen | Enterprise DK | In Process | 2025-03-12 |  |  | 3rd Party |  |  |  | 2025-07-04 | [7 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Service Window 27 may 2025 |  | -1005.25 | Dan-Foam ApS | 102892-008 | C32553-1135648-01 | 102892-008-001 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-28 | 2025-05-02 | Change |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | On track |  | 518.2 | Dan-Foam ApS | 102892-008 | C32553-1135649-01 | 102892-008-002 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-28 | 2025-05-02 | Change |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Service Window 27 may 2025 |  | 0 | Dan-Foam ApS | 102892-008 | C32553-1135650-01 | 102892-008-003 | Shazia Mobin | Enterprise DK | Created | 2025-03-27 | 2025-05-28 | 2025-05-02 | Own OnNet |  |  |  | 2025-04-25 |  | 2025-05-20 |  | 2025-05-02 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
[6 empty] | 2012 | Danica Ejendomme P/S | 88343 | NKA-048437 |  | Jan Dibbern | Enterprise DK | In Process | 2023-06-16 | 2025-06-30 | 2025-06-30 | Own OnNet | 2023-05-16 | 2023-06-27 13:24:00.000 | 2023-06-27 13:25:00.000 |  |  | 2023-06-29 | 2023-06-28 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 2012 | Danica Ejendomme P/S | 88343 | NKA-048438 |  | Jan Dibbern | Enterprise DK | In Process | 2023-06-16 | 2025-06-30 | 2025-06-30 | Own with Digging | 2023-06-16 | 2024-06-07 12:33:00.000 | 2024-06-07 12:33:00.000 |  |  | 2025-06-30 | 2023-06-28 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | On track |  | 350 | Danmarks Meteorologiske Institut | 102835 | NKA-059003 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-19 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-24 |  |  | 2025-06-13 |  | 2025-06-03 | 2025-05-13 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 821 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129804-01 | 100489-187-001 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-25 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-25 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 85 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129806-01 | 100489-187-003 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 94 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129808-01 | 100489-187-005 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 85 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129810-01 | 100489-187-007 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 146 | Danmarks Tekniske Universitet | 100489-187 | F30176-1129812-01 | 100489-187-009 | Michael Kronbach Leth | Public DK | In Process | 2024-07-08 | 2025-06-06 | 2025-04-18 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-09-25 |  | 2025-04-18 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 638 | Danmarks Tekniske Universitet | 100489-188 | F30176-1130153-01 | 100489-188-001 | Michael Kronbach Leth | Public DK | In Process | 2024-07-23 | 2025-06-30 | 2025-04-25 | Own OnNet |  |  |  | 2025-04-11 |  | 2024-10-07 |  | 2025-04-25 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 629 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130598-01 | 100489-189-001 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 92 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130600-01 | 100489-189-003 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own OnNet |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 96 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130602-01 | 100489-189-005 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 85 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130604-01 | 100489-189-007 | Michael Kronbach Leth | Public DK | Created | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 163 | Danmarks Tekniske Universitet | 100489-189 | F30176-1130606-01 | 100489-189-009 | Michael Kronbach Leth | Public DK | In Process | 2024-08-23 | 2025-06-30 | 2025-02-28 | Own with Digging |  |  |  | 2025-02-21 |  | 2024-11-13 |  | 2025-02-28 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 117 | Danmarks Tekniske Universitet | 100489-192 | F30176-1134864-01 | 100489-192-001 | Michael Kronbach Leth | Public DK | Created | 2025-02-22 | 2025-06-30 | 2025-06-20 | Own OnNet |  |  |  | 2025-06-13 |  | 2025-05-16 |  | 2025-06-20 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Kunde er utilgængelig hele tiden. |  | 283 | Danmarks Tekniske Universitet | 100489-195 | F30176-1135247-01 | 100489-195-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-12 | 2025-06-30 |  | Own OnNet | [5 empty] | 2025-06-01 |  |  | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Will be RFS in June |  | 188 | Danmarks Tekniske Universitet | 100489-196 | F30176-1136654-01 | 100489-196-001 | Michael Kronbach Leth | Public DK | In Process | 2025-04-30 | 2025-06-30 | 2025-06-30 | Own with Digging |  |  |  | 2025-06-27 |  | 2025-07-17 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track, installation uge 31 efter kunden ønske |  | 475 | Danpilot Svendborg | 104609 | NKA-060072 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-05-05 |  |  | 2025-07-25 |  | 2025-07-18 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | Pending on OpenNet tool fix |  | 540 | DANSK AVIS OMDELING A/S | 101097 | NKA-058161 |  | Martin Rasmussen | Enterprise DK | In Process | 2024-12-27 | 2025-05-30 | 2025-04-11 | 3rd Party | [7 empty] | 2025-04-11 | 2025-04-11 | 2025-05-30 |  | New Sales | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | Pending on OpenNet tool fix |  | 540 | DANSK AVIS OMDELING A/S | 101097 | NML-058162 |  | Martin Rasmussen | Enterprise DK | In Process | 2024-12-27 | 2025-05-30 | 2025-04-11 | 3rd Party | 2025-01-23 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-05-30 |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2495 | DANSK AVIS OMDELING A/S | 103525 | NKA-060488 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2495 | DANSK AVIS OMDELING A/S | 103525 | NKA-060489 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1995 | DANSK AVIS OMDELING A/S | 103525 | NKA-060490 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | 2025-05-21 |  |  |  |  | 2025-07-18 | 2025-05-23 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1995 | DANSK AVIS OMDELING A/S | 103525 | NKA-060491 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 |  |  | Own OnNet | 2025-05-21 |  |  |  |  | 2025-07-18 | 2025-05-23 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060492 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-08 | 2025-05-23 14:45:00.000 |  | 2025-07-04 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060493 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-08 | 2025-05-23 14:12:00.000 |  | 2025-07-04 |  | 2025-07-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060494 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-05-08 | 2025-05-09 13:15:00.000 | 2025-05-13 10:13:00.000 | 2025-07-11 |  | 2025-07-04 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 2520 | DANSK AVIS OMDELING A/S | 103525 | NKA-060495 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-05-08 | 2025-05-09 13:17:00.000 | 2025-05-13 10:13:00.000 | 2025-07-11 |  | 2025-07-04 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060496 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:16:00.000 | 2025-05-22 13:55:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060497 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:37:00.000 | 2025-05-22 13:55:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060498 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:16:00.000 | 2025-05-22 13:57:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060499 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:38:00.000 | 2025-05-22 13:57:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060500 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:17:00.000 | 2025-05-22 13:58:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 1372.5 | DANSK AVIS OMDELING A/S | 103525 | NSF-060501 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-28 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-05-21 | 2025-05-22 10:39:00.000 | 2025-05-22 13:58:00.000 | 2025-05-30 |  | 2025-08-08 | 2025-04-28 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 2472.5 | Dansk Brand- og sikringsteknisk Institut | 102685 | NKA-058841 |  | Peter Madsen | Enterprise DK | In Process | 2025-02-10 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-03-13 |  |  |  |  | 2025-03-28 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | This is the "B-end" for above circuit(NKA-058841). It's a "EPL" solution(point-2-point). There is no work needed, other than configuration, for NOC-997185, but it can't be done until the "A-end" connection has been delivered. |  |  | Dansk Brand- og sikringsteknisk Institut | 102685 | NOC-997185 |  | Peter Madsen | Enterprise DK | In Process | 2025-02-10 | 2025-07-11 | 2025-07-11 | Change | 2021-02-25 | [6 empty] | 2025-07-11 | 2025-07-11 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 4275 | Dansk Cater A/S | 101461-008 | F31427-1136260-01 | 101461-008-001 | Cecilie Heidner Nielsen | Enterprise DK | In Process | 2025-04-15 | 2025-05-28 | 2025-08-28 | Own with Digging |  |  |  | 2025-05-28 |  | 2025-07-06 |  | 2025-08-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 4575 | Dansk Cater A/S | 101461-008 | F31427-1136262-01 | 101461-008-003 | Cecilie Heidner Nielsen | Enterprise DK | In Process | 2025-04-15 | 2025-05-28 | 2025-08-28 | Own with Digging |  |  |  | 2025-05-28 |  | 2025-07-06 |  | 2025-08-28 | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | Delivered | Delivered |  |  | 2166 | Dansk Retursystem A/S | 100785 | NKA-057824 |  | Peter Madsen | Enterprise DK | In Process | 2024-12-10 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-12-13 | 2025-04-09 08:10:00.000 | 2025-04-11 10:06:00.000 |  |  | 2025-03-14 |  | 2025-10-01 | 2025-10-01 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | Pending that the customers' building is ready for delivery. It's a new site being constructed. Won't be ready for delivery until at least august/september. |  | 2091 | Dansk Retursystem A/S | 100785 | NKA-057825 |  | Peter Madsen | Enterprise DK | In Process | 2024-12-10 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-12-13 |  |  |  |  | 2025-03-14 |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1125 | Dansk Revision A/S | 102738 | NKA-060732 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-14 | 2025-08-15 | 2025-08-15 | 3rd Party | 2025-05-15 |  |  | 2025-08-15 |  | 2025-07-18 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1125 | Dansk Revision A/S | 102738 | NML-060733 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-14 | 2025-08-15 | 2025-08-15 | 3rd Party | 2025-05-15 |  |  | 2025-08-15 |  | 2025-07-18 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet |  | 4500 | Danske Commodities A/S | 101109-042 | F31073-1125802-01 | 101109-042-001 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet |  | 4600 | Danske Commodities A/S | 101109-042 | F31073-1125804-01 | 101109-042-003 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet |  | 3900 | Danske Commodities A/S | 101109-042 | F31073-1125806-01 | 101109-042-005 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Building is not ready yet |  | 4000 | Danske Commodities A/S | 101109-042 | F31073-1125808-01 | 101109-042-007 | Camilla Olesen | Enterprise DK | In Process | 2024-02-27 | 2025-06-27 | 2025-06-27 | Own OnNet |  |  |  | 2025-06-20 |  | 2024-07-02 |  | 2025-06-27 | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 1600 | Danske Commodities A/S | 101109-053 | C31073-1136532-01 | 101109-053-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-27 | 2025-07-01 | 2025-07-01 | Own OnNet |  |  |  | 2025-06-27 |  | 2025-07-17 |  | 2025-07-01 | 2025-07-01 | 2025-07-01 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 0 | Danske Commodities A/S | 101109-053 | C31073-1136533-01 | 101109-053-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-27 | 2025-07-01 |  | Own OnNet | [5 empty] | 2025-07-17 |  |  | 2025-07-01 | 2025-07-01 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NKA-058049 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NKA-058057 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | Own OnNet
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NML-058048 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NML-058056 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track |  | 837 | Danske Olieberedskabslagre | 100670 | NML-058074 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-20 |  |  | 3rd Party
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | -777 | Danske Olieberedskabslagre | 103254 | NKA-058049 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | -777 | Danske Olieberedskabslagre | 103254 | NKA-058057 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | The fiber is moved the 2nd of june |  | 60 | Danske Olieberedskabslagre | 103254 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-26 |  |  | Change
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | The fiber is moved the 2nd of june |  |  | Danske Olieberedskabslagre | 105234 | NKA-058075 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-16 |  |  | Change
[6 empty] | 955 | Danske Olieberedskabslagre | 105625 | NKA-060745 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-14 | 2025-06-23 | 2025-06-23 | 3rd Party | 2025-04-16 | [6 empty] | 2025-06-23 | 2025-06-23 |  |  | New Sales | BO
[6 empty] | 955 | Danske Olieberedskabslagre | 105625 | NML-060744 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-14 | 2025-06-23 | 2025-06-23 | 3rd Party | [7 empty] | 2025-06-23 | 2025-06-23 |  |  | New Sales | BO
[7 empty] | Danske Olieberedskabslagre | 105853 | NML-058062 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-21 | 2025-06-06 | 2025-06-06 | Change | 2025-01-20 | 2025-04-24 10:20:00.000 | 2025-04-25 09:46:00.000 | 2025-06-06 |  | 2025-05-23 | 2025-05-26 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 680 | Deichmann Sko AB | 97337 | NKA-055297 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | 3rd Party | 2024-07-17 |  |  |  |  | 2025-01-31 | 2024-07-17 | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 680 | Deichmann Sko AB | 97337 | NKA-055333 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | 2024-07-17 |  |  |  |  | 2024-06-20 | 2024-07-17 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann Sko AB | 97337 | NMA-055299 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | 3rd Party | [7 empty] | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann Sko AB | 97337 | NMA-055335 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann Sko AB | 97337 | NSW-055298 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-11-14 | 2025-11-14 | Own OnNet | [7 empty] | 2025-11-14 | 2025-11-14 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann Sko AB | 97337 | NSW-055334 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 720 | Deichmann-Sko ApS | 97347 | NKA-055384 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own with Digging | 2024-11-11 | 2025-05-13 12:53:00.000 | 2025-05-20 11:38:00.000 | 2025-06-20 |  | 2025-04-25 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 720 | Deichmann-Sko ApS | 97347 | NKA-055408 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-28 | 2024-11-11 14:04:00.000 | 2024-11-11 14:04:00.000 | 2025-05-30 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 720 | Deichmann-Sko ApS | 97347 | NKA-055429 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2024-11-11 | 2025-01-28 09:09:00.000 | 2025-04-14 12:10:00.000 | 2025-05-30 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 720 | Deichmann-Sko ApS | 97347 | NKA-055435 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-11-11 | 2025-01-28 10:18:00.000 | 2025-05-08 13:02:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 720 | Deichmann-Sko ApS | 97347 | NKA-055447 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own with Digging | 2024-11-11 | 2024-11-12 16:57:00.000 | 2025-05-12 08:23:00.000 | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NMA-055385 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NMA-055409 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NMA-055430 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NMA-055436 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NMA-055448 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NSW-055386 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NSW-055410 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NSW-055431 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-05-28 | 2025-05-28 | Own OnNet | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NSW-055437 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Håndteres af Natascha |  | 50 | Deichmann-Sko ApS | 97347 | NSW-055449 |  | Kristijan Krsteski | Enterprise DK | In Process | 2024-06-28 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | On Track | On Track | On Track |  | 900 | DGI | 103177 | NKA-059646 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-07 | 2025-05-15 13:17:00.000 | 2025-05-21 09:11:00.000 |  |  | 2025-05-09 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Pending GC Norway |  | 900 | Diningsix A/S | 104919 | NKA-060447 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-23 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[6 empty] | 625 | DLF Seeds A/S | 105685 | NKA-060839 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-21 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 625 | DLF Seeds A/S | 105685 | NML-060840 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-21 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 2821 | Dovista A/S | 103016 | NII-060186 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 2821 | Dovista A/S | 103016 | NII-060187 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5956 | Dovista A/S | 103016 | NII-060188 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5956 | Dovista A/S | 103016 | NII-060189 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-12 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5655 | Dovista A/S | 103016 | NII-060190 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5655 | Dovista A/S | 103016 | NII-060191 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5581 | Dovista A/S | 103016 | NII-060192 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5581 | Dovista A/S | 103016 | NII-060193 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  | 3428 | Dovista A/S | 103016 | NII-060194 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 3428 | Dovista A/S | 103016 | NII-060195 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-06-19 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 3361.5 | Dovista A/S | 103016 | NII-060196 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 3361.5 | Dovista A/S | 103016 | NII-060197 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5581 | Dovista A/S | 103016 | NII-060198 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 5581 | Dovista A/S | 103016 | NII-060199 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 | [5 empty] | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 4149 | Dovista A/S | 104664 | NII-060200 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-21 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Pending delivery date from vendor. Deliveries abroad can take much longer than domestec deliveries. |  | 4149 | Dovista A/S | 104664 | NII-060201 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-31 | 2025-09-01 | 2025-09-01 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-08-21 | 2025-03-31 | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 1050 | DSV A/S | 100789-088 | C30752-1136045-01 | 100789-088-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-07 | 2025-06-20 | 2025-06-20 | Own OnNet |  |  |  | 2025-06-13 |  | 2025-06-27 | 2025-05-26 | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 60 | DSV A/S | 100789-088 | C30752-1136046-01 | 100789-088-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-07 | 2025-06-20 |  | Own OnNet | [5 empty] | 2025-06-27 | 2025-05-26 |  | 2025-06-20 | 2025-06-20 |  | New Sales | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 670 | Elis Danmark A/S | 102414 | NKA-060542 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 585 | Elis Danmark A/S | 102414 | NKA-060544 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Own with Digging | 2025-05-19 |  |  |  |  | 2025-08-08 |  | 2025-08-08 | 2025-08-08 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 670 | Elis Danmark A/S | 102414 | NML-060543 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 585 | Elis Danmark A/S | 102414 | NML-060545 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | 3rd Party | 2025-05-19 |  |  |  |  | 2025-08-08 |  | 2025-08-08 | 2025-08-08 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -122.8 | Elis Danmark A/S | 102414 | NSW-044170 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-27 | 2025-06-27 | Change | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044175 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Change | [7 empty] | 2025-08-08 | 2025-08-08 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044178 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-15 | 2025-08-15 | Change | [7 empty] | 2025-08-15 | 2025-08-15 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044181 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-07-04 | 2025-07-04 | Change | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044183 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-07-04 | 2025-07-04 | Change | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044186 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-07-04 | 2025-07-04 | Change | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044189 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Change | [7 empty] | 2025-08-08 | 2025-08-08 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044195 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-13 | 2025-06-13 | Change | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044197 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-13 | 2025-06-13 | Change | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044203 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-20 | 2025-06-20 | Change | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044206 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-27 | 2025-06-27 | Change | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -101.2 | Elis Danmark A/S | 102414 | NSW-044209 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-27 | 2025-06-27 | Change | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044212 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-27 | 2025-06-27 | Change | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044215 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-20 | 2025-06-20 | Change | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044218 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-20 | 2025-06-20 | Change | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044221 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Change | [7 empty] | 2025-08-08 | 2025-08-08 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-044226 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Change | [7 empty] | 2025-08-08 | 2025-08-08 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 850 | Elis Danmark A/S | 102414 | NSW-044229 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-08-08 | 2025-08-08 | Change | [7 empty] | 2025-08-08 | 2025-08-08 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | -90 | Elis Danmark A/S | 102414 | NSW-046860 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-20 | 2025-06-20 | Change | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 470 | Elis Danmark A/S | 102414 | NSW-060546 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-04-30 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 1.Order entry and validation | 1.1 Waiting on customer confirmation or input | Kunde mener at have købt redundans |  | 1320 | ENTERTAINMENT TRADING A/S | 105207 | NKA-060412 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-05-14 |  |  | 2025-06-20 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.6 Order in queue: Being processed | Kunde mener at have købt redundans |  | 387.5 | ENTERTAINMENT TRADING A/S | 105207 | NMA-060414 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 1.Order entry and validation | 2.6 Order in queue: Being processed | Uklarheder om korrekt salg |  | 387.5 | ENTERTAINMENT TRADING A/S | 105207 | NSW-060413 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-04-22 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) |  |  | 999 | European Energy A/S | 97899 | NKA-055965 |  | Merete Helme | Enterprise DK | In Process | 2024-08-27 | 2025-06-13 | 2025-06-13 | 3rd Party | 2024-09-02 |  |  | 2025-06-06 |  |  | 2025-03-06 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Service Window needs to be planned |  | 1650 | Fiftytwo A/S | 96513 | NKA-055062 |  | Line Skov | Enterprise DK | In Process | 2024-06-26 | 2025-06-06 | 2025-06-06 | Own OnNet | 2024-07-08 | [5 empty] | 2024-09-10 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.1 Waiting on customer confirmation or input | Service Window needs to be planned |  | 1650 | Fiftytwo A/S | 96513 | NKA-055063 |  | Line Skov | Enterprise DK | In Process | 2024-06-26 | 2025-06-06 | 2025-06-06 | Own OnNet | 2024-07-08 | [5 empty] | 2024-09-10 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 697.5 | FLAMMEN A/S | 102960 | NKA-060444 |  | Merete Helme | Enterprise DK | In Process | 2025-04-23 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-01 |  |  | 2025-07-04 |  | 2025-07-18 | 2025-05-07 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 697.5 | FLAMMEN A/S | 102960 | NML-060445 |  | Merete Helme | Enterprise DK | In Process | 2025-04-23 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-01 |  |  | 2025-07-04 |  | 2025-07-18 | 2025-05-07 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg |  | 1495 | Fleggaard It ApS | 93857 | NKA-054774 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-11-13 | [6 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg |  | 1295 | Fleggaard It ApS | 93857 | NKA-054775 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-28 | 2025-05-28 | Own OnNet | 2024-06-19 | 2024-06-26 11:38:00.000 | 2024-07-02 10:03:00.000 | 2024-07-31 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | physical: On track - Config: Awating Kasper Duborg |  | 1495 | Fleggaard It ApS | 93857 | NKA-054776 |  | Jesper Olsen | Enterprise DK | In Process | 2024-06-14 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-11-13 | [6 empty] | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | On track |  | 2037 | FLSMIDTH A/S | 96792 | NKA-058793 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-06 | 2025-07-18 | 2025-07-18 | Own with Digging | 2025-02-07 |  |  |  |  | 2025-05-02 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | On track |  | 2037 | FLSMIDTH A/S | 96792 | NKA-058794 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-02-06 | 2025-07-18 | 2025-07-18 | Own with Digging | 2025-02-07 |  |  |  |  | 2025-05-02 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.4 Other installation obstacles and infratructure issues | Need clarification on configuration in data center. |  | 1586 | FOA Fag og Arbejde | 103456 | NKA-059764 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-13 | 2025-08-22 | 2025-08-22 | 3rd Party | 2025-05-15 |  |  |  |  | 2025-08-22 |  | 2025-08-22 | 2025-08-22 |  |  | New Sales | BO
|  | 8. Ready for service | 2.6 Order in queue: Being processed | 8. Ready for service |  | 4130 | FOA Fag og Arbejde | 98150 | NKA-059241 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own OnNet | 2025-03-10 |  |  |  |  | 2025-05-16 | [5 empty] | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Reliant on line 249 |  | -1846.86 | FOA Fag og Arbejde | 98150 | NOC-997378 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Change |  | 2018-01-04 15:18:00.000 | 2018-01-04 15:18:00.000 | [8 empty] | Change | BO
|  | 2. Delivery planning | 2.5 Internal or external data/documentation incomplete/ incorrect | Needed to obtain correct location for Dark Fiber from customer |  | 1775 | FOA Fag og Arbejde | 98150 | NSF-059243 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own with Digging | 2025-03-10 | 2025-05-07 07:36:00.000 | 2025-05-21 14:37:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-03-03 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.5 Internal or external data/documentation incomplete/ incorrect | Needed to obtain correct location for Dark Fiber from customer |  | 1775 | FOA Fag og Arbejde | 98150 | NSF-059244 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-03-03 |  |  | Own with Digging | 2025-03-10 | 2025-05-07 07:37:00.000 | 2025-05-22 10:40:00.000 |  |  | 2025-05-16 | 2025-03-03 |  |  |  |  | New Sales | BO
[6 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 101523 | NKA-058262 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | 3rd Party
[6 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 101523 | NKA-058263 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | 3rd Party
[7 empty] | Forsvaret og Forsvarsministeriets styrelser | 101766 | NKA-058262 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | Change
[7 empty] | Forsvaret og Forsvarsministeriets styrelser | 101766 | NKA-058263 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-07 |  |  | Change
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 925 | Forsvaret og Forsvarsministeriets styrelser | 102351 | NKA-058631 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-28 |  |  | 3rd Party
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 925 | Forsvaret og Forsvarsministeriets styrelser | 102351 | NKA-058632 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-28 |  |  | 3rd Party
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track, installation uge 25 |  | 675 | Forsvaret og Forsvarsministeriets styrelser | 104956 | NKA-060250 |  | Eva Eisner | Public DK | In Process | 2025-04-03 |  |  | 3rd Party
[6 empty] | 7625 | Forsvaret og Forsvarsministeriets styrelser | 105717 | NKA-060846 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-21 |  |  | Own OnNet
[6 empty] | 7625 | Forsvaret og Forsvarsministeriets styrelser | 105717 | NKA-060847 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-21 |  |  | Own OnNet
[6 empty] | 475 | Forsvaret og Forsvarsministeriets styrelser | 91996 | NKA-002013 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-22 |  |  | Change
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready | customer has written in contract that they can postpone RFS until june |  | 7100 | Foss Analytical A/S | 98346 | NKA-056204 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-09-12 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-09-23 | 2024-11-25 13:35:00.000 | 2024-12-12 13:09:00.000 | 2025-03-19 |  | 2025-03-28 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready | customer has written in contract that they can postpone RFS until june |  | 7100 | Foss Analytical A/S | 98346 | NKA-056205 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-09-12 | 2025-05-28 | 2025-05-28 | Own with Digging | 2024-09-23 | 2024-11-25 13:35:00.000 | 2024-12-12 13:09:00.000 | 2025-03-19 |  | 2025-03-28 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 4. Final design | 3.1 Pending external 3rd party: Any 3rd party | awaiting TDC for instal dates. |  | 1195 | FRELSENS HÆR SOCIALTJENESTEN | 103003 | NKA-060669 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | 3rd Party | 2025-05-19 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Pending delivery date from vendor. |  | 615 | Friluftsland A/S | 105554 | NKA-060736 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-14 | 2025-08-29 | 2025-08-29 | 3rd Party | 2025-05-15 |  |  |  |  | 2025-08-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Pending delivery date from vendor. |  | 615 | Friluftsland A/S | 105554 | NML-060737 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-14 | 2025-08-29 | 2025-08-29 | 3rd Party | 2025-05-15 |  |  |  |  | 2025-08-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
[6 empty] | 3995 | Frode Laursen A/S | 105079 | NKA-060620 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-06 | 2025-10-01 | 2025-10-01 | 3rd Party | [7 empty] | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. |  | 4500 | Frode Laursen A/S | 89081 | NKA-023538 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2018-03-07 |  |  |  |  | 2018-06-29 |  | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. |  | 2500 | Frode Laursen A/S | 89081 | NKA-033837 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2021-03-25 | [5 empty] | 2025-04-03 | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. |  | 6000 | Frode Laursen A/S | 89081 | NOC-998343 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2014-03-12 | [6 empty] | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Change of MTU size and CPE. Project is handled by another person/department(Mikael Mulvad). Customer has been invoiced as of 01/04-2025 even though we have not signed of the work itself, as this was agreed between the customer and GC account manager. |  | 4000 | Frode Laursen A/S | 89081 | NOC-998373 |  | Peter Madsen | Enterprise DK | In Process | 2023-08-03 | 2025-06-27 | 2025-06-27 | Change | 2014-03-12 | [6 empty] | 2025-06-27 | 2025-06-27 |  | 2025-02-11 00:00:00.000 | Change | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | On track |  | 1760 | GENERAL LOGISTICS SYSTEMS DENMARK A/S | 103151 | NKA-059759 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-12 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-17 | 2025-04-04 12:25:00.000 | 2025-04-24 10:10:00.000 | 2025-06-20 |  |  | 2025-04-29 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035601 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035602 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035680 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-01 09:47:00.000 | 2021-11-01 09:47:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035695 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035708 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035711 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035748 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035770 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035792 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035793 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change |  | 2021-11-17 08:35:00.000 | 2021-11-17 08:36:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035794 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035797 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | 2021-07-16 | 2021-11-09 08:20:00.000 | 2021-11-09 08:20:00.000 |  |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track |  | 0 | GENTOFTE KOMMUNE | 102771 | NKA-035798 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | The Technical part is not agreed on yet (Netteam) |  | 2257.71 | Give Uddannelsescenter | 102537 | NBM-058824 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-02-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-21 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready | RFS December 2025 |  | 550 | Glostrup Kommune | 100034 | NKA-056919 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | 3rd Party | 2024-11-18 |  |  |  |  | 2025-01-31 |  | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready | RFS December 2025 |  | 227.5 | Glostrup Kommune | 100034 | NMA-056921 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | 3rd Party | 2024-11-18 |  |  |  |  | 2025-01-31 |  | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready | RFS December 2025 |  | 227.5 | Glostrup Kommune | 100034 | NSW-056920 |  | Michael Kronbach Leth | Public DK | In Process | 2024-10-24 | 2025-12-26 | 2025-12-26 | Own OnNet | [7 empty] | 2025-12-26 | 2025-12-26 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awating 3. party to get back with an offer for the internal mowement off the fiber |  |  | Glostrup Kommune | 105649 | NKA-041535 |  | Morten Skytte | Public DK | In Process | 2025-05-09 | 2025-07-01 | 2025-07-01 | Change | 2022-06-09 | [6 empty] | 2025-07-01 | 2025-07-01 |  |  | Change | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Awating ordre for new L2 connection |  | 25 | Guldborgsund Kommune | 105041 | NKA-033744 |  | Morten Skytte | Public DK | In Process | 2025-04-10 | 2025-06-30 | 2025-06-30 | Change | 2021-03-15 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 300 | Guldborgsund Kommune | 105144 | NKA-060502 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-28 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-28 |  |  | 2025-06-17 |  | 2025-06-17 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 300 | Guldborgsund Kommune | 105648 | NKA-060720 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-13 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-05-22 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 300 | Guldborgsund Kommune | 105648 | NKA-060721 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-13 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-05-22 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Hard to make appointment with end customer for CPE installation |  | 950 | Haderslev kommune | 89321 | NKA-050356 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-02 |  |  | 2025-05-16 |  | 2025-02-24 | 2025-02-27 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050357 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.4 Other installation obstacles and infratructure issues | No link from 3.part when trying to migrate in SW - new to be schuled |  | 1400 | Haderslev kommune | 89321 | NKA-050369 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-09 | 2025-04-25 12:17:00.000 | 2025-04-25 12:17:00.000 | 2025-04-23 |  | 2025-02-25 | 2025-01-17 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.2 Customer not reachable / unresponsive | Hard to make appointment with end customer for CPE installation |  | 1400 | Haderslev kommune | 89321 | NKA-050376 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-02 |  |  | 2025-05-16 |  | 2025-03-07 | 2025-02-28 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050381 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050382 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050383 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050384 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050385 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050386 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050387 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050388 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050389 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050390 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own with Digging | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050395 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Part of larger project - customer is getting billed 50 % |  | 475 | Haderslev kommune | 89321 | NKA-050396 |  | Morten Skytte | Public DK | In Process | 2023-09-29 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050350 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-05-28 | 2025-05-28 | Change | 2024-07-18 |  |  |  |  | 2024-08-28 |  | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050355 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050356 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-02 |  |  |  |  | 2025-02-24 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050357 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050369 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-09 | 2025-04-25 12:17:00.000 | 2025-04-25 12:17:00.000 |  |  | 2025-02-25 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050374 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050376 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | 2025-01-02 |  |  |  |  | 2025-03-07 | [5 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050377 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050381 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050382 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050383 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050384 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050385 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050386 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050387 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050388 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050389 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050390 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050395 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050396 |  | Morten Skytte | Public DK | In Process | 2024-12-06 | 2025-12-31 | 2025-12-31 | Change | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | Change | BO
|  | 8. Ready for service | 2.5 Internal or external data/documentation incomplete/ incorrect | Just needs to be signed off |  | 40 | Haderslev kommune | 89440 | NKA-050397 |  | Morten Skytte | Public DK | In Process | 2024-12-06 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 1050 | Halberg A/S | 105673 | NKA-060682 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-05-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 8. Ready for service | 2.6 Order in queue: Being processed | On track - part of the total Harboe Solution and is a part of a tempary service gateway - therefore 0 mrc |  | 0 | Harboes Bryggeri A/S | 102376 | NCI-058640 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-01-28 |  |  | Own OnNet | [6 empty] | 2025-02-11 |  |  |  |  | New Sales | BO
|  | 8. Ready for service | 2.6 Order in queue: Being processed | On track - part of the total Harboe Solution and is a part of a tempary service gateway - therefore 0 mrc |  | 0 | Harboes Bryggeri A/S | 102376 | NSW-058639 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2025-01-28 |  |  | Own OnNet | [6 empty] | 2025-02-11 |  |  |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Long lead time in Germany op to 26 weeks ordred 13-01-2025 - but ot is on track |  | 4950 | Harboes Bryggeri A/S | 98586 | NKA-056499 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own with Digging | 2025-01-13 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | New vendor found because the first vendor wanted 40.000 euro. So we are starting all over |  | 7600 | Harboes Bryggeri A/S | 98586 | NKA-056501 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own with Digging | 2025-01-13 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Long lead time in Germany op to 26 weeks ordred 13-01-2025 |  | 1370 | Harboes Bryggeri A/S | 98586 | NSW-056498 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Germany vendor wants 45.000 euro to compelete the installation, and that is more the expected. Therefore Carsten Jørgensen is helping with an alternative, but germany third party vendor is moving slow |  | 1680 | Harboes Bryggeri A/S | 98586 | NSW-056500 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow a technical meeting is agreed in week 21 and after that meeting we know when to migret |  | 840 | Harboes Bryggeri A/S | 98586 | NSW-056502 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 8. Ready for service | 1.1 Waiting on customer confirmation or input | Need to make a servicewindow a technical meeting is agreed in week 21 and after that meeting we know when to migret |  | 2670 | Harboes Bryggeri A/S | 98586 | NSW-056504 |  | Jeppe Mutinda Mbinda | Enterprise DK | In Process | 2024-09-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Handed over from Enterprice were ther warent made a status since |  | 900 | Hempel Fonden | 101434 | NKA-058108 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-23 | Own OnNet | 2025-01-02 | 2025-01-07 11:58:00.000 | 2025-01-10 09:55:00.000 | 2025-05-27 |  | 2025-03-07 | 2025-01-31 | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Handed over from Enterprice were ther warent made a status since |  | 200 | Hempel Fonden | 101434 | NMA-058110 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-23 | 3rd Party | [6 empty] | 2025-02-07 | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Handed over from Enterprice were ther warent made a status since |  | 200 | Hempel Fonden | 101434 | NSW-058109 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2024-12-20 | 2025-05-30 | 2025-05-23 | Own OnNet | [6 empty] | 2025-02-07 | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input |  |  |  | Herningsholm Erhvervsskole & Gymnasier S/I | 102088 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2025-02-12 |  |  | Change | 2019-01-29 | 2023-12-01 13:12:00.000 | 2023-12-01 13:12:00.000 |  |  |  | 2025-05-01 |  |  |  |  | Change | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Will Be RFS in June |  |  | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Will Be RFS in June |  | 720 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-042377 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Change | 2022-05-02 |  | 2022-06-01 09:42:00.000 |  |  | 2022-09-14 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Will Be RFS in June |  | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060067 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Own OnNet | 2025-04-15 | 2025-05-06 14:35:00.000 | 2025-05-21 13:39:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Will Be RFS in June |  | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060068 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-04-15 | 2025-05-06 14:47:00.000 | 2025-05-21 13:40:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Will Be RFS in June |  | 845 | Herningsholm Erhvervsskole & Gymnasier S/I | 103011 | NKA-060069 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-04-15 | 2025-05-09 07:21:00.000 | 2025-05-22 12:26:00.000 | 2025-06-20 |  | 2025-06-13 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Afventer SW med kunden i Juli måned. |  | 6000 | Herningsholm Erhvervsskole & Gymnasier S/I | 88766 | NKA-001283 |  | Michael Kronbach Leth | Public DK | In Process | 2023-09-11 | 2025-07-30 | 2025-07-30 | Change |  | 2023-10-24 13:56:00.000 | 2023-10-24 13:56:00.000 | 2024-03-14 |  |  |  | 2025-07-30 | 2025-07-30 |  |  | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | Pending on OpenNet tool fix |  | 850 | Hi Five A/S | 104285 | NKA-059846 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 4. Final design | 3.4 Other installation obstacles and infratructure issues | Vendor shift after site survey |  | 1725 | Hjørring Gymnasium og HF-Kursus | 101158 | NKA-006159 |  | Morten Skytte | Public DK | In Process | 2024-12-03 | 2025-06-30 | 2025-06-30 | Change | 2014-01-09 |  |  | 2025-06-27 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | Delivered | Delivered |  |  | 1495 | HKScan Denmark A/S | 102177 | NDD-059703 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-04-29 | 2025-06-20 | 2025-06-20 |  | 2025-04-29 00:00:00.000 | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | This is DDoS protection. Pending delivery of the fiber(20/06-2025), that this DDoS protection needs to protect. |  | 1495 | HKScan Denmark A/S | 102177 | NDD-059704 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-04-29 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Confirmed delivery date: 20/06 |  | 1450 | HKScan Denmark A/S | 102177 | NKA-059698 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-11 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-21 | 2025-04-08 13:32:00.000 | 2025-05-13 10:06:00.000 | 2025-06-13 |  |  | 2025-05-21 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  | 527.39 | Hoffmann A/S | 103075 | NOC-995822 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-06-20 | 2025-06-20 | Change |  | 2016-09-14 14:21:00.000 | 2016-09-14 14:21:00.000 | 2025-06-16 |  |  |  | 2025-06-20 | 2025-06-20 |  | 2025-05-16 00:00:00.000 | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | FIXED DATE: 16/06 |  | 486.39 | Hoffmann A/S | 103075 | NOC-995895 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-06-20 | 2025-06-20 | Change |  |  |  | 2025-06-16 |  |  |  | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | No link when doing SW week 18 - FIBIA |  |  | Horsens kommune | 100321 | NKA-057346 |  | Morten Skytte | Public DK | In Process | 2024-11-06 |  |  | Change |  | 2025-05-16 15:17:00.000 | 2025-05-16 15:17:00.000 | [8 empty] | Change | BO
[6 empty] | 1750 | Horsens kommune | 103677 | NKA-060757 |  | Michael Kronbach Leth | Public DK | In Process | 2025-05-15 |  |  | Own OnNet | 2025-05-21 | [10 empty] | New Sales | BO
[6 empty] | 1750 | Horsens kommune | 103677 | NKA-060758 |  | Michael Kronbach Leth | Public DK | In Process | 2025-05-15 |  |  | Own OnNet | 2025-05-21 | [10 empty] | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060203 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-05-06 | 2025-05-09 12:39:00.000 |  | 2025-07-04 |  | 2025-07-18 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060204 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-24 |  |  | 2025-07-25 |  | 2025-07-18 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060205 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 08:00:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060206 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-24 | 2025-04-29 08:38:00.000 | 2025-05-07 12:47:00.000 | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060207 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 09:30:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1230 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060208 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-24 | 2025-04-29 08:59:00.000 | 2025-05-07 12:29:00.000 | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 5723 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060209 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-24 |  |  | 2025-06-13 |  | 2025-07-18 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 5723 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060210 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-24 |  |  | 2025-06-13 |  |  |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1360 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060213 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 09:57:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1500 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060214 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-04-24 | 2025-04-25 08:41:00.000 |  | 2025-07-11 |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Delivery in progress. Customer first wanted delivery no earlier than mid-July due to their current ISP contract. |  | 1660 | HUSCOMPAGNIET HOLDING A/S | 103188 | NKA-060215 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-01 | 2025-07-25 | 2025-07-25 | Own OnNet | 2025-04-24 | 2025-05-05 07:45:00.000 | 2025-05-14 14:50:00.000 | 2025-07-18 |  | 2025-07-18 |  | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1250 | HUSCOMPAGNIET HOLDING A/S | 105286 | NKA-060559 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-01 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-19 |  |  | 2025-07-04 |  | 2025-06-30 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048925 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048931 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2024-07-02 |  | 2024-08-13 09:05:00.000 |  |  | 2024-09-13 | [5 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048933 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048935 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048937 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048939 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | [11 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-048947 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2023-11-06 | [10 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-053054 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change |  | 2024-05-28 14:34:00.000 | 2024-05-08 14:29:00.000 | [8 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-053055 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change |  | 2024-06-19 13:46:00.000 | 2024-06-19 13:46:00.000 | [8 empty] | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  |  | I/S VESTFORBRÆNDING | 103060 | NKA-056750 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-14 |  |  | Change | 2024-10-11 |  |  |  |  | 2024-12-20 | [5 empty] | Change | BO
[6 empty] | 352.5 | I/S VESTFORBRÆNDING | 103561 | NKA-060799 |  | Michael Kronbach Leth | Public DK | In Process | 2025-05-19 |  |  | 3rd Party | 2025-05-26 | [10 empty] | New Sales | BO
[6 empty] | 352.5 | I/S VESTFORBRÆNDING | 103561 | NML-060800 |  | Michael Kronbach Leth | Public DK | In Process | 2025-05-19 |  |  | 3rd Party | 2025-05-26 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | RFS 31-10-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104556 | NKA-060023 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-10-31 | 2025-10-31 | 3rd Party | 2025-04-04 |  |  |  |  | 2025-06-13 |  | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | RFS 31-10-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104556 | NKA-060025 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | RFS 31-10-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104556 | NML-060024 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-10-31 | 2025-10-31 | 3rd Party | [5 empty] | 2025-06-13 |  | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | RFS 31-10-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104556 | NML-060026 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-28 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Afventer datoer fra FPM |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060375 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | RFS 30-06-25 |  | 475 | I/S VESTFORBRÆNDING | 104579 | NKA-060377 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-06-30 | 2025-06-30 | Own OnNet | 2025-04-15 | 2025-05-09 12:39:00.000 | 2025-05-14 08:46:00.000 | 2025-05-30 |  | 2025-06-27 | 2025-05-20 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060378 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060380 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-04-15 | 2025-05-19 14:29:00.000 |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060382 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NKA-060384 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060376 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060379 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party |  |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060381 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060383 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 104579 | NML-060385 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-15 |  |  | 2025-07-04 |  | 2025-06-27 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Afventer datoer fra FPM |  | 475 | I/S VESTFORBRÆNDING | 88172 | NKA-048922 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-03-12 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[6 empty] | 252.5 | I/S VESTFORBRÆNDING | 88172 | NKA-048925 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-06-30 | 2025-06-30 | 3rd Party | 2023-11-06 |  |  | 2025-06-20 |  |  | 2024-06-27 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 237.5 | I/S VESTFORBRÆNDING | 88172 | NKA-048937 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-06-30 | 2025-06-30 | 3rd Party | 2023-11-06 |  |  | 2025-06-20 |  |  | 2024-06-27 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 88172 | NKA-048939 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-07-31 | 2025-07-31 | 3rd Party |  |  |  | 2025-05-22 |  |  |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
[6 empty] | 252.5 | I/S VESTFORBRÆNDING | 88172 | NML-048926 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-06-30 | 2025-06-30 | 3rd Party | 2023-11-06 |  |  | 2025-06-20 |  |  | 2024-06-27 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 15 | I/S VESTFORBRÆNDING | 88172 | NML-048938 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-06-30 | 2025-06-30 | 3rd Party | 2023-11-06 |  |  | 2025-06-20 |  |  | 2024-06-27 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 31-07-25 |  | 252.5 | I/S VESTFORBRÆNDING | 88172 | NML-048940 |  | Michael Kronbach Leth | Public DK | In Process | 2023-06-30 | 2025-07-31 | 2025-07-31 | 3rd Party | 2023-11-06 |  |  | 2025-05-22 |  |  |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
[6 empty] | 252.5 | I/S VESTFORBRÆNDING | 97012 | NKA-055617 |  | Michael Kronbach Leth | Public DK | In Process | 2024-07-16 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-07-23 |  |  | 2025-06-20 |  |  | 2024-09-11 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 252.5 | I/S VESTFORBRÆNDING | 97012 | NML-055618 |  | Michael Kronbach Leth | Public DK | In Process | 2024-07-16 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-07-23 |  |  | 2025-06-20 |  |  | 2024-09-11 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Awaiting Lokalbane for date |  | 93.75 | INFRASTRUKTURSELSKABET LJ A/S | 107101-006 | F36205-1130134-01 | 107101-006-001 | Mette Vinther | Public DK | In Process | 2024-07-23 | 2025-08-29 | 2025-08-29 | Own OnNet |  |  |  | 2025-08-22 |  | 2024-09-10 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | New Sales | AX
[6 empty] | 847.5 | Innargi Project I P/S | 95009 | NKA-058403 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2025-01-15 | 2025-06-02 | 2025-06-02 | 3rd Party | 2025-01-17 |  |  | 2025-05-27 |  |  | 2025-02-25 | 2025-06-02 | 2025-06-02 |  |  | New Sales | BO
[6 empty] | 847.5 | Innargi Project I P/S | 95009 | NML-058404 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2025-01-15 | 2025-06-02 | 2025-06-02 | 3rd Party | 2025-01-17 |  |  | 2025-05-27 |  |  | 2025-02-25 | 2025-06-02 | 2025-06-02 |  |  | New Sales | BO
[6 empty] | 350 | It-Forsyningen I/S | 105498 | NKA-046566 |  | Morten Skytte | Public DK | In Process | 2025-05-09 |  |  | Change | 2023-02-10 | 2023-04-25 15:45:00.000 | 2023-04-25 15:45:00.000 | [8 empty] | Change | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NKA-055072 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NKA-055074 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NKA-055076 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NML-055071 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-07-03 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NML-055073 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-07-03 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 75 | It-Forsyningen I/S | 91816 | NML-055075 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-26 | 2025-06-30 | 2025-06-30 | 3rd Party | 2024-07-03 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.1 Waiting on customer confirmation or input | Delivered - needs a ServiceWindow |  | 1038 | Jem & Fix A/S | 100796 | NKA-057361 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-11-13 | 2025-05-28 | 2025-05-28 | 3rd Party | 2024-11-14 |  |  |  |  | 2025-01-31 | 2025-02-02 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.2.1 Pending internal 3rd party: GC Norway | Delay GC Norway |  | 1038 | Jem & Fix A/S | 101288 | NKA-058314 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-01-10 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-01-13 |  |  |  |  | 2025-02-04 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 850 | Jem & Fix A/S | 103386 | NKA-059840 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 | 2025-08-01 | 2025-08-01 | Own with Digging | 2025-03-26 | 2025-03-27 10:43:00.000 | 2025-05-13 08:47:00.000 | 2025-06-13 |  | 2025-08-01 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready | Ordered |  | 850 | Jem & Fix A/S | 103386 | NKA-059841 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-19 | 2025-09-19 | 2025-09-19 | Own with Digging | 2025-05-19 |  |  |  |  | 2025-09-19 |  | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 850 | Jem & Fix A/S | 104367 | NKA-059866 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-20 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-09 | 2025-05-19 12:42:00.000 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Waiting for customer to provide delivery date and contact information |  | 850 | Jem & Fix A/S | 105311 | NKA-060462 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-24 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Waiting for customer to provide delivery date and contact information |  | 850 | Jem & Fix A/S | 105311 | NKA-060463 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-24 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 850 | Jem & Fix A/S | 88683 | NKA-048998 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-04-22 | 2025-04-24 12:14:00.000 | 2025-05-02 08:05:00.000 | 2025-06-06 |  | 2025-07-11 | 2025-05-23 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1.1 Pending external 3rd party: Open-Net | Can't order in OpenNet |  | 850 | Jem & Fix A/S | 88683 | NKA-049011 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-07-18 | 2025-07-18 | Own OnNet | [7 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 850 | Jem & Fix A/S | 88683 | NKA-049014 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-05-06 | 2025-05-08 11:36:00.000 | 2025-05-16 10:31:00.000 | 2025-06-13 |  | 2025-07-18 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1.1 Pending external 3rd party: Open-Net | Can't order in OpenNet |  | 850 | Jem & Fix A/S | 88683 | NKA-049085 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-07-18 | 2025-07-18 | Own OnNet | [7 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 850 | Jem & Fix A/S | 88683 | NKA-049106 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-12-20 | 2025-01-17 09:30:00.000 | 2025-03-18 12:38:00.000 | 2025-06-06 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 5. Configuration | Other (incl. termination, on hold, unassigned statuses etc.) | On track |  | 850 | Jem & Fix A/S | 88683 | NKA-049113 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-06-30 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-01-21 | 2025-02-25 06:48:00.000 | 2025-03-18 10:12:00.000 | 2025-06-06 |  | 2025-06-13 | 2025-05-19 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 0 | Jem & Fix A/S | 97729 | NKA-049113 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-07-19 | 2025-06-13 | 2025-06-13 | Change | 2025-01-21 | 2025-02-25 06:48:00.000 | 2025-03-18 10:12:00.000 |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1650 | Johs. Rasmussen, Svebølle A/S | 102816 | NKA-060581 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-05 |  |  | 2025-07-04 |  | 2025-07-04 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 200 | Johs. Rasmussen, Svebølle A/S | 102816 | NML-060580 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-06-06 | 2025-06-06 | 3rd Party |  |  |  | 2025-06-04 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | -285.8 | Johs. Rasmussen, Svebølle A/S | 102816 | NOC-997751 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-02 | 2025-06-06 | 2025-06-06 | Change | 2016-10-06 |  |  | 2025-06-04 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party |  |  | 5934 | Jysk A/S | 107550-009 | C36587-1135568-01 | 107550-009-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-26 | 2025-05-30 |  | Own OnNet | [5 empty] | 2025-06-13 |  |  | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 5. Configuration | 2.1 Order forgotten, but back on track to be processed | Old BTO order taken over from other segment. Needs technical clarification and clarification with sales. Involved team changed multiple times in both sales and delivery. |  | 1308 | Jysk CTS A/S | 89637 | NKA-049663 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-08-22 | 2025-06-13 | 2025-06-13 | Own OnNet | 2023-09-08 | [5 empty] | 2025-01-28 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 599.94 | Jyske Bank A/S | 101491-013 | B31457-1136860-01 | 101491-013-001 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Change | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | Change | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 0 | Jyske Bank A/S | 101491-013 | B31457-1136861-01 | 101491-013-002 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Change | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | Change | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 0 | Jyske Bank A/S | 101491-013 | B31457-1136862-01 | 101491-013-003 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Change | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | Change | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 0 | Jyske Bank A/S | 101491-013 | B31457-1136863-01 | 101491-013-004 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Change | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | Change | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | -160.0133 | Jyske Bank A/S | 101491-013 | C31457-1136865-01 | 101491-013-006 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Change | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | Change | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 60 | Jyske Bank A/S | 101491-013 | C31457-1136866-01 | 101491-013-007 | Shazia Mobin | Enterprise DK | Created | 2025-05-14 | 2025-06-12 |  | Own OnNet | [5 empty] | 2025-09-16 |  |  | 2025-06-12 | 2025-06-12 |  | New Sales | AX
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 550 | Kalundborg kommune | 93742 | NKA-023151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-17 |  |  | Change | 2018-02-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001355 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001357 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-21 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001358 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-10 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001361 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001362 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-09-04 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001364 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001365 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001368 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-10-14 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001369 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001370 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-20 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001371 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001372 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-08-31 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001374 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001375 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001376 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001377 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-001378 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2012-06-06 |  |  |  |  | 2012-08-07 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-004657 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change |  |  |  | 2025-03-03 | [7 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-004681 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-09-25 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-005732 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-10-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-005733 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2013-10-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-007073 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-03-06 |  |  |  |  | 2014-04-22 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-008423 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-06-16 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-008678 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2014-07-14 |  |  |  |  | 2014-09-08 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-015322 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-07-08 |  |  |  |  | 2016-09-02 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-015571 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:21:00.000 | 2016-08-04 16:21:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-015572 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:22:00.000 | 2016-08-04 16:22:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-015573 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-08-04 | 2016-08-04 16:22:00.000 | 2016-08-04 16:22:00.000 |  |  | 2016-09-30 | [5 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-016769 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2016-12-06 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-019741 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-02-23 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-020063 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 | 2025-06-30 | 2025-06-30 | Change | 2017-04-03 |  |  | 2025-03-31 |  |  |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-021079 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-07-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-021361 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-08-25 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-021785 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-09-26 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-022148 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-10-30 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-022164 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-10-30 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-022346 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2017-11-14 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 25 | Kalundborg kommune | 94451 | NKA-022777 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-05 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-022923 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-19 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-022946 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-01-19 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-023066 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-01 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-023116 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-07 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-023151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-15 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-023194 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-02-16 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-024172 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2018-04-06 |  |  |  |  | 2018-06-08 | 2024-10-24 |  |  |  |  | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-027189 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-03-06 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-028218 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-07-16 | 2019-10-01 08:52:00.000 | 2019-10-01 08:52:00.000 | [8 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-028441 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2019-08-09 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-034959 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 | 2025-07-31 | 2025-07-31 | Change | 2021-06-08 | [6 empty] | 2025-07-31 | 2025-07-31 |  |  | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-034973 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2021-06-17 | [10 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 650 | Kalundborg kommune | 94451 | NKA-044605 |  | Michael Kronbach Leth | Public DK | In Process | 2024-03-05 |  |  | Change | 2022-10-18 |  |  | 2025-03-03 | [7 empty] | Change | BO
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | SW planlægning med kunde |  | 950 | Kalundborg kommune | 96656 | NKA-004657 |  | Michael Kronbach Leth | Public DK | In Process | 2024-05-29 |  |  | Change | [11 empty] | Change | BO
|  | Delivered | Delivered | Klarmeldt d. 21/5-25 |  | 1760 | KK WIND SOLUTIONS A/S | 103535 | NKA-060226 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-02 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-07 | 2025-04-08 09:15:00.000 | 2025-05-02 09:09:00.000 | 2025-05-21 |  | 2025-06-06 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[6 empty] | 560 | Kolding Kommune Rådhuset | 82944 | NKA-003429 |  | Michael Kronbach Leth | Public DK | In Process | 2022-09-27 |  |  | Change
|  | 7. Service activation | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation from GC NO |  | -641.03 | KPMG ACOR TAX PARTNERSELSKAB | 90629 | NKA-029266 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-11-06 | 2025-06-13 | 2025-06-13 | Change | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2024-03-13 00:00:00.000 | Change | BO
|  | 7. Service activation | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation from GC NO |  | 3366 | KPMG ACOR TAX PARTNERSELSKAB | 90629 | NKA-050904 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2023-11-06 | 2025-06-13 | 2025-06-13 | 3rd Party | 2023-11-16 | [6 empty] | 2025-06-13 | 2025-06-13 |  | 2024-03-13 00:00:00.000 | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  |  | Kromann Reumert | 94179 | NKA-056733 |  | Peter Madsen | Enterprise DK | In Process | 2024-11-27 | 2025-07-04 | 2025-07-04 | Change | 2025-01-06 | 2025-02-20 09:54:00.000 | 2025-02-20 09:54:00.000 |  |  | 2025-06-30 |  | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  |  | Kromann Reumert | 94179 | NKA-056734 |  | Peter Madsen | Enterprise DK | In Process | 2024-11-27 | 2025-07-04 | 2025-07-04 | Change | 2025-01-06 | 2025-03-27 12:59:00.000 | 2025-03-27 12:59:00.000 |  |  | 2025-06-30 |  | 2025-07-04 | 2025-07-04 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 522 | Kromann Reumert | 98424 | NDD-056737 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 522 | Kromann Reumert | 98424 | NDD-056738 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 2720 | Kromann Reumert | 98424 | NKA-056733 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-01-06 | 2025-02-20 09:54:00.000 | 2025-02-20 09:54:00.000 | 2025-06-27 |  | 2025-06-30 | 2025-04-01 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 2720 | Kromann Reumert | 98424 | NKA-056734 |  | Peter Madsen | Enterprise DK | In Process | 2024-10-09 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-01-06 | 2025-03-27 12:59:00.000 | 2025-03-27 12:59:00.000 | 2025-06-27 |  | 2025-06-30 | 2025-04-01 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 11732.5 | Københavns Kommune | 101858 | NDD-058420 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet |  |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 11732.5 | Københavns Kommune | 101858 | NDD-058422 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet |  |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 11732.5 | Københavns Kommune | 101858 | NKA-058419 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 11732.5 | Københavns Kommune | 101858 | NKA-058421 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 12015 | Københavns Kommune | 101858 | NKA-058423 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 12015 | Københavns Kommune | 101858 | NKA-058424 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 4140 | Københavns Kommune | 101858 | NKA-058425 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-03-27 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | On track - part of a Datacenter Solution |  | 4140 | Københavns Kommune | 101858 | NKA-058426 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-01-16 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-24 |  |  | 2025-04-03 |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | RFS 30-06-25 |  | 1070 | Københavns Kommune | 101913 | NKA-058550 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 | 2025-06-30 | 2025-06-30 | Own OnNet | 2025-03-05 | 2025-04-11 08:11:00.000 | 2025-04-28 08:07:00.000 | 2025-05-09 |  | 2025-05-09 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 490 | Københavns Kommune | 103611 | NKA-060829 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-20 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-05-21 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 490 | Københavns Kommune | 105122 | NKA-060367 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-07-02 | 2025-07-02 | 3rd Party | 2025-04-15 |  |  | 2025-06-27 |  |  | 2025-05-07 | 2025-07-02 | 2025-07-02 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Awaits FiberPM |  | 490 | Københavns Kommune | 105194 | NKA-060435 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-22 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-04-22 | 2025-05-23 13:32:00.000 |  | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 490 | Københavns Kommune | 105868 | NKA-060835 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-21 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-05-21 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[6 empty] | 910 | Københavns Kommune | 105899 | NKA-023307 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-26 |  |  | Change | 2018-03-12 | [10 empty] | Change | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | RFS 31-07-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055121 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-01-22 |  |  |  |  | 2025-04-04 | 2025-03-24 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | RFS 31-08-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055125 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-12-03 |  |  |  |  | 2025-02-14 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055126 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2024-12-03 | 2025-04-23 09:33:00.000 | 2025-04-28 13:20:00.000 | 2025-05-16 |  | 2025-02-14 | 2025-05-09 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. |  | 1270 | Københavns Kommune | 97026 | NKA-055128 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2024-12-03 |  |  |  |  | 2025-02-14 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055134 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2024-12-12 | 2025-05-01 08:40:00.000 | 2025-05-05 09:54:00.000 | 2025-05-23 |  | 2025-02-28 | 2025-05-12 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055135 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-04-23 17:32:00.000 | 2025-04-25 13:05:00.000 | 2025-05-16 |  | 2025-04-26 | 2025-05-08 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055137 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-23 09:49:00.000 | 2025-04-25 14:07:00.000 | 2025-05-16 |  | 2025-04-25 | 2025-05-08 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | RFS 31-06-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055138 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-02-14 | 2025-04-23 09:51:00.000 | 2025-04-25 14:22:00.000 | 2025-06-06 |  | 2025-04-25 | 2025-05-08 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055143 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-05-01 07:45:00.000 | 2025-05-05 12:11:00.000 | 2025-05-23 |  | 2025-04-25 | 2025-05-09 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.4 Other installation obstacles and infratructure issues | Afvist i FOKKA - Afventer ny Pre-Ordre |  | 1270 | Københavns Kommune | 97026 | NKA-055144 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Stillads rundt om skolen Deadline: 31-08-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055149 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055150 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055151 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055156 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-10 08:31:00.000 | 2025-04-22 15:08:00.000 | 2025-05-09 |  | 2025-04-25 | 2025-05-08 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055159 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055165 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055170 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-05-01 08:48:00.000 | 2025-05-05 13:10:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055172 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055173 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-03-18 11:37:00.000 | 2025-03-28 13:48:00.000 |  |  | 2025-04-25 | 2025-04-02 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055176 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-02 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Grave tilladelse, m.m. |  | 1270 | Københavns Kommune | 97026 | NKA-055177 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-05-01 08:57:00.000 | 2025-05-06 08:24:00.000 | 2025-05-23 |  | 2025-04-25 | 2025-05-12 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Gravetermin d. 23-05-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055179 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055181 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | Own with Digging | 2025-02-14 | 2025-05-08 12:36:00.000 | 2025-05-13 09:28:00.000 | 2025-05-30 |  | 2025-04-25 | 2025-05-21 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055182 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | Own with Digging | 2025-02-14 | 2025-05-08 12:52:00.000 | 2025-05-13 10:18:00.000 | 2025-05-30 |  | 2025-04-25 | 2025-05-21 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Mgl. Klarmelding fra TDC |  | 1270 | Københavns Kommune | 97026 | NKA-055184 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Mgl. Klarmelding fra TDC |  | 1270 | Københavns Kommune | 97026 | NKA-055185 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-01 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | TDC RFS d. 24-07-25 |  | 1270 | Københavns Kommune | 97026 | NKA-055191 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-07 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1270 | Københavns Kommune | 97026 | NKA-055193 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-25 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.4 Other installation obstacles and infratructure issues | Mgl. Besigtigelse. |  | 1270 | Københavns Kommune | 97026 | NKA-055194 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[6 empty] | 1270 | Københavns Kommune | 97026 | NKA-055195 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-16 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055196 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-05-01 08:02:00.000 | 2025-05-06 11:16:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 4. Final design | 3.4 Other installation obstacles and infratructure issues | Graveterming d. 16-05-2025. |  | 1270 | Københavns Kommune | 97026 | NKA-055198 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-05-19 12:41:00.000 | 2025-05-26 13:32:00.000 | 2025-06-13 |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055199 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-02-14 | 2025-04-23 16:13:00.000 | 2025-04-28 10:40:00.000 |  |  | 2025-04-25 | 2025-05-08 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055204 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-04-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055206 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-30 12:39:00.000 | 2025-05-13 10:55:00.000 | 2025-05-30 |  | 2025-04-25 | 2025-05-21 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055207 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2024-12-12 |  |  |  |  | 2025-02-28 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055208 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-15 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055212 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-02-05 |  |  |  |  | 2025-04-18 | 2025-05-02 | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055216 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055217 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-04-23 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055218 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-10 08:20:00.000 | 2025-04-15 14:04:00.000 |  |  | 2025-04-25 | 2025-05-09 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055219 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-25 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055220 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 |  |  | Own with Digging | 2025-02-14 | 2025-04-10 08:28:00.000 | 2025-04-22 13:53:00.000 |  |  | 2025-04-25 | 2025-05-08 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055221 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055224 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-30 09:31:00.000 | 2025-05-07 10:05:00.000 |  |  | 2025-04-25 | 2025-05-12 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055225 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-23 09:43:00.000 | 2025-04-28 12:28:00.000 |  |  | 2025-04-25 | 2025-05-08 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055226 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-01-23 |  |  |  |  | 2025-04-04 | 2025-03-19 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055229 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055232 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055233 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 |  |  |  |  | 2025-04-25 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055234 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2025-04-23 16:22:00.000 | 2025-04-24 09:50:00.000 |  |  | 2025-04-25 | 2025-05-14 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.1 Pending external 3rd party: Any 3rd party | Afventer datoer, svar på gravetilladelser og installation |  | 1270 | Københavns Kommune | 97026 | NKA-055240 |  | Michael Kronbach Leth | Public DK | In Process | 2024-06-27 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-02-14 | 2024-08-21 12:07:00.000 | 2025-02-23 21:16:00.000 | 2025-05-30 |  | 2025-04-25 | 2025-05-21 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | Cancelled/terminated/On hold | 2.4 Pending equipment/product to be ready for installations | technology need to answer what equipment to use |  | -528 | LEGO System A/S | 101442-031 | C31408-1131198-01 | 101442-031-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-09-19 | 2025-06-06 |  | Change | [5 empty] | 2024-11-25 |  |  | 2025-06-06 | 2025-06-06 |  | Change | AX
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 1750 | Lidl Danmark K/S | 102865 | NGF-059283 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-05 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-04-24 | [5 empty] | 2025-03-05 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 1815 | Lidl Danmark K/S | 102937 | NDD-059641 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059307 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-04-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059308 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059309 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059310 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059311 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059312 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059313 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059314 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059315 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059316 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059317 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059318 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059319 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059320 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059321 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059322 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059323 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059324 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059325 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059326 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059327 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-05-15 |  |  | 2025-08-01 |  | 2025-07-24 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059328 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-05-15 |  |  | 2025-08-01 |  | 2025-07-24 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059329 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059330 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059331 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059332 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059335 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059336 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059339 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059340 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059343 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059344 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059345 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 | [6 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059346 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 | [6 empty] | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059347 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-05-15 |  |  | 2025-06-27 |  | 2025-06-16 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059348 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059349 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-28 13:25:00.000 | 2025-05-01 11:13:00.000 | 2025-05-23 |  | 2025-05-16 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059350 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-28 13:25:00.000 | 2025-05-01 11:13:00.000 | 2025-05-23 |  | 2025-05-16 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059351 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059352 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059353 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-03-24 | 2025-05-12 10:09:00.000 | 2025-05-19 15:24:00.000 | 2025-06-20 |  | 2025-05-30 |  | 2025-06-27 | 2025-06-27 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059354 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-03-24 | 2025-05-12 10:09:00.000 | 2025-05-19 15:25:00.000 | 2025-06-20 |  | 2025-05-30 |  | 2025-06-27 | 2025-06-27 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059355 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059356 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059357 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059358 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059360 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-21 | 2025-05-05 09:57:00.000 | 2025-05-06 09:48:00.000 | 2025-05-20 |  | 2025-05-16 | 2025-05-23 | 2025-05-28 | 2025-05-28 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059361 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059362 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059363 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-03-27 08:54:00.000 | 2025-04-15 13:20:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059364 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-03-27 08:56:00.000 | 2025-04-15 13:37:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059365 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059366 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059367 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059368 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059369 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059370 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059373 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059374 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059375 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059376 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059377 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 |  |  |  |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059378 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 |  |  |  |  | 2025-05-16 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059379 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059380 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059381 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059382 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059383 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059384 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059385 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-24 | 2025-05-28 | 2025-05-28 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059386 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-24 | 2025-05-28 | 2025-05-28 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059387 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059388 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059389 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059390 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059391 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059392 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059393 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059394 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059395 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-07 14:17:00.000 | 2025-04-09 10:12:00.000 | 2025-05-05 |  | 2025-05-16 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059396 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-04-15 | 2025-04-07 14:17:00.000 | 2025-04-09 10:05:00.000 | 2025-05-05 |  |  | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-01 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059397 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059398 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059399 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059400 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059401 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059402 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059403 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059404 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059405 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059406 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059407 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059408 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059409 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059410 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059411 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059412 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059413 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059414 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059415 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059416 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059417 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059418 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059419 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059420 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059421 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059422 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059423 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059424 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059425 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-05 14:20:00.000 | 2025-05-21 |  | 2025-05-23 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059426 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-06 07:46:00.000 | 2025-05-21 |  | 2025-05-16 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059427 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059428 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059429 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059430 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059431 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059432 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059433 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-23 | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059434 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-23 | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059435 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059436 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059437 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059438 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059439 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059440 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059441 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059442 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059443 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059444 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059445 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [10 empty] | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059446 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [10 empty] | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059447 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059448 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059449 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-04-10 | 2025-04-11 11:33:00.000 | 2025-05-15 10:52:00.000 | 2025-08-08 |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059450 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-04-10 | 2025-04-11 11:32:00.000 | 2025-05-15 12:29:00.000 | 2025-08-04 |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059451 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059452 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059453 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-30 | 2025-05-12 12:38:00.000 | 2025-05-14 08:50:00.000 | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059454 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-04-30 | 2025-05-12 12:37:00.000 | 2025-05-14 08:51:00.000 | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059455 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059456 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059457 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059458 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059459 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059460 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059461 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059462 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059463 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059464 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059465 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059466 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059467 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059468 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059471 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-30 | 2025-05-30 | 3rd Party | [6 empty] | 2025-05-25 | 2025-05-30 | 2025-05-30 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059472 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-30 | 2025-05-30 | 3rd Party | [6 empty] | 2025-05-25 | 2025-05-30 | 2025-05-30 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059473 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-14 18:41:00.000 | 2025-05-01 07:28:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059474 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-04-14 18:42:00.000 | 2025-05-01 07:29:00.000 | 2025-05-23 |  | 2025-05-30 | 2025-05-25 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059475 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059476 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059477 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  | 2025-04-09 08:38:00.000 |  |  |  |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059478 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  | 2025-04-09 08:37:00.000 |  |  |  |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059479 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059480 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059481 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059482 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059483 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059484 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059485 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059486 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059487 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-03-24 | 2025-05-12 09:07:00.000 | 2025-05-20 14:24:00.000 | 2025-06-20 |  | 2025-06-13 |  | 2025-06-27 | 2025-06-27 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059488 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-03-24 | 2025-05-12 09:06:00.000 | 2025-05-20 14:25:00.000 | 2025-06-20 |  | 2025-06-13 |  | 2025-06-27 | 2025-06-27 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059489 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059490 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-06 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059491 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059492 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059493 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059494 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059495 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-04-29 14:46:00.000 | 2025-05-16 13:04:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059496 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-04-29 14:46:00.000 | 2025-05-16 13:05:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059497 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059498 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059499 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059500 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059501 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-23 | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059502 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [6 empty] | 2025-05-23 | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059503 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059504 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059505 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059506 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059507 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059508 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059509 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059510 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059511 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059512 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059513 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059514 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-13 | 2025-06-13 | 3rd Party | [7 empty] | 2025-06-13 | 2025-06-13 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059515 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059516 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059517 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059518 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059523 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059524 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059525 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-05-19 | [6 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059526 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-19 | [6 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059527 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059528 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-15 | 2025-08-15 | 3rd Party | [7 empty] | 2025-08-15 | 2025-08-15 |  | 2025-05-12 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059529 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059530 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059531 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059532 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059533 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059534 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059537 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059538 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059539 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059540 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | 3rd Party | [7 empty] | 2025-05-28 | 2025-05-28 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059541 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-03-21 | 2025-05-12 12:10:00.000 |  | 2025-06-27 |  | 2025-05-30 |  | 2025-07-04 | 2025-07-04 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059542 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-03-21 | 2025-05-12 12:11:00.000 |  | 2025-06-27 |  | 2025-05-30 |  | 2025-07-04 | 2025-07-04 |  | 2025-05-16 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059543 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059544 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059545 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059546 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059547 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059548 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059549 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059550 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059551 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059552 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059553 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-23 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059554 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-23 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059555 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059556 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-18 | 2025-07-18 | 3rd Party | [7 empty] | 2025-07-18 | 2025-07-18 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059557 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059558 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059559 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059560 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059561 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059562 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059563 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059564 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059565 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059566 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059567 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059568 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | 3rd Party | [7 empty] | 2025-06-06 | 2025-06-06 |  | 2025-05-05 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059571 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059572 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059573 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-28 | 2025-04-30 10:19:00.000 | 2025-05-21 14:10:00.000 | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059574 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-04-28 | 2025-04-30 10:20:00.000 | 2025-05-21 14:10:00.000 | 2025-06-13 |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059575 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059576 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059577 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059578 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059579 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059580 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-14 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059581 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059582 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059583 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own with Digging | 2025-03-24 | 2025-05-14 08:49:00.000 |  | 2025-06-27 |  | 2025-05-23 |  | 2025-07-04 | 2025-07-04 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059584 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-03-24 | 2025-05-14 08:49:00.000 |  | 2025-06-27 |  | 2025-05-23 |  | 2025-07-04 | 2025-07-04 |  | 2025-05-20 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059585 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059586 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059589 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059590 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059591 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-04-30 10:51:00.000 | 2025-05-19 13:35:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059592 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-04-30 10:51:00.000 | 2025-05-19 13:36:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059593 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059594 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059595 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059596 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059597 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party |  |  | 2025-04-30 10:26:00.000 |  |  |  |  | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059598 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059599 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059600 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059601 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059602 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059603 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-24 | 2025-05-01 09:47:00.000 | 2025-05-06 10:15:00.000 | 2025-05-26 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059604 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-24 | 2025-05-01 09:48:00.000 | 2025-05-06 10:16:00.000 | 2025-05-26 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-13 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059605 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059606 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-04 | 2025-07-04 | 3rd Party | [7 empty] | 2025-07-04 | 2025-07-04 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059607 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-24 | 2025-04-28 12:49:00.000 | 2025-05-01 13:48:00.000 | 2025-05-21 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059608 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-24 | 2025-04-28 12:48:00.000 | 2025-05-01 13:49:00.000 | 2025-05-21 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059609 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059610 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-01 | 2025-08-01 | 3rd Party | [7 empty] | 2025-08-01 | 2025-08-01 |  | 2025-05-21 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059611 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059612 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-08-08 | 2025-08-08 | 3rd Party | [7 empty] | 2025-08-08 | 2025-08-08 |  | 2025-05-07 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059613 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own with Digging | 2025-03-24 | 2025-05-06 10:35:00.000 | 2025-05-19 10:35:00.000 | 2025-06-13 |  | 2025-05-23 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059614 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-03-24 | 2025-05-06 10:36:00.000 | 2025-05-19 10:36:00.000 | 2025-06-13 |  | 2025-05-23 |  | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059617 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-25 | 2025-07-25 | 3rd Party | [7 empty] | 2025-07-25 | 2025-07-25 |  | 2025-05-23 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059618 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059619 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059620 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  | 2025-05-08 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059621 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059622 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059623 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059624 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059625 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059626 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-01 | 2025-05-28 | 2025-05-28 |  | 2025-05-04 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059627 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059628 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-19 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059629 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059630 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-07-11 | 2025-07-11 | 3rd Party | [7 empty] | 2025-07-11 | 2025-07-11 |  | 2025-05-15 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 102937 | NKA-059631 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 102937 | NKA-059632 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 |  |  | Own with Digging | [11 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 1800 | Lidl Danmark K/S | 102937 | NKA-059635 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-11 | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | 2025-05-02 |  |  |  | 2025-06-06 | 2025-06-06 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 1800 | Lidl Danmark K/S | 102937 | NKA-059636 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-03-06 | 2025-06-06 | 2025-06-06 | Own OnNet |  | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | 2025-05-02 |  |  |  | 2025-06-06 | 2025-06-06 |  | 2025-05-02 00:00:00.000 | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 850 | Lidl Danmark K/S | 105410 | NKA-060548 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party |  |  | 2025-05-01 07:40:00.000 | [8 empty] | New Sales | BO
|  | 1.9 PMO delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | PMO |  | 800 | Lidl Danmark K/S | 105410 | NKA-060549 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-30 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 850 | Lidl Danmark K/S | 105699 | NKA-060803 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
[6 empty] | 800 | Lidl Danmark K/S | 105699 | NKA-060804 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059407 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059408 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059409 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059410 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059411 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059412 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059413 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059414 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059415 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059416 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059417 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059418 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059419 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059420 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059421 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059422 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059423 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059424 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059425 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-05 14:20:00.000 |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059426 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-29 13:19:00.000 | 2025-05-06 07:46:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059427 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059428 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059429 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059430 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059431 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059432 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059433 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059434 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059435 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059436 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059437 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059438 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059439 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059440 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059441 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059442 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059443 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059444 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059445 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059446 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059447 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059448 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059449 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-10 | 2025-04-11 11:33:00.000 | 2025-05-15 10:52:00.000 |  |  | 2025-08-15 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059450 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-10 | 2025-04-11 11:32:00.000 | 2025-05-15 12:29:00.000 |  |  | 2025-08-15 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059451 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059452 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059453 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-30 | 2025-05-12 12:38:00.000 | 2025-05-14 08:50:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059454 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-30 | 2025-05-12 12:37:00.000 | 2025-05-14 08:51:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059455 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059456 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059457 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059458 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059459 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059460 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059461 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059462 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059463 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059464 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059465 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059466 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059467 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059468 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059469 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-07 14:41:00.000 | 2025-04-07 14:41:00.000 |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059470 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-07 14:41:00.000 | 2025-04-07 14:42:00.000 |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059471 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059472 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059473 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-14 18:41:00.000 | 2025-05-01 07:28:00.000 |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059474 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-14 18:42:00.000 | 2025-05-01 07:29:00.000 |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059475 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059476 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059477 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-24 |  | 2025-04-09 08:38:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059478 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-24 |  | 2025-04-09 08:37:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059479 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059480 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059481 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059482 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059483 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059484 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059485 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059486 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059487 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-12 09:07:00.000 | 2025-05-20 14:24:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059488 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-12 09:06:00.000 | 2025-05-20 14:25:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059489 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059490 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059491 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059492 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059493 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059494 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059495 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-29 14:46:00.000 | 2025-05-16 13:04:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059496 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-29 14:46:00.000 | 2025-05-16 13:05:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059497 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059498 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059499 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059500 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059501 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059502 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059503 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059504 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059505 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059506 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059507 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059508 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059509 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059510 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059511 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059512 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059513 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059514 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059515 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059516 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059517 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059518 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059519 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-09 09:52:00.000 | 2025-04-24 08:29:00.000 |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059520 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-09 09:53:00.000 | 2025-04-24 08:28:00.000 |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059521 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059522 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059523 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059524 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059525 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-05-19 | [10 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059526 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-05-19 | [10 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059527 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059528 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059529 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059530 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059531 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059532 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059533 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059534 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059535 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059536 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059537 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059538 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059539 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059540 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059541 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-21 | 2025-05-12 12:10:00.000 |  |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059542 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-21 | 2025-05-12 12:11:00.000 |  |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059543 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059544 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059545 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059546 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059547 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059548 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059549 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059550 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059551 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059552 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059553 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059554 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059555 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059556 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059557 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059558 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059559 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059560 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059561 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059562 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059563 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059564 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059565 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059566 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059567 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059568 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059569 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-21 | 2025-04-14 20:39:00.000 | 2025-04-30 12:40:00.000 |  |  | 2025-05-30 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059570 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-14 | 2025-04-14 20:41:00.000 | 2025-04-30 12:41:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059571 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059572 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059573 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-28 | 2025-04-30 10:19:00.000 | 2025-05-21 14:10:00.000 |  |  | 2025-06-20 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059574 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-04-28 | 2025-04-30 10:20:00.000 | 2025-05-21 14:10:00.000 |  |  | 2025-06-20 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059575 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059576 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059577 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059578 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059579 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059580 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059581 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059582 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059583 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-14 08:49:00.000 |  |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059584 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-14 08:49:00.000 |  |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059585 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059586 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059587 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-09 11:44:00.000 | 2025-04-24 13:04:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059588 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-09 11:45:00.000 | 2025-04-24 13:04:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059589 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059590 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059591 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-30 10:51:00.000 | 2025-05-19 13:35:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059592 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-30 10:51:00.000 | 2025-05-19 13:36:00.000 |  |  | 2025-06-13 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059593 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059594 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059595 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059596 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059597 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change |  |  | 2025-04-30 10:26:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059598 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059599 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059600 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059601 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059602 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059603 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-01 09:47:00.000 | 2025-05-06 10:15:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059604 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-01 09:48:00.000 | 2025-05-06 10:16:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059605 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059606 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059607 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-28 12:49:00.000 | 2025-05-01 13:48:00.000 |  |  | 2025-06-06 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059608 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-28 12:48:00.000 | 2025-05-01 13:49:00.000 |  |  | 2025-06-06 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059609 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059610 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059611 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059612 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059613 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-06 10:35:00.000 | 2025-05-19 10:35:00.000 |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059614 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-05-06 10:36:00.000 | 2025-05-19 10:36:00.000 |  |  | 2025-05-23 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059615 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059616 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059617 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059618 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059619 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059620 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059621 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059622 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059623 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059624 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059625 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059626 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-24 | 2025-04-03 13:05:00.000 | 2025-04-25 09:53:00.000 |  |  | 2025-05-16 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059627 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059628 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059629 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059630 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059631 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059632 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | [11 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059633 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-03-13 12:49:00.000 | 2025-03-27 10:50:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059634 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-03-13 12:49:00.000 | 2025-03-27 10:50:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059635 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-11 | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059636 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change |  | 2025-03-13 12:51:00.000 | 2025-03-27 10:51:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059637 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-03-12 08:34:00.000 | 2025-03-28 14:01:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059638 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-03-28 11:13:00.000 | 2025-04-03 12:26:00.000 | [8 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059639 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-04-03 13:53:00.000 | 2025-04-07 12:58:00.000 |  |  | 2025-04-25 | [5 empty] | Change | BO
[7 empty] | Lidl Danmark K/S | 105709 | NKA-059640 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-05-20 |  |  | Change | 2025-03-07 | 2025-04-03 13:54:00.000 | 2025-04-07 13:38:00.000 |  |  | 2025-04-25 | [5 empty] | Change | BO
|  | On Track | On Track | On Track |  | 1355 | Light Brick A/S | 105384 | NKA-044433 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-04-28 |  |  | Change | 2022-08-05 | 2022-08-12 08:24:00.000 | 2022-08-12 08:23:00.000 |  |  |  | 2025-04-29 |  |  |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1250 | Lokaltog A/S | 101174-010 | C31138-1130914-01 | 101174-010-001 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-30 | 2025-05-23 | Own with Digging |  |  |  | 2025-05-23 |  | 2024-11-07 | 2025-02-17 | 2025-05-23 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 0 | Lokaltog A/S | 101174-010 | C31138-1130920-01 | 101174-010-007 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-30 | 2025-05-23 | Own OnNet |  |  |  | 2025-05-23 |  | 2024-11-07 |  | 2025-05-23 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 0 | Lokaltog A/S | 101174-010 | C31138-1130921-01 | 101174-010-008 | Camilla Villumsen Kaimer | Public DK | Created | 2024-09-01 | 2025-05-30 | 2025-05-23 | Own OnNet |  |  |  | 2025-05-23 |  | 2024-11-07 |  | 2025-05-23 | 2025-05-30 | 2025-05-30 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party |  |  | 2835 | MAERSK A/S | 107525-005 | C36565-1135209-01 | 107525-005-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-11 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-06-11 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party |  |  | 4200 | MAERSK A/S | 107525-005 | C36565-1135211-01 | 107525-005-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-11 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-06-11 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[6 empty] | 1672 | Magleby Efterskole S/I | 105540 | NKA-010524 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-22 | 2025-06-02 | 2025-06-02 | Change | [6 empty] | 2025-05-26 | 2025-06-02 | 2025-06-02 |  |  | Change | BO
[6 empty] | 1000 | Meyers A/S | 105620 | NKA-060667 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 2140 | Molslinjen A/S | 104668 | NKA-059995 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-26 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-03-28 | 2025-04-24 09:08:00.000 | 2025-05-07 13:14:00.000 | 2025-06-20 |  | 2025-05-30 | 2025-05-12 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1452 | Munck Havne & Anlæg A/S | 104526 | NKA-060249 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-03 | 2025-07-25 | 2025-07-25 | 3rd Party | 2025-04-10 |  |  | 2025-07-18 |  | 2025-07-11 | 2025-04-23 | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing Service Gateway ordre in BO |  | -982.5 | Næstved Kommune | 79364 | NKA-006801 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-06-30 | 2025-06-30 | Change | 2014-01-22 |  |  |  |  | 2014-03-07 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing Service Gateway ordre in BO |  | -982.5 | Næstved Kommune | 79364 | NKA-007204 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-06-30 | 2025-06-30 | Change | 2014-03-24 | [6 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing Service Gateway ordre in BO |  | 650 | Næstved Kommune | 79364 | NSW-041184 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing Service Gateway ordre in BO |  | 650 | Næstved Kommune | 79364 | NSW-041185 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2022-03-25 | 2025-06-30 | 2025-06-30 | Own OnNet | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 1237 | Nagel Danmark A/S | 98152 | NKA-056844 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-10-18 | 2025-06-13 | 2025-06-13 | Own OnNet | 2024-11-01 | 2025-04-08 13:27:00.000 | 2025-05-09 10:22:00.000 | 2025-06-06 |  | 2025-01-17 | 2025-05-21 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready for installations | On track |  | 1237 | Nagel Danmark A/S | 98152 | NKA-056845 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-10-18 | 2025-06-13 | 2025-06-13 | Own with Digging | 2024-11-01 | 2025-04-08 13:29:00.000 | 2025-05-09 11:51:00.000 | 2025-06-06 |  | 2025-01-17 | 2025-05-21 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136120-01 | 103690-003-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136122-01 | 103690-003-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136124-01 | 103690-003-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own with Digging | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136126-01 | 103690-003-007 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136128-01 | 103690-003-009 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | 3rd Party | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1255 | Naviair | 103690-003 | C33271-1136130-01 | 103690-003-011 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-09 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-08-06 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awaiting TDC |  | 1700 | NCC Danmark A/S | 101119-042 | C31083-1135942-01 | 101119-042-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-03 | 2025-07-18 |  | 3rd Party | [5 empty] | 2025-06-26 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awaiting TDC |  | 0 | NCC Danmark A/S | 101119-042 | C31083-1135943-01 | 101119-042-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-04-03 | 2025-07-18 |  | Own OnNet | [5 empty] | 2025-06-26 |  |  | 2025-07-18 | 2025-07-18 |  | New Sales | AX
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Pending delivery date from GC NO |  | 1400 | Nellemann Holding AS | 101723 | NKA-060265 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-05-30 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Pending delivery date from GC NO |  | 495 | Nellemann Holding AS | 101723 | NMA-060267 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-13 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Pending delivery date from GC NO |  | 495 | Nellemann Holding AS | 101723 | NSW-060266 |  | Peter Madsen | Enterprise DK | In Process | 2025-04-04 | 2025-06-27 | 2025-06-27 | Own OnNet | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133207-01 | 101045-063-001 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133208-01 | 101045-063-002 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own OnNet | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | 5850 | Nets Danmark A/S | 101045-063 | C31009-1133210-01 | 101045-063-004 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | 5850 | Nets Danmark A/S | 101045-063 | C31009-1133211-01 | 101045-063-005 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | 3950 | Nets Danmark A/S | 101045-063 | C31009-1133213-01 | 101045-063-007 | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-05 |  |  | Own with Digging | [5 empty] | 2025-03-12 | [5 empty] | New Sales | AX
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input |  |  | -206.7167 | Nets Danmark A/S | 101045-064 | C31009-1133295-01 | 101045-064-005 | Henrik Møller Fyhn | Enterprise DK | Created | 2024-12-10 | 2025-06-06 |  | Change | [5 empty] | 2025-02-26 | 2025-01-31 |  | 2025-06-06 | 2025-06-06 |  | Change | AX
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Kunden ønsker denne haste leveret |  | 4900 | NIC. CHRISTIANSEN GRUPPEN A/S | 106520-010 | C35716-1135836-01 | 106520-010-001 | Michael Kronbach Leth | Enterprise DK | In Process | 2025-03-31 | 2025-06-03 |  | Own OnNet | [5 empty] | 2025-06-04 |  |  | 2025-06-03 | 2025-06-03 |  | New Sales | AX
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Lav prioritet hos kunden |  | 4900 | NIC. CHRISTIANSEN GRUPPEN A/S | 106520-010 | C35716-1135838-01 | 106520-010-003 | Michael Kronbach Leth | Enterprise DK | In Process | 2025-03-31 | 2025-06-03 |  | Own OnNet | [5 empty] | 2025-06-04 |  |  | 2025-06-03 | 2025-06-03 |  | New Sales | AX
[6 empty] | 3025 | NIRAS A/S | 100351 | NKA-057331 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-11-12 | 2025-06-27 | 2025-06-27 | Own with Digging | 2024-02-13 | 2025-02-20 09:56:00.000 | 2025-02-20 09:56:00.000 | 2025-06-27 |  | 2024-11-14 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[6 empty] | 3025 | NIRAS A/S | 100351 | NKA-057332 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-11-12 | 2025-06-27 | 2025-06-27 | Own with Digging | 2024-11-13 | 2025-03-27 11:46:00.000 | 2025-03-27 11:46:00.000 | 2025-06-27 |  | 2024-02-14 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[6 empty] | 400 | Norddjurs Kommune | 77244 | NKA-022194 |  | Morten Skytte | Public DK | In Process | 2021-12-28 |  |  | Change
[6 empty] | 325 | Norddjurs Kommune | 77244 | NSW-039758 |  | Morten Skytte | Public DK | In Process | 2021-12-28 |  |  | Own OnNet
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | NETTEAM |  | -19882.52 | Nordstern ApS | 104653 | NBM-057421 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-05-05 | 2025-05-28 | 2025-05-28 | Change | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 765 | Normal A/S | 105830 | NKA-060820 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-19 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-05-21 | 2025-05-23 10:56:00.000 |  | 2025-08-04 |  | 2025-08-01 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | Cancelled/terminated/On hold | 3.4 Other installation obstacles and infratructure issues | awaiting permission to use 3P cable tunnel |  | 1050 | Novo Nordisk A/S | 100573 | NDD-057468 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-21 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | Cancelled/terminated/On hold | 3.4 Other installation obstacles and infratructure issues | awaiting permission to use 3P cable tunnel |  | 1050 | Novo Nordisk A/S | 100573 | NKA-057467 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-21 | 2025-12-31 | 2025-12-31 | Own with Digging | 2025-05-09 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 4525 | Novo Nordisk A/S | 102632 | NDD-059037 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-09-12 | 2025-09-12 | Own OnNet |  |  |  | 2025-06-13 |  |  |  | 2025-09-12 | 2025-09-12 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 4525 | Novo Nordisk A/S | 102632 | NDD-059038 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-09-12 | 2025-09-12 | Own OnNet |  |  |  | 2025-06-13 |  |  |  | 2025-09-12 | 2025-09-12 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 4525 | Novo Nordisk A/S | 102632 | NKA-059035 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-09-12 | 2025-09-12 | Own with Digging | 2025-03-03 | 2025-04-07 14:45:00.000 | 2025-05-26 13:07:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-09-12 | 2025-09-12 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 4525 | Novo Nordisk A/S | 102632 | NKA-059036 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-21 | 2025-09-12 | 2025-09-12 | Own with Digging | 2025-03-03 | 2025-05-01 12:37:00.000 | 2025-05-26 13:08:00.000 | 2025-06-13 |  | 2025-09-05 |  | 2025-09-12 | 2025-09-12 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059181 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:35:00.000 | 2025-04-02 10:36:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059182 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:59:00.000 | 2025-04-02 10:59:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059183 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:36:00.000 | 2025-04-02 10:36:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059184 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:00:00.000 | 2025-04-02 11:00:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059185 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:37:00.000 | 2025-04-02 10:37:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059186 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:00:00.000 | 2025-04-02 11:00:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059187 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:38:00.000 | 2025-04-02 10:38:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059188 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:01:00.000 | 2025-04-02 11:01:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059189 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:38:00.000 | 2025-04-02 10:39:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059190 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:02:00.000 | 2025-04-02 11:02:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059191 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:39:00.000 | 2025-04-02 10:39:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059192 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 11:34:00.000 | 2025-04-02 11:34:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059193 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:41:00.000 | 2025-04-02 10:41:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059194 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:28:00.000 | 2025-04-02 13:29:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059195 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:41:00.000 | 2025-04-02 10:42:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059196 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:29:00.000 | 2025-04-02 13:29:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059197 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:42:00.000 | 2025-04-02 10:43:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059198 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:30:00.000 | 2025-04-02 13:30:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059199 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:43:00.000 | 2025-04-02 10:43:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059200 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:30:00.000 | 2025-04-02 13:30:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059201 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:44:00.000 | 2025-04-02 10:45:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059202 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:31:00.000 | 2025-04-02 13:31:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059203 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:49:00.000 | 2025-04-02 10:50:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059204 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:32:00.000 | 2025-04-02 13:32:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059205 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:50:00.000 | 2025-04-02 10:50:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059206 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:33:00.000 | 2025-04-02 13:33:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059207 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:51:00.000 | 2025-04-02 10:51:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059208 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:33:00.000 | 2025-04-02 13:34:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059209 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:51:00.000 | 2025-04-02 10:52:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059210 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:34:00.000 | 2025-04-02 13:35:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059211 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:52:00.000 | 2025-04-02 10:52:00.000 |  |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059212 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:35:00.000 | 2025-04-02 13:35:00.000 | 2025-05-09 |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059213 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:53:00.000 | 2025-04-02 10:53:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059214 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 13:41:00.000 | 2025-04-02 13:42:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059215 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-05 | 2025-04-02 10:56:00.000 | 2025-04-02 10:56:00.000 | 2025-05-09 |  | 2025-05-16 | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready |  |  | 450 | Novo Nordisk A/S | 102754 | NSF-059216 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2025-02-28 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-03 | 2025-04-02 13:42:00.000 | 2025-04-02 13:42:00.000 |  |  |  | 2025-02-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | Other (incl. termination, on hold, unassigned statuses etc.) | On track |  | 4308 | Novo Nordisk A/S | 104162-014 | F33710-1123338-01 | 104162-014-012 | Henrik Møller Fyhn | Enterprise DK | In Process | 2023-10-18 | 2025-06-26 | 2025-01-06 | Own OnNet |  |  |  | 2024-06-07 |  | 2023-11-24 |  | 2025-01-06 | 2025-06-26 | 2025-06-26 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 95116 | NDD-053971 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-04-05 | 2025-08-29 | 2025-08-29 | Own OnNet |  |  |  | 2024-05-22 |  |  | 2024-05-29 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 95116 | NKA-053970 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-04-05 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-04-09 | 2024-05-28 14:41:00.000 | 2024-04-15 13:22:00.000 | 2024-05-22 |  | 2024-05-03 | 2024-05-29 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 0 | Novo Nordisk A/S | 96292 | NDD-051424 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Change | [6 empty] | 2025-02-24 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 500 | Novo Nordisk A/S | 96292 | NDD-057882 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Own OnNet | [6 empty] | 2025-02-25 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 0 | Novo Nordisk A/S | 96292 | NKA-051423 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-12-13 | 2025-06-06 | 2025-06-06 | Change | 2023-12-13 | 2024-03-22 07:55:00.000 | 2024-03-22 07:55:00.000 |  |  | 2024-04-26 |  | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | Delivered | Delivered | Delivered |  | 2000 | Novo Nordisk A/S | 96443 | NDD-054872 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  | 2025-02-05 00:00:00.000 | New Sales | BO
|  | Cancelled/terminated/On hold | 1.3 Customer requested delay / change of timeline or site not ready | On Hold |  | 2000 | Novo Nordisk A/S | 96443 | NDD-054873 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own OnNet |  |  |  | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | Delivered | Delivered | Delivered |  | 7100 | Novo Nordisk A/S | 96443 | NKA-054870 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2024-06-28 | 2024-09-04 11:04:00.000 | 2024-09-04 11:04:00.000 | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  | 2025-02-05 00:00:00.000 | New Sales | BO
|  | Cancelled/terminated/On hold | 1.3 Customer requested delay / change of timeline or site not ready | On Hold |  | 7100 | Novo Nordisk A/S | 96443 | NKA-054871 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-06-21 | 2025-08-01 | 2025-08-01 | Own with Digging | 2024-06-28 | 2024-09-04 11:03:00.000 | 2024-09-04 11:03:00.000 | 2024-11-29 |  |  | 2025-01-16 | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 98917 | NDD-057021 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own OnNet |  |  |  | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 98917 | NDD-057022 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own OnNet |  |  |  | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 98917 | NKA-057019 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-11-06 | 2024-11-13 15:44:00.000 | 2024-11-15 13:15:00.000 | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.3 Customer requested delay / change of timeline or site not ready | Awaitng building completion |  | 4550 | Novo Nordisk A/S | 98917 | NKA-057020 |  | Henrik Møller Fyhn | Enterprise DK | In Process | 2024-11-01 | 2025-10-01 | 2025-10-01 | Own with Digging | 2024-11-06 | 2024-11-13 15:44:00.000 | 2024-11-19 09:55:00.000 | 2025-06-27 |  |  |  | 2025-10-01 | 2025-10-01 |  |  | New Sales | BO
|  | Delivered | Delivered | On track |  | 2047 | Novozymes A/S | 103672-023 | F33253-1136086-01 | 103672-023-003 | Shazia Mobin | Enterprise DK | Created | 2025-04-08 | 2025-07-04 |  | Own with Digging | [5 empty] | 2025-06-29 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | On Track | On Track | On Track |  | 329.5 | Nymølle Stenindustrier A/S | 102906 | NKA-059045 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-21 |  |  | Own OnNet | 2025-03-03 |  |  |  |  | 2025-05-02 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | On Track | On Track | On Track |  | 329.5 | Nymølle Stenindustrier A/S | 102906 | NML-059044 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-21 |  |  | 3rd Party | [5 empty] | 2025-05-02 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Pending delivery date. |  | 1800 | Per Aarsleff A/S | 105735 | NKA-060729 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-14 |  |  | Own with Digging | 2025-05-15 |  |  |  |  | 2025-07-31 | [5 empty] | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060274 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | Own OnNet | 2025-05-14 | 2025-05-15 09:51:00.000 |  | 2025-11-28 |  | 2025-12-01 |  | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060276 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-03 | 2025-10-03 | Own OnNet | 2025-05-15 |  |  |  |  | 2025-10-03 |  | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060278 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-31 | 2025-10-31 | 3rd Party | 2025-05-15 |  |  |  |  | 2025-10-31 |  | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060280 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-08 | 2025-05-02 13:30:00.000 | 2025-05-14 09:02:00.000 | 2025-06-06 |  | 2025-05-30 | 2025-05-21 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060282 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | Own OnNet | 2025-05-15 | 2025-05-16 10:08:00.000 |  | 2025-11-28 |  | 2025-12-05 |  | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060284 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-04-08 | 2025-05-14 13:57:00.000 | 2025-05-20 08:54:00.000 | 2025-06-13 |  | 2025-05-30 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060286 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-09-26 | 2025-09-26 | 3rd Party |  |  |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-26 | 2025-09-26 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060288 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-31 | 2025-10-31 | Own with Digging | 2025-05-21 |  |  |  |  | 2025-10-31 |  | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060290 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-09-26 | 2025-09-26 | 3rd Party | 2025-05-15 |  |  | 2025-09-26 |  | 2025-09-26 |  | 2025-09-26 | 2025-09-26 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060292 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-11-28 | 2025-11-28 | Own OnNet | 2025-05-15 |  |  |  |  | 2025-11-28 |  | 2025-11-28 | 2025-11-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NKA-060294 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-11-28 | 2025-11-28 | Own OnNet | 2025-05-15 |  |  |  |  | 2025-11-28 |  | 2025-11-28 | 2025-11-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060275 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | 3rd Party |  |  |  | 2025-11-28 |  |  |  | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060277 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-03 | 2025-10-03 | 3rd Party | [7 empty] | 2025-10-03 | 2025-10-03 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060279 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-31 | 2025-10-31 | 3rd Party | [7 empty] | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060281 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  |  | 2025-06-06 |  |  | 2025-05-21 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060283 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-12-05 | 2025-12-05 | 3rd Party | 2025-05-15 |  |  | 2025-11-28 |  | 2025-12-05 |  | 2025-12-05 | 2025-12-05 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060285 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-05-15 |  |  | 2025-06-13 |  |  |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060287 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-09-26 | 2025-09-26 | 3rd Party | 2025-05-15 |  |  | 2025-09-19 |  |  |  | 2025-09-26 | 2025-09-26 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060289 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-10-31 | 2025-10-31 | 3rd Party | [5 empty] | 2025-10-31 |  | 2025-10-31 | 2025-10-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060291 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-09-26 | 2025-09-26 | 3rd Party | 2025-05-15 |  |  | 2025-09-26 |  |  |  | 2025-09-26 | 2025-09-26 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060293 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-11-28 | 2025-11-28 | 3rd Party | [7 empty] | 2025-11-28 | 2025-11-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 700 | Q-Park Operations Denmark A/S | 103570 | NML-060295 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2025-04-04 | 2025-11-28 | 2025-11-28 | 3rd Party | [7 empty] | 2025-11-28 | 2025-11-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | -1091.3833 | Region Midtjylland | 100464-018 | C30130-1136192-01 | 100464-018-003 | Michael Kronbach Leth | Public DK | In Process | 2025-04-14 | 2025-06-30 |  | Change | [5 empty] | 2025-07-02 |  |  | 2025-06-30 | 2025-06-30 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 4750 | Region Sjælland | 92989 | NGF-052964 |  | Michael Kronbach Leth | Public DK | In Process | 2024-01-22 | 2025-06-30 | 2025-06-30 | Own with Digging | 2024-11-25 | 2025-01-10 12:15:00.000 | 2025-01-24 09:45:00.000 |  |  | 2025-02-07 | 2024-01-22 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 29500 | Region Syddanmark | 100730-063 | C30693-1109649-01 | 100730-063-001 | Michael Kronbach Leth | Public DK | In Process | 2022-02-15 | 2025-08-22 |  | Own with Digging | [5 empty] | 2022-10-01 |  |  | 2025-08-22 | 2025-08-22 |  | New Sales | AX
[6 empty] | 29500 | Region Syddanmark | 100730-063 | C30693-1109650-01 | 100730-063-002 | Michael Kronbach Leth | Public DK | In Process | 2022-02-15 | 2025-06-13 |  | Own with Digging | [5 empty] | 2022-10-01 |  |  | 2025-06-13 | 2025-06-13 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 8490 | Region Syddanmark | 100730-079 | C30693-1134744-01 | 100730-079-001 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 |  | Change | [5 empty] | 2025-05-05 | 2025-04-14 |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 8490 | Region Syddanmark | 100730-079 | C30693-1134746-01 | 100730-079-003 | Michael Kronbach Leth | Public DK | Created | 2025-02-12 | 2025-05-28 |  | Change | [5 empty] | 2025-05-05 | 2025-04-14 |  | 2025-05-28 | 2025-05-28 |  | Change | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 332 | Region Syddanmark | 105413 | NKA-060524 |  | Michael Kronbach Leth | Public DK | In Process | 2025-04-29 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-04-29 |  |  | 2025-06-20 |  | 2025-06-11 |  | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 8. Ready for service | Delivered | SW planlægning med kunde |  | 3350 | Roskilde Kommune | 102148 | NKA-001880 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 |  |  | Change | 2025-05-02 | 2025-05-02 13:40:00.000 | 2025-05-07 10:20:00.000 | 2025-05-26 |  | 2025-05-30 | [5 empty] | Change | BO
|  | 8. Ready for service | Delivered | SW planlægning med kunde |  | 3200 | Roskilde Kommune | 102148 | NKA-019998 |  | Michael Kronbach Leth | Public DK | In Process | 2025-01-22 |  |  | Change | 2025-05-02 |  |  | 2025-05-26 | [7 empty] | Change | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060649 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060650 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060651 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060652 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060653 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060654 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 1199 | Røverkøb A/S | 105266 | NKA-060655 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 | 2025-07-31 | 2025-07-31 | 3rd Party | 2025-05-09 | [6 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060656 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060657 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060658 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060659 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060660 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060661 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060662 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060663 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060664 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own OnNet | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060665 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
[6 empty] | 669 | Røverkøb A/S | 105266 | NKA-060666 |  | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-08 |  |  | Own with Digging | 2025-05-09 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | Awaits permit from building owner |  | 6710 | Samsøe & Samsøe Whole Sale ApS | 80781 | NKA-042995 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2022-06-07 | 2025-12-31 | 2025-12-31 | 3rd Party | 2022-10-03 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 5050 | Samsøe & Samsøe Whole Sale ApS | 97292 | NKA-055088 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2024-06-26 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-02-19 |  |  |  |  | 2024-12-13 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | Awaits permit from building owner |  | 4125 | Samsøe & Samsøe Whole Sale ApS | 97335 | NKA-055099 |  | Jane Birgitte Høgaard | Enterprise DK | In Process | 2024-06-26 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-06-24 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | ZEN omlægning |  | 750 | SDI Media A/S | 93136 | NKA-052897 |  | Merete Helme | Enterprise DK | In Process | 2024-01-15 | 2025-06-27 | 2025-06-27 | Own OnNet | 2024-01-16 | 2024-01-18 09:32:00.000 | 2024-01-18 09:39:00.000 | 2024-03-15 |  | 2024-02-09 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | OpenNet had internal Delay - refused to inform reason. |  | 2600 | Semco Maritime A/S | 101823 | NKA-058912 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-13 |  |  | 3rd Party | 2025-02-13 |  |  | 2025-06-06 |  | 2025-05-27 | 2025-03-24 |  |  |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | OpenNet had internal Delay - refused to inform reason. |  | 1950 | Semco Maritime A/S | 93328 | NKA-056039 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-01-08 |  |  | 2025-06-06 |  | 2025-03-13 | 2025-04-25 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Can't get proper information from customer |  | 1100 | Semco Maritime A/S | 93328 | NKA-056041 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | Own with Digging | 2025-02-10 | 2025-02-11 11:46:00.000 | 2025-03-05 14:21:00.000 |  |  | 2025-05-09 | 2025-04-28 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Can't get proper information from customer |  | 1500 | Semco Maritime A/S | 93328 | NKA-056043 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | Own with Digging | 2025-02-10 | 2025-02-11 11:46:00.000 | 2025-03-05 14:47:00.000 |  |  | 2025-05-09 | 2025-03-14 |  |  |  |  | New Sales | BO
|  | 2. Delivery planning | 1.3 Customer requested delay / change of timeline or site not ready | Miscommunication delaying delivery |  | 4400 | Semco Maritime A/S | 93328 | NKA-056051 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | Cancelled/terminated/On hold | Other (incl. termination, on hold, unassigned statuses etc.) | Cancelled |  | 3080 | Semco Maritime A/S | 93328 | NKA-056053 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | Site survey passed on 16/04 |  | 3080 | Semco Maritime A/S | 93328 | NKA-056054 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | On Track | On Track |  | 3080 | Semco Maritime A/S | 93328 | NKA-056055 |  | Andrew David Lindsey | Enterprise DK | In Process | 2024-09-02 |  |  | 3rd Party | 2024-09-30 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 2375 | Skanderborg Kommune | 100219 | NKA-057799 |  | Michael Kronbach Leth | Public DK | In Process | 2024-12-10 | 2025-06-02 | 2025-06-02 | Own OnNet | 2024-12-16 |  |  | 2025-05-09 |  | 2025-09-01 |  | 2025-06-02 | 2025-06-02 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 2375 | Skanderborg Kommune | 100962 | NKA-057798 |  | Michael Kronbach Leth | Public DK | In Process | 2024-12-10 | 2025-09-01 | 2025-09-01 | Own OnNet | [5 empty] | 2025-09-01 |  | 2025-09-01 | 2025-09-01 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 11130 | Sluseholmen 7 A/S | 97750 | NBM-055817 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-08-14 | 2025-09-30 | 2025-09-30 | Own OnNet | [7 empty] | 2025-09-30 | 2025-09-30 |  |  | New Sales | BO
|  | 1.9 PMO delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 1675 | Sluseholmen 7 A/S | 97750 | NBM-055818 |  | Flemming Skovdal | Enterprise DK | In Process | 2024-08-14 | 2025-09-30 | 2025-09-30 | Own OnNet | [7 empty] | 2025-09-30 | 2025-09-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | SDWAN not onboarded in provisoning config, but is asked to do it. OBS. sælger lovet expidite uden salg |  | 1350 | Sol og Strand Feriehusudlejning A/S | 104712 | NKA-060021 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-05-13 |  |  | 2025-06-20 |  | 2025-06-10 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | SDWAN not onboarded in provisoning config, but is asked to do it. OBS. sælger lovet expidite uden salg |  | 275 | Sol og Strand Feriehusudlejning A/S | 104712 | NMA-060020 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 | 2025-06-20 | 2025-06-20 | 3rd Party | [6 empty] | 2025-05-21 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | SDWAN not onboarded in provisoning config, but is asked to do it. OBS. sælger lovet expidite uden salg |  | 275 | Sol og Strand Feriehusudlejning A/S | 104712 | NSW-060019 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-03-28 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-05-21 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 1350 | SOLAR A/S | 103691 | NKA-059916 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-04-14 10:10:00.000 | 2025-05-05 13:11:00.000 | 2025-05-30 |  |  |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 710 | SOLAR A/S | 103691 | NSW-059917 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-03-24 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | Pending contract from 3rd party vendor |  | -2234.14 | Sommerland Sjælland A/S | 105276 | NKA-009830 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-16 | 2025-06-06 | 2025-06-06 | Change | 2017-12-18 | [5 empty] | 2025-05-26 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | Waiting for dates from Fiber |  | 0 | Spar Nord Bank A/S | 100525-117 | F30221-1136761-01 | 100525-117-001 | Camilla Olesen | Enterprise DK | Created | 2025-05-07 | 2025-07-31 |  | Change | [5 empty] | 2025-07-21 |  |  | 2025-07-31 | 2025-07-31 |  | Change | AX
[6 empty] | 0 | Spar Nord Bank A/S | 100525-118 | F30221-1136939-01 | 100525-118-001 | Michael Kronbach Leth | Enterprise DK | In Process | 2025-05-15 | 2025-07-04 | 2025-07-04 | Change |  |  |  | 2025-06-27 |  | 2025-08-07 |  | 2025-07-04 | 2025-07-04 | 2025-07-04 |  | Change | AX
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | NETTEAM |  | 1773 | Staten og Kommunernes Indkøbsservice A/S | 103085 | NBM-059303 |  | Natascha Orlung Baisgaard Andersen | Public DK | In Process | 2025-03-06 | 2025-05-23 | 2025-05-23 | 3rd Party |  |  |  | 2025-05-09 |  | 2025-05-16 | 2025-04-02 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 845 | Statens IT | 102515 | NKA-058786 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-05 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-02-06 | 2025-03-17 11:17:00.000 | 2025-03-17 11:17:00.000 | 2025-06-13 |  |  | 2025-05-07 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 845 | Statens IT | 102921 | NKA-060364 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-08-06 | 2025-08-06 | 3rd Party |  |  |  | 2025-08-01 |  |  |  | 2025-08-06 | 2025-08-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaits feedback from Sales |  | 3125 | Statens IT | 102971 | NKA-059157 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-02-27 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-04-24 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | On track |  | 845 | Statens IT | 103149 | NKA-059898 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-24 | 2025-06-11 | 2025-06-11 | 3rd Party | 2025-04-15 |  |  | 2025-06-06 |  | 2025-05-27 |  | 2025-06-11 | 2025-06-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 7237.5 | Statens IT | 103184 | NGF-060061 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 7237.5 | Statens IT | 103184 | NGF-060062 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 2325 | Statens IT | 103184 | NGF-060063 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 7650 | Statens IT | 103184 | NGF-060064 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 7650 | Statens IT | 103184 | NGF-060065 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 3150 | Statens IT | 103184 | NGF-060066 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 1589.75 | Statens IT | 103184 | NSF-060059 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | On track - no delivery date/deadline, part of a Datacenter solution |  | 1589.75 | Statens IT | 103184 | NSF-060060 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-28 | 2025-12-31 | 2025-12-31 | Own with Digging | [6 empty] | 2025-03-28 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Customer just approved new solution |  | 0 | Statens IT | 103385 | NKA-057946 |  | Morten Skytte | Public DK | In Process | 2025-03-14 | 2025-06-13 | 2025-06-13 | Change | 2024-12-20 | 2025-02-07 13:04:00.000 | 2025-02-14 13:47:00.000 | 2025-03-21 |  | 2025-03-04 |  | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Customer just approved new solution |  | 3125 | Statens IT | 103385 | NKA-059775 |  | Morten Skytte | Public DK | In Process | 2025-03-14 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-03-14 | 2025-04-25 10:52:00.000 | 2025-05-09 14:13:00.000 | 2025-06-06 |  |  | 2025-05-13 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 1.1 Waiting on customer confirmation or input | On track |  | 845 | Statens IT | 104610 | NKA-059970 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-25 | 2025-07-11 | 2025-07-11 | Own with Digging | 2025-03-26 | 2025-04-02 11:12:00.000 | 2025-05-15 14:28:00.000 | 2025-07-04 |  | 2025-07-11 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | On track |  | 845 | Statens IT | 104656 | NKA-059925 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-03-25 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-26 |  |  | 2025-06-13 |  | 2025-06-10 | 2025-05-19 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awating date from 3. part |  | 845 | Statens IT | 104926 | NKA-060252 |  | Morten Skytte | Public DK | In Process | 2025-04-03 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awating date from 3. part |  | 290 | Statens IT | 104926 | NMA-060254 |  | Morten Skytte | Public DK | In Process | 2025-04-03 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Awating date from 3. part |  | 290 | Statens IT | 104926 | NSW-060253 |  | Morten Skytte | Public DK | In Process | 2025-04-03 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 845 | Statens IT | 105148 | NKA-060366 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-11 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-04-15 |  |  | 2025-06-10 |  |  | 2025-05-19 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[6 empty] | 350 | Statens IT | 105711 | NKA-060693 |  | Morten Skytte | Public DK | In Process | 2025-05-12 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 845 | Statens IT | 105804 | NKA-060822 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-19 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-05-20 | 2025-05-22 11:53:00.000 |  | 2025-06-20 |  |  |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
[6 empty] | 720 | Statens IT | 85895 | NKA-006121 |  | Bonnie Jensen | Public DK | In Process | 2023-02-14 |  |  | Change
[6 empty] | 925 | Statens IT | 87327 | NKA-000521 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 845 | Statens IT | 87327 | NKA-001316 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 845 | Statens IT | 87327 | NKA-008572 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 920 | Statens IT | 87327 | NKA-012063 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 845 | Statens IT | 87327 | NKA-022293 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 845 | Statens IT | 87327 | NKA-035134 |  | Bonnie Jensen | Public DK | In Process | 2023-04-14 |  |  | Change
[6 empty] | 845 | Statens IT | 90910 | NKA-011368 |  | Bonnie Jensen | Public DK | In Process | 2023-10-02 |  |  | Change
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer status og datoer fra 3.part |  | 450 | Stevns Kommune | 98576 | NKA-056300 |  | Michael Kronbach Leth | Public DK | In Process | 2024-09-19 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-09-30 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1 Pending external 3rd party: Any 3rd party | Afventer status og datoer fra 3.part |  | 325 | Stevns Kommune | 98576 | NSW-056301 |  | Michael Kronbach Leth | Public DK | In Process | 2024-09-19 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
[6 empty] | 9693 | Sund & Bælt Holding A/S | 82790 | NKA-041907 |  | Oliver Mariager | Public DK | In Process | 2023-02-08 |  |  | Change
[6 empty] | 1907.4 | Sund & Bælt Holding A/S | 82790 | NKA-046742 |  | Oliver Mariager | Public DK | In Process | 2023-02-08 |  |  | Own with Digging
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | Just startet |  | 3079 | Sydbank A/S | 104165-012 | C33713-1136323-01 | 104165-012-001 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 |  |  | 3rd Party | [5 empty] | 2025-07-09 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | Other (incl. termination, on hold, unassigned statuses etc.) | Just startet |  | 3079 | Sydbank A/S | 104165-012 | C33713-1136325-01 | 104165-012-003 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-04-16 |  |  | 3rd Party | [5 empty] | 2025-07-09 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 8500 | Syddansk Erhvervsskole | 103009 | NDD-059299 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-06 | 2025-12-31 | 2025-12-31 | Own OnNet | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 8500 | Syddansk Erhvervsskole | 103009 | NKA-059298 |  | Michael Kronbach Leth | Public DK | In Process | 2025-03-06 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-03-07 |  | 2025-03-06 09:46:00.000 |  |  | 2025-05-20 |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track |  | 4125 | Syddansk Erhvervsskole | 104736 | NKA-010125 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-21 | 2025-05-28 | 2025-05-28 | Change | [7 empty] | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track, installation uge 24 |  | 1625 | Syddansk Erhvervsskole | 105422 | NKA-060523 |  | Eva Eisner | Public DK | In Process | 2025-04-29 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-04-29 | 2025-04-30 10:15:00.000 | 2025-04-30 10:15:00.000 | 2025-06-13 |  | 2025-06-20 | 2025-05-12 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[6 empty] | 845 | Syddansk Erhvervsskole | 105892 | NKA-060850 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-22 |  |  | Own OnNet | 2025-05-22 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 1990 | Syddansk Universitet (university Of Southern Denmark) | 100964-007 | F30928-1135939-01 | 100964-007-001 | Shazia Mobin | Public DK | In Process | 2025-04-03 | 2025-06-06 | 2025-05-30 | Own with Digging |  |  |  | 2025-05-30 |  | 2025-06-25 |  | 2025-05-30 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
[6 empty] | 4000 | Syddansk Universitet (university Of Southern Denmark) | 100964-008 | F30928-1136815-01 | 100964-008-001 | Michael Kronbach Leth | Public DK | Created | 2025-05-09 |  |  | Own with Digging | [5 empty] | 2025-07-31 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 9588 | Søstrene Grenes Import A/S | 100998-028 | C30962-1135204-01 | 100998-028-001 | Michael Kronbach Leth | Enterprise DK | Created | 2025-03-11 | 2025-08-29 |  | 3rd Party | [5 empty] | 2025-06-02 |  |  | 2025-08-29 | 2025-08-29 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | SW planlægning med kunde |  | 9762 | Søstrene Grenes Import A/S | 100998-028 | C30962-1135206-01 | 100998-028-003 | Michael Kronbach Leth | Enterprise DK | Created | 2025-03-11 | 2025-08-29 |  | 3rd Party | [5 empty] | 2025-06-02 |  |  | 2025-08-29 | 2025-08-29 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 1450 | T HANSEN GRUPPEN A/S | 103415 | NKA-059743 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-01 | 2025-04-10 11:00:00.000 | 2025-05-05 14:44:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 425 | T HANSEN GRUPPEN A/S | 103415 | NMA-059745 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | 3rd Party | [5 empty] | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 2300 | T HANSEN GRUPPEN A/S | 103415 | NSF-059746 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-01 | 2025-04-10 10:49:00.000 | 2025-05-07 10:42:00.000 |  |  | 2025-05-02 | 2025-03-12 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 425 | T HANSEN GRUPPEN A/S | 103415 | NSW-059744 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-12 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 750 | T HANSEN GRUPPEN A/S | 103609 | NKA-059877 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | Own with Digging | 2025-03-25 |  |  |  |  | 2025-10-24 |  | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 162.5 | T HANSEN GRUPPEN A/S | 103609 | NMA-059879 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | 3rd Party | 2025-03-25 | [6 empty] | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 162.5 | T HANSEN GRUPPEN A/S | 103609 | NSW-059878 |  | Jesper Olsen | Enterprise DK | In Process | 2025-03-20 | 2025-09-19 | 2025-09-19 | Own OnNet | [7 empty] | 2025-09-19 | 2025-09-19 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation date |  | 3850 | T HANSEN GRUPPEN A/S | 104597 | NKA-060269 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-06-06 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation and fiber from GC NO |  | 3850 | T HANSEN GRUPPEN A/S | 104597 | NKA-060270 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-30 | [5 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation and fiber from GC NO |  | 537.5 | T HANSEN GRUPPEN A/S | 104597 | NMA-060272 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-23 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation date |  | 537.5 | T HANSEN GRUPPEN A/S | 104597 | NSW-060271 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.2.1 Pending internal 3rd party: GC Norway | Waiting for installation and fiber from GC NO |  | 895 | T HANSEN GRUPPEN A/S | 104597 | NSW-060273 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-04-04 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 1400 | T HANSEN GRUPPEN A/S | 105700 | NKA-060750 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | 3rd Party | 2025-05-19 |  |  |  |  | 2025-07-25 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 275 | T HANSEN GRUPPEN A/S | 105700 | NMA-060752 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | 3rd Party | 2025-05-19 |  |  |  |  | 2025-07-25 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 275 | T HANSEN GRUPPEN A/S | 105700 | NSW-060751 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 1400 | T HANSEN GRUPPEN A/S | 105701 | NKA-060753 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | 3rd Party | 2025-05-19 |  |  |  |  | 2025-08-12 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 275 | T HANSEN GRUPPEN A/S | 105701 | NMA-060755 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | 3rd Party | 2025-05-19 |  |  |  |  | 2025-08-12 | [5 empty] | New Sales | BO
|  | 2. Delivery planning | 3.2.2 Pending internal 3rd party: GC Sweden |  |  | 275 | T HANSEN GRUPPEN A/S | 105701 | NSW-060754 |  | Martin Rasmussen | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | [11 empty] | New Sales | BO
[6 empty] | 1685 | T HANSEN GRUPPEN A/S | 105726 | NKA-040716 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-15 |  |  | Change | 2022-03-02 |  |  |  |  | 2022-03-25 | [5 empty] | Change | BO
[6 empty] | 2350 | T HANSEN GRUPPEN A/S | 105726 | NKA-060748 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | 2025-05-16 | 2025-05-19 13:09:00.000 | 2025-05-26 10:55:00.000 | 2025-06-20 | [7 empty] | New Sales | BO
[6 empty] | 315.5 | T HANSEN GRUPPEN A/S | 105726 | NMA-040718 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-15 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 67 | T HANSEN GRUPPEN A/S | 105726 | NSW-040717 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-15 |  |  | Change | [11 empty] | Change | BO
[6 empty] | 645 | T HANSEN GRUPPEN A/S | 105726 | NSW-060749 |  | Jesper Olsen | Enterprise DK | In Process | 2025-05-15 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 2.2 Pending internal approval (e.g., fokka, vendor choice, etc.) | Waiting for new vendor |  | 845 | Techcollege | 105617 | NKA-060635 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-05-08 | 2025-12-31 | 2025-12-31 | 3rd Party | [7 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 3.4 Other installation obstacles and infratructure issues | Waiting for service windows and tests |  | 13500 | Techcollege | 91284 | NKA-001435 |  | Jane Birgitte Høgaard | Public DK | In Process | 2024-01-30 | 2025-06-30 | 2025-06-30 | Change | 2024-02-28 | 2024-03-01 09:04:00.000 | 2024-03-04 15:38:00.000 | 2024-12-09 |  | 2024-05-03 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 8. Ready for service | 3.4 Other installation obstacles and infratructure issues | Waiting for service windows and tests |  | 13500 | Techcollege | 91284 | NKA-020212 |  | Jane Birgitte Høgaard | Public DK | In Process | 2024-01-30 | 2025-06-30 | 2025-06-30 | Change | 2017-04-18 | 2017-08-17 14:00:00.000 | 2017-08-17 14:00:00.000 | 2024-12-09 |  | 2017-10-31 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.0066667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135708-01 | 107596-003-001 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.0066667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135709-01 | 107596-003-002 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135710-01 | 107596-003-003 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.96667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135711-01 | 107596-003-004 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.11 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135712-01 | 107596-003-005 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135713-01 | 107596-003-006 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.19667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135714-01 | 107596-003-007 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.3 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135715-01 | 107596-003-008 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135716-01 | 107596-003-009 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.72333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135718-01 | 107596-003-011 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.46 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135719-01 | 107596-003-012 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135720-01 | 107596-003-013 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135722-01 | 107596-003-015 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135723-01 | 107596-003-016 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.41333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135725-01 | 107596-003-018 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135727-01 | 107596-003-020 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135728-01 | 107596-003-021 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135729-01 | 107596-003-022 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.70333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135731-01 | 107596-003-024 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135732-01 | 107596-003-025 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.11333 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135734-01 | 107596-003-027 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.61667 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135735-01 | 107596-003-028 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135736-01 | 107596-003-029 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.1 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135738-01 | 107596-003-031 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | -0.52 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135739-01 | 107596-003-032 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Change | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135740-01 | 107596-003-033 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
|  | 5. Configuration | 2.6 Order in queue: Being processed | Awaiting redoc from provisioning |  | 0 | The UK Branch Office of Awaze A/S (UC ) | 107596-003 | C36620-1135742-01 | 107596-003-035 | Cecilie Heidner Nielsen | Enterprise DK | Created | 2025-03-28 | 2025-06-27 |  | Own OnNet | [5 empty] | 2025-04-25 |  |  | 2025-06-27 | 2025-06-27 |  | New Sales | AX
[6 empty] | 600 | Thisted Kommune | 105750 | NKA-060873 |  | Eva Eisner | Public DK | In Process | 2025-05-26 |  |  | 3rd Party | 2025-05-26 |  | 2025-05-26 09:46:00.000 | [8 empty] | New Sales | BO
[6 empty] | 177.5 | Thisted Kommune | 105750 | NMA-060875 |  | Eva Eisner | Public DK | In Process | 2025-05-26 |  |  | 3rd Party | 2025-05-26 | [10 empty] | New Sales | BO
[6 empty] | 177.5 | Thisted Kommune | 105750 | NSW-060874 |  | Eva Eisner | Public DK | In Process | 2025-05-26 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 2625 | Thornico IT A/S | 101568-032 | C31534-1135243-01 | 101568-032-016 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-03-12 | 2025-06-20 | 2025-06-20 | 3rd Party |  |  |  | 2025-06-18 |  | 2025-06-02 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | New Sales | AX
[6 empty] | 1672 | Thorsgård Efterskole | 105453 | NKA-000670 |  | Eva Eisner | Public DK | In Process | 2025-05-23 |  |  | Change | [5 empty] | 2025-05-19 | [5 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Waiting for rack info from the customer |  | 4320 | Topsoe A/S | 100779 | NKA-057949 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-12-18 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-01-06 |  |  |  |  | 2025-02-28 | 2025-02-20 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready | On track |  | 1450 | twoday Danmark A/S | 90369 | NKA-055478 |  | Nanna Søndergaard Skov | Enterprise DK | In Process | 2024-06-28 | 2025-09-05 | 2025-09-05 | Own OnNet | 2024-07-04 | 2024-10-02 13:48:00.000 | 2024-10-02 13:48:00.000 | 2025-08-29 |  | 2025-03-01 | 2024-10-14 | 2025-09-05 | 2025-09-05 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Awating 3 part to fix error |  | 892 | Tønder Kommune | 102621 | NKA-058895 |  | Morten Skytte | Public DK | In Process | 2025-02-12 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-16 |  |  | 2025-04-25 |  | 2025-04-25 | 2025-05-26 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
[6 empty] | 895 | Tønder Kommune | 97010 | NKA-055059 |  | Morten Skytte | Public DK | In Process | 2024-06-25 |  |  | Own OnNet
[6 empty] | 895 | Tønder Kommune | 97010 | NKA-055060 |  | Morten Skytte | Public DK | In Process | 2024-06-25 |  |  | Own OnNet
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | OBS. sælger lovet expidite uden salg |  | -436.69 | Unisport A/S | 105569 | NBM-041174 |  | Signe Fogh Mach Andersen | Enterprise DK | In Process | 2025-05-13 | 2025-05-30 | 2025-05-30 | Change |  |  |  | 2025-05-30 |  |  |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 2. Delivery planning | 1.2 Customer not reachable / unresponsive |  |  | 5100 | Urban Partners A/S | 101892 | NII-058952 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 | 2025-08-15 | 2025-08-15 | Own OnNet | [6 empty] | 2025-02-17 | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1 Pending external 3rd party: Any 3rd party | Difficulties |  | 4600 | Urban Partners A/S | 102056 | NII-058975 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 | 2025-07-16 | 2025-07-16 | 3rd Party | [6 empty] | 2025-02-17 | 2025-07-16 | 2025-07-16 |  |  | New Sales | BO
|  | On Track |  |  |  | 1600 | Urban Partners A/S | 102056 | NKA-058974 |  | Andrew David Lindsey | Enterprise DK | In Process | 2025-02-17 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-07 |  |  |  |  | 2025-04-11 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  | 1399 | Vattenfall Vindkraft A/S | 103303 | NKA-059771 |  | Peter Madsen | Enterprise DK | In Process | 2025-03-13 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-03-24 |  |  | 2025-05-30 |  | 2025-06-03 | 2025-05-14 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 812.25 | Vejle Kommune | 100606-089 | C30318-1135745-01 | 100606-089-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-30 | 2025-11-07 |  | Own OnNet | [5 empty] | 2025-06-16 |  |  | 2025-11-07 | 2025-11-07 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 100 | Vejle Kommune | 100606-089 | C30318-1135746-01 | 100606-089-002 | Michael Kronbach Leth | Public DK | Created | 2025-03-30 | 2025-11-07 |  | Own OnNet | [5 empty] | 2025-06-16 |  |  | 2025-11-07 | 2025-11-07 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 812.25 | Vejle Kommune | 100606-090 | C30318-1135825-01 | 100606-090-001 | Michael Kronbach Leth | Public DK | Created | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-06-16 | 2025-05-22 | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 0 | Vejle Kommune | 100606-090 | C30318-1135826-01 | 100606-090-002 | Michael Kronbach Leth | Public DK | Created | 2025-03-31 | 2025-06-06 |  | Own OnNet | [5 empty] | 2025-06-16 | 2025-05-22 |  | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 2265 | Vejle Kommune | 100606-093 | C30318-1128873-02 | 100606-093-007 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Opgradering | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 2265 | Vejle Kommune | 100606-093 | C30318-1128876-02 | 100606-093-008 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Opgradering | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 163.5 | Vejle Kommune | 100606-093 | C30318-1136287-01 | 100606-093-001 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change |  |  |  | 2025-05-12 |  | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 163.5 | Vejle Kommune | 100606-093 | C30318-1136288-01 | 100606-093-002 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 | 2025-06-27 |  | Change | [5 empty] | 2025-07-07 | 2025-05-23 |  | 2025-06-27 | 2025-06-27 |  | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 163.5 | Vejle Kommune | 100606-093 | C30318-1136289-01 | 100606-093-003 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change |  |  |  | 2025-05-12 |  | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 163.5 | Vejle Kommune | 100606-093 | C30318-1136290-01 | 100606-093-004 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Change | [5 empty] | 2025-07-07 | [5 empty] | Change | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 0 | Vejle Kommune | 100606-093 | C30318-1136291-01 | 100606-093-005 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Own OnNet | [5 empty] | 2025-07-07 | [5 empty] | New Sales | AX
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | 0 | Vejle Kommune | 100606-093 | C30318-1136292-01 | 100606-093-006 | Michael Kronbach Leth | Public DK | Created | 2025-04-15 |  |  | Own OnNet | [5 empty] | 2025-07-07 | [5 empty] | New Sales | AX
|  | 4. Final design | 2.6 Order in queue: Being processed | On track, installtaion uge 28 |  | 600 | Vesthimmerlands Kommune | 104738 | NKA-060022 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-04-24 |  |  | 2025-07-11 |  | 2025-07-03 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track, installtaion uge 28 |  | 30 | Vesthimmerlands Kommune | 104740 | NKA-060022 |  | Eva Eisner | Public DK | In Process | 2025-03-28 | 2025-07-18 | 2025-07-18 | Change | 2025-04-24 |  |  |  |  | 2025-07-03 |  | 2025-07-18 | 2025-07-18 |  |  | Change | BO
|  | 3. Installation preparation and digging order | 3.1.1 Pending external 3rd party: Open-Net | On track |  | 600 | Vesthimmerlands Kommune | 105255 | NKA-060401 |  | Jane Birgitte Høgaard | Public DK | In Process | 2025-04-16 | 2025-07-23 | 2025-07-23 | 3rd Party | 2025-05-06 |  |  | 2025-07-18 |  | 2025-07-15 |  | 2025-07-23 | 2025-07-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 756 | Vestjyllands Andel A.M.B.A. | 102098 | NKA-060830 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-20 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-22 |  |  | 2025-07-04 |  | 2025-07-02 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Pending installation date |  | 756 | Vestjyllands Andel A.M.B.A. | 102098 | NKA-060832 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-20 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-21 |  |  | 2025-07-11 |  | 2025-07-01 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed |  |  | 756 | Vestjyllands Andel A.M.B.A. | 102098 | NML-060831 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-20 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-22 |  |  | 2025-07-04 |  |  |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Pending installation date |  | 756 | Vestjyllands Andel A.M.B.A. | 102098 | NML-060833 |  | Peter Madsen | Enterprise DK | In Process | 2025-05-20 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-21 |  |  | 2025-07-11 |  |  |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 400.95 | Viborg Kommune | 103119 | NKA-059264 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | Own OnNet | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 400.95 | Viborg Kommune | 103119 | NKA-059265 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 400.95 | Viborg Kommune | 103119 | NKA-059266 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 400.95 | Viborg Kommune | 103119 | NKA-059267 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | Own OnNet | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 400.95 | Viborg Kommune | 103119 | NKA-059268 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party | [7 empty] | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 546.75 | Viborg Kommune | 103119 | NKA-059269 |  | Morten Skytte | Public DK | In Process | 2025-03-04 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-17 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 2300 | Wismo Group A/S | 101534-018 | C31500-1133908-01 | 101534-018-015 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 50 | Wismo Group A/S | 101534-018 | C31500-1133909-01 | 101534-018-016 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 2300 | Wismo Group A/S | 101534-018 | C31500-1133911-01 | 101534-018-018 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 50 | Wismo Group A/S | 101534-018 | C31500-1133912-01 | 101534-018-019 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 0 | Wismo Group A/S | 101534-018 | C31500-1133913-01 | 101534-018-020 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1700 | Wismo Group A/S | 101534-018 | C31500-1133914-01 | 101534-018-021 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 50 | Wismo Group A/S | 101534-018 | C31500-1133915-01 | 101534-018-022 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1700 | Wismo Group A/S | 101534-018 | C31500-1133917-01 | 101534-018-024 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | 3rd Party | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 50 | Wismo Group A/S | 101534-018 | C31500-1133918-01 | 101534-018-025 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 0 | Wismo Group A/S | 101534-018 | C31500-1133919-01 | 101534-018-026 | Henrik Møller Fyhn | Enterprise DK | Created | 2025-01-08 | 2025-05-28 |  | Own OnNet | [5 empty] | 2025-03-13 |  |  | 2025-05-28 | 2025-05-28 |  | New Sales | AX
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) |  | -3458.02 | ZeroNorth A/S | 101796 | NBM-040748 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-06-30 | 2025-06-30 | Change | 2025-03-10 |  |  |  |  | 2025-04-30 |  | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) |  | 126.66 | ZeroNorth A/S | 101796 | NBM-047894 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-06-30 | 2025-06-30 | Change | [7 empty] | 2025-06-30 | 2025-06-30 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Not standard solution to india including time contrains (Netteam) |  | 4718 | ZeroNorth A/S | 101796 | NBM-058731 |  | Natascha Orlung Baisgaard Andersen | Enterprise DK | In Process | 2025-01-31 | 2025-06-30 | 2025-06-30 | 3rd Party | 2025-03-10 |  |  |  |  | 2025-04-30 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Awating GC to establies new line |  | 2851.86 | Øresunds Internationale Skole S/I | 100271 | NKA-011021 |  | Morten Skytte | Public DK | In Process | 2024-11-29 |  |  | Change |  | 2021-01-27 09:41:00.000 | 2021-01-27 12:39:00.000 | [8 empty] | Change | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 600 | Aarhus Motion | 105070 | NBM-060351 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  | 2025-06-13 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 200 | Aarhus Motion | 105070 | NMA-060350 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-06-13 | 2025-05-19 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 200 | Aarhus Motion | 105070 | NSW-060349 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-10 | 2025-06-13 | 2025-06-13 | Own OnNet | [6 empty] | 2025-05-19 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-05-05 |  |  | 2025-05-28 |  | 2025-05-16 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1361.89 | ABCforsikringsagentur A/S | 105230 | NBM-060388 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-14 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-15 |  |  | 2025-05-28 |  | 2025-06-13 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | -1050.89 | ABCforsikringsagentur A/S | 105465 | NBM-060387 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-05-28 | 2025-05-28 | Change | 2025-05-05 |  |  | 2025-05-28 |  | 2025-05-16 | 2025-05-05 | 2025-05-28 | 2025-05-28 |  |  | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NKA-060181 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-04-07 | 2025-04-23 15:01:00.000 | 2025-05-15 12:56:00.000 | 2025-06-20 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 697.5 | Advokatfirmaet Grønbæk & Huuse I/S | 103258 | NML-060182 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-07 |  |  | 2025-06-20 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 9. Documentation and vendor invoice | Other (incl. termination, on hold, unassigned statuses etc.) | This line is delivered - but there is an eror in BO order, but it should have been completed. Dont understand why it is on the list? |  | 121.38 | ALFABO | 74844 | NKA-036952 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2021-09-07 |  |  | 3rd Party | 2021-09-24 |  |  |  |  | 2021-10-04 | 2021-09-24 |  |  |  | 2023-04-24 00:00:00.000 | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations |  |  | 1350 | Al-Irchad Skolen | 102553 | NBM-059109 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 899 | Al-Irchad Skolen | 102553 | NKA-059110 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-13 | 2025-05-21 10:24:00.000 |  | 2025-06-20 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 200 | Al-Irchad Skolen | 102553 | NMA-059107 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-31 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed |  |  | 200 | Al-Irchad Skolen | 102553 | NSW-059108 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-26 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 2500 | Archon DK ApS | 105548 | NBM-060607 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-06 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 1395 | Archon DK ApS | 105548 | NKA-060608 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-05-06 | 2025-05-12 11:59:00.000 | 2025-05-13 08:51:00.000 | 2025-05-30 |  | 2025-05-30 | 2025-05-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
[6 empty] | 895 | AS3 A/S | 101070 | NKA-057739 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-12-06 | 2025-08-01 | 2025-08-01 | Own with Digging | 2025-05-21 |  |  |  |  | 2025-08-01 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
[6 empty] | 895 | AS3 A/S | 101070 | NKA-057754 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-12-06 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 895 | AS3 A/S | 101070 | NKA-057758 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-12-06 | 2025-07-11 | 2025-07-11 | Own OnNet | 2025-05-21 |  |  |  |  | 2025-07-11 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
[6 empty] | 1095 | AS3 A/S | 105464 | NKA-060862 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-05-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
[6 empty] | 945 | AS3 A/S | 105464 | NKA-060863 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-05-22 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-05-26 |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
|  | On Track | On Track | On Track |  | 697.5 | BESS Frederiksværk I ApS | 101911 | NKA-058435 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 | 2025-06-30 | 2025-06-30 | 3rd Party |  |  |  | 2025-06-20 |  |  | 2025-01-23 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | On Track | On Track | On Track |  | 697.5 | BESS Frederiksværk I ApS | 101911 | NML-058436 |  | Andrew David Lindsey | SMB Portfolio DK | In Process | 2025-01-16 | 2025-06-30 | 2025-06-30 | 3rd Party |  |  |  | 2025-06-20 |  |  | 2025-01-23 | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Awaiting design. |  | 1186 | Best Ejendomme A/S | 105526 | NKA-060558 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-05-02 |  |  |  |  | 2025-06-20 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | Jepmbi: Jeg har rykket RFS dato fra d 30-05-2025 til slut august. Ser ud til SE mangler info fra kunden, og kunden har ikke vendt tilbage siden marts 2025. |  | 520 | BHS Logistics A/S | 79039 | NSW-041031 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 1.1 Waiting on customer confirmation or input | Jepmbi: Jeg har rykket RFS dato fra d 30-05-2025 til slut august. Ser ud til SE mangler info fra kunden, og kunden har ikke vendt tilbage siden marts 2025. |  | 520 | BHS Logistics A/S | 79039 | NSW-041032 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2022-03-18 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 665.5 | Bluebyte ApS | 103578 | NKA-059827 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-03-20 | 2025-04-04 07:37:00.000 | 2025-04-28 14:37:00.000 | 2025-05-28 |  |  | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 665.5 | Bluebyte ApS | 103578 | NML-059828 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-19 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-03-20 |  |  | 2025-05-28 |  |  | 2025-05-13 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 800 | BRUUN & STENGADE A/S | 101934 | NKA-060091 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-10 | 2025-05-12 13:13:00.000 | 2025-05-16 14:58:00.000 | 2025-06-13 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 200 | BRUUN & STENGADE A/S | 101934 | NMA-060093 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-10 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 200 | BRUUN & STENGADE A/S | 101934 | NSW-060092 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | -312.71 | BSC Drift ApS | 104739 | NKA-028998 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Change | 2019-10-18 | 2019-10-28 11:15:00.000 | 2019-10-29 07:50:00.000 |  |  | 2019-12-17 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | Change | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 230 | BSC Drift ApS | 104739 | NMA-060117 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-06 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 230 | BSC Drift ApS | 104739 | NSW-060118 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [6 empty] | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 4. Final design | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 895 | Bysted & Partners ApS | 103106 | NKA-060120 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-09 | 2025-05-20 16:29:00.000 | 2025-05-22 14:17:00.000 | 2025-06-13 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 150 | Bysted & Partners ApS | 103106 | NMA-060122 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 150 | Bysted & Partners ApS | 103106 | NSW-060121 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
[6 empty] | 1315 | Copenhagen Bamboo ApS | 101143 | NKA-057576 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-26 | 2025-06-06 | 2025-06-06 | Own with Digging | 2024-12-06 | 2025-04-03 13:06:00.000 | 2025-04-23 09:56:00.000 | 2025-05-30 |  | 2025-03-07 | 2025-04-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready for installations | OBS. sælger lovet expidite uden salg |  | 1388.81 | Copenhagen Coffee Lab Holding ApS | 105359 | NBM-060697 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-05-13 |  |  | 2025-06-06 |  | 2025-07-04 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 5. Configuration |  | OBS. sælger lovet expidite uden salg |  | 860 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060694 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-05-13 | 2025-05-14 12:02:00.000 | 2025-05-14 10:33:00.000 | 2025-05-30 |  | 2025-07-04 | 2025-05-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  |  |  | 760 | Copenhagen Coffee Lab Holding ApS | 105359 | NKA-060698 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-13 |  |  | 2025-06-13 |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | OBS. sælger lovet expidite uden salg |  | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060696 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 | 2025-05-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  |  |  | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NMA-060700 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order |  | OBS. sælger lovet expidite uden salg |  | 200 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060695 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-05-30 | 2025-05-30 | Own OnNet | [6 empty] | 2025-05-16 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation |  |  |  | 150 | Copenhagen Coffee Lab Holding ApS | 105359 | NSW-060699 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-12 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 895 | Dansk Vegetarisk Forening (DVF) | 103541 | NKA-060076 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-09 | 2025-05-13 10:33:00.000 | 2025-05-16 08:28:00.000 | 2025-06-13 |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NMA-060078 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-09 |  |  |  |  | 2025-05-16 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations | Awaiting Fiber PM - Delivery proceeding as planned |  | 200 | Dansk Vegetarisk Forening (DVF) | 103541 | NSW-060077 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-06 | 2025-06-06 | Own OnNet | [7 empty] | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.2 Customer not reachable / unresponsive | Wating for the buildingowner to accept the design plan |  | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056366 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-06-27 | 2025-06-27 | Own with Digging | 2024-10-15 |  |  |  |  | 2025-01-10 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.3 Third party resource constraint | Delay on digging from TDC |  | 1220 | DANSKE KONCEPT RESTAURANTER A/S | 97023 | NKA-056374 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2024-09-23 | 2025-06-20 | 2025-06-20 | 3rd Party |  |  |  | 2025-06-20 |  |  | 2025-05-06 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overlevert til Jeppe |  |  | Danske Shoppingcentre P/S | 100107 | NSW-037789 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2024-10-17 |  |  | Change | [11 empty] | Change | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1391 | Den selvejende institution Friplejehjemmet Alba Marie | 103605 | NKA-060268 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-04-08 | 2025-05-01 10:53:00.000 | 2025-05-07 10:47:00.000 | 2025-05-30 |  | 2025-07-18 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | -180.9967 | DIS Sølvgade A/S | 103176-004 | C32793-1136828-01 | 103176-004-001 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Change | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | Change | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136829-01 | 103176-004-002 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136830-01 | 103176-004-003 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136831-01 | 103176-004-004 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 3624 | DIS Sølvgade A/S | 103176-004 | C32793-1136833-01 | 103176-004-006 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own with Digging | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 0 | DIS Sølvgade A/S | 103176-004 | C32793-1136834-01 | 103176-004-007 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 30 | DIS Sølvgade A/S | 103176-004 | C32793-1136835-01 | 103176-004-008 | Henrik Møller Fyhn | SMB Portfolio DK | Created | 2025-05-13 | 2025-07-04 |  | Own OnNet | [5 empty] | 2025-07-31 |  |  | 2025-07-04 | 2025-07-04 |  | New Sales | AX
|  | 4. Final design | 3.1 Pending external 3rd party: Any 3rd party | Awaiting EWI |  | 2643 | Ecm Industries A/S | 94182 | NKA-053149 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-02-06 | 2025-08-08 | 2025-08-08 | 3rd Party | 2024-07-25 | [6 empty] | 2025-08-08 | 2025-08-08 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned |  | 3569 | Ejendomsanpartsselskabet MT 04 | 91727 | NBM-060202 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-30 | 2025-05-23 | 3rd Party | 2025-04-02 |  |  | 2025-05-23 |  | 2025-05-02 | 2025-05-13 | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned |  | -929.74 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-30 | 2025-05-23 | Change | 2016-08-03 | 2016-07-11 11:49:00.000 | 2016-07-08 12:28:00.000 | 2025-05-19 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | Change | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed | Awating Equipment (Netteam) and installation - The delivery is proceeding as planned |  | -248.28 | Ejendomsanpartsselskabet MT 04 | 91727 | NKA-015321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-01 | 2025-05-30 | 2025-05-23 | Change | 2016-08-03 | 2016-07-11 11:52:00.000 | 2016-07-08 12:29:00.000 | 2025-05-19 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | Change | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 1416 | Eurographic Group A/S | 102676 | NKA-059039 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-30 | 2025-05-23 | Own OnNet | 2025-03-05 | 2025-03-18 09:18:00.000 | 2025-03-20 13:38:00.000 | 2025-04-07 |  |  | 2025-04-03 | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 612 | Eurographic Group A/S | 102676 | NMA-059041 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-30 | 2025-05-23 | 3rd Party | 2025-04-15 |  |  |  |  | 2025-05-09 |  | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
|  | 7. Service activation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 612 | Eurographic Group A/S | 102676 | NSW-059040 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-05-30 | 2025-05-23 | Own OnNet | [7 empty] | 2025-05-23 | 2025-05-23 | 2025-05-30 |  | New Sales | BO
[6 empty] | 1247.96 | EVE Group ApS | 105702 | NBM-060810 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-08-15 | 2025-08-15 | 3rd Party | 2025-05-22 |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
[6 empty] | 1282.04 | EVE Group ApS | 105702 | NBM-060813 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-22 |  |  |  |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
[6 empty] | 600 | EVE Group ApS | 105702 | NKA-060808 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-08-15 | 2025-08-15 | Own with Digging | 2025-05-22 |  |  |  |  | 2025-08-08 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
[6 empty] | 600 | EVE Group ApS | 105702 | NKA-060811 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-07-18 | 2025-07-18 | Own OnNet | 2025-05-22 | 2025-05-23 12:12:00.000 |  | 2025-06-13 |  | 2025-07-11 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
[6 empty] | 600 | EVE Group ApS | 105702 | NML-060809 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-08-15 | 2025-08-15 | 3rd Party | 2025-05-22 |  |  |  |  | 2025-08-08 |  | 2025-08-15 | 2025-08-15 |  |  | New Sales | BO
[6 empty] | 600 | EVE Group ApS | 105702 | NML-060812 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-22 |  |  | 2025-06-13 |  | 2025-07-11 |  | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 5. Configuration | 3.4 Other installation obstacles and infratructure issues | Postponing installation due to lack of clarification in the sales phase. Technical clarification and errors in physical installation. |  | 3870.05 | Flyers ApS | 102767 | NBM-058991 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-19 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-02-25 |  |  | 2025-05-09 |  | 2025-04-25 | 2025-02-25 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 775 | FUEGO ApS | 98741 | NBM-058935 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet | [6 empty] | 2025-03-06 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1000 | FUEGO ApS | 98741 | NKA-058932 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-27 | 2025-06-27 | Own with Digging |  |  |  | 2025-06-17 |  | 2025-05-30 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 100 | FUEGO ApS | 98741 | NMA-058934 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | 3rd Party | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 100 | FUEGO ApS | 98741 | NSW-058933 |  | Kristijan Krsteski | SMB Portfolio DK | In Process | 2025-02-14 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Wrong segment GCC seg not SMB |  |  | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136868-01 | 106418-746-001 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2025-05-14 | 2025-08-15 |  | 3rd Party | [5 empty] | 2025-08-13 |  |  | 2025-08-15 | 2025-08-15 |  | New Sales | AX
|  | 2. Delivery planning | 2.6 Order in queue: Being processed | Wrong segment GCC seg not SMB |  |  | GlobalConnect GmbH (Intercompany 2) | 106418-746 | C30781-1136871-01 | 106418-746-004 | Camilla Villumsen Kaimer | SMB Portfolio DK | Created | 2025-05-14 | 2025-08-15 |  | Own with Digging | [5 empty] | 2025-08-13 |  |  | 2025-08-15 | 2025-08-15 |  | New Sales | AX
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting Fiber PM - Delivery proceeding as planned |  | 1592.7 | Go Autonomous ApS | 101916 | NBM-060238 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-08 | [6 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting Fiber PM - Delivery proceeding as planned |  | 1592.71 | Go Autonomous ApS | 101916 | NBM-060240 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting Fiber PM - Delivery proceeding as planned |  | 1400 | Go Autonomous ApS | 101916 | NKA-060237 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-07 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 1.3 Customer requested delay / change of timeline or site not ready | Awaiting Fiber PM - Delivery proceeding as planned |  | 1400 | Go Autonomous ApS | 101916 | NKA-060239 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-03 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-07 |  |  |  |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track - in production at 3. party |  | 1140 | Hoffmann Professional A/S | 105172 | NKA-060438 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party | 2025-04-30 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track - in production at 3. party |  | 230 | Hoffmann Professional A/S | 105172 | NMA-060439 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track - in production at 3. party |  | 230 | Hoffmann Professional A/S | 105172 | NSW-060440 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.4 Other installation obstacles and infratructure issues | Peding Sales, and finilaizing of installation (Netteam) Handed over to Martin Ramsussen. |  | 14438.31 | I/S Ugebladsdistribution | 98963 | NBM-056549 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2024-09-30 | 2025-06-27 | 2025-06-27 | 3rd Party | 2024-10-31 |  |  |  |  | 2025-03-31 | 2025-05-07 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 1629 | Imerco A/S | 102528 | NKA-058919 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-02-13 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-03-07 |  |  | 2025-05-30 |  |  |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 979 | Imerco A/S | 103321 | NKA-060453 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2025-04-24 | 2025-05-30 | 2025-05-30 | Own with Digging | 2025-04-24 | 2025-05-01 07:59:00.000 | 2025-04-29 13:03:00.000 | 2025-05-30 |  | 2025-05-16 | 2025-05-09 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Waiting for delivery of fiber |  | 979 | Imerco A/S | 93095 | NKA-052428 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-07-18 | 2025-07-18 | 3rd Party |  |  | 2024-01-03 07:45:00.000 |  |  |  | 2025-05-02 | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Waiting for delivery of fiber |  | 979 | Imerco A/S | 93095 | NKA-052430 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-28 | 2025-05-28 | 3rd Party |  |  |  | 2025-05-30 |  |  | 2025-05-23 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Waiting for delivery of fiber |  | 979 | Imerco A/S | 93095 | NKA-052431 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party |  |  | 2024-01-27 18:31:00.000 |  |  |  | 2025-05-02 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 979 | Imerco A/S | 93095 | NKA-052432 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-22 |  |  | 2025-06-13 |  | 2025-06-03 | 2025-04-29 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | 3. party hasn't delivered the fiber on time |  | 979 | Imerco A/S | 93095 | NKA-052436 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-07-04 | 2025-07-04 | 3rd Party |  |  |  | 2025-07-11 |  |  | 2025-03-25 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1.1 Pending external 3rd party: Open-Net | Can't order in OpenNet |  | 979 | Imerco A/S | 93095 | NKA-052440 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-08-08 | 2025-08-08 | 3rd Party | 2025-05-20 |  |  | 2025-08-08 |  | 2025-07-29 |  | 2025-08-08 | 2025-08-08 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1.1 Pending external 3rd party: Open-Net | Can't order in OpenNet |  | 979 | Imerco A/S | 93095 | NKA-052441 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 979 | Imerco A/S | 93095 | NKA-052451 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-03-10 |  |  | 2025-05-23 |  | 2025-05-16 | 2025-05-05 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 1.Order entry and validation | 3.1.1 Pending external 3rd party: Open-Net | Can't order in OpenNet |  | 979 | Imerco A/S | 93095 | NKA-052454 |  | Nanna Søndergaard Skov | SMB Portfolio DK | In Process | 2023-12-21 | 2025-05-30 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | Waiting for netplan |  | 1185 | Inco Svendborg Slagtehus A/S | 105563 | NKA-060611 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-05-06 | 2025-05-16 09:38:00.000 |  | 2025-06-20 |  | 2025-07-25 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed |  |  | 695 | India Royale ApS | 104999 | NKA-060320 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-14 | 2025-05-15 14:41:00.000 | 2025-05-19 12:48:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 150 | India Royale ApS | 104999 | NMA-060322 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-14 |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 150 | India Royale ApS | 104999 | NSW-060321 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-09 | 2025-06-13 | 2025-06-13 | Own OnNet | [7 empty] | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.4 Other installation obstacles and infratructure issues | Awaiting SW/Installation execution |  | 2440 | Intech | 103238 | NBM-060096 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-04-02 |  |  | 2025-05-09 |  | 2025-05-09 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.4 Other installation obstacles and infratructure issues | Awaiting SW/Installation execution |  | -2416.06 | Intech | 103238 | NOC-997264 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-31 | 2025-06-20 | 2025-06-20 | Change |  |  |  | 2025-05-09 |  |  |  | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 995 | i-team Danmark ApS | 105696 | NKA-060722 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 150 | i-team Danmark ApS | 105696 | NMA-060723 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-05-13 |  |  |  |  | 2025-07-04 |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed |  |  | 150 | i-team Danmark ApS | 105696 | NSW-060724 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-13 | 2025-07-04 | 2025-07-04 | Own OnNet | [7 empty] | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
[6 empty] | 592 | Kirkbi Invest A/S | 105894 | NKA-060854 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-05-22 |  |  | Own OnNet
[6 empty] | 592 | Kirkbi Invest A/S | 105894 | NML-060855 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-05-22 |  |  | 3rd Party
|  | 7. Service activation | 2.6 Order in queue: Being processed | Expedite - Waiting for service window |  | 1395 | Kontorfællesskabet Wilders Plads ApS | 105521 | NKA-060646 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-08 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-05-09 | 2025-05-22 11:25:00.000 | 2025-05-22 13:53:00.000 | 2025-05-30 |  | 2025-06-27 |  | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 829.13 | Lise Frandsen ApS | 105407 | NBM-060606 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-08 |  |  | 2025-05-28 |  | 2025-05-30 |  | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 83.12 | Lise Frandsen ApS | 105407 | NKA-025349 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-05-30 | 2025-05-30 | Change | 2018-08-14 |  |  | 2025-05-28 |  |  |  | 2025-05-30 | 2025-05-30 |  |  | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 2120 | Lokal Forsikring G/S | 91200 | NKA-052835 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-23 10:01:00.000 | 2024-02-23 10:01:00.000 |  |  |  |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 2120 | Lokal Forsikring G/S | 91200 | NKA-052836 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own with Digging | 2024-01-25 | 2024-02-23 10:01:00.000 | 2024-02-23 10:01:00.000 |  |  | 2024-03-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052837 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party | 2024-01-25 |  | 2025-05-12 12:52:00.000 |  |  | 2024-03-20 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052838 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-01-26 13:32:00.000 | 2024-01-26 13:32:00.000 | 2024-03-07 |  | 2024-02-16 | 2024-07-15 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052839 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-03-11 | 2024-03-20 11:12:00.000 | 2024-03-20 11:14:00.000 |  |  | 2024-05-24 | 2025-02-21 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052840 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-19 07:45:00.000 | 2024-02-19 07:45:00.000 |  |  | 2024-03-22 | 2025-02-18 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052841 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052842 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | 3rd Party | 2024-01-25 |  | 2025-05-12 12:48:00.000 |  |  |  | 2025-03-24 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052843 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | 3rd Party | 2024-01-25 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 970 | Lokal Forsikring G/S | 91200 | NKA-052844 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | 2024-01-25 | 2024-02-28 07:25:00.000 | 2024-02-28 07:25:00.000 | 2024-03-18 |  | 2024-03-15 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 825 | Lokal Forsikring G/S | 91200 | NSW-052845 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 825 | Lokal Forsikring G/S | 91200 | NSW-052846 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052847 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052848 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052849 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052850 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052851 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052852 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-06-27 | 2025-06-27 | Own OnNet | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052853 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 530 | Lokal Forsikring G/S | 91200 | NSW-052854 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2024-01-10 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052845 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052847 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052848 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052849 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052850 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052851 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052852 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052853 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Overleveret til Natascha |  | 390 | Lokal Forsikring G/S | 98237 | NSW-052854 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-18 |  |  | Change | [11 empty] | Change | BO
|  | 3. Installation preparation and digging order | 1.2 Customer not reachable / unresponsive | Waiting on customer on this lokation |  | 662 | Lomax A/S | 102189 | NBM-059710 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.4 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange |  | 950 | Lomax A/S | 102189 | NBM-059711 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.4 Other installation obstacles and infratructure issues | Long lead time on MLAN equitment is the main challange |  | 950 | Lomax A/S | 102189 | NBM-059712 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 4. Final design | 1.3 Customer requested delay / change of timeline or site not ready | Kunden vil have en tegning på ekstra switch i forbindelse med redundans - det påvirker leverancen for fiber |  | 2580.06 | Lomax A/S | 102189 | NBM-059713 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | [7 empty] | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready | Kunden vil have en tegning på ekstra switch i forbindelse med redundans - det påvirker leverancen for fiber |  | 2747.5 | Lomax A/S | 102189 | NKA-059706 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | 2025-03-11 | 2025-03-17 10:21:00.000 | 2025-03-31 14:14:00.000 | 2025-05-01 |  | 2025-05-02 | 2025-04-09 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 1.3 Customer requested delay / change of timeline or site not ready | Kunden vil have en tegning på ekstra switch i forbindelse med redundans - det påvirker leverancen for fiber |  | 2747.5 | Lomax A/S | 102189 | NKA-059707 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | Own OnNet | 2025-03-11 | 2025-03-17 10:21:00.000 | 2025-03-31 14:15:00.000 | 2025-05-01 |  | 2025-05-02 | 2025-04-09 | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 8. Ready for service | 2.3 Internal resource constraints (e.g., no one to work on the order) | Fiber ready but firewall not ready yet |  | 2550 | Lomax A/S | 102189 | NKA-059709 |  | Jeppe Mutinda Mbinda | SMB Portfolio DK | In Process | 2025-03-11 | 2025-08-29 | 2025-08-29 | 3rd Party | 2025-03-12 |  |  | 2025-05-07 |  | 2025-04-10 |  | 2025-08-29 | 2025-08-29 |  |  | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 1245 | LUTHERSK MISSIONSFORENING | 102804 | NKA-059162 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own with Digging | 2025-03-19 | 2025-04-29 11:04:00.000 | 2025-05-13 14:28:00.000 | 2025-06-06 |  | 2025-06-06 | 2025-05-20 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 225 | LUTHERSK MISSIONSFORENING | 102804 | NMA-059163 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-05-01 |  |  |  |  | 2025-06-13 | 2025-05-20 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Awaiting design and network plan before req for configuration - Delivery proceeding as planned |  | 225 | LUTHERSK MISSIONSFORENING | 102804 | NSW-059164 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-06-13 | 2025-06-13 | Own OnNet | [6 empty] | 2025-05-20 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 600 | Macarons Design I/S | 103494 | NBM-059950 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party |  |  |  | 2025-05-30 |  | 2025-06-20 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  | 200 | Macarons Design I/S | 103494 | NMA-059948 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | 3rd Party | 2025-04-03 |  |  |  |  | 2025-06-20 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  | 200 | Macarons Design I/S | 103494 | NSW-059949 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 5. Configuration | 2.4 Pending equipment/product to be ready for installations |  |  | 895 | Mano Event ApS | 100141 | NKA-059654 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-06-06 | 2025-06-06 | Own with Digging | 2025-03-13 | 2025-04-10 06:58:00.000 | 2025-05-01 14:02:00.000 | 2025-05-30 |  | 2025-06-06 | 2025-05-07 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect |  |  | 150 | Mano Event ApS | 100141 | NMA-059656 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-04-25 |  |  |  |  | 2025-05-30 | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect |  |  | 150 | Mano Event ApS | 100141 | NSW-059655 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-07 | 2025-05-30 | 2025-05-30 | Own OnNet | [6 empty] | 2025-05-07 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 895 | Møbelkompagniet ApS | 104652 | NKA-060045 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-04-03 | 2025-05-07 10:21:00.000 | 2025-05-15 11:40:00.000 | 2025-06-20 |  | 2025-06-27 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 577.5 | Møbelkompagniet ApS | 104652 | NKA-060048 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-03 |  |  | 2025-06-06 |  | 2025-06-27 | 2025-04-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 180 | Møbelkompagniet ApS | 104652 | NMA-060047 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | 3rd Party | [11 empty] | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 577.5 | Møbelkompagniet ApS | 104652 | NML-060049 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-04-03 |  |  | 2025-06-06 |  |  | 2025-04-28 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Overleveret til Natascha |  | 180 | Møbelkompagniet ApS | 104652 | NSW-060046 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-28 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 7. Service activation | 2.4 Pending equipment/product to be ready for installations |  |  | 600 | NGZC ApS | 105044 | NBM-060260 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-04 |  |  | 2025-05-23 |  | 2025-05-23 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 200 | NGZC ApS | 105044 | NMA-060259 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-04 |  |  |  |  | 2025-05-23 | 2025-05-14 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 200 | NGZC ApS | 105044 | NSW-060258 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-04-04 | 2025-06-13 | 2025-06-13 | Own OnNet | [6 empty] | 2025-05-14 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 1095 | Norrlyst ApS | 104558 | NKA-059937 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | 2025-04-02 | 2025-04-25 09:26:00.000 | 2025-05-05 10:12:00.000 | 2025-05-30 |  | 2025-05-30 | 2025-05-13 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 180 | Norrlyst ApS | 104558 | NMA-059939 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | 3rd Party | 2025-05-05 |  |  |  |  | 2025-05-30 | 2025-05-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 7. Service activation | 2.6 Order in queue: Being processed |  |  | 180 | Norrlyst ApS | 104558 | NSW-059938 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-25 | 2025-05-30 | 2025-05-30 | Own OnNet | [6 empty] | 2025-05-14 | 2025-05-30 | 2025-05-30 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.1 Order forgotten, but back on track to be processed | Awaiting production at 3. party |  | 1149 | NOVARAM ApS | 100681 | NKA-059024 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-02-21 | 2025-09-02 | 2025-05-02 | 3rd Party | 2025-04-23 |  |  | 2025-06-27 |  |  | 2025-02-26 | 2025-05-02 | 2025-05-02 | 2025-09-02 |  | New Sales | BO
|  | 4. Final design |  |  |  | 1095 | Optinor ApS | 103352 | NKA-060551 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-27 | 2025-06-27 | Own with Digging | 2025-05-01 | 2025-05-21 08:04:00.000 |  | 2025-06-20 |  | 2025-07-11 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 4. Final design |  |  |  | 200 | Optinor ApS | 103352 | NMA-060553 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-27 | 2025-06-27 | 3rd Party | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 4. Final design |  |  |  | 200 | Optinor ApS | 103352 | NSW-060552 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-01 | 2025-06-27 | 2025-06-27 | Own OnNet | [7 empty] | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1095 | Psykologhuset Trekanten ApS | 104667 | NKA-059980 |  | Peter Madsen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-05-28 | 2025-05-28 | Own OnNet | 2025-03-27 | 2025-04-22 14:10:00.000 | 2025-05-08 10:31:00.000 | 2025-05-30 |  | 2025-06-13 | 2025-05-08 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | OBS. sælger lovet expidite uden salg |  | 1410 | Radiant ApS | 105341 | NBM-060525 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-06 | 2025-06-06 | 3rd Party | 2025-05-01 |  |  | 2025-06-02 |  | 2025-06-20 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | OBS. sælger lovet expidite uden salg |  | 1195 | Radiant ApS | 105341 | NKA-060526 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-04-29 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-05-02 | 2025-05-05 14:18:00.000 | 2025-05-08 12:18:00.000 | 2025-05-30 |  | 2025-06-20 | 2025-05-19 | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afv tekniker |  | 1695 | Raw Power Games ApS | 97083 | NKA-055484 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2024-07-01 | 2025-06-13 | 2025-06-13 | 3rd Party | 2024-08-27 |  |  | 2025-06-06 |  |  | 2025-05-13 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
[6 empty] | 1693 | Reversec Denmark A/S | 105807 | NKA-060791 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-16 |  |  | Own OnNet | [5 empty] | 2025-07-11 | [5 empty] | New Sales | BO
[6 empty] | 300 | Reversec Denmark A/S | 105807 | NMA-060793 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-16 |  |  | 3rd Party | [5 empty] | 2025-07-11 | [5 empty] | New Sales | BO
[6 empty] | 300 | Reversec Denmark A/S | 105807 | NSW-060792 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-16 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On-track |  | 700 | salting & dyrby ApS | 104811 | NKA-060426 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-05-23 | [5 empty] | 2025-05-23 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On-track |  | 700 | salting & dyrby ApS | 104811 | NML-060427 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-04-22 | 2025-06-13 | 2025-06-13 | 3rd Party | 2025-04-23 |  |  |  |  | 2025-06-13 | 2025-05-23 | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track. Pending delivery/sign off. |  | 1944 | Skousen NO | 100710 | NKA-057251 |  | Peter Madsen | SMB Portfolio DK | In Process | 2024-11-08 | 2025-07-31 | 2025-04-25 | 3rd Party | [5 empty] | 2025-05-01 | 2025-02-13 | 2025-04-25 | 2025-04-25 | 2025-07-31 | 2025-04-08 00:00:00.000 | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed |  |  | 1355 | Stavnskær Fragt A/S | 105016 | NKA-060603 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-05 | 2025-07-25 | 2025-07-25 | Own OnNet | 2025-05-06 | 2025-05-07 12:27:00.000 | 2025-05-14 14:42:00.000 | 2025-06-06 |  | 2025-07-25 | 2025-05-20 | 2025-07-25 | 2025-07-25 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.4 Pending equipment/product to be ready for installations | Order is on track |  | 4051 | STRATU ApS | 106547-008 | F35739-1136632-01 | 106547-008-001 | Cecilie Heidner Nielsen | SMB Portfolio DK | Created | 2025-04-30 | 2025-06-06 | 2025-06-06 | Own OnNet |  |  |  | 2025-05-30 |  | 2025-07-22 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | New Sales | AX
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaiting IP VPN for cloud access |  | 695 | Taconic Biosciences A/S | 104948 | NCI-060727 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaiting IP VPN for cloud access |  | 1700 | Taconic Biosciences A/S | 104948 | NKA-060725 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | 2025-05-16 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input | Awaiting IP VPN for cloud access |  | 1700 | Taconic Biosciences A/S | 104948 | NML-060726 |  | Jesper Olsen | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 1909.46 | Vaekst ApS | 101973 | NBM-060807 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-05-21 |  |  |  |  | 2025-07-18 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
[6 empty] | 1000 | Vaekst ApS | 101973 | NKA-060806 |  | Signe Fogh Mach Andersen | SMB Portfolio DK | In Process | 2025-05-19 | 2025-07-11 | 2025-07-11 | Own OnNet | 2025-05-21 | 2025-05-21 09:55:00.000 |  |  |  | 2025-07-11 |  | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 1242 | Vækst+ ApS | 104703 | NKA-059996 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-06 | 2025-06-06 | Own OnNet | 2025-04-08 | 2025-04-09 09:05:00.000 | 2025-05-08 07:27:00.000 | 2025-06-02 |  | 2025-05-30 |  | 2025-06-06 | 2025-06-06 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 895 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NKA-059149 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 |  |  | Own OnNet | 2025-03-20 | [10 empty] | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NMA-059151 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | 3rd Party | [7 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
|  | 2. Delivery planning | 1.1 Waiting on customer confirmation or input |  |  | 150 | VESTBO MEDICAL V/JØRGEN VESTBO | 103140 | NSW-059150 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-02-27 | 2025-07-31 | 2025-07-31 | Own OnNet | [7 empty] | 2025-07-31 | 2025-07-31 |  |  | New Sales | BO
[6 empty] | 695 | Windar Photonics A/S | 105828 | NKA-060836 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-21 |  |  | Own OnNet | 2025-05-26 |  |  |  |  | 2025-07-11 | [5 empty] | New Sales | BO
[6 empty] | 150 | Windar Photonics A/S | 105828 | NMA-060838 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-21 |  |  | 3rd Party | [11 empty] | New Sales | BO
[6 empty] | 150 | Windar Photonics A/S | 105828 | NSW-060837 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-21 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 5. Configuration | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing information about JEUDAN |  | 1095 | WOBA ApS | 104677 | NKA-059976 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet | 2025-04-07 | 2025-04-07 10:48:00.000 | 2025-04-24 08:08:00.000 |  |  | 2025-06-06 |  | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing information about JEUDAN |  | 180 | WOBA ApS | 104677 | NMA-059977 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | 3rd Party | 2025-04-07 |  |  |  |  | 2025-06-06 |  | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.5 Internal or external data/documentation incomplete/ incorrect | Missing information about JEUDAN |  | 180 | WOBA ApS | 104677 | NSW-059978 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-03-26 | 2025-06-27 | 2025-05-30 | Own OnNet | [7 empty] | 2025-05-30 | 2025-05-30 | 2025-06-27 |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | -312.19 | Voldgiftsinstituttet | 105411 | NKA-030523 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Change | 2020-05-06 | 2020-05-12 14:32:00.000 | 2020-08-03 10:18:00.000 |  |  | 2020-06-24 |  | 2025-06-20 | 2025-06-20 |  |  | Change | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 200 | Voldgiftsinstituttet | 105411 | NMA-060616 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-05-12 |  |  |  |  | 2025-06-13 |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 5. Configuration | 2.3 Internal resource constraints (e.g., no one to work on the order) | Awaiting SW planning |  | 200 | Voldgiftsinstituttet | 105411 | NSW-060617 |  | Natascha Orlung Baisgaard Andersen | SMB Portfolio DK | In Process | 2025-05-06 | 2025-06-20 | 2025-06-20 | Own OnNet | [7 empty] | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  | 995 | Wolt Services Danmark ApS | 105303 | NKA-060446 |  | Martin Rasmussen | SMB Portfolio DK | In Process | 2025-04-23 | 2025-06-27 | 2025-06-27 | Own OnNet | 2025-04-24 | 2025-05-20 10:47:00.000 | 2025-05-20 10:47:00.000 | 2025-06-20 |  | 2025-06-13 |  | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 597.5 | ADDvision ApS | 102224 | NKA-059275 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-27 | 2025-05-27 | 3rd Party | 2025-03-06 | [5 empty] | 2025-03-13 | 2025-05-27 | 2025-05-27 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | Follow NKA-059275 |  | 597.5 | ADDvision ApS | 102224 | NML-059276 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-03-05 | 2025-05-27 | 2025-05-27 | 3rd Party | 2025-03-06 | [5 empty] | 2025-03-13 | 2025-05-27 | 2025-05-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 2.1 Order forgotten, but back on track to be processed | Afventer opstart af kundens leverance. |  | -4.2 | A-One Solutions ApS | 101317 | NKA-044529 |  | Michael Kronbach Leth | SMB Portfolio DK | In Process | 2024-12-03 |  |  | Change | 2022-09-15 | 2022-12-30 11:10:00.000 | 2022-12-30 11:10:00.000 | [8 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 597.5 | Basic & More A/S | 105734 | NKA-060730 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | 2025-05-19 | [10 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Follow NKA-060730 |  | 597.5 | Basic & More A/S | 105734 | NML-060731 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 |  |  | 3rd Party | 2025-05-19 | [10 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 2200 | DANSK CAMPING UNION | 102100 | NKA-058445 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-01-17 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  | 2025-06-19 |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 2100 | DANSK CAMPING UNION | 102499 | NKA-058785 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-02-05 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 2100 | DANSK CAMPING UNION | 103124 | NKA-059177 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-02-28 | 2025-07-01 | 2025-07-01 | Own OnNet | 2025-03-03 |  |  | 2025-05-19 |  | 2025-06-04 |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track, Fibia leverer 4/6 |  |  | Dansk Miljørådgivning A/S (DMR Geoteknik, DMR Skimmel & DMR Arbejdsmiljø) | 103430 | NKA-014092 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-11 | 2025-06-13 | 2025-06-13 | Change | 2025-04-07 |  |  |  |  | 2025-05-09 | 2025-04-10 | 2025-06-13 | 2025-06-13 |  |  | Change | BO
|  | 6. Cabling splicing and installation |  |  |  | 475 | Forsvarsministeriets Ejendomsstyrelse | 103026 | NKA-059934 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-25 | 2025-06-13 | 2025-06-13 | Own OnNet | 2025-04-04 | 2025-04-30 12:51:00.000 | 2025-05-16 09:54:00.000 | 2025-06-13 |  | 2025-06-13 |  | 2025-06-13 | 2025-06-13 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer leveringsdato fra 3.part |  | 845 | Forsvarsministeriets Ejendomsstyrelse | 103320 | NKA-060338 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-04-10 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-04-22 |  | 2025-04-11 07:29:00.000 |  |  |  |  | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 1.1 Waiting on customer confirmation or input | Awaits power supply in the shop |  | 2500 | Ganni A/S | 100380 | NKA-057859 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2024-12-13 | 2025-12-31 | 2025-12-31 | 3rd Party | 2024-12-13 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 597.5 | Hildebrandt & Brandi Danmark A/S | 103074 | NKA-059851 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-07-04 | 2025-07-04 | Own OnNet | 2025-03-27 | 2025-04-03 08:49:00.000 | 2025-04-07 10:20:00.000 | 2025-06-27 |  | 2025-05-16 | 2025-04-08 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed | On track |  | 597.5 | Hildebrandt & Brandi Danmark A/S | 103074 | NML-059852 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-07-04 | 2025-07-04 | 3rd Party | 2025-03-27 |  |  | 2025-06-27 |  | 2025-05-16 | 2025-04-08 | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | on track |  | 1310 | Hudklinik v/Henrik Rask Kralund | 103099 | NKA-060073 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-28 | 2025-06-27 | 2025-06-27 | 3rd Party | 2025-04-08 |  |  | 2025-06-20 |  | 2025-06-11 | 2025-05-01 | 2025-06-27 | 2025-06-27 |  |  | New Sales | BO
|  | 2. Delivery planning | 3.1.1 Pending external 3rd party: Open-Net |  |  | 1555 | Ingeniør Huse A/S | 105821 | NKA-060802 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-19 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  | 3. Installation preparation and digging order | 2.3 Internal resource constraints (e.g., no one to work on the order) | Afventer leveringsdato |  | 597.5 | Koppers Denmark ApS | 101089 | NKA-059858 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-12-31 | 2025-12-31 | Own OnNet | 2025-03-27 |  |  |  |  | 2025-05-16 | 2025-04-04 | 2025-12-31 | 2025-12-31 |  |  | New Sales | BO
|  | 8. Ready for service | 2.3 Internal resource constraints (e.g., no one to work on the order) | Fast track, NML er sendt til billing |  | 597.5 | Koppers Denmark ApS | 101089 | NML-059859 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-20 | 2025-12-31 | 2025-12-31 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-05-16 | 2025-04-04 | 2025-12-31 | 2025-12-31 |  | 2025-04-22 00:00:00.000 | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 1895 | Lelectric A/S | 102363 | NKA-060451 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-04-23 | 2025-07-09 | 2025-07-09 | 3rd Party | 2025-04-28 |  |  | 2025-07-04 |  |  | 2025-05-05 | 2025-07-09 | 2025-07-09 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track, installation uge 29 |  | 2255 | Moldow A/S | 105337 | NKA-060471 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-04-25 | 2025-07-18 | 2025-07-18 | 3rd Party | 2025-05-01 |  |  | 2025-07-11 |  | 2025-07-18 | 2025-05-19 | 2025-07-18 | 2025-07-18 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | On track |  | 1495 | Møgelhøj Arkitekter P/S | 102749 | NKA-058872 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-02-11 | 2025-06-20 | 2025-06-20 | 3rd Party | 2025-02-17 |  |  | 2025-06-13 |  | 2025-04-16 | 2025-02-26 | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Stille awating final date for delivery |  | 1300 | Naturstyrelsen | 100652 | NKA-057903 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-12-16 | 2025-07-11 | 2025-07-11 | 3rd Party | 2025-03-05 |  |  | 2025-07-11 |  | 2025-04-24 | 2025-03-18 | 2025-07-11 | 2025-07-11 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Confirmed delivery |  | 1300 | Naturstyrelsen | 100652 | NKA-057905 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-12-16 | 2025-06-29 | 2025-06-29 | 3rd Party | 2025-03-05 |  |  | 2025-08-25 |  | 2025-04-23 | 2025-03-25 | 2025-06-29 | 2025-06-29 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Nr. Snede Fængsel | 103616 | NKA-004029 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change | 2013-03-18 |  |  | 2025-06-04 | [7 empty] | Change | BO
|  |  |  | Part of migration project |  | 0 | Nr. Snede Fængsel | 103616 | NKA-005319 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-17 |  |  | Change |  |  |  | 2025-06-10 | [7 empty] | Change | BO
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Deleyed due to local restriction on site |  | 1100 | Skive Kommune | 94395 | NKA-054245 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-04-29 | 2025-07-07 | 2025-07-07 | 3rd Party | 2024-06-07 |  |  | 2025-06-30 |  | 2024-08-15 | 2024-07-01 | 2025-07-07 | 2025-07-07 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 103416 | NKA-059719 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-03-11 | 2025-07-04 | 2025-07-04 | 3rd Party |  |  |  | 2025-06-27 |  |  |  | 2025-07-04 | 2025-07-04 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060326 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060327 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060328 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060329 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-19 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060330 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060331 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060332 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 |  |  | Own OnNet | [11 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 105145 | NKA-060333 |  | Morten Skytte | SMB Portfolio DK | In Process | 2025-04-09 | 2025-07-01 | 2025-07-01 | 3rd Party |  |  |  | 2025-06-23 |  |  |  | 2025-07-01 | 2025-07-01 |  |  | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 98971 | NKA-056784 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-10-14 |  |  | 3rd Party | 2024-11-05 |  |  | 2024-12-16 |  | 2025-01-15 | [5 empty] | New Sales | BO
|  |  |  | Part of migration project |  | 0 | Telenor A/S | 99904 | NKA-056783 |  | Morten Skytte | SMB Portfolio DK | In Process | 2024-10-14 |  |  | 3rd Party | 2024-11-05 |  |  | 2024-12-16 |  | 2025-01-15 | [5 empty] | New Sales | BO
|  | 5. Configuration | 2.6 Order in queue: Being processed | On track, installation uge 30 |  | 995 | Unicontrol ApS | 102597 | NKA-059967 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | Own OnNet | 2025-03-27 | 2025-03-28 07:11:00.000 | 2025-05-15 12:41:00.000 | 2025-07-25 |  | 2025-05-16 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 200 | Unicontrol ApS | 102597 | NMA-059968 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | 3rd Party | 2025-03-27 |  |  |  |  | 2025-05-16 |  | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 4. Final design | 2.6 Order in queue: Being processed | On track |  | 200 | Unicontrol ApS | 102597 | NSW-059969 |  | Eva Eisner | SMB Portfolio DK | In Process | 2025-03-25 | 2025-08-01 | 2025-08-01 | Own OnNet | [7 empty] | 2025-08-01 | 2025-08-01 |  |  | New Sales | BO
|  | 3. Installation preparation and digging order | 2.6 Order in queue: Being processed | On track |  | 1200 | VICURAS DK A/S | 105621 | NKA-060728 |  | Jane Birgitte Høgaard | SMB Portfolio DK | In Process | 2025-05-14 | 2025-06-20 | 2025-06-20 | Own OnNet | 2025-05-14 | 2025-05-23 13:29:00.000 |  | 2025-06-13 |  |  |  | 2025-06-20 | 2025-06-20 |  |  | New Sales | BO
[7 empty] | Home.Earth Nærheden ApS | 101420 | NKA-057955 |  | Christoffer Møller Andersen |  | In Process | 2024-12-18 | 2025-05-09 | 2025-05-09 | 3rd Party | 2025-01-07 |  |  |  | 2025-04-30 |  | 2025-02-01 | 2025-05-09 | 2025-05-09 |  |  | New Sales | BO
[7 empty] | Home.Earth Nærheden ApS | 101420 | NKA-057956 |  | Christoffer Møller Andersen |  | In Process | 2024-12-18 | 2025-05-09 | 2025-05-09 | 3rd Party | 2025-01-07 |  |  |  | 2025-04-30 |  | 2025-02-01 | 2025-05-09 | 2025-05-09 |  |  | New Sales | BO
[7 empty] | Truckplanner A/S | 105461 | NKA-060623 |  | Christoffer Møller Andersen |  | In Process | 2025-05-06 | 2025-05-16 | 2025-05-16 | Own OnNet
|  | 3. Installation preparation and digging order | 3.1 Pending external 3rd party: Any 3rd party | Afventer TDC klarmelder |  |  | Ejendomsselskabet Lyngby Hovedgade 78 ApS | 99947 | NKA-056809 |  | Christoffer Møller Andersen |  | In Process | 2024-10-15 | 2025-06-13 | 2025-06-13 | 3rd Party
[7 empty] | Two Degrees Properties Nordhavn ApS | 98197 | NKA-057536 |  | Flemming Skovdal |  | In Process | 2024-11-25 | 2025-06-30 | 2025-06-30 | Own with Digging | 2024-11-26 | 2025-01-27 13:17:00.000 | 2025-01-29 13:44:00.000 | 2025-04-22 | 2025-05-22 | 2025-02-21 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[7 empty] | Redhavnskvarteret Holding ApS | 98198 | NKA-057538 |  | Flemming Skovdal |  | In Process | 2024-11-25 | 2025-06-30 | 2025-06-30 | Own with Digging | 2024-11-26 | 2025-01-27 12:55:00.000 | 2025-01-29 12:47:00.000 | 2025-04-22 | 2025-05-22 | 2025-02-21 |  | 2025-06-30 | 2025-06-30 |  |  | New Sales | BO
[7 empty] | alles Lægehus A/S | 102225 | NKA-058577 |  | Kristijan Krsteski |  | In Process | 2025-01-23 | 2025-04-03 | 2025-04-03 | 3rd Party | 2025-03-05 |  |  | 2025-04-03 | 2025-04-03 |  | 2025-03-27 | 2025-04-03 | 2025-04-03 |  | 2025-04-23 17:11:00.000 | New Sales | BO
[7 empty] | I/S Ugebladsdistribution | 98610 | NKA-056540 |  | Martin Rasmussen |  | In Process | 2024-09-30 | 2025-02-17 | 2024-11-29 | Own OnNet | 2024-10-08 | 2024-10-10 13:24:00.000 | 2024-10-29 13:06:00.000 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2025-02-21 | 2024-11-29 | 2024-11-29 | 2025-02-17 |  | New Sales | BO
[7 empty] | I/S Ugebladsdistribution | 98610 | NML-056541 |  | Martin Rasmussen |  | In Process | 2024-09-30 | 2025-02-17 | 2024-11-29 | 3rd Party | 2024-10-08 |  |  | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2025-02-21 | 2024-11-29 | 2024-11-29 | 2025-02-17 |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Fejlmeldt til TDC-afventer |  |  | Suaning Import | 102078 | NKA-058362 |  | Merete Helme |  | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-02-12 |  |  |  | 2025-05-22 |  | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Fejlmeldt til TDC-afventer |  |  | Suaning Import | 102078 | NMA-058364 |  | Merete Helme |  | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | 3rd Party | 2025-02-12 |  |  |  | 2025-05-22 |  | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 3.1 Pending external 3rd party: Any 3rd party | Fejlmeldt til TDC-afventer |  |  | Suaning Import | 102078 | NSW-058363 |  | Merete Helme |  | In Process | 2025-01-14 | 2025-05-23 | 2025-05-23 | Own OnNet |  |  |  |  | 2025-05-22 |  | 2025-04-10 | 2025-05-23 | 2025-05-23 |  |  | New Sales | BO
|  | 6. Cabling splicing and installation | 2.6 Order in queue: Being processed |  |  |  | Allunite A/S | 102186 | NKA-058524 |  | Merete Helme |  | In Process | 2025-01-21 | 2005-06-06 | 2005-06-06 | Own OnNet | 2025-02-06 | 2025-02-28 14:04:00.000 | 2025-03-18 08:27:00.000 | 2025-05-23 | 2025-05-23 | 2025-03-28 | 2025-05-08 | 2005-06-06 | 2005-06-06 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  |  | Keepers ApS | 102583 | NKA-059116 |  | Merete Helme |  | In Process | 2025-02-26 | 2025-06-03 | 2025-06-03 | Own OnNet | 2025-03-03 | 2025-03-19 13:20:00.000 | 2025-04-10 10:51:00.000 | 2025-05-20 | 2025-05-22 | 2024-04-25 |  | 2025-06-03 | 2025-06-03 |  |  | New Sales | BO
[7 empty] | Skive Kommune | 81372 | NKA-043482 |  | Morten Skytte |  | In Process | 2022-06-30 | 2024-09-10 | 2024-09-10 | Own with Digging | 2023-02-13 | 2023-04-13 09:37:00.000 | 2023-04-13 09:38:00.000 | 2023-05-25 | 2024-09-10 | 2023-05-19 | 2023-10-23 | 2024-09-10 | 2024-09-10 |  | 2023-06-30 00:00:00.000 | New Sales | BO
|  | 8. Ready for service | 3.4 Other installation obstacles and infratructure issues | CUSTOMER |  |  | Labelless Media ApS | 101484 | NBM-058251 |  | Natascha Orlung Baisgaard Andersen |  | In Process | 2025-01-07 | 2025-05-20 | 2025-05-20 | 3rd Party | 2025-01-07 |  |  | 2025-05-09 | 2025-05-22 | 2025-02-28 | 2025-04-15 | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
[7 empty] | Labelless Media ApS | 101484 | NKA-058250 |  | Natascha Orlung Baisgaard Andersen |  | In Process | 2025-01-07 | 2025-05-09 | 2025-05-09 | Own OnNet | 2025-01-07 | 2025-01-27 06:47:00.000 |  | 2025-05-01 | 2025-05-01 | 2025-02-28 | 2025-04-29 | 2025-05-09 | 2025-05-09 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  |  | Labelless Media ApS | 101484 | NMA-058253 |  | Natascha Orlung Baisgaard Andersen |  | In Process | 2025-01-07 | 2025-05-20 | 2025-05-20 | 3rd Party | 2025-01-07 |  |  |  | 2025-05-22 | 2025-02-28 | 2025-04-29 | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
|  | Delivered | Delivered |  |  |  | Labelless Media ApS | 101484 | NSW-058252 |  | Natascha Orlung Baisgaard Andersen |  | In Process | 2025-01-07 | 2025-05-20 | 2025-05-20 | Own OnNet |  |  |  |  | 2025-05-22 |  | 2025-04-29 | 2025-05-20 | 2025-05-20 |  |  | New Sales | BO
[7 empty] | Macarons Design I/S | 103494 | NKA-059947 |  | Natascha Orlung Baisgaard Andersen |  | In Process | 2025-03-25 | 2025-05-28 | 2025-05-28 | Own with Digging | 2025-04-01 | 2025-04-10 08:03:00.000 | 2025-04-29 10:56:00.000 | 2025-05-15 | 2025-05-15 | 2025-06-20 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  |  | New Sales | BO