## Step Metrics Summary
Step | Avg Days in Step | Avg Orders per Day | Avg MRC per Day | 0.13408
1. Order entry and validation | 0 | 0 | 0 | 0
1.9 PMO delivery planning | 7.68 | 351.38 | 325347.35 | 43.6222
2. Delivery planning | 7.22 | 387.38 | 406045.78 | 54.4421
3. Installation preparation and digging order | 6.52 | 277.88 | 303828.2 | 40.7369
4. Final design | 6.13 | 65.12 | 64875.5 | 8.6984
5. Configuration | 5.45 | 260.38 | 259526.64 | 34.797
6. Cabling splicing and installation | 6.47 | 335.88 | 393104.25 | 52.707
7. Service activation | 7.13 | 68.62 | 65223 | 8.745
8. Ready for service | 5.79 | 37.62 | 48438.14 | 6.4945
9. Vendor invoice | 0 | 0 | 0 | 0
Delivered | 2.72 | 111.25 | 66656.75 | 8.9373
Cancelled/terminated/On hold | 3.16 | 26.88 | 30222.39 | 4.0522
Data as of 20250519 - 20250526

## Step Entry-Exit Summary
Step | Entered | Stayed | Exited
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 0 | 339 | 27
2. Delivery planning | 5 | 331 | 93
3. Installation preparation and digging order | 25 | 247 | 70
4. Final design | 23 | 45 | 16
5. Configuration | 80 | 212 | 90
6. Cabling splicing and installation | 50 | 306 | 57
7. Service activation | 1 | 72 | 4
8. Ready for service | 18 | 32 | 9
9. Vendor invoice | 0 | 0 | 0
Delivered | 153 | 173 | 1
Cancelled/terminated/On hold | 10 | 58 | 1
Interval between T1 and T2: 20250519 - 20250526

## DPM Avg Orders per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 9 | 2 | 0 | 3 | 7 | 0 | 1 | 0 | 0 | 0.88
Camilla Olesen | 0 | 0 | 2 | 0.75 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 6 | 1.5 | 2 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 6.5 | 0 | 27 | 2.5 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 50 | 7 | 3 | 10.38 | 7.25 | 2.62 | 1.25 | 0 | 4 | 0
Eva Eisner | 0 | 0 | 0 | 5 | 5.25 | 1.62 | 7.25 | 0 | 1.5 | 0 | 4.75 | 0.75
Flemming Skovdal | 0 | 2.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0
Henrik Møller Fyhn | 0 | 0 | 2 | 6 | 2 | 41.88 | 46.62 | 0.75 | 0.88 | 0 | 3.38 | 15.75
Jane Birgitte Høgaard | 0 | 0 | 16 | 24.75 | 0.75 | 68.12 | 6.5 | 0 | 2 | 0 | 46.62 | 0
Jeppe Mutinda Mbinda | 0 | 13.5 | 51.5 | 1 | 1 | 9.5 | 8 | 0 | 5.5 | 0 | 14.5 | 0
Jesper Olsen | 0 | 0 | 3 | 6 | 6 | 2 | 15.88 | 0 | 0.62 | 0 | 0 | 0.25
Julie Lillethorup Kierkegaard | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 55.62 | 0.38 | 0 | 0 | 35.5 | 3 | 0 | 0 | 1 | 1
Line Skov | 0 | 0 | 1.25 | 32.88 | 13.5 | 4.5 | 35.88 | 0 | 0.12 | 0 | 8.5 | 1
Martin Rasmussen | 0 | 0 | 22.75 | 0 | 0 | 0.75 | 10.5 | 0 | 0 | 0 | 1.25 | 0
Merete Helme | 0 | 0 | 15.38 | 21 | 5.25 | 9.88 | 40 | 0.5 | 0.75 | 0 | 5.62 | 2.62
Mette Vinther | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 83.25 | 63.62 | 7.38 | 32.12 | 31.38 | 12 | 0.25 | 0 | 1.12 | 0
Morten Skytte | 0 | 0 | 15 | 9 | 1 | 3.25 | 7.5 | 2 | 21.25 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 331.25 | 9 | 31.62 | 6.62 | 10.5 | 19 | 4.25 | 0.75 | 0 | 4.25 | 1.25
Natascha Orlung Baisgaard Andersen | 0 | 0 | 3.88 | 14 | 6.5 | 17.5 | 7 | 37.5 | 1.62 | 0 | 7.25 | 0
Peter Madsen | 0 | 0 | 15.75 | 14.12 | 5 | 6 | 26.25 | 4 | 0.12 | 0 | 5.38 | 0.88
Shazia Mobin | 0 | 0 | 26 | 26.5 | 0 | 2.5 | 10 | 0 | 0 | 0 | 3.5 | 0
Signe Fogh Mach Andersen | 0 | 0 | 6 | 4.75 | 1.88 | 3.88 | 6.38 | 0 | 0 | 0 | 0 | 2.5
Data as of 20250519 - 20250526

## DPM Avg MRC per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 23172 | 4550 | 0 | 1453.14 | 11631.2 | 0 | 4130 | 0 | 0 | 2695
Camilla Olesen | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 5096 | 1950 | 0 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 6622.5 | 0 | -6.64 | 10688.5 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 31029.88 | 6122.5 | 1800 | 4418.66 | 7247.09 | 671.25 | 1559.38 | 0 | 3999.25 | 0
Eva Eisner | 0 | 0 | 0 | 3311.88 | 3533.75 | 2168.12 | 4959.38 | 0 | 1045 | 0 | 2983.75 | 398.75
Flemming Skovdal | 0 | 23227.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.07 | 0
Henrik Møller Fyhn | 0 | 0 | 6158 | 14475.5 | 9050 | 30900 | 103913.6 | 373.5 | 1984.38 | 0 | 9825 | 21315.12
Jane Birgitte Høgaard | 0 | 0 | 45633.25 | 35383.75 | 633.75 | 81513.75 | 4631.88 | 0 | 27000 | 0 | 4679.38 | 0
Jeppe Mutinda Mbinda | 0 | 15486.51 | 36979.36 | 662 | 2580.06 | 9421.25 | 9785 | 0 | 6946.25 | 0 | 16610.26 | 0
Jesper Olsen | 0 | 0 | 4095 | 4149 | 6309 | 2650 | 15120.75 | 0 | 468.75 | 0 | 0 | 0
Julie Lillethorup Kierkegaard | 0 | 9506.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 25561 | 285 | 0 | 0 | 11545 | 3833 | 0 | 0 | 487.5 | 560
Line Skov | 0 | 0 | -311.23 | 24470.25 | 14012.5 | 7675.53 | 27130.58 | 0 | 174.38 | 0 | 5145.75 | 1595
Martin Rasmussen | 0 | 0 | 35936.25 | 0 | 0 | 696.5 | 25786.31 | 0 | 0 | 0 | 955 | 0
Merete Helme | 0 | 0 | 10582.67 | 14963.23 | 5053.25 | 11652.75 | 43554.75 | 100 | 388.01 | 0 | 4903.25 | 916.64
Mette Vinther | 0 | 0 | 0 | 93.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 112206.17 | 66608.63 | 5000.31 | 71588.12 | 29365.38 | 0 | 818.75 | 0 | 683.75 | 0
Morten Skytte | 0 | 0 | 7925 | 6460 | 1725 | 6786.49 | 6598.25 | 408.53 | 1649.62 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 277127.5 | 12606 | 27585.62 | 5122.75 | 10253 | 14680.25 | 4986.72 | 653.62 | 0 | 4599.5 | 1002.5
Natascha Orlung Baisgaard Andersen | 0 | 0 | 1195 | 4457 | 2570.75 | -9946.77 | 2550.68 | 37850 | 1400 | 0 | -72.87 | 0
Peter Madsen | 0 | 0 | 30047.45 | 60528.25 | 6550 | 17605 | 32772.7 | 17000 | 220 | 0 | 8655.12 | 864.38
Shazia Mobin | 0 | 0 | 18648.68 | 21389.97 | 0 | 3675.5 | 8395 | 0 | 0 | 0 | 3166.04 | 0
Signe Fogh Mach Andersen | 0 | 0 | 4581.3 | 1709.38 | 934.38 | 1926.24 | 3797.95 | 0 | 0 | 0 | 0 | 875
Data as of 20250519 - 20250526

## DPM Avg Days in Step
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 7
Camilla Olesen | 0 | 0 | 8 | 6 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 8 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 6.5 | 0 | 8 | 6.67 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 8 | 8 | 8 | 7.55 | 7.25 | 5.25 | 5 | 0 | 3.2 | 0
Eva Eisner | 0 | 0 | 0 | 6.67 | 7 | 6.5 | 5.27 | 0 | 6 | 0 | 1.81 | 2
Flemming Skovdal | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Henrik Møller Fyhn | 0 | 0 | 8 | 6.86 | 8 | 7.98 | 5.83 | 3 | 2.33 | 0 | 2.08 | 2.93
Jane Birgitte Høgaard | 0 | 0 | 6.4 | 6.83 | 3 | 5.51 | 5.2 | 0 | 8 | 0 | 2.44 | 0
Jeppe Mutinda Mbinda | 0 | 4 | 7.1 | 8 | 8 | 1.38 | 8 | 0 | 6.29 | 0 | 3.74 | 0
Jesper Olsen | 0 | 0 | 8 | 8 | 8 | 8 | 7.06 | 0 | 5 | 0 | 0 | 2
Julie Lillethorup Kierkegaard | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 7.95 | 1 | 0 | 0 | 7.89 | 8 | 0 | 0 | 2 | 8
Line Skov | 0 | 0 | 5 | 5.98 | 5.4 | 4.5 | 6.24 | 0 | 1 | 0 | 2.52 | 8
Martin Rasmussen | 0 | 0 | 7.28 | 0 | 0 | 2 | 6.46 | 0 | 0 | 0 | 2.5 | 0
Merete Helme | 0 | 0 | 6.47 | 6.72 | 5.25 | 6.08 | 6.4 | 4 | 1.5 | 0 | 3.21 | 3.5
Mette Vinther | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 7.84 | 6.28 | 5.9 | 4.43 | 6.28 | 8 | 1 | 0 | 1.8 | 0
Morten Skytte | 0 | 0 | 8 | 8 | 8 | 6.5 | 6.67 | 3.2 | 7.73 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 7.98 | 8 | 7.44 | 5.89 | 6.46 | 7.24 | 6.8 | 3 | 0 | 2.43 | 2
Natascha Orlung Baisgaard Andersen | 0 | 0 | 7.75 | 7.47 | 5.78 | 7.78 | 5.6 | 7.69 | 6.5 | 0 | 7.25 | 0
Peter Madsen | 0 | 0 | 4.06 | 5.38 | 8 | 8 | 5.83 | 8 | 1 | 0 | 3.91 | 2.33
Shazia Mobin | 0 | 0 | 8 | 7.31 | 0 | 5 | 8 | 0 | 0 | 0 | 2.55 | 0
Signe Fogh Mach Andersen | 0 | 0 | 3.69 | 3.17 | 5 | 3.88 | 5.67 | 0 | 0 | 0 | 0 | 5
Data as of 20250519 - 20250526

## 1.9 PMO delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Flemming Skovdal | 0 | 3 | 0
Jeppe Mutinda Mbinda | 0 | 0 | 27
Julie Lillethorup Kierkegaard | 0 | 4 | 0
Nanna Søndergaard Skov | 0 | 332 | 0

## 2. Delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 9 | 0
Camilla Olesen | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 50 | 0
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 1 | 15 | 4
Jeppe Mutinda Mbinda | 0 | 6 | 52
Jesper Olsen | 0 | 3 | 0
Kristijan Krsteski | 3 | 53 | 0
Line Skov | 0 | 1 | 1
Martin Rasmussen | 0 | 24 | 1
Merete Helme | 0 | 16 | 3
Michael Kronbach Leth | 0 | 83 | 2
Morten Skytte | 0 | 15 | 0
Nanna Søndergaard Skov | 0 | 9 | 0
Natascha Orlung Baisgaard Andersen | 1 | 3 | 0
Peter Madsen | 0 | 11 | 20
Shazia Mobin | 0 | 26 | 0
Signe Fogh Mach Andersen | 0 | 3 | 10

## 3. Installation preparation and
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 2 | 0
Camilla Olesen | 0 | 1 | 0
Cecilie Heidner Nielsen | 0 | 6 | 2
Christoffer Møller Andersen | 0 | 7 | 0
Eva Eisner | 0 | 5 | 1
Henrik Møller Fyhn | 0 | 7 | 0
Jane Birgitte Høgaard | 4 | 22 | 3
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Kristijan Krsteski | 0 | 0 | 3
Line Skov | 1 | 30 | 13
Merete Helme | 0 | 21 | 4
Mette Vinther | 0 | 1 | 0
Michael Kronbach Leth | 0 | 56 | 24
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 1 | 31 | 3
Natascha Orlung Baisgaard Andersen | 0 | 13 | 2
Peter Madsen | 16 | 4 | 1
Shazia Mobin | 0 | 25 | 4
Signe Fogh Mach Andersen | 3 | 0 | 10

## 4. Final design
Delivery Project Manager | Entered | Stayed | Exited
Christoffer Møller Andersen | 0 | 3 | 0
Eva Eisner | 0 | 5 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 1 | 0 | 1
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Line Skov | 11 | 5 | 4
Merete Helme | 2 | 3 | 3
Michael Kronbach Leth | 2 | 5 | 2
Morten Skytte | 0 | 1 | 0
Nanna Søndergaard Skov | 2 | 4 | 3
Natascha Orlung Baisgaard Andersen | 2 | 5 | 2
Peter Madsen | 0 | 5 | 0
Signe Fogh Mach Andersen | 3 | 0 | 0

## 5. Configuration
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 3 | 0
Camilla Villumsen Kaimer | 0 | 6 | 0
Cecilie Heidner Nielsen | 0 | 27 | 0
Christoffer Møller Andersen | 0 | 10 | 1
Eva Eisner | 1 | 0 | 1
Henrik Møller Fyhn | 0 | 42 | 0
Jane Birgitte Høgaard | 1 | 33 | 66
Jeppe Mutinda Mbinda | 52 | 3 | 0
Jesper Olsen | 0 | 2 | 0
Line Skov | 3 | 4 | 2
Martin Rasmussen | 0 | 0 | 3
Merete Helme | 5 | 7 | 1
Michael Kronbach Leth | 10 | 37 | 11
Morten Skytte | 0 | 4 | 0
Nanna Søndergaard Skov | 3 | 8 | 2
Natascha Orlung Baisgaard Andersen | 2 | 16 | 0
Peter Madsen | 0 | 6 | 0
Shazia Mobin | 0 | 4 | 0
Signe Fogh Mach Andersen | 3 | 0 | 3

## 6. Cabling splicing and install
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 7 | 0
Camilla Olesen | 0 | 4 | 0
Camilla Villumsen Kaimer | 0 | 2 | 0
Cecilie Heidner Nielsen | 2 | 1 | 0
Christoffer Møller Andersen | 0 | 8 | 0
Eva Eisner | 2 | 5 | 4
Henrik Møller Fyhn | 0 | 52 | 12
Jane Birgitte Høgaard | 3 | 3 | 4
Jeppe Mutinda Mbinda | 0 | 8 | 0
Jesper Olsen | 0 | 17 | 1
Kristijan Krsteski | 0 | 36 | 0
Line Skov | 4 | 29 | 13
Martin Rasmussen | 4 | 7 | 2
Merete Helme | 1 | 36 | 13
Michael Kronbach Leth | 23 | 17 | 0
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 0 | 18 | 3
Natascha Orlung Baisgaard Andersen | 0 | 10 | 0
Peter Madsen | 4 | 25 | 5
Shazia Mobin | 0 | 10 | 0
Signe Fogh Mach Andersen | 7 | 2 | 0

## 7. Service activation
Delivery Project Manager | Entered | Stayed | Exited
Camilla Villumsen Kaimer | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 3 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Kristijan Krsteski | 0 | 3 | 0
Merete Helme | 0 | 0 | 1
Michael Kronbach Leth | 0 | 12 | 0
Morten Skytte | 0 | 5 | 0
Nanna Søndergaard Skov | 1 | 4 | 0
Natascha Orlung Baisgaard Andersen | 0 | 37 | 2
Peter Madsen | 0 | 4 | 0

## 8. Ready for service
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 1 | 0
Christoffer Møller Andersen | 2 | 0 | 0
Eva Eisner | 1 | 1 | 1
Henrik Møller Fyhn | 3 | 0 | 2
Jane Birgitte Høgaard | 0 | 2 | 0
Jeppe Mutinda Mbinda | 0 | 5 | 2
Jesper Olsen | 1 | 0 | 0
Line Skov | 1 | 0 | 1
Merete Helme | 4 | 0 | 2
Michael Kronbach Leth | 2 | 0 | 0
Morten Skytte | 0 | 22 | 0
Nanna Søndergaard Skov | 2 | 0 | 0
Natascha Orlung Baisgaard Andersen | 1 | 1 | 0
Peter Madsen | 1 | 0 | 1