## Step Metrics Summary
Step | Avg Days in Step | Avg Orders per Day | Avg MRC per Day
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 8.6 | 349.89 | 323971.71
2. Delivery planning | 8 | 381.22 | 398685.07
3. Installation preparation and digging order | 7.29 | 276.22 | 304655.62
4. Final design | 6.73 | 65.78 | 65645.28
5. Configuration | 6.12 | 259.67 | 262050.82
6. Cabling splicing and installation | 7.24 | 335.22 | 393115.08
7. Service activation | 7.87 | 68.22 | 65162.66
8. Ready for service | 6.54 | 37.78 | 48963.62
9. Vendor invoice | 0 | 0 | 0
Delivered | 3.05 | 116 | 69012.89
Cancelled/terminated/On hold | 3.38 | 25.56 | 28841.46
Data as of 20250519 - 20250527

## Step Entry-Exit Summary
Step | Entered | Stayed | Exited
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 0 | 339 | 27
2. Delivery planning | 5 | 331 | 93
3. Installation preparation and digging order | 25 | 245 | 74
4. Final design | 25 | 45 | 15
5. Configuration | 80 | 212 | 92
6. Cabling splicing and installation | 52 | 297 | 66
7. Service activation | 2 | 72 | 4
8. Ready for service | 18 | 32 | 10
9. Vendor invoice | 0 | 0 | 0
Delivered | 168 | 173 | 1
Cancelled/terminated/On hold | 10 | 58 | 1
Interval between T1 and T2: 20250519 - 20250527

## DPM Avg Orders per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 9 | 2 | 0 | 3 | 7 | 0 | 1 | 0 | 0.56 | 0.89
Camilla Olesen | 0 | 0 | 2 | 0.78 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 6 | 1.44 | 2 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 6.44 | 0 | 27 | 2.56 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 50 | 7 | 3 | 10.33 | 7.22 | 2.56 | 1.33 | 0 | 3.78 | 0
Eva Eisner | 0 | 0 | 0 | 5 | 5.22 | 1.56 | 7 | 0 | 1.44 | 0 | 4.67 | 0.67
Flemming Skovdal | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0
Henrik Møller Fyhn | 0 | 0 | 2 | 6 | 2 | 41.89 | 46.78 | 0.67 | 0.89 | 0 | 3.22 | 14.56
Jane Birgitte Høgaard | 0 | 0 | 16 | 24.78 | 0.89 | 63 | 6.44 | 0 | 2 | 0 | 49 | 0
Jeppe Mutinda Mbinda | 0 | 12 | 46.44 | 1 | 1 | 14.56 | 8 | 0 | 5.44 | 0 | 15.89 | 0
Jesper Olsen | 0 | 0 | 3 | 6 | 6 | 2 | 15.44 | 0.11 | 0.67 | 0 | 0.22 | 0.22
Julie Lillethorup Kierkegaard | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 55.67 | 0.33 | 0 | 0 | 35.44 | 3 | 0 | 0 | 0.89 | 1
Line Skov | 0 | 0 | 1.22 | 32.44 | 14 | 4.44 | 35.44 | 0 | 0.11 | 0 | 9.44 | 1
Martin Rasmussen | 0 | 0 | 22.89 | 0 | 0 | 0.67 | 10.56 | 0 | 0 | 0 | 1.11 | 0
Merete Helme | 0 | 0 | 15.33 | 21 | 5.22 | 10 | 39.33 | 0.44 | 0.67 | 0 | 6.11 | 2.67
Mette Vinther | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 82.89 | 62.56 | 7.33 | 31.56 | 32.33 | 12 | 0.44 | 0 | 1 | 0
Morten Skytte | 0 | 0 | 15 | 9 | 1 | 3.22 | 7.44 | 1.78 | 21.22 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 331.22 | 9 | 31.56 | 6.56 | 10.56 | 18.89 | 4.22 | 0.78 | 0 | 4 | 1.11
Natascha Orlung Baisgaard Andersen | 0 | 0 | 3.89 | 13.89 | 6.56 | 17.56 | 6.89 | 37.44 | 1.67 | 0 | 7.22 | 0
Peter Madsen | 0 | 0 | 15.22 | 14.67 | 5 | 6 | 26.33 | 4 | 0.11 | 0 | 5.44 | 0.78
Shazia Mobin | 0 | 0 | 26 | 26.33 | 0 | 2.44 | 10 | 0 | 0 | 0 | 3.33 | 0
Signe Fogh Mach Andersen | 0 | 0 | 5.67 | 4.44 | 2 | 3.89 | 6.67 | 0 | 0 | 0 | 0 | 2.67
Data as of 20250519 - 20250527

## DPM Avg MRC per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 23172 | 4550 | 0 | 1453.14 | 11631.2 | 0 | 4130 | 0 | 371.33 | 2737.78
Camilla Olesen | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 5096 | 1872.22 | 0 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 6376.67 | 0 | -6.64 | 10934.33 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 31029.88 | 6122.5 | 1800 | 4310.54 | 7177.65 | 647.78 | 1663.33 | 0 | 3866 | 0
Eva Eisner | 0 | 0 | 0 | 3377.5 | 3506.11 | 2037.78 | 4887.78 | 0 | 995.28 | 0 | 2895.56 | 354.44
Flemming Skovdal | 0 | 23595.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.06 | 0
Henrik Møller Fyhn | 0 | 0 | 6158 | 14550.44 | 9050 | 30900 | 104173.93 | 332 | 1974.44 | 0 | 9744.44 | 20132.56
Jane Birgitte Høgaard | 0 | 0 | 45546.72 | 35366.67 | 751.11 | 81719.44 | 4708.33 | 0 | 27000 | 0 | 4327.22 | 0
Jeppe Mutinda Mbinda | 0 | 13765.79 | 33925.61 | 662 | 2580.06 | 12475 | 9785 | 0 | 6847.78 | 0 | 18206.12 | 0
Jesper Olsen | 0 | 0 | 4095 | 4149 | 6309 | 2650 | 14627.89 | 155 | 500 | 0 | 218 | 0
Julie Lillethorup Kierkegaard | 0 | 9506.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 25592.67 | 253.33 | 0 | 0 | 11505 | 3833 | 0 | 0 | 433.33 | 560
Line Skov | 0 | 0 | -361.51 | 24160.22 | 14678.67 | 7607.68 | 26858.37 | 0 | 155 | 0 | 5531 | 1595
Martin Rasmussen | 0 | 0 | 36016.94 | 0 | 0 | 619.11 | 25844.81 | 0 | 0 | 0 | 848.89 | 0
Merete Helme | 0 | 0 | 10603.1 | 15081.38 | 5049.67 | 11776.61 | 43071.93 | 88.89 | 344.9 | 0 | 5472.89 | 868.91
Mette Vinther | 0 | 0 | 0 | 93.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 111180.47 | 65632 | 4952.22 | 71217.22 | 30549.33 | 0 | 1455.56 | 0 | 607.78 | 0
Morten Skytte | 0 | 0 | 7925 | 6460 | 1725 | 6696.53 | 6578.11 | 363.14 | 1559.67 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 277103.89 | 12606 | 27529.44 | 5067.89 | 10159.67 | 14572.89 | 4959.53 | 675.44 | 0 | 4644 | 891.11
Natascha Orlung Baisgaard Andersen | 0 | 0 | 1195 | 4357.33 | 2628.89 | -9905.24 | 2459.49 | 37783.33 | 1466.67 | 0 | -100.51 | 0
Peter Madsen | 0 | 0 | 27059.45 | 63181.11 | 6550 | 17605 | 32491.48 | 17000 | 195.56 | 0 | 8823.78 | 768.33
Shazia Mobin | 0 | 0 | 18648.68 | 21188.39 | 0 | 3620.11 | 8395 | 0 | 0 | 0 | 3091 | 0
Signe Fogh Mach Andersen | 0 | 0 | 4292.05 | 1563.89 | 996.67 | 2018.88 | 3990.33 | 0 | 0 | 0 | 0 | 933.33
Data as of 20250519 - 20250527

## DPM Avg Days in Step
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 9 | 9 | 0 | 9 | 9 | 0 | 9 | 0 | 1 | 8
Camilla Olesen | 0 | 0 | 9 | 7 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 9 | 6.5 | 9 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 7.25 | 0 | 9 | 7.67 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 9 | 9 | 9 | 8.45 | 8.12 | 5.75 | 6 | 0 | 3.4 | 0
Eva Eisner | 0 | 0 | 0 | 7.5 | 7.83 | 7 | 5.73 | 0 | 6.5 | 0 | 2 | 2
Flemming Skovdal | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Henrik Møller Fyhn | 0 | 0 | 9 | 7.71 | 9 | 8.98 | 6.58 | 3 | 2.67 | 0 | 2.23 | 3.05
Jane Birgitte Høgaard | 0 | 0 | 7.2 | 7.69 | 2.67 | 5.73 | 5.8 | 0 | 9 | 0 | 2.88 | 0
Jeppe Mutinda Mbinda | 0 | 4 | 7.21 | 9 | 9 | 2.38 | 9 | 0 | 7 | 0 | 4.61 | 0
Jesper Olsen | 0 | 0 | 9 | 9 | 9 | 9 | 7.72 | 1 | 6 | 0 | 1 | 2
Julie Lillethorup Kierkegaard | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 8.95 | 1 | 0 | 0 | 8.86 | 9 | 0 | 0 | 2 | 9
Line Skov | 0 | 0 | 5.5 | 6.64 | 5.73 | 5 | 6.65 | 0 | 1 | 0 | 2.83 | 9
Martin Rasmussen | 0 | 0 | 8.24 | 0 | 0 | 2 | 7.31 | 0 | 0 | 0 | 2.5 | 0
Merete Helme | 0 | 0 | 7.26 | 7.56 | 5.88 | 6.92 | 7.08 | 4 | 1.5 | 0 | 3.24 | 4
Mette Vinther | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kronbach Leth | 0 | 0 | 8.78 | 6.95 | 6.6 | 4.9 | 7.28 | 9 | 2 | 0 | 1.8 | 0
Morten Skytte | 0 | 0 | 9 | 9 | 9 | 7.25 | 7.44 | 3.2 | 8.68 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 8.98 | 9 | 8.35 | 6.56 | 7.31 | 8.1 | 7.6 | 3.5 | 0 | 2.57 | 2
Natascha Orlung Baisgaard Andersen | 0 | 0 | 8.75 | 8.33 | 6.56 | 8.78 | 6.2 | 8.64 | 7.5 | 0 | 8.12 | 0
Peter Madsen | 0 | 0 | 4.42 | 6.29 | 9 | 9 | 6.58 | 9 | 1 | 0 | 3.77 | 2.33
Shazia Mobin | 0 | 0 | 9 | 8.17 | 0 | 5.5 | 9 | 0 | 0 | 0 | 2.73 | 0
Signe Fogh Mach Andersen | 0 | 0 | 3.92 | 3.33 | 6 | 4.38 | 6.67 | 0 | 0 | 0 | 0 | 6
Data as of 20250519 - 20250527

## 1.9 PMO delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Flemming Skovdal | 0 | 3 | 0
Jeppe Mutinda Mbinda | 0 | 0 | 27
Julie Lillethorup Kierkegaard | 0 | 4 | 0
Nanna Søndergaard Skov | 0 | 332 | 0

## 2. Delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 9 | 0
Camilla Olesen | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 50 | 0
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 1 | 15 | 4
Jeppe Mutinda Mbinda | 0 | 6 | 52
Jesper Olsen | 0 | 3 | 0
Kristijan Krsteski | 3 | 53 | 0
Line Skov | 0 | 1 | 1
Martin Rasmussen | 0 | 24 | 1
Merete Helme | 0 | 16 | 3
Michael Kronbach Leth | 0 | 83 | 2
Morten Skytte | 0 | 15 | 0
Nanna Søndergaard Skov | 0 | 9 | 0
Natascha Orlung Baisgaard Andersen | 1 | 3 | 0
Peter Madsen | 0 | 11 | 20
Shazia Mobin | 0 | 26 | 0
Signe Fogh Mach Andersen | 0 | 3 | 10

## 3. Installation preparation and
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 2 | 0
Camilla Olesen | 0 | 1 | 0
Cecilie Heidner Nielsen | 0 | 6 | 2
Christoffer Møller Andersen | 0 | 7 | 0
Eva Eisner | 0 | 5 | 1
Henrik Møller Fyhn | 0 | 7 | 0
Jane Birgitte Høgaard | 4 | 22 | 4
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Kristijan Krsteski | 0 | 0 | 3
Line Skov | 1 | 28 | 15
Merete Helme | 0 | 21 | 4
Mette Vinther | 0 | 1 | 0
Michael Kronbach Leth | 0 | 56 | 24
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 1 | 31 | 3
Natascha Orlung Baisgaard Andersen | 0 | 13 | 2
Peter Madsen | 16 | 4 | 2
Shazia Mobin | 0 | 25 | 4
Signe Fogh Mach Andersen | 3 | 0 | 10

## 4. Final design
Delivery Project Manager | Entered | Stayed | Exited
Christoffer Møller Andersen | 0 | 3 | 0
Eva Eisner | 0 | 5 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 1 | 0 | 0
Jeppe Mutinda Mbinda | 0 | 1 | 0
Jesper Olsen | 0 | 6 | 0
Line Skov | 13 | 5 | 4
Merete Helme | 2 | 3 | 3
Michael Kronbach Leth | 2 | 5 | 2
Morten Skytte | 0 | 1 | 0
Nanna Søndergaard Skov | 2 | 4 | 3
Natascha Orlung Baisgaard Andersen | 2 | 5 | 2
Peter Madsen | 0 | 5 | 0
Signe Fogh Mach Andersen | 3 | 0 | 0

## 5. Configuration
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 3 | 0
Camilla Villumsen Kaimer | 0 | 6 | 0
Cecilie Heidner Nielsen | 0 | 27 | 0
Christoffer Møller Andersen | 0 | 10 | 1
Eva Eisner | 1 | 0 | 1
Henrik Møller Fyhn | 0 | 42 | 0
Jane Birgitte Høgaard | 1 | 33 | 66
Jeppe Mutinda Mbinda | 52 | 3 | 0
Jesper Olsen | 0 | 2 | 0
Line Skov | 3 | 4 | 4
Martin Rasmussen | 0 | 0 | 3
Merete Helme | 5 | 7 | 1
Michael Kronbach Leth | 10 | 37 | 11
Morten Skytte | 0 | 4 | 0
Nanna Søndergaard Skov | 3 | 8 | 2
Natascha Orlung Baisgaard Andersen | 2 | 16 | 0
Peter Madsen | 0 | 6 | 0
Shazia Mobin | 0 | 4 | 0
Signe Fogh Mach Andersen | 3 | 0 | 3

## 6. Cabling splicing and install
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 7 | 0
Camilla Olesen | 0 | 4 | 0
Camilla Villumsen Kaimer | 0 | 2 | 0
Cecilie Heidner Nielsen | 2 | 1 | 0
Christoffer Møller Andersen | 0 | 8 | 0
Eva Eisner | 2 | 5 | 4
Henrik Møller Fyhn | 0 | 52 | 12
Jane Birgitte Høgaard | 3 | 3 | 4
Jeppe Mutinda Mbinda | 0 | 8 | 0
Jesper Olsen | 0 | 14 | 4
Kristijan Krsteski | 0 | 36 | 0
Line Skov | 6 | 26 | 16
Martin Rasmussen | 4 | 7 | 2
Merete Helme | 1 | 34 | 15
Michael Kronbach Leth | 23 | 17 | 0
Morten Skytte | 0 | 9 | 0
Nanna Søndergaard Skov | 0 | 18 | 3
Natascha Orlung Baisgaard Andersen | 0 | 10 | 0
Peter Madsen | 4 | 24 | 6
Shazia Mobin | 0 | 10 | 0
Signe Fogh Mach Andersen | 7 | 2 | 0

## 7. Service activation
Delivery Project Manager | Entered | Stayed | Exited
Camilla Villumsen Kaimer | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 3 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Jesper Olsen | 1 | 0 | 0
Kristijan Krsteski | 0 | 3 | 0
Merete Helme | 0 | 0 | 1
Michael Kronbach Leth | 0 | 12 | 0
Morten Skytte | 0 | 5 | 0
Nanna Søndergaard Skov | 1 | 4 | 0
Natascha Orlung Baisgaard Andersen | 0 | 37 | 2
Peter Madsen | 0 | 4 | 0

## 8. Ready for service
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 1 | 0
Christoffer Møller Andersen | 2 | 0 | 0
Eva Eisner | 1 | 1 | 1
Henrik Møller Fyhn | 3 | 0 | 2
Jane Birgitte Høgaard | 0 | 2 | 0
Jeppe Mutinda Mbinda | 0 | 5 | 2
Jesper Olsen | 1 | 0 | 0
Line Skov | 1 | 0 | 1
Merete Helme | 4 | 0 | 3
Michael Kronbach Leth | 2 | 0 | 0
Morten Skytte | 0 | 22 | 0
Nanna Søndergaard Skov | 2 | 0 | 0
Natascha Orlung Baisgaard Andersen | 1 | 1 | 0
Peter Madsen | 1 | 0 | 1