## Step Metrics Summary
Step | Avg Days in Step | Avg Orders per Day | Avg MRC per Day
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 6.65 | 66.5 | 67342.63
2. Delivery planning | 7.31 | 32 | 50048.19
3. Installation preparation and digging order | 6.4 | 45.62 | 46157.83
4. Final design | 0 | 0 | 0
5. Configuration | 6.46 | 46 | 51119.66
6. Cabling splicing and installation | 5.78 | 109.12 | 111229.37
7. Service activation | 7.16 | 39.38 | 40209.71
8. Ready for service | 3.42 | 5.12 | 4419.25
9. Vendor invoice | 0 | 0 | 0
Delivered | 3.58 | 40.25 | 37870.24
Cancelled/terminated/On hold | 4.25 | 2.12 | 633.14

## Step Entry-Exit Summary
Step | Entered | Stayed | Exited
1. Order entry and validation | 0 | 0 | 0
1.9 PMO delivery planning | 0 | 53 | 27
2. Delivery planning | 0 | 31 | 4
3. Installation preparation and digging order | 4 | 40 | 15
4. Final design | 0 | 0 | 0
5. Configuration | 3 | 39 | 13
6. Cabling splicing and installation | 18 | 81 | 50
7. Service activation | 1 | 41 | 2
8. Ready for service | 10 | 2 | 6
9. Vendor invoice | 0 | 0 | 0
Delivered | 78 | 12 | 0
Cancelled/terminated/On hold | 4 | 0 | 1

## DPM Avg Orders per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 2 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 6 | 1.5 | 2 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 0.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 12 | 1 | 0 | 3.38 | 4 | 2.38 | 1.25 | 0 | 2 | 0
Eva Eisner | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0.5 | 0 | 0.5 | 0
Henrik Møller Fyhn | 0 | 0 | 0 | 0.5 | 0 | 2 | 12.5 | 0.75 | 0.25 | 0 | 1.88 | 0
Jane Birgitte Høgaard | 0 | 0 | 0 | 0 | 0 | 0.5 | 4 | 0 | 0 | 0 | 1.5 | 0
Jeppe Mutinda Mbinda | 0 | 13.5 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 13.5 | 0
Jesper Olsen | 0 | 0 | 0 | 0 | 0 | 1 | 4.38 | 0 | 0.62 | 0 | 0 | 0
Julie Lillethorup Kierkegaard | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 1 | 0 | 0 | 0 | 0
Line Skov | 0 | 0 | 0 | 0.88 | 0 | 0 | 8.12 | 0 | 0.12 | 0 | 5.38 | 0
Martin Rasmussen | 0 | 0 | 2 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 1 | 0
Merete Helme | 0 | 0 | 1.12 | 0.75 | 0 | 5.25 | 14 | 0.5 | 0.12 | 0 | 4.62 | 1.88
Michael Kronbach Leth | 0 | 0 | 3.5 | 21.5 | 0 | 11.62 | 11.75 | 1 | 0 | 0 | 0.12 | 0
Morten Skytte | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 1.5 | 1 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 49 | 0 | 1.12 | 0 | 1.25 | 5 | 2.25 | 0.12 | 0 | 1.25 | 0
Natascha Orlung Baisgaard Andersen | 0 | 0 | 0 | 2 | 0 | 9 | 4 | 28 | 1 | 0 | 7 | 0
Peter Madsen | 0 | 0 | 2 | 0 | 0 | 2 | 4.12 | 0 | 0.12 | 0 | 1.5 | 0.25
Shazia Mobin | 0 | 0 | 7 | 15 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0
Signe Fogh Mach Andersen | 0 | 0 | 0.38 | 1.38 | 0 | 2 | 3.25 | 0 | 0 | 0 | 0 | 0

## DPM Avg MRC per Day
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 5936 | 1950 | 0 | 0 | 5471.2 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 5096 | 1950 | 0 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 2212.5 | 0 | 0 | 6637.5 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 13265.52 | 947.5 | 0 | 3624.62 | -477.91 | 422.5 | 1559.38 | 0 | 2800 | 0
Eva Eisner | 0 | 0 | 0 | 0 | 0 | 0 | 2066.25 | 0 | 447.5 | 0 | 273.75 | 0
Henrik Møller Fyhn | 0 | 0 | 0 | 88 | 0 | 14200 | 19936 | 373.5 | 800 | 0 | 3000 | 0
Jane Birgitte Høgaard | 0 | 0 | 0 | 0 | 0 | 2062.5 | 2146.88 | 0 | 0 | 0 | 1055.62 | 0
Jeppe Mutinda Mbinda | 0 | 15486.51 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 15486.51 | 0
Jesper Olsen | 0 | 0 | 0 | 0 | 0 | 1295 | 3596.25 | 0 | 468.75 | 0 | 0 | 0
Julie Lillethorup Kierkegaard | 0 | 9506.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 1773 | 0 | 0 | 0 | 0
Line Skov | 0 | 0 | 0 | 131.25 | 0 | 0 | 6084.62 | 0 | 174.38 | 0 | 3931.25 | 0
Martin Rasmussen | 0 | 0 | 1080 | 0 | 0 | 0 | 1660.75 | 0 | 0 | 0 | 556.25 | 0
Merete Helme | 0 | 0 | 182.64 | 149.62 | 0 | 7115.38 | 16453.63 | 100 | 186.88 | 0 | 3772.23 | 304.39
Michael Kronbach Leth | 0 | 0 | 15888.62 | 24236.44 | 0 | 14763.75 | 19196.5 | 0 | 0 | 0 | 158.75 | 0
Morten Skytte | 0 | 0 | 1725 | 0 | 0 | 0 | 4642 | 471.25 | 40 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 42350 | 0 | 1156.12 | 0 | 2347.5 | 4798.25 | 2261.75 | 122.38 | 0 | 3125 | 0
Natascha Orlung Baisgaard Andersen | 0 | 0 | 0 | 300 | 0 | -15290.83 | 1706 | 34807.71 | 400 | 0 | -321.62 | 0
Peter Madsen | 0 | 0 | -1542.44 | 0 | 0 | 11990 | 7825.25 | 0 | 220 | 0 | 4032.5 | 328.75
Shazia Mobin | 0 | 0 | 13064.73 | 14628.89 | 0 | 3177 | 2895 | 0 | 0 | 0 | 0 | 0
Signe Fogh Mach Andersen | 0 | 0 | 448.12 | 357.5 | 0 | 738.74 | 1386.19 | 0 | 0 | 0 | 0 | 0

## DPM Avg Days in Step
Delivery Project Manager | 1. Order entry and validation | 1.9 PMO delivery planning | 2. Delivery planning | 3. Installation preparation and digging order | 4. Final design | 5. Configuration | 6. Cabling splicing and installation | 7. Service activation | 8. Ready for service | 9. Vendor invoice | Delivered | Cancelled/terminated/On hold
Andrew David Lindsey | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
Camilla Villumsen Kaimer | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 8 | 0 | 0 | 0 | 0
Cecilie Heidner Nielsen | 0 | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
Christoffer Møller Andersen | 0 | 0 | 8 | 8 | 0 | 6.75 | 8 | 6.33 | 5 | 0 | 8 | 0
Eva Eisner | 0 | 0 | 0 | 0 | 0 | 0 | 5.33 | 0 | 4 | 0 | 1 | 0
Henrik Møller Fyhn | 0 | 0 | 0 | 4 | 0 | 8 | 4.76 | 3 | 1 | 0 | 1.36 | 0
Jane Birgitte Høgaard | 0 | 0 | 0 | 0 | 0 | 4 | 5.33 | 0 | 0 | 0 | 3 | 0
Jeppe Mutinda Mbinda | 0 | 4 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 4 | 0
Jesper Olsen | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 0 | 5 | 0 | 0 | 0
Julie Lillethorup Kierkegaard | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kristijan Krsteski | 0 | 0 | 0 | 0 | 0 | 0 | 7.6 | 8 | 0 | 0 | 0 | 0
Line Skov | 0 | 0 | 0 | 7 | 0 | 0 | 4.64 | 0 | 1 | 0 | 3.07 | 0
Martin Rasmussen | 0 | 0 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2.67 | 0
Merete Helme | 0 | 0 | 3 | 3 | 0 | 7 | 5.33 | 4 | 1 | 0 | 3.36 | 5
Michael Kronbach Leth | 0 | 0 | 7 | 6.37 | 0 | 5.81 | 5.53 | 8 | 0 | 0 | 1 | 0
Morten Skytte | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 8 | 0 | 0 | 0
Nanna Søndergaard Skov | 0 | 8 | 0 | 4.5 | 0 | 3.33 | 5.71 | 6 | 1 | 0 | 5 | 0
Natascha Orlung Baisgaard Andersen | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 0
Peter Madsen | 0 | 0 | 8 | 0 | 0 | 8 | 3.67 | 0 | 1 | 0 | 3 | 2
Shazia Mobin | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Signe Fogh Mach Andersen | 0 | 0 | 3 | 3.67 | 0 | 3.2 | 6.5 | 0 | 0 | 0 | 0 | 0

## 1.9 PMO delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Jeppe Mutinda Mbinda | 0 | 0 | 27
Julie Lillethorup Kierkegaard | 0 | 4 | 0
Nanna Søndergaard Skov | 0 | 49 | 0

## 2. Delivery planning
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 12 | 0
Jeppe Mutinda Mbinda | 0 | 1 | 0
Martin Rasmussen | 0 | 2 | 0
Merete Helme | 0 | 0 | 3
Michael Kronbach Leth | 0 | 4 | 0
Morten Skytte | 0 | 1 | 0
Peter Madsen | 0 | 2 | 0
Shazia Mobin | 0 | 7 | 0
Signe Fogh Mach Andersen | 0 | 0 | 1

## 3. Installation preparation and
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 1 | 0
Cecilie Heidner Nielsen | 0 | 0 | 2
Christoffer Møller Andersen | 0 | 1 | 0
Henrik Møller Fyhn | 0 | 1 | 0
Line Skov | 0 | 0 | 1
Merete Helme | 0 | 0 | 2
Michael Kronbach Leth | 0 | 19 | 8
Nanna Søndergaard Skov | 1 | 1 | 1
Natascha Orlung Baisgaard Andersen | 0 | 2 | 0
Shazia Mobin | 0 | 15 | 0
Signe Fogh Mach Andersen | 3 | 0 | 1

## 5. Configuration
Delivery Project Manager | Entered | Stayed | Exited
Camilla Villumsen Kaimer | 0 | 6 | 0
Christoffer Møller Andersen | 0 | 3 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Jane Birgitte Høgaard | 0 | 1 | 0
Jesper Olsen | 0 | 1 | 0
Merete Helme | 2 | 4 | 0
Michael Kronbach Leth | 0 | 9 | 7
Nanna Søndergaard Skov | 1 | 0 | 2
Natascha Orlung Baisgaard Andersen | 0 | 9 | 0
Peter Madsen | 0 | 2 | 0
Shazia Mobin | 0 | 2 | 0
Signe Fogh Mach Andersen | 0 | 0 | 3

## 6. Cabling splicing and install
Delivery Project Manager | Entered | Stayed | Exited
Andrew David Lindsey | 0 | 5 | 0
Camilla Villumsen Kaimer | 0 | 2 | 0
Cecilie Heidner Nielsen | 2 | 0 | 0
Christoffer Møller Andersen | 0 | 4 | 0
Eva Eisner | 0 | 2 | 4
Henrik Møller Fyhn | 0 | 12 | 9
Jane Birgitte Høgaard | 0 | 2 | 4
Jeppe Mutinda Mbinda | 0 | 2 | 0
Jesper Olsen | 0 | 4 | 1
Kristijan Krsteski | 0 | 10 | 0
Line Skov | 0 | 1 | 13
Martin Rasmussen | 0 | 1 | 2
Merete Helme | 0 | 11 | 10
Michael Kronbach Leth | 14 | 3 | 0
Morten Skytte | 0 | 4 | 0
Nanna Søndergaard Skov | 0 | 4 | 3
Natascha Orlung Baisgaard Andersen | 0 | 4 | 0
Peter Madsen | 0 | 3 | 4
Shazia Mobin | 0 | 5 | 0
Signe Fogh Mach Andersen | 2 | 2 | 0

## 7. Service activation
Delivery Project Manager | Entered | Stayed | Exited
Camilla Villumsen Kaimer | 0 | 2 | 0
Christoffer Møller Andersen | 0 | 2 | 1
Henrik Møller Fyhn | 0 | 2 | 0
Kristijan Krsteski | 0 | 1 | 0
Merete Helme | 0 | 0 | 1
Michael Kronbach Leth | 0 | 1 | 0
Morten Skytte | 0 | 3 | 0
Nanna Søndergaard Skov | 1 | 2 | 0
Natascha Orlung Baisgaard Andersen | 0 | 28 | 0

## 8. Ready for service
Delivery Project Manager | Entered | Stayed | Exited
Christoffer Møller Andersen | 2 | 0 | 0
Eva Eisner | 1 | 0 | 1
Henrik Møller Fyhn | 2 | 0 | 2
Jesper Olsen | 1 | 0 | 0
Line Skov | 1 | 0 | 1
Merete Helme | 1 | 0 | 1
Morten Skytte | 0 | 1 | 0
Nanna Søndergaard Skov | 1 | 0 | 0
Natascha Orlung Baisgaard Andersen | 0 | 1 | 0
Peter Madsen | 1 | 0 | 1